## POC POb Inputs
Contract Based Information from PIQ | [13 empty] | EOM Inputs 1 |  |  |  | EOM Inputs 2 |  |  |  | EOM Inputs 3 |  |  | EOM Inputs 4 |  |  |  | Contract Data at Booking & Monthly Changes (if needed)
Platform | Reporting Unit | C-ID | Customer Name | Sales Order # | POb Name (P-page Name) | POb ID | Rev Rec Method | Contract Currency | Total Trans Price Contract Curr | Allocated Transaction Price (USD) | Booking Date (LoA) | Estimated Completion Date | Blank | Allocated Trans Price (net LD) in Contract Curr | Amount of Probable LD Contract Curr | Updated Cost EAC Local Curr | Blank | Cumulative Cost Incurred /Received Local Curr | Interco Progress (Not Received) Local Curr | 3rd Party Progress (Not Received) Local Curr | Blank | Actual Shipment / Delivery Date (if complete) | If partial POB shipped: Enter Cumulative COGS | Blank | Billing Amount Contract Curr | Billing Amount Local Curr | Billing Date | Billing Invoice # | Total Third-Party Commission Local Curr | Contract Sales Destination | Disagg. Revenue OE vs AM | Straight Line POb Revenue Start Date | Straight Line POb Revenue End Date
AMSS | RU1015 | 8024 | JCI Industries, Inc | 1070285 | P - JCI 1070285/44708374 | 10660 | POC | USD | 252444 | 252443.98 | 2017-08-17 | 2018-06-21 |  | 252444 | 0 | 201955 |  | 0 | 120503.26 | 0 |  | 2018-03-14 | [6 empty] | 0 | US | AM
AMSS | RU1015 | 8741 | CANADIAN NATURAL RESOURCES LIMITED | 1070826 | P - CNRL 1070826/07829417 | 10748 | POC | CAD | 437213 | 343858.89 | 2017-08-30 | 2018-09-12 |  | 437213 | 0 | 243215 |  | 0 | 91453.52 | 0 | [5 empty] | 0 |  |  | 0 | CANADA | AM
AMSS | RU1015 | 10143 | Kincaid Generation | 1072613 | P - Kincaid Generation 1072613/660330000002710 | 13740 | POC | USD | 263863 | 263863 | 2017-09-29 | 2018-04-12 |  | 263863 | 0 | 143219.67 |  | 143219.67 | 0 | 0 |  | 2018-05-31 |  |  | 79158.9 |  | 2018-05-31 | 99910143 | 0 | US | AM
AMSS | RU1015 | 10144 | Chevron US Products Company | 1072381 | P - Chevron Products 1072381/0010449343 | 13683 | POC | USD | 391985 | 391985 | 2017-09-21 | 2018-02-15 |  | 391985 | 0 | [6 empty] | 2018-02-28 | [6 empty] | 0 | US | AM
AMSS | RU1015 | 10151 | Tennessee Valley Authority (TVA) | 1072383 | P - Tennessee Valley Auth 1072383 / 3232067 | 13480 | POC | USD | 494840 | 494840.25 | 2017-09-26 | 2018-04-12 |  | 494840 | 0 | [6 empty] | 2018-03-27 | [6 empty] | 0 | US | AM
AMSS | RU1015 | 10154 | Philadelphia Energy Solutions Refining & Marketing LLC | 1070841 | P - Philadelphia Energy 1070841/03182837 | 10454 | POC | USD | 602665 | 602665 | 2017-09-29 | 2018-07-19 |  | 602665 | 0 | 321079 |  | 0 | 0 | 0 | [8 empty] | 0 | US | AM
AMSS | RU1015 | 10591 | JCI | 1072493 | P - JCI 1072493 / 07111824 | 10946 | POC | USD | 515467 | 515467 | 2017-09-25 | 2018-03-29 |  | 515467 | 0 | [6 empty] | 2018-01-30 | [6 empty] | 0 | US | AM
AMSS | RU1015 | 13474 | Valero McKee Refinery | 076C8211 | P - Valero McKee Refinery - 076C8211/4504074104 Duplicate Bare Pump | 14337 | POC | USD | 393112 | 393112 | 2017-10-24 | 2018-06-11 |  | 393112 | 0 | 171410.19 |  | 171410.19 | 0 | 0 |  | 2018-05-25 |  |  | 117933.6 |  | 2018-05-30 | 600589172 | 0 | US | AM
AMSS | RU1015 | 13674 | Chevron Products Company | 07771256 | P - Chevron Products - 07771256/0000581458 Spare Bundle for Pump | 14322 | POC | USD | 492670 | 492670 | 2017-10-31 | 2018-06-22 |  | 492670 | 0 | 224326 |  | 186261.29 | 0 | 0 | [8 empty] | 0 | US | AM
AMSS | RU1015 | 13676 | Chevron Products Company | 07771191 | P - Chevron Products - 07771191/0010454844 P-737C Pump | 14329 | POC | USD | 311780 | 311780 | 2017-10-31 | 2018-07-31 |  | 311780 | 0 | 208341 |  | 143162.02 | 0 | 0 | [8 empty] | 0 | US | AM
AMSS | RU1015 | 15377 | Marathon Petroleum | 1076007 | P - Marathon Petroleum 028B3721/4101251223 Pump Upgrade | 15752 | POC | USD | 330559 | 330559 | 2017-11-16 | 2018-08-21 |  | 330559 | 0 | 174831 |  | 86559.22 | 0 | 0 | [8 empty] | 0 | US | AM
AMSS | RU1015 | 16121 | Pacificorp | 1076971/07771484 | P - Pacificorp 07771484 | 17302 | POC | USD | 320909 | 332159 | 2017-12-11 | 2018-10-12 |  | 320909 | 0 | 234450 |  | 0 | 39410.11 | 0 | [8 empty] | 0 | US | AM
AMSS | RU1015 | 16705 | Phillips 66 | 077-71205 | P - Phillips 66 - 07771205/4524417243 | 16807 | POC | USD | 479610 | 470412.31 | 2017-10-18 | 2018-04-18 |  | 479610 | 0 | 152975 |  | 60070.55 | 0 | 46460 | [8 empty] | 0 | US | AM
AMSS | RU1015 | 16710 | National Grid | 1074561 | P - National Grid -03183353/3200338757 Spare Element Assembly | 16819 | POC | USD | 299000 | 299000 | 2017-10-31 | 2018-04-20 |  | 299000 | 0 | 195612 | [5 empty] | 2018-04-05 | [6 empty] | 0 | US | AM
AMSS | RU1015 | 16714 | Diamond Green Diesel LLC | 028B0945 | P - Diamond Green Diesel 028B0945/4503916348 Duplicate Bare Pump | 16813 | POC | USD | 304290 | 304290 | 2017-05-31 | 2018-01-25 |  | 304290 | 0 | 203670 |  | 0 | 203670 | 0 |  | 2018-05-30 |  |  | 30429 |  | 2018-05-31 | 99916714 | 0 | US | AM
AMSS | RU1015 | 17037 | Colonial Pipeline Company | 1077406 and 1077396 | P - Colonial Pipeline 1077406 292244 | 17253 | POC | USD | 936770 | 936770 | 2017-12-20 | 2018-11-28 |  | 936770 | 0 | 514380 |  | 0 | 0 | 0 | [8 empty] | 0 | US | AM
AMSS | RU1015 | 17182 | Exxon Mobil | 1077407 | P Exxon Mobil 1077407 4540117458 | 17187 | POC | USD | 295115 | 295115.07 | 2017-12-13 | 2018-04-24 |  | 295115 | 0 | 128913.46 |  | 128913.46 | 0 | 0 |  | 2018-05-18 |  |  | 295115.07 |  | 2018-05-18 | 213521372 | 0 | US | AM
AMSS | RU1015 | 17308 | SUNCOR ENERGY OIL SANDS LIMITED PARTNERSHIP | 1070281 | P - Suncor 1070281/4502451638 DSJH Bare Pump | 15000 | POC | CAD | 543969 | 457067.57 | 2017-08-23 | 2018-04-19 |  | 543969 | 0 | [6 empty] | 2018-03-29 |  |  |  | 0 |  |  | 0 | CANADA | AM
AMSS | RU1015 | 17532 | Ameren | 1077759 | P Ameren 1077759 816028 | 17538 | POC | USD | 344750 | 344750 | 2017-12-27 | 2018-07-25 |  | 344750 | 0 | 172358 |  | 72390.89 | 0 | 0 |  |  |  |  | 68950 |  | 2018-05-08 | 600586972 | 0 | US | AM
AMSS | RU1015 | 18351 | Siewert Equipment | 1077755 | P Siewert Equipment 1077755 442161-00 | 18362 | POC | USD | 280000 | 280000 | 2017-12-19 | 2018-09-25 |  | 280000 | 0 | 214942 |  | 0 | 0 | 0 | [8 empty] | 0 | US | AM
AMSS | RU1015 | 18882 | Invista | 1077819 | P Invista 1077819 5500664609 | 18983 | POC | USD | 351859 | 351859.1 | 2017-12-29 | 2018-07-05 |  | 351859 | 0 | 119763 |  | 9092.6 | 0 | 0 |  |  | 37874.28 | [5 empty] | 0 | US | AM
AMSS | RU1015 | 19052 | Exelon | 1065791 | P Exelon 1065791 740-13951 | 19054 | POC | USD | 301677 | 301676.53 | 2017-06-09 | 2018-01-10 |  | 301677 | 0 | [6 empty] | 2018-03-31 | [6 empty] | 0 | US | AM
AMSS | RU1015 | 19382 | Lima Refining Company | 1077431/1077432 | P Lima Refining 1077431 8401231148 | 19615 | POC | USD | 200267 | 200267.2 | 2017-12-14 | 2018-07-20 |  | 200267 | 0 | 146648 |  | 63566.35 | 0 | 0 | [8 empty] | 0 | US | AM
AMSS | RU1015 | 19655 | Lima Refining | 1077799 | P Lima Refining 1077799 8401236008 | 19660 | POC | USD | 415534 | 415534.4 | 2017-12-29 | 2018-10-15 |  | 415534 | 0 | 276406 |  | 12291.6 | 0 | 0 | [8 empty] | 0 | US | AM
AMSS | RU1015 | 19708 | Lima Refining | 1077433/1077434 | P Lima Refining 1077433 8401231143 | 19735 | POC | USD | 604192 | 604192 | 2017-12-14 | 2018-05-13 |  | 604192 | 0 | 505526 |  | 56901.84 | 0 | 0 | [8 empty] | 0 | US | AM
AMSS | RU1015 | 19748 | Lima Refining | 1077798/1077795 | P Lima Refining 1077798 8401234499 | 19922 | POC | USD | 560555 | 124364.8 | 2017-12-22 | 2018-10-15 |  | 124365 | 0 | 100112 |  | 380.26 | 0 | 0 | [8 empty] | 0 | US | AM
AMSS | RU1015 | 19748 | Lima Refining | 1077798/1077795 | P Lima Refining 1077798 8401234499 | 19925 | POC | USD |  | 369966.4 | 2017-12-22 | 2018-10-15 |  | 369966 | 0 | 258248 |  | 22723.91 | 0 | 0 | [8 empty] | 0 | US | AM
AMSS | RU1015 | 19748 | Lima Refining | 1077798/1077795 | P Lima Refining 1077798 8401234499 | 19926 | POC | USD |  | 66224 | 2017-12-22 | 2018-10-15 |  | 66224 | 0 | 41032 |  | 2982.62 | 0 | 0 | [8 empty] | 0 | US | AM
AMSS | RU1015 | 19755 | Imperial Oil | 1077823 | P Imperial Oil 1077823 4540423463 | 20287 | POC | CAD | 405868 | 324694.34 | 2017-12-29 | 2018-12-14 |  | 405868 | 0 | 141936 |  | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | CANADA | AM
AMSS | RU1015 | 19757 | Phillips 66 | 1061615 | P Phillips 66 1061615 4523653097 | 20144 | POC | USD | 403020 | 403020 | 2017-03-31 | 2018-01-18 |  | 403020 | 0 | [6 empty] | 2018-02-15 | [6 empty] | 0 | US | AM
AMSS | RU1015 | 21422 | CANADIAN NATURAL RESOURCES LIMITED | 1055589 | P CNRL 1055589 859911 | 21424 | POC | CAD | 963726.22 | 521512.13 | 2016-12-21 | 2018-02-15 |  | 683989 | 0 | [6 empty] | 2017-08-30 |  |  |  | 0 |  |  | 0 | CANADA | AM
AMSS | RU1015 | 21422 | CANADIAN NATURAL RESOURCES LIMITED | 1055589 | P CNRL 1055589 859911 | 21441 | POC | CAD |  | 212837.68 | 2016-12-21 | 2018-02-15 |  | 279737.22 | 0 | 172280.47 |  | 0 | 172280.47 | 0 | [8 empty] | 0 | CANADA | AM
AMSS | RU1015 | 21680 | Marathon Petroleum | 1079547 | P Marathon Petroleum 1079547 4101366621 | 21683 | POC | USD | 906466 | 906466 | 2018-01-18 | 2019-01-24 |  | 906466 | 0 | 478380 |  | 0 | 0 | 0 | [8 empty] | 0 | US | AM
AMSS | RU1015 | 21687 | WRB Refining LP | 1079632/1079633 | P - WRB Refining 1079632 4524785880 | 21694 | POC | USD | 496266 | 496266 | 2018-01-29 | 2019-01-28 |  | 496266 | 0 | 273198 |  | 2720.94 | 0 | 0 | [8 empty] | 0 | US | AM
AMSS | RU1015 | 21699 | Phillips 66 | 1079672 | P Phillips 66 1079672 4524781519 | 21749 | POC | USD | 370490 | 370490 | 2018-01-30 | 2018-06-30 |  | 370490 | 0 | 152102 |  | 0 | 0 | 0 | [8 empty] | 0 | US | AM
AMSS | RU1015 | 21757 | Exelon / Fitzpatrick Station | 1079636 | P Exelon 1079636 00639946 | 21776 | POC | USD | 480000 | 480000 | 2018-01-19 | 2018-08-27 |  | 480000 | 0 | 328338 |  | 0 | 0 | 0 | [8 empty] | 0 | US | AM
AMSS | RU1015 | 22022 | Valero Texas City Refinery | 1079685 / CN0180042 | P Valero Texas City Refinery 1079685 4504169164 | 22024 | POC | USD | 275814 | 148714 | 2018-01-30 | 2018-08-06 |  | 148714 | 0 | 84648 |  | 18873.87 | 0 | 0 | [8 empty] | 0 | US | AM
AMSS | RU1015 | 22022 | Valero Texas City Refinery | 1079685 / CN0180042 | P Valero Texas City Refinery 1079685 4504169164 | 22025 | PIT | USD |  | 127100 | 2018-01-30 | 2018-08-06 |  | 127100 | 0 | 108000 |  | 0 | 0 | 0 | [8 empty] | 0 | US | AM
AMSS | RU1015 | 22893 | Chevron Products | 1080720 / 1080869 | P Chevron Products 1080720 0010471086 | 22902 | POC | USD | 387755 | 387755 | 2018-02-06 | 2018-08-03 |  | 387755 | 0 | 151612 |  | 6239.54 | 0 | 0 | [8 empty] | 0 | US | AM
AMSS | RU1015 | 22999 | Phillips 66 | 1081504 | P Phillips 66 1081504 4524917195 | 23001 | POC | USD | 317485 | 317485 | 2018-02-28 | 2018-09-26 |  | 317485 | 0 | 134876 |  | 17221.04 | 0 | 0 | [8 empty] | 0 | US | AM
AMSS | RU1015 | 23869 | WRB Refining LP | 1082652 | P WRB Refining 1082652 4524921605 | 23871 | POC | USD | 359070 | 359070 | 2018-03-06 | 2018-12-28 |  | 359070 | 0 | 206362 |  | 14956.63 | 0 | 0 | [8 empty] | 0 | US | AM
AMSS | RU1015 | 24086 | Lima Refining | 1083149 | P Lima Refining 1083149 8401241342 | 24092 | POC | USD | 295288 | 295288 | 2018-03-12 | 2018-08-16 |  | 295288 | 0 | 204468 |  | 14093.86 | 0 | 0 | [8 empty] | 0 | US | AM
AMSS | RU1015 | 24200 | WRB Refining | 1083261 | P WRB Refining 1083261 4524996468 | 25864 | POC | USD | 642442 | 642442 | 2018-03-28 | 2019-02-08 |  | 642442 | 0 | 356768 |  | 0 | 0 | 0 | [8 empty] | 0 | US | AM
AMSS | RU1015 | 24208 | Sheel Deer Park Refining | 1083281 | P Shell Deer Park Refining 1083281 4525026964 | 25873 | POC | USD | 253989 | 253989.4 | 2018-03-29 | 2019-01-08 |  | 253989 | 0 | 120645 |  | 5490.28 | 0 | 0 | [8 empty] | 0 | US | AM
AMSS | RU1015 | 25854 | Chevron US Products Company | 1083334 | P Chevron Products 1083334 10480585 | 25994 | POC | USD | 259859 | 259859.44 | 2018-03-29 | 2018-08-21 |  | 259859 | 0 | 129924 |  | 559.29 | 0 | 0 | [8 empty] | 0 | US | AM
IPO | RU1100 | 3822 | Samsung Heavy Industries Co., Ltd | ES34-9 | P-Samsung Heavy Industries Co. LTD-ES34-9-Two 14EJY Pumps + Motors + AGI Scope + Check Valve + Spares (ES34) | 9836 | POC | USD | 12212599 | 1202607.41 | 2017-02-08 | 2019-03-01 |  | 1202607.41 |  | 831712.01 | [12 empty] | 0 | ASIA | OE
IPO | RU1100 | 3822 | Samsung Heavy Industries Co., Ltd | ES34-9 | P-Samsung Heavy Industries Co. LTD-ES34-9-Three 25NKM Pumps + Motors + Check Valves + Spares (ES35) | 9979 | POC | USD |  | 3915389.2 | 2017-02-08 | 2019-03-01 |  | 3915389.2 |  | 2779335.4 |  |  | 257935.08 | [9 empty] | 0 | ASIA | OE
IPO | RU1100 | 3822 | Samsung Heavy Industries Co., Ltd | ES34-9 | P-Samsung Heavy Industries Co. LTD-ES34-9-Two 20CKXH Pumps + Motor + AGI Scope + Check Valve + Spares(ES36) | 9980 | POC | USD |  | 2135185 | 2017-02-08 | 2019-03-01 |  | 2135185 |  | 1599673.12 |  |  | 165575.77 | [9 empty] | 0 | ASIA | OE
IPO | RU1100 | 3822 | Samsung Heavy Industries Co., Ltd | ES34-9 | P-Samsung Heavy Industries Co. LTD-ES34-9-Spare 20CKXH Pump + Motor + Freight (ES37) | 9981 | POC | USD |  | 683526.4 | 2017-02-08 | 2019-03-01 |  | 683526.4 |  | 549987 |  |  | 82787.89 | [9 empty] | 0 | ASIA | AM
IPO | RU1100 | 3822 | Samsung Heavy Industries Co., Ltd | ES34-9 | P-Samsung Heavy Industries Co. LTD-ES34-9-Two 25KKM Pumps + Motors + AGI Scope + Check Valve + Spares (ES38) | 9982 | POC | USD |  | 2922097.22 | 2017-02-08 | 2019-03-01 |  | 2922097.22 |  | 2072680.13 |  |  | 151841.9 | [9 empty] | 0 | ASIA | OE
IPO | RU1100 | 3822 | Samsung Heavy Industries Co., Ltd | ES34-9 | P-Samsung Heavy Industries Co. LTD-ES34-9-Spare 25KKM Pump + Motor + Freight (ES39) | 9983 | POC | USD |  | 936058.99 | 2017-02-08 | 2019-03-01 |  | 936058.99 |  | 680321.03 |  |  | 75920.95 | [9 empty] | 0 | ASIA | AM
IPO | RU1100 | 3822 | Samsung Heavy Industries Co., Ltd | ES34-9 | P-Samsung Heavy Industries Co. LTD-ES34-9-Extended Warranty on 14EJY pumps (ES34) | 9984 | SL | USD |  | 42592.35 | 2017-02-08 | 2019-03-01 |  | 42592.35 | [14 empty] | 0 | ASIA | OE | 2020-02-01 | 2022-03-01
IPO | RU1100 | 3822 | Samsung Heavy Industries Co., Ltd | ES34-9 | P-Samsung Heavy Industries Co. LTD-ES34-9-Extended Warranty on all pumps not including 14EJY Pump (ES35-39) | 9985 | SL | USD |  | 375142.43 | 2017-02-08 | 2019-03-01 |  | 375142.43 | [14 empty] | 0 | ASIA | OE | 2020-09-01 | 2022-10-01
IPO | RU1100 | 4039 | Shell Offshore Inc. | ES40 | P-Shell Offshore Inc.- ES40 | 4289 | POC | USD | 2123778 | 2151128 | 2017-03-01 | 2018-06-30 |  | 2123778 |  | 1126244.82 |  |  | 66464.24 | [9 empty] | 0 | US | AM
IPO | RU1100 | 4076 | Kokosing Industrial Inc. | T803-5 | P-Kokosing Industrial-T803-5-Pull out Assemblies + Motors + Shafting + Engineering Software | 4145 | POC | USD | 2096519 | 1832987.3 | 2017-05-01 |  |  | 1832987.3 |  | 1201381.88 | [12 empty] | 104826 | US | AM
IPO | RU1100 | 4076 | Kokosing Industrial Inc. | T803-5 | P-Kokosing Industrial-T803-5-Spares | 4146 | POC | USD |  | 29627 | 2017-05-01 |  |  | 29627 |  | 28143.06 | [12 empty] | 0 | US | AM
IPO | RU1100 | 4076 | Kokosing Industrial Inc. | T803-5 | P-Kokosing Industrial-T803-5-Field Service: Educational Services | 4147 | POC | USD |  | 15707 | 2017-05-01 |  |  | 15707 |  | 13351 | [12 empty] | 0 | US | AM
IPO | RU1100 | 4076 | Kokosing Industrial Inc. | T803-5 | P-Kokosing Industrial-T803-5-Field Service: Field Measurements | 4148 | POC | USD |  | 15882 | 2017-05-01 |  |  | 15882 |  | 13500 | [12 empty] | 0 | US | AM
IPO | RU1100 | 4076 | Kokosing Industrial Inc. | T803-5 | P-Kokosing Industrial-T803-5-Field Service: Supervisory Support Services | 4149 | POC | USD |  | 52941 | 2017-05-01 |  |  | 52941 |  | 43852 | [12 empty] | 0 | US | AM
IPO | RU1100 | 4076 | Kokosing Industrial Inc. | T803-5 | P-Kokosing Industrial-T803-5-Field Service: Testing Services | 4150 | POC | USD |  | 17294 | 2017-05-01 |  |  | 17294 |  | 12540 | [12 empty] | 0 | US | AM
IPO | RU1100 | 4076 | Kokosing Industrial Inc. | T803-5 | P-Kokosing Industrial-T803-5-Extended Warranty | 4151 | SL | USD |  | 132080.7 | 2017-05-01 |  |  | 132080.7 | [14 empty] | 0 | US | AM | 2020-02-03 | 2024-08-03
IPO | RU1100 | 4077 | Kokosing Industrial Inc. | S6631-2 | P-Kokosing Industrial Inc.-S6631-2- S6631 - 6MFC Pump 1-2 + Inputs | 10770 | POC | USD | 369770 | 79712.52 | 2016-11-17 | 2018-03-23 |  | 83907.92 |  | 65267 | [12 empty] | 21638 | US | AM
IPO | RU1100 | 4077 | Kokosing Industrial Inc. | S6631-2 | P-Kokosing Industrial Inc.-S6631-2- S6632 - 8MFC Pump 1-4 + Inputs | 10771 | POC | USD |  | 283003.46 | 2016-11-17 | 2018-03-23 |  | 285862.08 |  | 204584 | [12 empty] | 0 | US | AM
IPO | RU1100 | 4084 | Jacobs Engineering Group | Taneytown Order #: E3231 Chesapeake Order #: 1244685 | P-Jacobs Engineering Group-E3231, 1244685-Three Taneytown Pumps | 9362 | POC | USD | 764412.24 | 329581.22 | 2017-03-21 | 2018-03-01 |  | 329581.22 |  | 378224 | [5 empty] | 2018-03-31 |  |  | 60441 |  | 2018-05-18 | 3001187/1217 | 0 | US | OE
IPO | RU1100 | 4084 | Jacobs Engineering Group | Taneytown Order #: E3231 Chesapeake Order #: 1244685 | P-Jacobs Engineering Group-E3231, 1244685-Chesapeake Pump 1 | 9369 | POC | USD |  | 9119.93 | 2017-03-21 | 2018-03-01 |  | 9120 | 0 | 7176.58 |  | 7176.58 |  |  |  | 2018-03-26 | [6 empty] | 0 | US | OE
IPO | RU1100 | 4084 | Jacobs Engineering Group | Taneytown Order #: E3231 Chesapeake Order #: 1244685 | P-Jacobs Engineering Group-E3231, 1244685-Chesapeake Pump 2-3 | 9370 | POC | USD |  | 23131.9 | 2017-03-21 | 2018-03-01 |  | 23132 |  | 19721.22 |  | 19721.22 |  |  |  | 2018-02-28 | [6 empty] | 0 | US | OE
IPO | RU1100 | 4084 | Jacobs Engineering Group | Taneytown Order #: E3231 Chesapeake Order #: 1244685 | P-Jacobs Engineering Group-E3231, 1244685-Chesapeake Pump 4-5 | 9371 | POC | USD |  | 20793.06 | 2017-03-21 | 2018-03-01 |  | 20793 |  | 15114.43 |  | 15114.43 |  |  |  | 2018-02-28 | [6 empty] | 0 | US | OE
IPO | RU1100 | 4084 | Jacobs Engineering Group | Taneytown Order #: E3231 Chesapeake Order #: 1244685 | P-Jacobs Engineering Group-E3231, 1244685-Chesapeake Pump 6-7 | 9372 | POC | USD |  | 21556.98 | 2017-03-21 | 2018-03-01 |  | 21556.98 |  | 13940.61 |  | 13940.61 |  |  |  | 2018-05-18 | [6 empty] | 0 | US | OE
IPO | RU1100 | 4084 | Jacobs Engineering Group | Taneytown Order #: E3231 Chesapeake Order #: 1244685 | P-Jacobs Engineering Group-E3231, 1244685-Chesapeake Pump 8-9 | 9373 | POC | USD |  | 30551.13 | 2017-03-21 | 2018-03-01 |  | 30551.13 |  | 25668.71 |  | 25668.71 |  |  |  | 2018-05-04 | [6 empty] | 0 | US | OE
IPO | RU1100 | 4084 | Jacobs Engineering Group | Taneytown Order #: E3231 Chesapeake Order #: 1244685 | P-Jacobs Engineering Group-E3231, 1244685-Chesapeake Pump 10 | 9375 | POC | USD |  | 9823.59 | 2017-03-21 | 2018-03-01 |  | 9824 |  | 6746.7 |  | 6746.7 |  |  |  | 2018-02-28 | [6 empty] | 0 | US | OE
IPO | RU1100 | 4084 | Jacobs Engineering Group | Taneytown Order #: E3231 Chesapeake Order #: 1244685 | P-Jacobs Engineering Group-E3231, 1244685-Chesapeake Pump 11-12 | 9376 | POC | USD |  | 19259.65 | 2017-03-21 | 2018-03-01 |  | 19260 |  | 13294.55 |  | 13294.55 |  |  |  | 2018-02-28 | [6 empty] | 0 | US | OE
IPO | RU1100 | 4084 | Jacobs Engineering Group | Taneytown Order #: E3231 Chesapeake Order #: 1244685 | P-Jacobs Engineering Group-E3231, 1244685-Chesapeake Pump 13-14 | 9377 | POC | USD |  | 19295.89 | 2017-03-21 | 2018-03-01 |  | 19296 |  | 13442.58 |  | 13442.58 |  |  |  | 2018-03-30 | [6 empty] | 0 | US | OE
IPO | RU1100 | 4084 | Jacobs Engineering Group | Taneytown Order #: E3231 Chesapeake Order #: 1244685 | P-Jacobs Engineering Group-E3231, 1244685-Chesapeake Pump 15-16 | 9378 | POC | USD |  | 20073.75 | 2017-03-21 | 2018-03-01 |  | 20074 |  | 13289.5 |  | 13289.5 |  |  |  | 2018-02-28 | [6 empty] | 0 | US | OE
IPO | RU1100 | 4084 | Jacobs Engineering Group | Taneytown Order #: E3231 Chesapeake Order #: 1244685 | P-Jacobs Engineering Group-E3231, 1244685-Chesapeake Pump 17-18 | 9379 | POC | USD |  | 19215.04 | 2017-03-21 | 2018-03-01 |  | 19215 |  | 13855.96 |  | 13855.96 |  |  |  | 2018-02-28 | [6 empty] | 0 | US | OE
IPO | RU1100 | 4084 | Jacobs Engineering Group | Taneytown Order #: E3231 Chesapeake Order #: 1244685 | P-Jacobs Engineering Group-E3231, 1244685-Chesapeake Pump 19-20 | 9380 | POC | USD |  | 24926.59 | 2017-03-21 | 2018-03-01 |  | 24927 |  | 19244.14 |  | 19244.14 |  |  |  | 2018-03-30 | [6 empty] | 0 | US | OE
IPO | RU1100 | 4084 | Jacobs Engineering Group | Taneytown Order #: E3231 Chesapeake Order #: 1244685 | P-Jacobs Engineering Group-E3231, 1244685-Chesapeake Pump 21 | 9381 | POC | USD |  | 20069.98 | 2017-03-21 | 2018-03-01 |  | 20070 |  | 9807.54 |  | 9807.54 |  |  |  | 2018-03-30 | [6 empty] | 0 | US | OE
IPO | RU1100 | 4084 | Jacobs Engineering Group | Taneytown Order #: E3231 Chesapeake Order #: 1244685 | P-Jacobs Engineering Group-E3231, 1244685-Chesapeake Pump 22 | 9382 | POC | USD |  | 10370.05 | 2017-03-21 | 2018-03-01 |  | 10370 |  | 6570.19 |  | 6570.19 |  |  |  | 2018-02-28 | [6 empty] | 0 | US | OE
IPO | RU1100 | 4084 | Jacobs Engineering Group | Taneytown Order #: E3231 Chesapeake Order #: 1244685 | P-Jacobs Engineering Group-E3231, 1244685-Chesapeake Pump 23-24 | 9383 | POC | USD |  | 19480.85 | 2017-03-21 | 2018-03-01 |  | 19480.85 |  | 19718.54 |  | 19718.54 |  |  |  | 2018-05-04 | [6 empty] | 0 | US | OE
IPO | RU1100 | 4084 | Jacobs Engineering Group | Taneytown Order #: E3231 Chesapeake Order #: 1244685 | P-Jacobs Engineering Group-E3231, 1244685-Chesapeake Pump 25-26 | 9384 | POC | USD |  | 32913.3 | 2017-03-21 | 2018-03-01 |  | 32913 |  | 33314.99 |  | 33314.99 |  |  |  | 2018-02-28 | [6 empty] | 0 | US | OE
IPO | RU1100 | 4084 | Jacobs Engineering Group | Taneytown Order #: E3231 Chesapeake Order #: 1244685 | P-Jacobs Engineering Group-E3231, 1244685-Chesapeake Pump 27 | 9385 | POC | USD |  | 15164.04 | 2017-03-21 | 2018-03-01 |  | 15164.04 |  | 12843.75 |  | 12843.75 |  |  |  | 2018-05-04 | [6 empty] | 0 | US | OE
IPO | RU1100 | 4084 | Jacobs Engineering Group | Taneytown Order #: E3231 Chesapeake Order #: 1244685 | P-Jacobs Engineering Group-E3231, 1244685-Chesapeake Pump 28-29 | 9386 | POC | USD |  | 28373.69 | 2017-03-21 | 2018-03-01 |  | 28374 |  | 23569.08 |  | 23569.08 |  |  |  | 2018-03-30 | [6 empty] | 0 | US | OE
IPO | RU1100 | 4084 | Jacobs Engineering Group | Taneytown Order #: E3231 Chesapeake Order #: 1244685 | P-Jacobs Engineering Group-E3231, 1244685-Chesapeake Pump 30 | 9387 | POC | USD |  | 13298.86 | 2017-03-21 | 2018-03-01 |  | 13299 |  | 9838.96 |  | 9838.96 |  |  |  | 2018-02-28 | [6 empty] | 0 | US | OE
IPO | RU1100 | 4084 | Jacobs Engineering Group | Taneytown Order #: E3231 Chesapeake Order #: 1244685 | P-Jacobs Engineering Group-E3231, 1244685-Chesapeake Pump 31-32 | 9389 | POC | USD |  | 46474.02 | 2017-03-21 | 2018-03-01 |  | 46474.02 |  | 35501.01 |  | 35501.01 |  |  |  | 2018-04-27 | [6 empty] | 0 | US | OE
IPO | RU1100 | 4084 | Jacobs Engineering Group | Taneytown Order #: E3231 Chesapeake Order #: 1244685 | P-Jacobs Engineering Group-E3231, 1244685-Chesapeake Pump 33-34 | 9390 | POC | USD |  | 29452.65 | 2017-03-21 | 2018-03-01 |  | 29453 |  | 28283.52 |  | 28283.52 |  |  |  | 2018-03-30 | [6 empty] | 0 | US | OE
IPO | RU1100 | 4084 | Jacobs Engineering Group | Taneytown Order #: E3231 Chesapeake Order #: 1244685 | P-Jacobs Engineering Group-E3231, 1244685-Chesapeake Pump Cancellation | 9392 | PIT | USD |  | 1484.33 | 2017-03-21 | 2018-03-01 |  | 1484 |  | 1551.2 |  | 1551.2 |  |  |  | 2018-03-25 | [6 empty] | 0 | US | OE
IPO | RU1100 | 4152 | WRB Refining | T806-7 | P-WRB Refining-T806-7-Pump replacement | 4157 | POC | USD | 260095 | 260095 | 2017-06-19 | 2018-01-31 |  | 260095 | [7 empty] | 2018-01-18 | [6 empty] | 0 | US | AM
IPO | RU1100 | 4158 | URS Energy & Construction | E3210-1 | P-URS Energy & Construction-E3210-1-all equipment and services on both orders. | 4934 | POC | USD | 714243 | 714243 | 2017-03-01 | 2018-07-30 |  | 714243 |  | 530457.49 | [12 empty] | 1987 | US | OE
IPO | RU1100 | 5192 | Envirolutions | T794-8 | P-Envirolutions-T794-8-6 Motor Stands + 10 Motors + 10 shafting | 5343 | POC | USD | 2271000 | 2271000 | 2016-12-29 | 2018-01-30 |  | 2271000 |  | 1826758 | [12 empty] | 0 | US | AM
IPO | RU1100 | 5194 | Equistar Chemicals | L555-9 | P-Equistar Chemicals-L555-9-30LN41 PUMP 1-9 | 5331 | POC | USD | 2936701.05 | 2876719.05 | 2015-11-16 | 2018-03-31 |  | 2876719.05 |  | 1791169 | [12 empty] | 0 | US | AM
IPO | RU1100 | 5194 | Equistar Chemicals | L555-9 | P-Equistar Chemicals-L555-9-STORAGE SERVICES | 5332 | SL | USD |  | 59981.95 | 2015-11-16 | 2018-03-31 |  | 59982 | [14 empty] | 0 | US | AM | 2016-10-03 | 2018-03-26
IPO | RU1100 | 5199 | Tooles Contracting Group | T800-1 | P-Tooles Contracting Group-T800-1-TWO 48MNZ PUMPS | 5241 | POC | USD | 2185000 | 1827592 | 2017-03-07 | 2018-01-30 |  | 1827592 |  | 801766 | [12 empty] | 109250 | US | AM
IPO | RU1100 | 5199 | Tooles Contracting Group | T800-1 | P-Tooles Contracting Group-T800-1-SPARES | 5242 | PIT | USD |  | 123671 | 2017-03-07 | 2018-01-30 |  | 123671 |  | 42048 | [12 empty] | 0 | US | AM
IPO | RU1100 | 5199 | Tooles Contracting Group | T800-1 | P-Tooles Contracting Group-T800-1-FIELD SERVICE | 5243 | POC | USD |  | 233737 | 2017-03-07 | 2018-01-30 |  | 233737 |  | 140242 | [12 empty] | 0 | US | AM
IPO | RU1100 | 5203 | Andy J Egan Co Inc. | T811-3 and T823 | P-Andy J Egan Co Inc.-T811-3 and T823-Four pull out assemblies + 4 Motors + 4 Shafting | 5239 | POC | USD | 1988641 | 1776201 | 2017-08-29 | 2018-01-31 |  | 1776201 |  | 1041638 | [12 empty] | 99432 | US | AM
IPO | RU1100 | 5203 | Andy J Egan Co Inc. | T811-3 and T823 | P-Andy J Egan Co Inc.-T811-3 and T823-Field Services | 5240 | POC | USD |  | 212440 | 2017-08-29 | 2018-01-31 |  | 212440 |  | 134610 | [12 empty] | 0 | US | AM
IPO | RU1100 | 5601 | Carter & Verplanck | S6635-6 | P-Carter & Verplanck-S6635-6 Pumps and Motors | 5681 | POC | USD | 719598 | 699966 | 2016-11-07 | 2018-06-30 |  | 699966 |  | 592454 | [12 empty] | 0 | US | AM
IPO | RU1100 | 5601 | Carter & Verplanck | S6635-6 | P-Carter & Verplanck-S6635-6-Spares | 5788 | PIT | USD |  | 19632 | 2016-11-07 | 2018-06-30 |  | 19632 |  | 14931 | [12 empty] | 0 | US | AM
IPO | RU1100 | 7434 | Ideal Electric Supply | Taneytown Order: S6651-2 Chesapeake Order: 1245991 | P-Ideal Electric Supply-S6651-2 + 1245991- 3 Taneytown Pumps | 9279 | POC | USD | 1175000 | 615727.55 | 2017-01-09 | 2018-05-09 |  | 615727.55 |  | 451993.5 | [12 empty] | 23097 | US | AM
IPO | RU1100 | 7434 | Ideal Electric Supply | Taneytown Order: S6651-2 Chesapeake Order: 1245991 | P-Ideal Electric Supply-S6651-2 + 1245991 -8 Chesapeake Pumps | 9283 | PIT | USD |  | 559272.45 | 2017-01-09 | 2018-05-09 |  | 559272.45 |  | 417424.78 | [12 empty] | 0 | US | OE
IPO | RU1100 | 7437 | Buckeye Partners | E3292 | P-Buckeye Partners-E3292- Pumps + Motors + Cans + Spares + Field Service | 12870 | POC | USD | 356737 | 356737 | 2017-11-10 | 2018-01-31 |  | 356737 | [7 empty] | 2018-01-18 | [6 empty] | 0 | US | OE
IPO | RU1100 | 8855 | Shell Chemical Appalachia | E3161-8,E3209,E3278,E3290-1,Chesapeake Portion | P-Shell Chemical -E3161-8,E3209,E3278,E3290-1,L571-E3161 Pumps plus spares | 20345 | POC | USD | 3636448.48 | 147796.33 | 2017-09-25 | 2018-05-24 |  | 147796.33 |  | 187857.79 | [12 empty] | 0 | US | OE
IPO | RU1100 | 8855 | Shell Chemical Appalachia | E3161-8,E3209,E3278,E3290-1,Chesapeake Portion | P-Shell Chemical -E3161-8,E3209,E3278,E3290-1,L571-E3162-8 E3209 Pumps plus spares | 20346 | POC | USD |  | 1604596.07 | 2017-09-25 | 2018-05-24 |  | 1604596.07 |  | 1558585 |  |  | 710412 | [9 empty] | 0 | US | OE
IPO | RU1100 | 8855 | Shell Chemical Appalachia | E3161-8,E3209,E3278,E3290-1,Chesapeake Portion | P-Shell Chemical -E3161-8,E3209,E3278,E3290-1-E3278 Pumps plus spares | 20347 | POC | USD |  | 1469362.25 | 2017-09-25 | 2018-05-24 |  | 1469362.25 |  | 1423073.16 |  |  | 710412 | [9 empty] | 0 | US | OE
IPO | RU1100 | 8855 | Shell Chemical Appalachia | E3161-8,E3209,E3278,E3290-1,Chesapeake Portion | P-Shell Chemical -E3161-8,E3209,E3278,E3290-1,L571-E3290 Pumps plus spares | 20348 | POC | USD |  | 29678.51 | 2017-09-25 | 2018-05-24 |  | 29678.51 |  | 57119.28 | [12 empty] | 0 | US | OE
IPO | RU1100 | 8855 | Shell Chemical Appalachia | E3161-8,E3209,E3278,E3290-1,Chesapeake Portion | P-Shell Chemical -E3161-8,E3209,E3278,E3290-1-E3291 Pumps plus spares | 20349 | POC | USD |  | 33227 | 2017-09-25 | 2018-05-24 |  | 33227 |  | 56257.09 | [12 empty] | 0 | US | OE
IPO | RU1100 | 8855 | Shell Chemical Appalachia | E3161-8,E3209,E3278,E3290-1,Chesapeake Portion | P-Shell Chemical -E3161-8,E3209,E3278,E3290-1,L571-Chesapeake 1222129 - 10 pumps and spares combined | 20350 | PIT | USD |  | 351788.32 | 2017-09-25 | 2018-05-24 |  | 351788.32 |  | 267516.7 | [12 empty] | 0 | US | OE
IPO | RU1100 | 8892 | MEGlobal Americas Inc. | L592-3 | P-MEGlobal Americas Inc.-L592-3 Pumps 1-7 + Motors 1-7 + Extended Warranty | 9323 | POC | USD | 2767490 | 2426212.79 | 2017-10-19 | 2018-03-31 |  | 2702961.79 | 276749 | 2048974.44 | [12 empty] | 0 | US | OE
IPO | RU1100 | 8892 | MEGlobal Americas Inc. | L592-3 | P-MEGlobal Americas Inc.-L592-3 Spare Parts | 10667 | POC | USD |  | 64528.21 | 2017-10-19 | 2018-03-31 |  | 64528.21 |  | 30299.67 | [12 empty] | 0 | US | AM
IPO | RU1100 | 8902 | Zachry Industrial | L590 | P-Zachry Industrial-L590- Two LNN Pumps + Motors + Spares | 10820 | POC | USD | 435200 | 435200 | 2017-04-21 | 2018-01-16 |  | 435200 | [7 empty] | 2018-02-18 | [6 empty] | 0 | US | OE
IPO | RU1100 | 8903 | Bechtel Infastructure | E3294-5 | P-Bechtel Infastructure-E3294-5- 9 Pumps + motors + cans + spares + testing | 10966 | POC | USD | 624886 | 624886 | 2017-06-26 | 2018-10-29 |  | 624886 |  | 647829.77 | [12 empty] | 0 | US | OE
IPO | RU1100 | 8904 | Zachry Industrial | E3296-8 | P-Zachry Industrial-E3296-8, E3307- 12ENH Pump + inputs +spares (E3296) | 12875 | POC | USD | 512049.33 | 123484.33 | 2017-11-15 | 2018-02-27 |  | 123484 | [7 empty] | 2018-02-18 | [6 empty] | 0 | US | OE
IPO | RU1100 | 8904 | Zachry Industrial | E3296-8 | P-Zachry Industrial-E3296-8, E3307- 16ENH Pump + inputs +field service (E3297) | 12876 | POC | USD |  | 157854.33 | 2017-11-15 | 2018-02-27 |  | 161854.33 | 4000 | [6 empty] | 2018-02-18 | [6 empty] | 0 | US | OE
IPO | RU1100 | 8904 | Zachry Industrial | E3296-8 | P-Zachry Industrial-E3296-8, E3307- 12ENH Pump + inputs +spares (E3298) | 12877 | POC | USD |  | 107161.34 | 2017-11-15 | 2018-02-27 |  | 107161 | [7 empty] | 2018-02-18 | [6 empty] | 0 | US | OE
IPO | RU1100 | 8904 | Zachry Industrial | E3296-8 | P-Zachry Industrial-E3296-8, E3307- 12ENH Pump + inputs +spares (E3307) | 12878 | POC | USD |  | 119550 | 2017-11-15 | 2018-02-27 |  | 119550 | [7 empty] | 2018-02-18 | [6 empty] | 0 | US | OE
IPO | RU1100 | 8905 | Bridgetex Pipeline Co. | E3299 | P-Bridgetex Pipeline-E3299-Pump | 9122 | POC | USD | 366550 | 366550 | 2017-09-07 | 2018-01-12 |  | 366550 | [7 empty] | 2018-01-01 | [6 empty] | 0 | US | AM
IPO | RU1100 | 8909 | Pepper-Lawson | S6723 | P-Pepper Lawson-S6723 & 1264898-Two Taneytown Pumps + Motors + Seal Water Stations + Field Service | 13442 | POC | USD | 575000 | 409407.99 | 2017-10-04 | 2018-05-18 |  | 409407.99 |  | 392630 | [12 empty] | 11058 | US | AM
IPO | RU1100 | 8909 | Pepper-Lawson | S6723 | P-Pepper Lawson-S6723 & 1264898- Taneytown Spare Parts | 13443 | PIT | USD |  | 41681.07 | 2017-10-04 | 2018-05-18 |  | 41681.07 |  | 37096 | [12 empty] | 0 | US | AM
IPO | RU1100 | 8909 | Pepper-Lawson | S6723 | P-Pepper Lawson-S6723 & 1264898- Two Chesapeake Pumps + Spare Parts | 13444 | PIT | USD |  | 123910.94 | 2017-10-04 | 2018-05-18 |  | 123910.94 |  | 49457.28 |  | 0 | [10 empty] | 0 | US | OE
IPO | RU1100 | 8912 | Marketlink LLC | E3302 | P-Marketlink,LLC-E3302-Pump+Motor+Can+Spares+Field Service | 11511 | POC | USD | 314147 | 314147 | 2017-08-22 | 2018-03-08 |  | 314147 |  | 276761.32 | [5 empty] | 2018-04-30 | [6 empty] | 0 | US | OE
IPO | RU1100 | 8918 | Minera Escondida | E3303 | P-Minera Escondida-E3303-Three Pumps + Motors + Spares + Seismic Restraint + VFD's | 13942 | POC | USD | 3056085.3 | 2931385.3 | 2017-07-31 | 2018-06-01 |  | 2931385.3 |  | 1965748.57 | [12 empty] | 46900 | LA | OE
IPO | RU1100 | 8918 | Minera Escondida | E3303 | P-Minera Escondida-E3303-Field Services | 13943 | POC | USD |  | 124700 | 2017-07-31 | 2018-06-01 |  | 124700 |  | 124700 | [12 empty] | 0 | LA | AM
IPO | RU1100 | 8920 | Jacobs Engineering Group | ES43-8, E3312-7 | P-Jacobs Engineering Group-ES43-8, E3312-7, E3365-Four 3 stage pumps + Motors + Accessories + Submersible Valves + Cable (ES43) | 13447 | POC | USD | 7399164.3 | 821323.11 | 2017-09-29 | 2018-10-17 |  | 818493.83 |  | 609688.26 | [12 empty] | 0 | US | OE
IPO | RU1100 | 8920 | Jacobs Engineering Group | ES43-8, E3312-7 | P-Jacobs Engineering Group-ES43-8, E3312-7, E3365-Eight 5 stage pumps + Motors + Accessories + Submersible Valves + transport track (ES44) | 13648 | POC | USD |  | 3301689.06 | 2017-09-29 | 2018-10-17 |  | 3290315.47 |  | 2237705.17 |  |  | 87382.49 | [9 empty] | 0 | US | OE
IPO | RU1100 | 8920 | Jacobs Engineering Group | ES43-8, E3312-7 | P-Jacobs Engineering Group-ES43-8, E3312-7, E3365-Spare 3 stage pump + Motor + Submersible Valves + Cable (ES45) | 13650 | POC | USD |  | 134587.52 | 2017-09-29 | 2018-10-17 |  | 134123.9 |  | 147867.8 | [12 empty] | 0 | US | OE
IPO | RU1100 | 8920 | Jacobs Engineering Group | ES43-8, E3312-7 | P-Jacobs Engineering Group-ES43-8, E3312-7, E3365-Spare 5 stage Submersible Pump + Motor + Submersible Valve (ES46) | 13651 | POC | USD |  | 309182.97 | 2017-09-29 | 2018-10-17 |  | 308117.9 |  | 202836.42 | [12 empty] | 0 | US | OE
IPO | RU1100 | 8920 | Jacobs Engineering Group | ES43-8, E3312-7 | P-Jacobs Engineering Group-ES43-8, E3312-7, E3365-Two 12EHL 5 stage Pumps + Motors + Accessories + Submersible Valves (ES47) | 13654 | POC | USD |  | 798032.66 | 2017-09-29 | 2018-10-17 |  | 795283.62 |  | 561329.84 |  |  | 21845.62 | [9 empty] | 0 | US | OE
IPO | RU1100 | 8920 | Jacobs Engineering Group | ES43-8, E3312-7 | P-Jacobs Engineering Group-ES43-8, E3312-7, E3365-Two 5ELM API Pumps + Motors + Suction Cans (E3312) | 13656 | POC | USD |  | 346614.48 | 2017-09-29 | 2018-10-17 |  | 345420.47 |  | 181245.85 | [12 empty] | 0 | US | OE
IPO | RU1100 | 8920 | Jacobs Engineering Group | ES43-8, E3312-7 | P-Jacobs Engineering Group-ES43-8, E3312-7, E3365-Two 6EKY Pumps + Motors + Suction Cans (E3313) | 13657 | POC | USD |  | 179468.57 | 2017-09-29 | 2018-10-17 |  | 178850.34 |  | 173843.53 | [12 empty] | 0 | US | OE
IPO | RU1100 | 8920 | Jacobs Engineering Group | ES43-8, E3312-7 | P-Jacobs Engineering Group-ES43-8, E3312-7, E3365-Two 6JKYH Pumps + Motors + Suction Cans (E3314) | 13658 | POC | USD |  | 368106.83 | 2017-09-29 | 2018-10-17 |  | 366838.78 |  | 280063.54 | [12 empty] | 0 | US | OE
IPO | RU1100 | 8920 | Jacobs Engineering Group | ES43-8, E3312-7 | P-Jacobs Engineering Group-ES43-8, E3312-7, E3365-Two 5ELM Pumps + Motors (E3315) | 13670 | POC | USD |  | 235158.08 | 2017-09-29 | 2018-10-17 |  | 234348.02 |  | 190831.63 | [12 empty] | 0 | US | OE
IPO | RU1100 | 8920 | Jacobs Engineering Group | ES43-8, E3312-7 | P-Jacobs Engineering Group-ES43-8, E3312-7, E3365-Two 1HPX7A Desio Sourced Pump + Inputs (E3316/E3365) | 13671 | POC | USD |  | 138255.59 | 2017-09-29 | 2018-10-17 |  | 163223 |  | 28446.3 |  |  | 12129.77 | [9 empty] | 0 | US | OE
IPO | RU1100 | 8920 | Jacobs Engineering Group | ES43-8, E3312-7 | P-Jacobs Engineering Group-ES43-8, E3312-7, E3365-Two 8PVSM12 Desio Sourced Pump + Inputs (E3317) | 13672 | POC | USD |  | 113656.29 | 2017-09-29 | 2018-10-17 |  | 113264.77 |  | 103434 | [12 empty] | 0 | US | OE
IPO | RU1100 | 8920 | Jacobs Engineering Group | ES43-8, E3312-7 | P-Jacobs Engineering Group-ES43-8, E3312-7, E3365-Two 10ELM Submersible Pumps + Motors + Accessories + Submersible Valves (ES48) | 13952 | POC | USD |  | 641798.13 | 2017-09-29 | 2018-10-17 |  | 650884.2 |  | 476002.59 | [12 empty] | 0 | US | OE
IPO | RU1100 | 9421 | Thieneman Construction | S6758 | P-Thieneman Construction-S6758- Two Pumps + Motors + Shafting + Spares | 12924 | POC | USD | 370000 | 332328 | 2017-09-27 | 2018-07-10 |  | 332328 |  | 261212.36 | [12 empty] | 13652 | US | AM
IPO | RU1100 | 9421 | Thieneman Construction | S6758 | P-Thieneman Construction-S6758- Field Service | 12925 | POC | USD |  | 37672 | 2017-09-27 | 2018-07-10 |  | 37672 |  | 29000 | [12 empty] | 0 | US | AM
IPO | RU1100 | 10502 | MEB General Contractors | S6761 | P-MEB General Contractors-S6761-Pumps + Motors + Field Service | 13157 | POC | USD | 1963000 | 1899058 | 2017-11-17 | 2018-09-25 |  | 1899058 |  | 1503184 | [12 empty] | 66900 | US | OE
IPO | RU1100 | 10502 | MEB General Contractors | S6761 | P-MEB General Contractors-S6761-Spare Parts | 13158 | PIT | USD |  | 63942 | 2017-11-17 | 2018-09-25 |  | 63942 |  | 52098 | [12 empty] | 0 | US | AM
IPO | RU1100 | 10512 | Steve P Rados, Inc | T816 | P-Steve P Rados, Inc-T816-Two Motors + Witness Testing + Field Service | 11521 | POC | USD | 823579 | 823579 | 2017-09-19 | 2018-09-30 |  | 823579 |  | 578502 | [12 empty] | 47436 | US | AM
IPO | RU1100 | 12824 | Bechtel Infastructure | L608 | P-Bechtel Infastructure-L608 & 1275412-Taneytown Pumps + Motors + Spare Parts | 12829 | POC | USD | 408432 | 343092 | 2017-11-03 | 2018-11-01 |  | 343092 |  | 288773.17 | [12 empty] | 0 | US | OE
IPO | RU1100 | 12824 | Bechtel Infastructure | L608 | P-Bechtel Infastructure-L608 & 1275412-Two Chesapeake Demineralizing Pumps | 12830 | POC | USD |  | 24150 | 2017-11-03 | 2018-11-01 |  | 24150 |  | 17629.5 |  | 0 | [10 empty] | 0 | US | OE
IPO | RU1100 | 12824 | Bechtel Infastructure | L608 | P-Bechtel Infastructure-L608 & 1275412-Two Chesapeake Service Water Pumps | 12831 | POC | USD |  | 20274 | 2017-11-03 | 2018-11-01 |  | 20274 |  | 17030.16 |  | 0 | [10 empty] | 0 | US | OE
IPO | RU1100 | 12824 | Bechtel Infastructure | L608 | P-Bechtel Infastructure-L608 & 1275412-Two Chesapeake Evap Cooler Makeup Pumps | 12832 | POC | USD |  | 20916 | 2017-11-03 | 2018-11-01 |  | 20916 |  | 16523.64 |  | 0 | [10 empty] | 0 | US | OE
IPO | RU1100 | 12833 | Plains Marketing | E3320 | P-Plains Marketing-E3320-Two Pumps + Two Motors + Two Suction Cans | 12836 | POC | USD | 649992 | 649992 | 2017-11-08 | 2018-04-06 |  | 649992 |  | 540572.64 | [12 empty] | 0 | US | OE
IPO | RU1100 | 12864 | Husky Oil Operations | E3318 | P-Husky Oil Operations-E3318- Pump + Motor + Suction can | 13164 | POC | USD | 389075 | 389075 | 2017-11-15 | 2018-03-22 |  | 389075 |  | 294603.66 | [12 empty] | 0 | CANADA | OE
IPO | RU1100 | 13714 | Plains Marketing | E3322 | P-Plains Marketing-E3322-Three Pumps + Three Motors + Three Suction Cans | 13721 | POC | USD | 984402 | 984402 | 2017-11-15 | 2018-04-16 |  | 984402 |  | 781157.77 | [12 empty] | 0 | US | OE
IPO | RU1100 | 15091 | Meglobal Americas, Inc. | E3282-3 | P-Meglobal Americas, Inc.-E3282-3- E3283 PUMPS + Inputs | 17531 | POC | USD | 362230.98 | 201139.07 | 2017-11-28 | 2018-03-29 |  | 202149.82 |  | 119968.13 | [5 empty] | 2018-01-03 | [6 empty] | 0 | US | OE
IPO | RU1100 | 15091 | Meglobal Americas, Inc. | E3282-3 | P-Meglobal Americas, Inc.-E3282-3- E3282 PUMP + Input | 17534 | POC | USD |  | 98145.09 | 2017-11-28 | 2018-03-29 |  | 98145.09 |  | 127679.41 | [5 empty] | 2018-03-31 | [6 empty] | 0 | US | OE
IPO | RU1100 | 15091 | Meglobal Americas, Inc. | E3282-3 | P-Meglobal Americas, Inc.-E3282-3 & 1260720- Chesapeake Pumps + immaterial warranty and spares | 20209 | POC | USD |  | 61936.07 | 2017-11-28 | 2018-03-29 |  | 61936.07 |  | 36665.1 |  | 36665.1 |  |  |  | 2018-04-13 | [6 empty] | 0 | US | OE
IPO | RU1100 | 15106 | Marathon Petroleum Corporation | E003300 | P-Marathon Petroleum-E3300-1 | 15469 | POC | USD | 378915 | 378915 | 2017-10-17 | 2018-01-10 |  | 378915 | [7 empty] | 2018-02-18 | [6 empty] | 0 | US | OE
IPO | RU1100 | 15107 | CB&I, LLC | E3279-80 | P-CB&I LLC-E3279-80-TannyTown - E279 pumps + Motor + Spares | 17835 | POC | USD | 539910 | 110680 | 2017-07-25 | 2018-01-19 |  | 110680 | [7 empty] | 2017-12-17 | [6 empty] | 0 | US | OE
IPO | RU1100 | 15107 | CB&I, LLC | E3279-80 | P-CB&I LLC-E3279-80-TannyTown - E280 pumps + Motor + Spares | 17837 | POC | USD |  | 220568 | 2017-07-25 | 2018-01-19 |  | 220568 | [7 empty] | 2017-12-17 | [6 empty] | 0 | US | OE
IPO | RU1100 | 15107 | CB&I, LLC | E3279-80 | P-CB&I LLC-E3279-80-Chessepeak-E279-280 pumps + Motor + Spares | 17838 | POC | USD |  | 114296.8 | 2017-07-25 | 2018-01-19 |  | 114297 |  | 105167.6 |  | 105167.6 |  |  |  | 2017-12-21 | [6 empty] | 0 | US | OE
IPO | RU1100 | 15107 | CB&I, LLC | E3279-80 | P-CB&I LLC-E3279-80-Chessepeak-E279-280 pumps + Motor + Spares | 17839 | POC | USD |  | 94365.2 | 2017-07-25 | 2018-01-19 |  | 94365 |  | 96561 |  | 96561 |  |  |  | 2018-03-30 | [6 empty] | 0 | US | OE
IPO | RU1100 | 15114 | Archer Western Construction | S006675 | P-Archer Wester Construction-S6675-6-Pumps on both orders + field service | 15848 | POC | USD | 495000 | 464205 | 2017-03-11 | 2018-01-02 |  | 464205 |  | 359441.51 | [12 empty] | 18298 | US | OE
IPO | RU1100 | 15114 | Archer Western Construction | S006675 | P-Archer Wester Construction-S6675-6-Spares on S6675 | 17812 | PIT | USD |  | 15235 | 2017-03-11 | 2018-01-02 |  | 15235 |  | 7499.42 | [5 empty] | 2018-02-24 | [6 empty] | 0 | US | AM
IPO | RU1100 | 15114 | Archer Western Construction | S006675 | P-Archer Wester Construction-S6675-6-Spares on S6676 | 22579 | PIT | USD |  | 15560 | 2017-03-11 | 2018-01-02 |  | 15560 |  | 10099.67 | [12 empty] | 0 |  | AM
IPO | RU1100 | 15119 | Zachry Industrial LLC | E3293, E3237 | P-Zachry Industrial Inc.-E3237, E3293-Taneytown - E3237 All Components including Boiler Blowdown Sump Pumps with Cans | 17848 | POC | USD | 434800 | 233630 | 2017-06-30 | 2018-02-08 |  | 233630 |  | 139500 | [5 empty] | 2017-11-15 | [6 empty] | 0 | US | OE
IPO | RU1100 | 15119 | Zachry Industrial LLC | E3293, E3237 | P-Zachry Industrial Inc.-E3237, E3293-Taneytown - E3293 All components including Injection Well Sump Pumps | 17849 | POC | USD |  | 150640 | 2017-06-30 | 2018-02-08 |  | 150640 |  | 112152.12 | [12 empty] | 0 | US | OE
IPO | RU1100 | 15119 | Zachry Industrial LLC | E3293, E3237 | P-Zachry Industrial Inc.-E3237, E3293-Chesapeake - Reclaimed Water Intake Pumps | 17850 | POC | USD |  | 50530 | 2017-06-30 | 2018-02-08 |  | 50530 |  | 40692 |  | 40692 |  |  |  | 2017-12-29 | [6 empty] | 0 | US | OE
IPO | RU1100 | 16687 | Florida Power & LIght Company | E3328 | P - Florida Power & Light Company - E3328 8 Stage Bowl Assembly | 16766 | POC | USD | 292601 | 292601 | 2017-11-30 | 2018-05-28 |  | 292601 |  | 202149.67 | [12 empty] | 0 | US | AM
IPO | RU1100 | 18676 | Magellan Pipeline Company | E3243 | P-Magellan Pipeline Co. LLC-E3243-Vertical Turbine Pumps | 18880 | POC | USD | 692950 | 672232 | 2017-03-08 | 2018-02-07 |  | 692950 | 20718 | [6 empty] | 2018-02-28 | [6 empty] | 0 | US | OE
IPO | RU1100 | 18677 | CB&I Inc. | L616 | P - CB&I Inc.-L616-Closed Cooling Water Pumps | 19081 | POC | USD | 263530 | 263530 | 2017-12-27 | 2018-12-31 |  | 263530 |  | 203415.13 | [12 empty] | 0 | US | OE
IPO | RU1100 | 18678 | CB&I, LLC | E3329-34 | P-CB&I LLC-E3329-Manufacture and delivery of Pump and Spares | 19976 | POC | USD | 1672978 | 292126 | 2017-12-12 | 2019-12-09 |  | 292126 |  | 310639.86 |  |  | 17847.3 | [9 empty] | 0 | US | OE
IPO | RU1100 | 18678 | CB&I, LLC | E3329-34 | P-CB&I LLC-E3330-Manufacture and Delivery of Pump and Spares | 19977 | POC | USD |  | 91007 | 2017-12-12 | 2019-12-09 |  | 91007 |  | 109296.61 | [12 empty] | 0 | US | OE
IPO | RU1100 | 18678 | CB&I, LLC | E3329-34 | P-CB&I LLC-E3331-Manufacture and Delivery of Pump and Spares | 19978 | POC | USD |  | 312311 | 2017-12-12 | 2019-12-09 |  | 312311 |  | 323367.19 |  |  | 17847.3 | [9 empty] | 0 | US | OE
IPO | RU1100 | 18678 | CB&I, LLC | E3329-34 | P-CB&I LLC-E3332-Manufacture and delivery of Pump and Spares | 19979 | POC | USD |  | 116600 | 2017-12-12 | 2019-12-09 |  | 116600 |  | 134271.51 | [12 empty] | 0 | US | OE
IPO | RU1100 | 18678 | CB&I, LLC | E3329-34 | P-CB&I LLC-E3333-Manufacture and Delivery of Pump and Spares | 19980 | POC | USD |  | 604032 | 2017-12-12 | 2019-12-09 |  | 604032 |  | 650755.74 | [12 empty] | 0 | US | OE
IPO | RU1100 | 18678 | CB&I, LLC | E3329-34 | P-CB&I LLC-E3334-Manufacture and Delivery of Pump and Spares | 19981 | POC | USD |  | 256902 | 2017-12-12 | 2019-12-09 |  | 256902 |  | 283939.54 |  |  | 16292.8 | [9 empty] | 0 | US | OE
IPO | RU1100 | 18679 | Bar Constructors Inc. | S6790, S6791, S6792, S6796 | P-Bar Constructors Inc.-S6790-2, S6796-Horizontal Split Case Pumps | 19063 | PIT | USD | 5799999.52 | 5531020.52 | 2017-12-22 | 2019-02-16 |  | 5531020.52 |  | 4141706 | [12 empty] | 200865 | US | OE
IPO | RU1100 | 18679 | Bar Constructors Inc. | S6790, S6791, S6792, S6796 | P-Bar Constructors Inc.-S6790-2, S6796-Horizontal Split Case Pumps Field Service | 19064 | POC | USD |  | 127680 | 2017-12-22 | 2019-02-16 |  | 127680 |  | 127680 | [12 empty] | 0 | US | AM
IPO | RU1100 | 18679 | Bar Constructors Inc. | S6790, S6791, S6792, S6796 | P-Bar Constructors Inc.-S6790-2, S6796-Horizontal Split Case Pumps Extended Warranty | 19065 | SL | USD |  | 141299.48 | 2017-12-22 | 2019-02-16 |  | 141299 | [14 empty] | 0 | US | OE
IPO | RU1100 | 18753 | Fluor Enterprises Inc Agent for Blanchard Refining Company LLC | E3194 | P-Fluor Enterprise-E3194 | 18994 | POC | USD | 278661 | 278661 | 2016-07-15 | 2018-09-30 |  | 278661 | [7 empty] | 2017-12-17 | [6 empty] | 0 | US | OE
IPO | RU1100 | 19036 | WF MAGANN CORP | T000789 | P-WF Magann-T789-54MCS Pump upgrade - 1 stage | 20691 | POC | USD | 692587 | 615230 | 2016-12-21 | 2018-01-24 |  | 615230 |  | 597698.7 | [12 empty] | 10866 | US | AM
IPO | RU1100 | 19036 | WF MAGANN CORP | T000789 | P-WF Magann-T789-Spare Parts | 20692 | POC | USD |  | 77357 | 2016-12-21 | 2018-01-24 |  | 77357 |  | 56452.12 | [5 empty] | 2018-02-01 | [6 empty] | 0 | US | AM
IPO | RU1100 | 19200 | PSI Prolew Inc | T000820 | P-PSI Prolew Inc-T820-Pump | 20437 | POC | USD | 396694 | 396694 | 2018-01-05 | 2018-12-28 |  | 396694 |  | 310231 | [12 empty] | 0 | US | AM
IPO | RU1100 | 19248 | Process Machinery Inc | L000617 | P-Process Machinery Inc-L617- Three Pumps (entire PO) | 20595 | POC | USD | 336588.99 | 336588.99 | 2017-12-28 | 2018-08-07 |  | 336588.99 |  | 272773.28 | [12 empty] | 0 | US | OE
IPO | RU1100 | 19337 | Carter & Verplanck Inc | S006585 and S006586 | P-Carter & Verplanck-S6585-6 Pumps + inputs for both orders | 20467 | POC | USD | 5073172 | 5073172 | 2016-06-30 | 2018-03-31 |  | 5073172 | [7 empty] | 2017-09-30 | [6 empty] | 0 | US | OE
IPO | RU1100 | 20129 | Noble Energy | E3263-9 | P-Noble Energy-E3263-E3269-E-3263-9/1257383-PBE-Chesapeake Portion Tag 6200 | 20721 | POC | USD | 1351010.5864 | 33562.5 | 2017-05-15 | 2018-03-26 |  | 33562.5 | 0 | 29720.96 |  | 29720.96 |  |  |  |  | 28531 | [5 empty] | 0 | US | OE
IPO | RU1100 | 20129 | Noble Energy | E3263-9 | P-Noble Energy-E3263-E3269-E-3263-9/1257383-PBE-Chesapeake Portion Tag 6390A/B | 20722 | POC | USD |  | 120277 | 2017-05-15 | 2018-03-26 |  | 120277 | 0 | 127311.29 |  | 127311.29 |  |  |  |  | 126403.72 | [5 empty] | 0 | US | OE
IPO | RU1100 | 20129 | Noble Energy | E3263-9 | P-Noble Energy-E3263-E3269-E-3263-9/1257383-PBE-Chesapeake Portion Tag 6800A/B | 20723 | POC | USD |  | 102210 | 2017-05-15 | 2018-03-26 |  | 102210 | 0 | 56193.85 |  | 56193.85 |  |  |  |  | 55491 | [5 empty] | 0 | US | OE
IPO | RU1100 | 20129 | Noble Energy | E3263-9 | P-Noble Energy-E3263-E3269-E-3263-9/1257383-PBH-6260A/B Taneytown order E3263-4 | 20724 | POC | USD |  | 185200 | 2017-05-15 | 2018-03-26 |  | 185200 |  | 136170.19 | [5 empty] | 2018-01-19 | [6 empty] | 0 | US | OE
IPO | RU1100 | 20129 | Noble Energy | E3263-9 | P-Noble Energy-E3263-E3269-E-3263-9/1257383-PBH-6360A/B Taneytown order E3265-6 | 20725 | POC | USD |  | 222395.86 | 2017-05-15 | 2018-03-26 |  | 228178 | 5782.14 | 140563.35 | [5 empty] | 2018-01-19 | [6 empty] | 0 | US | OE
IPO | RU1100 | 20129 | Noble Energy | E3263-9 | P-Noble Energy-E3263-E3269-E-3263-9/1257383-PBH-6370A/B-Taneytown order E3267 | 20726 | POC | USD |  | 187944.21 | 2017-05-15 | 2018-03-26 |  | 193395 | 5450.79 | 98831.4 | [5 empty] | 2018-01-19 | [6 empty] | 0 | US | OE
IPO | RU1100 | 20129 | Noble Energy | E3263-9 | P-Noble Energy-E3263-E3269-E-3263-9/1257383-PBH-6380A/B/C Taneytown Order E3268-9 | 20727 | POC | USD |  | 315747.4982 | 2017-05-15 | 2018-03-26 |  | 315747.4982 |  | 196872.49 | [5 empty] | 2018-01-19 | [6 empty] | 0 | US | OE
IPO | RU1100 | 20129 | Noble Energy | E3263-9 | P-Noble Energy-E3263-E3269-E-3263-9/1257383-PBE-Chesapeake Portion 6265A/B | 20739 | POC | USD |  | 70357.0588 | 2017-05-15 | 2018-03-26 |  | 70357.0588 | 0 | 52214.63 |  | 52214.63 |  |  |  |  | 51376.41 | [5 empty] | 0 | US | OE
IPO | RU1100 | 20129 | Noble Energy | E3263-9 | P-Noble Energy-E3263-E3269-E-3263-9/1257383-PBE-Chesapeake Portion Tag 6985 | 20740 | POC | USD |  | 33587.5294 | 2017-05-15 | 2018-03-26 |  | 33587.5294 | 0 | 24623.4 |  | 24973.4 |  |  |  |  | 17442.4 | [5 empty] | 0 | US | OE
IPO | RU1100 | 20129 | Noble Energy | E3263-9 | P-Noble Energy-E3263-E3269-E-3263-9/1257383-PBA-Chesapeake Tag 6295 | 20741 | POC | USD |  | 68496 | 2017-05-15 | 2018-03-26 |  | 68496 | 0 | 63146.45 |  | 56327 | [10 empty] | 0 | US | OE
IPO | RU1100 | 20899 | CB&I, Inc. | E3336-7 & 1280131 | P-CB&I Inc-E3336-7 & 1280131- E3336 Pumps + Motors + Spares + Freight | 21395 | POC | USD | 472420 | 115976 | 2018-01-05 | 2018-11-01 |  | 115976 |  | 118744.53 | [12 empty] | 0 | US | OE
IPO | RU1100 | 20899 | CB&I, Inc. | E3336-7 & 1280131 | P-CB&I Inc-E3336-7 & 1280131 - E3337 Pumps + Motors + Spares + Freight | 21781 | POC | USD |  | 136392 | 2018-01-05 | 2018-11-01 |  | 136392 |  | 150344.32 | [12 empty] | 0 |  | OE
IPO | RU1100 | 20899 | CB&I, Inc. | E3336-7 & 1280131 | P-CB&I Inc-E3336-7 & 1280131- Chesapeake 1280131_1 ESP3 Pump + Base+Test Performance | 22217 | POC | USD |  | 15552 | 2018-01-05 | 2018-11-01 |  | 15552 |  | 13841.28 |  | 0 | [10 empty] | 0 | US | OE
IPO | RU1100 | 20899 | CB&I, Inc. | E3336-7 & 1280131 | P-CB&I Inc-E3336-7 & 1280131 - Chesapeake 1280131_2 & 3: Pump + Base + Test Performance | 22218 | POC | USD |  | 204500 | 2018-01-05 | 2018-11-01 |  | 204500 |  | 177555 |  | 0 | [10 empty] | 0 | US | OE
IPO | RU1100 | 20902 | Buckeye Partners LP | E3345 | P-Buckeye Partners LP-E3345-Four pumps with Motors and Suction Cans | 21363 | POC | USD | 469312 | 469312 | 2018-01-12 | 2018-08-02 |  | 469312 |  | 370216 | [12 empty] | 0 | US | OE
IPO | RU1100 | 20903 | Jacobs Engineering Group | L619 | P-Jacobs Engineering Group-L619-Two water booster pumps + motors | 22212 | POC | USD | 318218 | 318218 | 2018-02-06 | 2018-09-12 |  | 318218 |  | 236758.82 | [12 empty] | 0 | US | OE
IPO | RU1100 | 21438 | KPL Northern States LLC | E3346 | P-KPL Northern States LLC-E3346 | 22236 | POC | USD | 380665 | 380665 | 2018-02-01 | 2018-07-17 |  | 380665 |  | 197838.89 | [12 empty] | 0 | US | OE
IPO | RU1100 | 21916 | AMEC Foster Wheeler USA | E3347 | P-AMEC Foster Wheeler USA-E3347 | 21994 | POC | USD | 506354 | 506354 | 2018-01-31 | 2018-11-19 |  | 506354 |  | 378892 |  |  | 27244.14 | [9 empty] | 0 | US | OE
IPO | RU1100 | 22540 | MVP Terminalling LLC | E3348 | P-MVP Terminalling LLC-E3348 pump + motor + suction can & soleplate | 22541 | POC | USD | 352175 | 345025 | 2018-02-08 | 2018-08-08 |  | 345025 |  | 241304.32 | [12 empty] | 0 | US | OE
IPO | RU1100 | 22540 | MVP Terminalling LLC | E3348 | P-MVP Terminalling LLC-E3348 spares | 22568 | PIT | USD |  | 7150 | 2018-02-08 | 2018-08-08 |  | 7150 |  | 3871.26 | [12 empty] | 0 | US | AM
IPO | RU1100 | 23220 | Burns & Mcdonnell | E3350-1 | P-Burns & Mcdonnell-E3350-1-All pumps + inputs | 23301 | POC | USD | 529068.89 | 529068.89 | 2018-02-28 | 2018-11-01 |  | 529068.89 |  | 400074 | [12 empty] | 0 | US | OE
IPO | RU1100 | 23244 | Syncrude Canada Ltd. | R96241 | P-Syncrude Canada LTD.-R96241 | 23302 | POC | CAD | 1532349.7983 | 1231426.24 | 2018-02-23 | 2018-08-15 |  | 1532349.7983 |  | 471416 | [9 empty] | 0 |  |  | 0 | CANADA | AM
IPO | RU1100 | 24068 | Exxonmobil Oil Corp | E3354 | P-Exxonmobil Oil Corp-E3354 | 24069 | POC | USD | 309793.12 | 309793.12 | 2018-03-23 | 2018-10-02 |  | 309793.12 |  | 225475 | [12 empty] | 0 | US | OE
IPO | RU1100 | 27260 | Zachry Industrial Inc | E3358 and E3359 | P-Zachry Industrial Inc-E3358-9 | 27267 | POC | USD | 255604 | 255604 | 2018-04-17 | 2018-11-01 |  | 255604 | [14 empty] | 0
IPO | RU1100 | 27364 | AMEC Foster Wheeler | E3360-3 | P-AMEC Foster Wheeler-E3360-3: E3360 three pumps with freight | 27365 | POC | USD | 1926750 | 515176.5 | 2018-04-25 | 2018-10-17 |  | 515176.5 | [14 empty] | 0
IPO | RU1100 | 27364 | AMEC Foster Wheeler | E3360-3 | P-AMEC Foster Wheeler-E3360-3: E3361 three pumps with freight | 27698 | POC | USD |  | 773641.5 | 2018-04-25 | 2018-10-17 |  | 773641.5 | [14 empty] | 0
IPO | RU1100 | 27364 | AMEC Foster Wheeler | E3360-3 | P-AMEC Foster Wheeler-E3360-3: E3362 two pumps with freight | 27699 | POC | USD |  | 444750 | 2018-04-25 | 2018-10-17 |  | 444750 | [14 empty] | 0
IPO | RU1100 | 27364 | AMEC Foster Wheeler | E3360-3 | P-AMEC Foster Wheeler-E3360-3: E3363 three pumps with freight | 27700 | POC | USD |  | 193182 | 2018-04-25 | 2018-10-17 |  | 193182 | [14 empty] | 0
IPO | RU1100 | 27572 | Burns & McDonnell | E3364 | P-Burns & McDonnell-E3364 Taneytown | 27573 | POC | USD | 939707 | 920950 | 2018-04-25 | 2019-02-15 |  | 920950 | [14 empty] | 0
IPO | RU1100 | 27572 | Burns & McDonnell | E3364 | P-Burns & McDonnell-E3364 Chesapeake Portion 1290371 | 27589 | PIT | USD |  | 18757 | 2018-04-25 | 2019-02-15 |  | 18757 | [14 empty] | 0
IPO | RU1100 | 28336 | Jacobs Field Services | E3367 | P-Jacobs Field Services-E3367 | 28337 | POC | USD | 749595 | 749595 | 2018-05-23 | 2019-02-28 |  | 749595 | [14 empty] | 0
IPO | RU1100 | 28342 | Jacobs Field Services | E3368 | P-Jacobs Field Services-E3368 | 28343 | POC | USD | 719510 | 719510 | 2018-05-23 | 2019-02-28 |  | 719510 | [14 empty] | 0
IPO | RU1105 | 10414 | Overland Contracting Inc. | NH00047, NH00048, NH00049, & NH00058 | P-Overland Contracting Inc.-NH00047-49, NH00058- 12EHMPump 1 + Motor + Barrel + Freight +Spares + Field Service (NH47) | 11535 | POC | USD | 414766 | 100109 | 2017-09-14 | 2018-06-29 |  | 100109 | 0 | [6 empty] | 2018-03-26 |  |  | 0 |  |  |  | 14890 | US | OE
IPO | RU1105 | 10414 | Overland Contracting Inc. | NH00047, NH00048, NH00049, & NH00058 | P-Overland Contracting Inc.-NH00047-49, NH00058- 16ENH Pump 1 + Motor + Barrel + Freight +Spares + Field Service (NH48) | 11564 | POC | USD |  | 135365 | 2017-09-14 | 2018-06-29 |  | 135365 | 0 | [6 empty] | 2018-03-26 | [6 empty] | 0 | US | OE
IPO | RU1105 | 10414 | Overland Contracting Inc. | NH00047, NH00048, NH00049, & NH00058 | P-Overland Contracting Inc.-NH00047-49, NH00058- 12EMM Pumps 1-2 + Motors + Freight +Spares + Field Service (NH49) | 11565 | POC | USD |  | 92146.2 | 2017-09-14 | 2018-06-29 |  | 92146 | 0 | [6 empty] | 2018-02-26 | [6 empty] | 0 | US | OE
IPO | RU1105 | 10414 | Overland Contracting Inc. | NH00047, NH00048, NH00049, & NH00058 | P-Overland Contracting Inc.-NH00047-49, NH00058- 12EHL Pumps + Motors + Freight +Spares + Field Service (NH58) | 17820 | POC | USD |  | 87146 | 2017-09-14 | 2018-06-29 |  | 87146 | 0 | [6 empty] | 2018-04-27 | [6 empty] | 0 | US | OE
IPO | RU1105 | 13729 | R.H. White Construction Co., Inc. | NH00054, NH00055, NH00056, NH00057 | P-R.H. White Construction-NH00054-NH00057-Intermediate Pump NH55-56 pumps with inputs | 15971 | POC | USD | 500000 | 181513 | 2017-10-25 | 2019-07-04 |  | 134629 | 0 | 124929.63 |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 11288 | US | OE
IPO | RU1105 | 13729 | R.H. White Construction Co., Inc. | NH00054, NH00055, NH00056, NH00057 | P-R.H. White Construction-NH00054-NH00057-Spent Backwash Water Pump NH57 | 15972 | POC | USD |  | 175072 | 2017-10-25 | 2019-07-04 |  | 108705 | 0 | 88382 |  | 0 | 0 | 0 | [8 empty] | 0 | US | OE
IPO | RU1105 | 13729 | R.H. White Construction Co., Inc. | NH00054, NH00055, NH00056, NH00057 | P-R.H. White Construction-NH00054-NH00057-Manganese Lift Pump NH54 | 15973 | POC | USD |  | 131415 | 2017-10-25 | 2019-07-04 |  | 77289 | 0 | 73462 |  | 0 | 0 | 0 | [8 empty] | 0 | US | OE
IPO | RU1105 | 13729 | R.H. White Construction Co., Inc. | NH00054, NH00055, NH00056, NH00057 | P-R.H. White Construction-NH00054-NH00057-Field Services NH54-57 | 15974 | PIT | USD |  | 12000 | 2017-10-25 | 2019-07-04 |  | 179377 | 0 | 133053 |  | 0 | 0 | 0 | [8 empty] | 0 | US | OE
EPO | RU1200 | 4692 | BP Exploration & Production, Inc. | RLCB03394 | P - BP Exploration Production Inc - RLCB03394 | 4706 | POC | USD | 9307243 | 8842818 | 2016-12-16 | 2018-02-12 |  | 9307243 |  | 11693720 |  | 10254938 | [10 empty] | 0 | US | OE
EPO | RU1200 | 4707 | Hengli Petrochemical (Dalian) Refinery Co. Ltd | RLCB03371 | P - Hengli Petrochemical - RLCB03371 | 7325 | POC | USD | 27585084 | 27585084 | 2017-02-10 | 2018-06-10 |  | 27585084 |  | 13199463 |  | 12250739 | [10 empty] | 1655105.04 | CHINA | OE
EPO | RU1200 | 7099 | Suncor Energy Oil Sands Ltd Part | RLCX00844 | P - Suncor Energy Oil Sands Ltd Part - RLCX00844 | 7112 | POC | CAD | 493240 | 387923.54 | 2017-07-21 | 2018-01-01 |  | 493240 |  | 139481 |  | 139481 |  |  |  | 2018-01-31 |  |  |  | 0 |  |  | 0 | CANADA | AM
EPO | RU1200 | 7456 | Slovnoft A.S. | RLCB03387 | P - Slovnoft A.S. - RLCB03387 | 7460 | POC | USD | 3441489 | 3441489 | 2016-11-21 | 2018-01-31 |  | 3441489 |  | 1769821 |  | 1709174 | [10 empty] | 0 | EUROPE | OE
EPO | RU1200 | 11514 | Kiewit Offshore Services, Ltd. | RLCB03384 | P-Kiewit Offshore Services-RLCB03384-Production Booster Pumps | 17325 | POC | USD | 5769975 | 5769975 | 2016-08-30 | 2018-10-05 |  | 5769975 |  | 7521594 |  | 6577496 | [10 empty] | 0 | US | OE
EPO | RU1200 | 11516 | Suncor Energy Oil Sands Limited Partnership | RLCX00854, RLCX00853, RLCX00855 | P-Suncor Energy Oil Sands Limited Partnership-RLCX00854, RLCX00853, RLCX00855-Manufacture and Delivery of Turnaround Equipment | 17811 | POC | CAD | 729650 | 584725.75 | 2017-08-16 | 2018-01-25 |  | 729650 |  | 293846 |  | 293846 |  |  |  | 2018-02-28 |  |  |  | 0 |  |  | 0 | CANADA | AM
EPO | RU1200 | 17933 | Suncor Energy Oil Sands Ltd. | RLCX00872 | P-Suncor-RLCX00872-Complete Rotary Joint Assembly | 18888 | POC | CAD | 330730.0006 | 256598.69 | 2017-11-14 | 2018-04-04 |  | 330730.0006 |  | 158037 |  | 158037 | [7 empty] | 0 |  |  | 0 | CANADA | AM
EPO | RU1200 | 18663 | Equilon Enterprises LLC | RLCX00881 | P - Equilon Enterprises LLC - RLCX00881-3 Ebullator Pump Casings | 19658 | POC | USD | 4600000 | 4600000 | 2017-12-21 | 2019-03-09 |  | 4600000 |  | 1082185 |  | 357820 | [10 empty] | 0 | US | AM
EPO | RU1200 | 18664 | Hyundai Eng. & Construction Co. Ltd. | RLCB03407 | P - Hyundai Eng. & Construction Co. Ltd. - RLCB03407 - Decoking System | 19628 | POC | USD | 2000003 | 2000000 | 2017-11-21 | 2018-06-15 |  | 2000003 |  | 1855608 |  | 1200700 | [10 empty] | 0 | US | AM
EPO | RU1200 | 18665 | ICA Fluor Daniel S. de R.L de C.V | RLCB03319-RLCB03334 | P - ICA Fluor Daniel - RLCB03319-3334 | 19683 | POC | USD | 12734922 | 12734922 | 2014-11-14 | 2018-03-31 |  | 12734922 |  | 9903708 |  | 9648717 | [10 empty] | 0 | LA | OE
EPO | RU1200 | 18666 | Motiva Enterprises LLC | RLCB03337 | P - Motiva Enterprises - RLCB03337 - Pump | 19710 | POC | USD | 4494657 | 4494657 | 2014-11-26 | 2018-03-31 |  | 4494657 |  | 1500193 |  | 1392099 | [10 empty] | 0 | US | AM
EPO | RU1200 | 18668 | Wolverine Pipeline Company | RLCB03397 | P-Wolverine Pipeline-RLCB03397-Manufacture and delivery of a Bare Pump. | 19500 | POC | USD | 529503 | 529503 | 2017-03-31 | 2018-02-15 |  | 529503 |  | 668442 |  | 668442 | [10 empty] | 0 | US | OE
EPO | RU1200 | 18671 | Shell Deer Park Refining | RLCB03403 | P - Shell Deer Park - RLCB03403 | 20619 | POC | USD | 3179626 | 3161476.3 | 2017-12-05 | 2018-12-29 |  | 3179626 |  | 2527235 |  | 762300 | [10 empty] | 0 | US | OE
EPO | RU1200 | 18673 | Tesoro Refining and Marketing Company LLC | RLCB03376 | P-Tesoro Refining Company-RLCB03376-First Stage Charge Pump | 19873 | POC | USD | 1345246 | 1345246.01 | 2016-01-27 | 2018-02-28 |  | 1345246 |  | 1486467 |  | 1486467 |  |  |  | 2018-02-28 | [6 empty] | 0 | US | OE
EPO | RU1200 | 23256 | UTE TSGI | RLCX00892 | P - UTE TSGI RLCX00892 - Decoking Control Valve RLCX00892 | 24022 | POC | USD | 1291024.78 | 122094 | 2018-03-19 | 2018-09-10 |  | 122094 |  | 76280 |  | 33839 | [10 empty] | 0
EPO | RU1200 | 23256 | UTE TSGI | RLCX00892 | P - UTE TSGI RLCX00892 - Decoking Rotary Joint RLCX00893 | 24023 | POC | USD |  | 175567.5 | 2018-03-19 | 2018-09-10 |  | 175567.5 |  | 102444 |  | 55673 | [10 empty] | 0
EPO | RU1200 | 23256 | UTE TSGI | RLCX00892 | P - UTE TSGI RLCX00892 - Autoshift Cutting Tool RLCX00894 | 24024 | POC | USD |  | 118454.78 | 2018-03-19 | 2018-09-10 |  | 118454.78 |  | 41014 |  | 20929 | [10 empty] | 0
EPO | RU1200 | 23256 | UTE TSGI | RLCX00892 | P - UTE TSGI RLCX00892 - Decoking Hose Set RLCX00895 | 24025 | POC | USD |  | 42457.5 | 2018-03-19 | 2018-09-10 |  | 42457.5 |  | 31589 |  | 29891 | [10 empty] | 0
EPO | RU1200 | 23256 | UTE TSGI | RLCX00892 | P - UTE TSGI RLCX00892 - WIK Injector Pump Parts 195-42934 | 24026 | POC | USD |  | 728996.76 | 2018-03-19 | 2018-09-10 | [5 empty] | 0 | [10 empty] | 0
EPO | RU1200 | 23256 | UTE TSGI | RLCX00892 | P - UTE TSGI RLCX00892 - Decoking Spare Parts Bundle RLCN14235 | 24027 | POC | USD |  | 832451.09 | 2018-03-19 | 2018-09-10 |  | 832451 |  | 266363 |  | 61880 | [10 empty] | 0
EPO | RU1200 | 26153 | Fluor Enterprises Inc. | RLCB03425 | P - Fluor Enterprise RLCB03425 | 26154 | POC | USD | 283897 | 283897 | 2018-03-29 | 2018-07-30 |  | 283897 |  | 201300 |  | 55266 | [10 empty] | 0
EPO | RU1200 | 26341 | National Petroleum Construction Company NPCC | RLCV00040 | P - National Petroleum Construction Company RLCV00040: TSG Labor - Startup and Commissioning Support | 27209 | POC | USD | 627687 | 627687 | 2018-02-07 | 2018-06-01 |  | 627687 |  | 489433 |  | 59090 | [10 empty] | 0
EPO | RU1205 | 7101 | State Nuclear Power Engineering Co | RLCU00209 | P-State Nuclear Power Engineering-RCLU00209-Unit 1 RCLU00221 original | 17303 | POC | USD | 4211641.9 | 1434286.3 | 2014-12-06 | 2018-02-27 |  | 1434286.3 |  | 1614152 |  | 863258 | [10 empty] | 0 | US | AM
EPO | RU1205 | 7101 | State Nuclear Power Engineering Co | RLCU00209 | P-State Nuclear Power Engineering-RCLU00209-Unit 2 RCLU00222 original | 17304 | POC | USD |  | 1281194.3 | 2014-12-06 | 2018-02-27 |  | 1281194.3 |  | 1563367 |  | 722512 | [10 empty] | 0 | US | AM
EPO | RU1205 | 7101 | State Nuclear Power Engineering Co | RLCU00209 | P-State Nuclear Power Engineering-RCLU00209-Unit 3 RCLU00209 original | 17305 | POC | USD |  | 1496161.3 | 2014-12-06 | 2018-02-27 |  | 1496161.3 |  | 1604291 |  | 809864 | [10 empty] | 0 | US | AM
EPO | RU1205 | 7110 | Ontario Power Generation | RLCZ00251 | P - Ontario Power Generation - RLCZ00251 RLCZ00204 | 7226 | POC | USD | 6127860 | 3540479.01 | 2016-06-22 | 2018-12-20 | [9 empty] | 2016-12-31 | [6 empty] | 0 | CANADA | AM
EPO | RU1205 | 7110 | Ontario Power Generation | RLCZ00251 | P - Ontario Power Generation - RLCZ00251 RLCZ00250 | 7356 | POC | USD |  | 588796 | 2016-06-22 | 2018-12-20 | [9 empty] | 2016-12-31 | [6 empty] | 0 | CANADA | AM
EPO | RU1205 | 7110 | Ontario Power Generation | RLCZ00251 | P - Ontario Power Generation - RLCZ00251 | 7357 | POC | USD |  | 3407340 | 2016-06-22 | 2018-12-20 | [9 empty] | 2017-12-31 | [6 empty] | 0 | CANADA | AM
EPO | RU1205 | 7110 | Ontario Power Generation | RLCZ00251 | P - Ontario Power Generation - RLCZ00251 RLCZ00252 | 7358 | POC | USD |  | 2943980 | 2016-06-22 | 2018-12-20 |  | 2943980 |  | 2125448 |  | 1791408 | [10 empty] | 0 | CANADA | AM
EPO | RU1205 | 7110 | Ontario Power Generation | RLCZ00251 | P - Ontario Power Generation - RLCZ00251 RLCZ00253 | 7359 | POC | USD |  | 2943980 | 2016-06-22 | 2018-12-20 |  | 2943980 |  | 2061774 |  | 1411036 | [10 empty] | 0 | CANADA | AM
EPO | RU1205 | 7110 | Ontario Power Generation | RLCZ00251 | P - Ontario Power Generation - RLCZ00251 Oversight Complete RLCD00895 | 12807 | PIT | USD |  | 104015 | 2016-06-22 | 2018-12-20 |  | 104015 | [14 empty] | 0 | CANADA | AM
EPO | RU1205 | 7110 | Ontario Power Generation | RLCZ00251 | P - Ontario Power Generation - RLCZ00251 Oversight RLCD00895 | 16127 | PIT | USD |  | 102985 | 2016-06-22 | 2018-12-20 |  | 102985 | [14 empty] | 0 | CANADA | AM
EPO | RU1205 | 7110 | Ontario Power Generation | RLCZ00251 | P - Ontario Power Generation - RLCZ00251 Test RLCZ00204 | 20092 | POC | USD |  | 1474407 | 2016-06-22 | 2018-12-20 | [9 empty] | 2017-12-31 | [6 empty] | 0 | CANADA | AM
EPO | RU1205 | 7110 | Ontario Power Generation | RLCZ00251 | P - Ontario Power Generation - RLCZ00251 Writing RLCD00895 | 20093 | PIT | USD |  | 32900 | 2016-06-22 | 2018-12-20 |  | 32900 | [14 empty] | 0 | CANADA | AM
EPO | RU1205 | 7473 | Wolf Creek Nuclear Operating Corp | RLCU00244 | P - Wolf Creek Nuclear - RLCU00244 | 7475 | POC | USD | 1447873 | 1447873 | 2017-02-01 | 2018-03-19 |  | 1447873 |  | 1240220 |  | 1045591 | [10 empty] | 0 | US | AM
EPO | RU1205 | 7577 | First Energy | RLCU00192 | P - First Energy - RLCU00192 | 7797 | POC | USD | 2814058 | 2814058 | 2013-10-10 | 2018-05-30 |  | 2814058 |  | 3969849 |  | 3674288 | [10 empty] | 0 | US | AM
EPO | RU1205 | 8044 | Talen Energy | RLCD00752 | P - Talen Energy - RLCD00752 | 8045 | POC | USD | 691706 | 691706.07 | 2014-12-29 | 2018-03-31 |  | 691706 |  | 528291 |  | 849907 | [10 empty] | 0 | US | AM
EPO | RU1205 | 8044 | Talen Energy | RLCD00752 | P - Talen Energy - RLCD00752/CC0146631 Field Machining Memphis | 27948 | POC | USD |  | 101180 | 2014-12-29 | 2018-03-31 | [16 empty] | 0
EPO | RU1205 | 8044 | Talen Energy | RLCD00752 | P - Talen Energy - RLCD00752 Balance | 27949 | POC | USD |  | 60813.93 | 2014-12-29 | 2018-03-31 | [16 empty] | 0
EPO | RU1205 | 9073 | Duke Energy Carolinas LLC | RLCZ00382/RLCZ00383 | P-Duke Energy Carolinas-RLCZ00382-N7500 Seal and Tools/tester RLCD00925 | 17334 | POC | USD | 4220853 | 494652 | 2017-07-31 | 2020-03-31 | [9 empty] | 2017-12-31 | [6 empty] | 0 | US | AM
EPO | RU1205 | 9073 | Duke Energy Carolinas LLC | RLCZ00382/RLCZ00383 | P-Duke Energy Carolinas-RLCZ00382-On-site Training RLCD00927 | 17335 | PIT | USD |  | 45600 | 2017-07-31 | 2020-03-31 |  | 45600 | [14 empty] | 0 | US | AM
EPO | RU1205 | 9073 | Duke Energy Carolinas LLC | RLCZ00382/RLCZ00383 | P-Duke Energy Carolinas-RLCZ00382-On-site Installation RLCD00929 | 17336 | POC | USD |  | 120000 | 2017-07-31 | 2020-03-31 |  | 115000 |  | 70380 |  | 34519 | [10 empty] | 0 | US | AM
EPO | RU1205 | 9073 | Duke Energy Carolinas LLC | RLCZ00382/RLCZ00383 | P-Duke Energy Carolinas-RLCZ00382-1000 Hour Test RLCZ00382 | 17337 | POC | USD |  | 1491893 | 2017-07-31 | 2020-03-31 |  | 1491893 | [7 empty] | 2018-02-28 | [6 empty] | 0 | US | AM
EPO | RU1205 | 9073 | Duke Energy Carolinas LLC | RLCZ00382/RLCZ00383 | P-Duke Energy Carolinas-RLCZ00382-Brunswick Recirculating Pump Seals RLCZ00383 | 17338 | POC | USD |  | 2568360 | 2017-07-31 | 2020-03-31 |  | 2568360 |  | 1524073 |  | 840549 | [10 empty] | 0 | US | AM
EPO | RU1205 | 9987 | Ontario Power Generation | RLCU00245 | P - Ontario Power Generation - RLCU00245 | 9990 | POC | USD | 330569.6 | 330569.6 | 2017-02-02 | 2018-01-29 |  | 330569.6 |  | 475758 |  | 475758 | [10 empty] | 0 | CANADA | AM
EPO | RU1205 | 10550 | Entergy Operations Inc - ANO | RLCZ00388 | P - Entergy ANO - RLCZ00388 | 10551 | POC | USD | 346041 | 273980 | 2017-07-17 | 2018-01-15 |  | 274148 |  |  |  | 274148 |  |  |  | 2018-01-31 | [6 empty] | 0 | US | AM
EPO | RU1205 | 10550 | Entergy Operations Inc - ANO | RLCZ00388 | P - Entergy ANO - RLCZ00388 | 10610 | POC | USD |  | 4416 | 2017-07-17 | 2018-01-15 |  | 4416 |  |  |  | 4416 |  |  |  | 2018-01-31 | [6 empty] | 0 | US | AM
EPO | RU1205 | 10550 | Entergy Operations Inc - ANO | RLCZ00388 | P - Entergy ANO - RLCZ00388 | 10611 | POC | USD |  | 67477 | 2017-07-17 | 2018-01-15 |  | 67477 |  |  |  | 67477 |  |  |  | 2018-01-31 | [6 empty] | 0 | US | AM
EPO | RU1205 | 11513 | Dominion Energy Nuclear Connecticut Inc | RLCZ00413 | P - Dominion Nuclear Connecticut - RLCZ00413 | 17496 | POC | USD | 262927 | 262927 | 2017-09-26 | 2018-02-05 |  | 262927 |  | 120836 |  | 120836 | [10 empty] | 0 | US | AM
EPO | RU1205 | 13139 | Bruce Power LP | RLCU00252 | P - Bruce Power - RLCU00252 | 13140 | POC | USD | 2330278 | 2330278 | 2017-11-23 | 2018-12-19 |  | 2330278 |  | 1214951 |  | 267935 | [10 empty] | 0 | CANADA | AM
EPO | RU1205 | 14505 | Bruce Power | RLCA08672 | P - BRUCE POWER - RLCA08672-SHAFT PUMP. Pump SIZE - PPN. PUMP TYPE - DVSS;S/ SERIAL # 70TT0461/76 | 17324 | POC | USD | 555820 | 555820 | 2017-10-31 | 2018-06-08 |  | 555820 | [7 empty] | 2018-03-30 | [6 empty] | 0 | CANADA | AM
EPO | RU1205 | 15581 | Duke Energy Carolinas LLC | RLCZ00432 | P-Duke Energy Carolinas LLC -RLCZ00432-N9000 Seal Cartridge_02/26/18_1of2 | 18453 | POC | USD | 1816734 | 983370 | 2017-11-22 | 2018-09-14 |  | 983370 |  | 463138 |  | 145004 | [10 empty] | 0 | US | AM
EPO | RU1205 | 15581 | Duke Energy Carolinas LLC | RLCZ00432 | P-Duke Energy Carolinas LLC -RLCZ00432-N9000 Seal Cartridge_09/18/18_2of2 | 18454 | POC | USD |  | 833364 | 2017-11-22 | 2018-09-14 |  | 833364 |  | 463138 |  | 145004 | [10 empty] | 0 | US | AM
EPO | RU1205 | 18658 | Dominion Nuclear Connecticut | RLCZ00439 | P-Dominion Nuclear Connecticut-RLCZ00439-Nuclear Pump Cartridge and Seal Refurbishment Kit | 20095 | POC | USD | 416410.01 | 416410.01 | 2017-12-14 | 2018-07-06 |  | 416410.01 |  | 99723 |  | 99723 | [10 empty] | 0 | US | AM
EPO | RU1205 | 18662 | Entergy Louisiana LLC | RLCZ00404 | P - Entergy Louisiana LLC-RLCZ00404-Parts for N-9000 Seal Cartridge | 20080 | POC | USD | 273579 | 273579 | 2017-09-01 | 2018-01-09 |  | 273579 |  | 11244 |  | 11244 |  |  |  | 2018-01-31 | [6 empty] | 0 | US | AM
EPO | RU1205 | 18667 | Ontario Power Generation | RLCU00232 | P - Ontario Power Generation-RLCU00232-(1) 3X11 VB Pump Assemblies w/seals Pre2018 | 20156 | POC | USD | 2102368 | 2102368 | 2016-12-30 | 2018-01-31 |  | 2102368 |  | 1762237 |  | 1757725 | [10 empty] | 0 | CANADA | AM
EPO | RU1205 | 18669 | Ontario Power Generation Inc | RLCU00251 | P - Ontario Power Generation Inc - RLCU00251 - Rotating Element Ball Assembly | 20085 | POC | USD | 2064278 | 2064278 | 2017-10-12 | 2018-05-24 |  | 2064278 |  | 693230 |  | 434979 | [10 empty] | 0 | CANADA | AM
EPO | RU1205 | 18670 | Ontario Power Generation | RLCZ00416 | P-Ontario Power Generation Inc.-RLCZ00416-(3) Flange Seal Cartridge Pressure Boundary | 20586 | POC | USD | 452838 | 452838 | 2017-10-12 | 2018-05-22 |  | 452838 |  | 212595 |  | 206800 | [10 empty] | 0 | CANADA | AM
EPO | RU1205 | 18891 | Bruce Power LP | RLCD00913 | P - Bruce Power L.P. - RLCD00913 | 20329 | POC | USD | 268516 | 268516 | 2017-04-20 | 2018-04-30 |  | 268516 |  | 132333 |  | 114077 | [10 empty] | 0 | CANADA | AM
EPO | RU1205 | 22577 | Exelon | RLCU00254 | P - Exelon RLCU00254 - Rotating Assembly | 22916 | POC | USD | 988660 | 988660 | 2018-02-01 | 2019-02-27 |  | 988660 |  | 837410 |  | 106735 | [10 empty] | 0
EPO | RU1205 | 23258 | TerraPower | RLCU00255 | P - TerraPower, LLC RLCU00255 | 23806 | POC | USD | 274439.34 | 274439.34 | 2018-03-09 | 2018-09-14 |  | 274439.34 |  | 180568 |  | 53722 | [10 empty] | 0
EPO | RU1225 | 8036 | Exelon Business Service Co | CC0136213 | P - Exelon Business Service Co. - CC0136213 | 9245 | POC | USD | 742000 | 742000 | 2017-05-22 | 2018-05-16 |  | 742000 |  | 450000 |  | 285383 | [10 empty] | 0 | US | AM
EPO | RU1225 | 13067 | Energy Nowrthwest | CC0166964 | P - Energy NW - CC0166964-FLS to ref rep test and pump and comp | 17259 | POC | USD | 1838926.95 | 1838926.95 | 2017-04-07 | 2018-07-11 |  | 1838926.95 |  | 1055000 |  | 882871 | [10 empty] | 0 | US | AM
EPO | RU1225 | 14486 | E S Fox Limited | CC0177311 | P - E S Fox Ltd - CC0177311 | 14487 | POC | USD | 1695200 | 1695200 | 2017-11-14 | 2018-05-15 |  | 1695200 |  | 1053596 |  | 847499 | [10 empty] | 0 | CANADA | AM
EPO | RU1225 | 15067 | E S Fox Ltd | 0177256 | P - E S Fox Ltd - CC0177256/657264 Inspection, Technical Report and Shipment | 20322 | POC | USD | 283283 | 283283 | 2017-05-02 | 2018-05-31 |  | 283283 |  | 33000 |  | 22427 | [10 empty] | 0 | CANADA | AM
EPO | RU1225 | 15589 | Wolf Creek Nuclear Corp | CC0177220 | P - Wolf Creek Nuclear Corp_CC0177220 | 15592 | POC | USD | 299567 | 299567 | 2017-08-17 | 2017-12-22 |  | 299567 |  | 145000 |  | 67107 | [10 empty] | 0 | US | AM
EPO | RU1225 | 15596 | STP Nuclear Operating Company | CC0167110 | P - STP Nuclear Operating CO - CC0167110 | 15599 | POC | USD | 277209 | 277209 | 2017-01-26 | 2018-01-31 |  | 277209 |  | 156775 |  | 156775 |  |  |  | 2018-01-01 | [6 empty] | 0 | US | AM
EPO | RU1225 | 15611 | Next Era Energy Point Beach Nuclear Plant | CC0146407 | P - NextEra Energy Point Beach - CC0146407 - Rotating Element Rebuild | 15710 | POC | USD | 1438386.56 | 716551 | 2017-12-29 | 2019-01-04 |  | 716551 | [7 empty] | 2015-12-30 | [6 empty] | 0 | US | AM
EPO | RU1225 | 15611 | Next Era Energy Point Beach Nuclear Plant | CC0146407 | P - NextEra Energy Point Beach - CC0146407 - Complete Casing Kit | 22214 | POC | USD |  | 721835.56 | 2017-12-29 | 2019-01-04 |  | 721835.56 |  | 423400 |  | 82264 | [10 empty] | 0
EPO | RU1225 | 18350 | Exelon Generation | CC0177331 | P - Exelon Generation - CC0177331/00634366 (1) Rotating Element | 18527 | POC | USD | 625000 | 625000 | 2017-12-13 | 2018-04-24 |  | 625000 |  | 453400 |  | 21657 | [10 empty] | 0 | US | AM
EPO | RU1225 | 18660 | Entergy Operations Inc. | CC0177329 | P - Entergy Arkansas, Inc. - CC0177329/10532431 | 19320 | POC | USD | 304234 | 304234 | 2017-12-11 | 2018-07-06 |  | 304234 |  | 110000 |  | 473 | [10 empty] | 0 | US | AM
EPO | RU1225 | 18661 | Entergy Nuclear Operations, Inc. Grand Gulf | CC0177338 | P - Entergy Operations, Inc. - CC0177338/10531490 REV001 RHR Pump Bowl Assembly | 19687 | POC | USD | 883673 | 883673 | 2017-12-19 | 2018-07-31 |  | 883673 |  | 519000 |  | 89379 | [10 empty] | 0 | US | AM
EPO | RU1225 | 22034 | Entergy | CC0187345 | P - Entergy - CC0187345 - Lower Column Pump Assembly | 22161 | POC | USD | 784290 | 324012 | 2018-01-24 | 2018-09-28 |  | 324012 |  | 133151 |  | 32974 | [10 empty] | 0
EPO | RU1225 | 22034 | Entergy | CC0187345 | P - Entergy-CC0187345 - Upper and Middle Column Pump Assembly | 22162 | POC | USD |  | 460278 | 2018-01-24 | 2018-09-28 |  | 460278 |  | 189149 |  | 0 | [10 empty] | 0
EPO | RU1225 | 22115 | Tennessee Valley Authority | CC0177326 | P - TVA CC0177326 - Back Pull-Out Assemblies for RWCU Pump | 22216 | POC | USD | 259740.8 | 259740.8 | 2018-01-09 | 2018-05-04 |  | 259740.8 |  | 153000 |  | 86547 | [10 empty] | 0
EPO | RU1225 | 22998 | DTE Energy | CC0187361 | P - DTE Energy CC0187361 - Condenser Pump Bowl Assembly | 23015 | POC | USD | 399798 | 399798 | 2018-02-22 | 2018-10-04 |  | 399798 |  | 273788 |  | 102341 | [10 empty] | 0
EPO | RU1225 | 26400 | TVA - Tennessee Valley Authority | CC0187405 | WAIVER - P - TVA Browns Ferry Nuclear CC0187405: Back Pull-Out Assemblies for RWCU Pump | 27093 | POC | USD | 264937.12 | 264937.12 | 2018-04-17 | 2018-08-10 |  | 264937.12 |  | 151960 |  | 3232 | [10 empty] | 0
EPO | RU1225 | 26446 | Entergy | CC0187404 | WAIVER - P - Entergy CC0187404 1st Stage, Series and Top Case Pump Spares | 27704 | POC | USD | 545362 | 545362 | 2018-04-16 | 2019-03-05 |  | 545362 |  | 211506 |  | 0 | [10 empty] | 0
IPO | RU1320 | 7724 | Los Alamos National Security, LLC (LANS) | 4000049018 | P-Los Alamos-4000049018-Pump 1 with control & motor panels | 12619 | POC | USD | 441158 | 208303 | 2017-06-13 | 2018-05-14 |  | 208303 |  | 187839.0986 | [12 empty] | 0 | US | OE
IPO | RU1320 | 7724 | Los Alamos National Security, LLC (LANS) | 4000049018 | P-Los Alamos-4000049018-Pump 2 with control & motor panels | 12620 | POC | USD |  | 208303 | 2017-06-13 | 2018-05-14 |  | 208303 |  | 187839.0986 | [12 empty] | 0 | US | OE
IPO | RU1320 | 7724 | Los Alamos National Security, LLC (LANS) | 4000049018 | P-Los Alamos-4000049018-Spare Parts | 12621 | POC | USD |  | 24552 | 2017-06-13 | 2018-05-14 |  | 24552 |  | 23979.7783 | [12 empty] | 0 | US | OE
IPO | RU1320 | 10156 | BP WEST COAST PRODUCTS LLC | 4000050354 | P- BP WEST COAST PRODUCTS LLC - 4000050354- Liquid Blowdown Compressor Skid + shell and tube exchanger + bare shaft compressor | 13165 | POC | USD | 980956.01 | 980956.01 | 2017-10-02 | 2018-07-23 |  | 980956.01 |  | 895790.6974 | [12 empty] | 0 | US | OE
IPO | RU1320 | 10202 | CH2M Hill | 4000050494 | P-CH2M Hill-4000050494-Pump 1 - Custom Boost Dry VAC system | 15347 | POC | USD | 2014557 | 741633.5 | 2017-09-29 | 2018-11-12 | [9 empty] | 2017-12-29 | [6 empty] | 0 | US | OE
IPO | RU1320 | 10202 | CH2M Hill | 4000050494 | P-CH2M Hill-4000050494-Pump 2 - Custom Boost Dry VAC system | 15348 | POC | USD |  | 741633.5 | 2017-09-29 | 2018-11-12 |  | 757789 | [7 empty] | 2018-03-26 | [6 empty] | 0 | US | OE
IPO | RU1320 | 10202 | CH2M Hill | 4000050494 | P-CH2M Hill-4000050494-Pump 3 - Custom Boost Dry VAC system | 15349 | POC | USD |  | 644754.72 | 2017-09-29 | 2018-11-12 |  | 628384 |  | 560953.0419 | [12 empty] | 0 | US | OE
IPO | RU1320 | 10202 | CH2M Hill | 4000050494 | P-CH2M Hill-4000050494-Pump 4 - Custom Boost Dry VAC system | 15350 | POC | USD |  | 644754.72 | 2017-09-29 | 2018-11-12 |  | 628384 |  | 560953.0419 | [12 empty] | 0 | US | OE
IPO | RU1320 | 14478 | Noble Energy Mediterranean Ltd. | 4000047599 | P-Noble Energy-4000047599-Flare Gas Recovery System | 15734 | POC | USD | 1457350 | 1457350 | 2017-04-04 | 2018-01-31 |  | 1457350 |  | 1359892.0545 | [12 empty] | 0 | US | OE
IPO | RU1320 | 19219 | Oxy Vinyls LP | 4000051498 | P - Oxy Vinyls - 4000051498- Two liquid Ring Compressor Systems + Freight + Field Service | 20577 | POC | USD | 905600 | 905600 | 2017-12-29 | 2018-11-07 |  | 905600 |  | 832055 | [12 empty] | 0 | US | OE
IPO | RU1320 | 19265 | Los Alamos National Security LLC | 4000046473 | P - Los Alamos - 4000046473 | 20602 | POC | USD | 389856 | 389855.75 | 2016-12-07 | 2018-02-28 |  | 389856 | [14 empty] | 0 | US | OE
IPO | RU1320 | 23357 | SC Johnson & Son, Inc. | 4000052220 | P - SC Johnson - 4000052220 - pumping systems 1-2 | 23417 | POC | USD | 268061 | 255830 | 2018-02-27 | 2018-06-15 |  | 255830 |  | 228705.9297 | [12 empty] | 0
IPO | RU1320 | 23357 | SC Johnson & Son, Inc. | 4000052220 | P - SC Johnson - 4000052220 - commissioning and start up | 23422 | POC | USD |  | 12231 | 2018-02-27 | 2018-06-15 |  | 12231 |  | 10934.2228 | [12 empty] | 0
IPO | RU1320 | 25871 | BP Products North America - WorleyParsons Canada Services Ltd | 4000052777 | P - BP Whiting Brine Conditioning - 4000052777 - Three K-400A/B/C Vaccum Pumps | 26093 | POC | USD | 1302233.2 | 1022613.8 | 2018-03-28 | 2019-01-04 |  | 1022624 |  | 777194.088 | [12 empty] | 0
IPO | RU1320 | 25871 | BP Products North America - WorleyParsons Canada Services Ltd | 4000052777 | P - BP Whiting Brine Conditioning - 4000052777- Two 401A/B Vaccum Pumps | 26094 | POC | USD |  | 279609.2 | 2018-03-28 | 2019-01-04 |  | 279609.2 |  | 212502.84 | [12 empty] | 0
EPO | RU1350 | 18516 | Occidental Chemical Corporation | 10000382 | P - Occidental Chemical Corporation (Oxy) 10000382/4502323919 | 18524 | POC | USD | 546300 | 546300 | 2016-12-30 | 2018-01-31 |  | 546300 | [7 empty] | 2018-02-20 | [6 empty] | 0 | US | AM
EPO | RU1350 | 18532 | HDGSK JV | 10000386 | P - HDGSK JV (Kambala) 10000386/IONE-OO-PO-MP-5075 Slurry Pumps | 18612 | POC | USD | 2511000 | 2511000 | 2015-07-31 | 2018-01-17 |  | 2511000 | [14 empty] | 27900 | IRAQ | OE
IPO | RU1405 | 3951 | Meglobal Americas, Inc. | 052-41866 | P-Meglobal-1260478-P - Meglobal 58RH44XX-HQ133913 Pump 1 A/B | 4050 | POC | USD | 680467.64 | 85295.37 | 2017-06-23 | 2018-01-31 |  | 85295.37 |  | 69317.97 |  | 68553.33 |  |  |  |  | 68553 |  | 16294 |  | 2018-05-10 | 3001200 | 0 | US | OE
IPO | RU1405 | 3951 | Meglobal Americas, Inc. | 052-41866 | P-Meglobal-1260478-P - Meglobal 58RH44XX-HQ133913 Pump 2 | 4051 | POC | USD |  | 36096.85 | 2017-06-23 | 2018-01-31 |  | 36096.85 |  | 32203 |  | 31821.11 |  |  |  |  | 31821.11 | [5 empty] | 0 | US | OE
IPO | RU1405 | 3951 | Meglobal Americas, Inc. | 052-41866 | P-Meglobal-1260478-P - Meglobal 58RH44XX-HQ133913 Pump 3 | 4052 | POC | USD |  | 40095.61 | 2017-06-23 | 2018-01-31 |  | 40095.61 |  | 35196.78 |  | 34814.46 |  |  |  |  | 34814.46 | [5 empty] | 0 | US | OE
IPO | RU1405 | 3951 | Meglobal Americas, Inc. | 052-41866 | P-Meglobal-1260478-P - Meglobal 58RH44XX-HQ133913 Pump 4 | 4053 | POC | USD |  | 15550.33 | 2017-06-23 | 2018-01-31 |  | 15550.33 |  | 11310.45 |  | 11310.45 |  |  |  | 2018-04-02 | [6 empty] | 0 | US | OE
IPO | RU1405 | 3951 | Meglobal Americas, Inc. | 052-41866 | P-Meglobal-1260478-P - Meglobal 58RH44XX-HQ133913 Pump 5 A/B | 4054 | POC | USD |  | 59328.86 | 2017-06-23 | 2018-01-31 |  | 59328.86 |  | 58370.27 |  | 57605.63 |  |  |  |  | 57605.63 | [5 empty] | 0 | US | OE
IPO | RU1405 | 3951 | Meglobal Americas, Inc. | 052-41866 | P-Meglobal-1260478-P - Meglobal 58RH44XX-HQ133913 Pump 6 A/B | 4055 | POC | USD |  | 111376.66 | 2017-06-23 | 2018-01-31 |  | 111376.66 |  | 106442.44 |  | 95634.05 |  |  |  |  | 95634.05 | [5 empty] | 0 | US | OE
IPO | RU1405 | 3951 | Meglobal Americas, Inc. | 052-41866 | P-Meglobal-1260478-P - Meglobal 58RH44XX-HQ133913 Pump 7 A/B | 4056 | POC | USD |  | 46213.98 | 2017-06-23 | 2018-01-31 |  | 46213.98 |  | 45855.08 |  | 32883.88 |  |  |  |  | 32883.88 | [5 empty] | 0 | US | OE
IPO | RU1405 | 3951 | Meglobal Americas, Inc. | 052-41866 | P-Meglobal-1260478-P - Meglobal 58RH44XX-HQ133913 Pump 8 A/B | 4057 | POC | USD |  | 34586.18 | 2017-06-23 | 2018-01-31 |  | 34586.18 |  | 29034.11 |  | 29034.11 |  |  |  |  | 29034.11 | [5 empty] | 0 | US | OE
IPO | RU1405 | 3951 | Meglobal Americas, Inc. | 052-41866 | P-Meglobal-1260478-P - Meglobal 58RH44XX-HQ133913 Pump 9 | 4058 | POC | USD |  | 31023.67 | 2017-06-23 | 2018-01-31 |  | 31023.67 |  | 26625.72 |  | 26625.72 |  |  |  | 2018-04-23 | [6 empty] | 0 | US | OE
IPO | RU1405 | 3951 | Meglobal Americas, Inc. | 052-41866 | P-Meglobal-1260478-P - Meglobal 58RH44XX-HQ133913 Pump 10 A/B | 4059 | POC | USD |  | 60099.66 | 2017-06-23 | 2018-01-31 |  | 60099.66 |  | 49590.15 |  | 49590.15 |  |  |  | 2018-04-02 | [6 empty] | 0 | US | OE
IPO | RU1405 | 3951 | Meglobal Americas, Inc. | 052-41866 | P-Meglobal-1260478-P - Meglobal 58RH44XX-HQ133913 Pump 11 A/B | 4060 | POC | USD |  | 76346.62 | 2017-06-23 | 2018-01-31 |  | 76346.62 |  | 80089.58 |  | 65493.73 |  |  |  |  | 65493.73 | [5 empty] | 0 | US | OE
IPO | RU1405 | 3951 | Meglobal Americas, Inc. | 052-41866 | P-Meglobal-1260478-P - Meglobal 58RH44XX-HQ133913 Pump 12 A/B | 4061 | POC | USD |  | 24537.58 | 2017-06-23 | 2018-01-31 |  | 24537.58 |  | 17551.71 |  | 17551.71 |  |  |  | 2018-04-02 | [6 empty] | 0 | US | OE
IPO | RU1405 | 3951 | Meglobal Americas, Inc. | 052-41866 | P-Meglobal-1260478-P - Meglobal 58RH44XX-HQ133913 Pump 13 A/B | 4062 | POC | USD |  | 47575.1 | 2017-06-23 | 2018-01-31 |  | 47575.1 |  | 42818.38 |  | 42818.38 |  |  |  | 2018-04-02 | [6 empty] | 0 | US | OE
IPO | RU1405 | 3951 | Meglobal Americas, Inc. | 052-41866 | P-Meglobal-1260478-P - Meglobal 58RH44XX-HQ133913 Pump 14 | 4063 | POC | USD |  | 12341.17 | 2017-06-23 | 2018-01-31 |  | 12341.17 |  | 8016.8 |  | 8016.8 |  |  |  | 2018-04-02 | [6 empty] | 0 | US | OE
IPO | RU1405 | 5181 | Dangote Oil Refining Co. LTD | 1262872 | P - Dangote Oil Refining 1262872 Pumps 1A/B | 5250 | POC | USD | 275353 | 66078 | 2017-07-11 | 2018-04-05 |  | 66078 |  | 42678.68 |  | 7188.36 | [10 empty] | 2753.53 | OTHERAFRICA | OE
IPO | RU1405 | 5181 | Dangote Oil Refining Co. LTD | 1262872 | P - Dangote Oil Refining 1262872 Pumps 2A/B | 5251 | POC | USD |  | 67532 | 2017-07-11 | 2018-04-05 |  | 67532 |  | 44194.12 |  | 7188.36 | [10 empty] | 0 | OTHERAFRICA | OE
IPO | RU1405 | 5181 | Dangote Oil Refining Co. LTD | 1262872 | P - Dangote Oil Refining 1262872 Pumps 3A/B | 5252 | POC | USD |  | 41460 | 2017-07-11 | 2018-04-05 |  | 41460 |  | 25624.34 |  | 4639.8 | [10 empty] | 0 | OTHERAFRICA | OE
IPO | RU1405 | 5181 | Dangote Oil Refining Co. LTD | 1262872 | P - Dangote Oil Refining 1262872 Pumps 4A/B | 5253 | POC | USD |  | 53016 | 2017-07-11 | 2018-04-05 |  | 53016 |  | 35774.4 |  | 6334.87 | [10 empty] | 0 | OTHERAFRICA | OE
IPO | RU1405 | 5181 | Dangote Oil Refining Co. LTD | 1262872 | P - Dangote Oil Refining 1262872 Pumps 5A/B | 5254 | POC | USD |  | 42098 | 2017-07-11 | 2018-04-05 |  | 42098 |  | 28051.7 |  | 4639.8 | [10 empty] | 0 | OTHERAFRICA | OE
IPO | RU1405 | 5181 | Dangote Oil Refining Co. LTD | 1262872 | P - Dangote Oil Refining 1262872 Spares | 5255 | POC | USD |  | 5169 | 2017-07-11 | 2018-04-05 |  | 5169 |  | 15314.18 |  | 0 | [10 empty] | 0 | OTHERAFRICA | OE
IPO | RU1405 | 5841 | Meglobal Americas | 1260734 | P-Meglobal-1260734-P - Meglobal 58RH44XX-HQ133876 Pump 1 A/B | 5866 | POC | USD | 493946.58 | 56233.55 | 2017-06-23 | 2018-01-31 |  | 56233.55 |  | 53953.54 |  | 53953.54 |  |  |  | 2018-04-02 | [6 empty] | 0 | US | OE
IPO | RU1405 | 5841 | Meglobal Americas | 1260734 | P-Meglobal-1260734-P - Meglobal 58RH44XX-HQ133876 Pump 2 A/B | 5867 | POC | USD |  | 24712.3 | 2017-06-23 | 2018-01-31 |  | 24712.3 |  | 24544.46 |  | 24544.46 |  |  |  | 2018-04-02 | [6 empty] | 0 | US | OE
IPO | RU1405 | 5841 | Meglobal Americas | 1260734 | P-Meglobal-1260734-P - Meglobal 58RH44XX-HQ133876 Pump 3 A/B | 5868 | POC | USD |  | 73501.55 | 2017-06-23 | 2018-01-31 |  | 73501.55 |  | 70525.53 |  | 69760.89 |  |  |  |  | 69760.89 | [5 empty] | 0 | US | OE
IPO | RU1405 | 5841 | Meglobal Americas | 1260734 | P-Meglobal-1260734-P - Meglobal 58RH44XX-HQ133876 Pump 4 A/B | 5869 | POC | USD |  | 42057.65 | 2017-06-23 | 2018-01-31 |  | 42057.65 |  | 42803.05 |  | 42803.05 |  |  |  | 2018-04-02 | [6 empty] | 0 | US | OE
IPO | RU1405 | 5841 | Meglobal Americas | 1260734 | P-Meglobal-1260734-P - Meglobal 58RH44XX-HQ133876 Pump 5 A/B | 5870 | POC | USD |  | 101803.83 | 2017-06-23 | 2018-01-31 |  | 101803.83 |  | 66187.41 |  | 65422.77 |  |  |  |  | 65422.77 | [5 empty] | 0 | US | OE
IPO | RU1405 | 5841 | Meglobal Americas | 1260734 | P-Meglobal-1260734-P - Meglobal 58RH44XX-HQ133876 Pump 6 | 5871 | POC | USD |  | 52694.74 | 2017-06-23 | 2018-01-31 |  | 52694.74 |  | 30196.53 |  | 29814.21 |  |  |  |  | 29814.21 | [5 empty] | 0 | US | OE
IPO | RU1405 | 5841 | Meglobal Americas | 1260734 | P-Meglobal-1260734-P - Meglobal 58RH44XX-HQ133876 Pump 7 A/B | 5872 | POC | USD |  | 65726.97 | 2017-06-23 | 2018-01-31 |  | 65727 |  | 66780.3 |  | 66780.3 |  |  |  | 2018-02-28 | [6 empty] | 0 | US | OE
IPO | RU1405 | 5841 | Meglobal Americas | 1260734 | P-Meglobal-1260734-P - Meglobal 58RH44XX-HQ133876 Pump 8 | 5873 | POC | USD |  | 7782.19 | 2017-06-23 | 2018-01-31 |  | 7782 |  | 6925.24 |  | 6925.24 |  |  |  | 2018-02-28 | [6 empty] | 0 | US | OE
IPO | RU1405 | 5841 | Meglobal Americas | 1260734 | P-Meglobal-1260734-P - Meglobal 58RH44XX-HQ133876 Pump 9 | 5874 | POC | USD |  | 26750.64 | 2017-06-23 | 2018-01-31 |  | 26750.64 |  | 30974.08 |  | 30591.76 |  |  |  |  | 30591.76 | [5 empty] | 0 | US | OE
IPO | RU1405 | 5841 | Meglobal Americas | 1260734 | P-Meglobal-1260734-P - Meglobal 58RH44XX-HQ133876 Pump 10 A/B | 5875 | POC | USD |  | 31206.58 | 2017-06-23 | 2018-01-31 |  | 31206.58 |  | 27109.8 |  | 27109.88 |  |  |  | 2018-04-23 | [6 empty] | 0 | US | OE
IPO | RU1405 | 5841 | Meglobal Americas | 1260734 | P-Meglobal-1260734-P - Meglobal 58RH44XX-HQ133876 Spares | 5876 | POC | USD |  | 3474.74 | 2017-06-23 | 2018-01-31 |  | 3474.74 |  | 2762.56 |  | 2762.56 |  |  |  | 2018-04-23 | [6 empty] | 0 | US | OE
IPO | RU1405 | 5841 | Meglobal Americas | 1260734 | P-Meglobal-1260734-P - Meglobal 58RH44XX-HQ133876 Warranty | 5877 | SL | USD |  | 8001.8 | 2017-06-23 | 2018-01-31 |  | 8002 | [14 empty] | 0 | US | OE | 2019-07-25 | 2021-01-15
IPO | RU1405 | 8896 | SUEZ TREATMENT SOLUTIONS CANADA LP | 1255824 | P-Suez Treatment Solutions-1255824 Pumps 1 A/B/C/D | 9365 | POC | USD | 351245.83 | 237652.83 | 2017-04-27 | 2018-05-01 |  | 237652.83 |  | 201062.03 |  | 201062.03 | [10 empty] | 0 | US | OE
IPO | RU1405 | 8896 | SUEZ TREATMENT SOLUTIONS CANADA LP | 1255824 | P-Suez Treatment Solutions-1255824-P - Suez Treatment 1255824 Pumps 2 A/B | 9366 | POC | USD |  | 38750.85 | 2017-04-27 | 2018-05-01 |  | 38751 |  | 20796 |  | 20796 |  |  |  | 2017-10-16 | [6 empty] | 0 | US | OE
IPO | RU1405 | 8896 | SUEZ TREATMENT SOLUTIONS CANADA LP | 1255824 | P-Suez Treatment Solutions-1255824 Pumps 3 A/B | 9367 | POC | USD |  | 74842.32 | 2017-04-27 | 2018-05-01 |  | 74842 |  | 45832 |  | 45832 |  |  |  | 2017-10-16 | [6 empty] | 0 | US | OE
IPO | RU1405 | 9330 | Fluor Federal Solutions | 1256881 | P-Fluor Federal-1256881-P - Fluor Federal 1256881 Line 1 | 9851 | POC | USD | 961788.74 | 7178.32 | 2017-07-19 | 2018-10-30 |  | 7839 |  | 8505.27 |  | 8505.27 |  |  |  | 2018-01-16 |  |  | 4601 |  | 2018-05-16 | 3001192/1247 | 0 | US | OE
IPO | RU1405 | 9330 | Fluor Federal Solutions | 1256881 | P-Fluor Federal-1256881-P - Fluor Federal 1256881 Line 2 | 10824 | POC | USD |  | 16486.19 | 2017-07-19 | 2018-10-30 |  | 18371 |  | 18954.98 |  | 18954.98 |  |  |  | 2018-01-16 | [6 empty] | 0 | US | OE
IPO | RU1405 | 9330 | Fluor Federal Solutions | 1256881 | P-Fluor Federal-1256881-P - Fluor Federal 1256881 Line 3 | 10825 | POC | USD |  | 18582.53 | 2017-07-19 | 2018-10-30 |  | 22427 |  | 20507 |  | 20507 |  |  |  | 2018-03-20 | [6 empty] | 0 | US | OE
IPO | RU1405 | 9330 | Fluor Federal Solutions | 1256881 | P-Fluor Federal-1256881-P - Fluor Federal 1256881 Line 4 | 10826 | POC | USD |  | 64167.6 | 2017-07-19 | 2018-10-30 |  | 81032.78 |  | 76044.13 |  | 76044.13 |  |  |  | 2018-04-26 | [6 empty] | 0 | US | OE
IPO | RU1405 | 9330 | Fluor Federal Solutions | 1256881 | P-Fluor Federal-1256881-P - Fluor Federal 1256881 Line 5 | 10827 | POC | USD |  | 34548.53 | 2017-07-19 | 2018-10-30 |  | 43491.03 |  | 42535.84 |  | 42535.84 |  |  |  | 2018-04-27 | [6 empty] | 0 | US | OE
IPO | RU1405 | 9330 | Fluor Federal Solutions | 1256881 | P-Fluor Federal-1256881-P - Fluor Federal 1256881 Line 6 | 10828 | POC | USD |  | 18626.97 | 2017-07-19 | 2018-10-30 |  | 22481 |  | 26237.61 |  | 26237.61 |  |  |  | 2018-03-19 | [6 empty] | 0 | US | OE
IPO | RU1405 | 9330 | Fluor Federal Solutions | 1256881 | P-Fluor Federal-1256881-P - Fluor Federal 1256881 Line 7 | 10829 | POC | USD |  | 17430.05 | 2017-07-19 | 2018-10-30 |  | 21319.83 |  | 13737.36 |  | 674.9 | [10 empty] | 0 | US | OE
IPO | RU1405 | 9330 | Fluor Federal Solutions | 1256881 | P-Fluor Federal-1256881-P - Fluor Federal 1256881 Line 8 | 10830 | POC | USD |  | 52290.15 | 2017-07-19 | 2018-10-30 |  | 63959.48 |  | 41212.08 |  | 2024.71 | [10 empty] | 0 | US | OE
IPO | RU1405 | 9330 | Fluor Federal Solutions | 1256881 | P-Fluor Federal-1256881-P - Fluor Federal 1256881 Line 9 | 10831 | POC | USD |  | 17044.15 | 2017-07-19 | 2018-10-30 |  | 20854.1 |  | 13433.22 |  | 1256.39 | [10 empty] | 0 | US | OE
IPO | RU1405 | 9330 | Fluor Federal Solutions | 1256881 | P-Fluor Federal-1256881-P - Fluor Federal 1256881 Line 11 | 10832 | POC | USD |  | 34088.31 | 2017-07-19 | 2018-10-30 |  | 41708.2 |  | 26866.44 |  | 2512.79 | [10 empty] | 0 | US | OE
IPO | RU1405 | 9330 | Fluor Federal Solutions | 1256881 | P-Fluor Federal-1256881-P - Fluor Federal 1256881 Line 12 | 10833 | POC | USD |  | 67384.17 | 2017-07-19 | 2018-10-30 |  | 82460 |  | 53108.32 |  | 3914.66 | [10 empty] | 0 | US | OE
IPO | RU1405 | 9330 | Fluor Federal Solutions | 1256881 | P-Fluor Federal-1256881-P - Fluor Federal 1256881 Line 13 | 10834 | POC | USD |  | 64428.46 | 2017-07-19 | 2018-10-30 |  | 78892.81 |  | 53523 |  | 3658.97 | [10 empty] | 0 | US | OE
IPO | RU1405 | 9330 | Fluor Federal Solutions | 1256881 | P-Fluor Federal-1256881-P - Fluor Federal 1256881 Line 14 | 10835 | POC | USD |  | 32214.23 | 2017-07-19 | 2018-10-30 |  | 39446.4 |  | 26761.8 |  | 1829.49 | [10 empty] | 0 | US | OE
IPO | RU1405 | 9330 | Fluor Federal Solutions | 1256881 | P-Fluor Federal-1256881-P - Fluor Federal 1256881 Line 15 | 10836 | POC | USD |  | 103915.54 | 2017-07-19 | 2018-10-30 |  | 127116.69 |  | 81900.24 |  | 5871.99 | [10 empty] | 0 | US | OE
IPO | RU1405 | 9330 | Fluor Federal Solutions | 1256881 | P-Fluor Federal-1256881-P - Fluor Federal 1256881 Line 17 | 10837 | POC | USD |  | 36880.65 | 2017-07-19 | 2018-10-30 |  | 45078.22 |  | 29067.2 |  | 1957.33 | [10 empty] | 0 | US | OE
IPO | RU1405 | 9330 | Fluor Federal Solutions | 1256881 | P-Fluor Federal-1256881-P - Fluor Federal 1256881 Line 18 | 10838 | POC | USD |  | 19985.24 | 2017-07-19 | 2018-10-30 |  | 24797 |  | 18550.43 |  | 18550.43 |  |  |  | 2018-03-19 | [6 empty] | 0 | US | OE
IPO | RU1405 | 9330 | Fluor Federal Solutions | 1256881 | P-Fluor Federal-1256881-P - Fluor Federal 1256881 Line 19 | 10839 | POC | USD |  | 10210.27 | 2017-07-19 | 2018-10-30 |  | 11379 |  | 9757.6 |  | 9757.6 |  |  |  | 2018-01-16 | [6 empty] | 0 | US | OE
IPO | RU1405 | 9330 | Fluor Federal Solutions | 1256881 | P-Fluor Federal-1256881-P - Fluor Federal 1256881 Line 21 | 10840 | POC | USD |  | 22968.72 | 2017-07-19 | 2018-10-30 |  | 28574.55 |  | 24577.85 |  | 24577.85 |  |  |  | 2018-04-05 | [6 empty] | 0 | US | OE
IPO | RU1405 | 9330 | Fluor Federal Solutions | 1256881 | P-Fluor Federal-1256881-P - Fluor Federal 1256881 Line 22 | 10841 | POC | USD |  | 34728.36 | 2017-07-19 | 2018-10-30 |  | 42600.06 |  | 30202.06 |  | 0 | [10 empty] | 0 | US | OE
IPO | RU1405 | 9330 | Fluor Federal Solutions | 1256881 | P-Fluor Federal-1256881-P - Fluor Federal 1256881 Line 23 | 10842 | POC | USD |  | 64627.04 | 2017-07-19 | 2018-10-30 |  | 79371.27 |  | 56204.48 |  | 0 | [10 empty] | 0 | US | OE
IPO | RU1405 | 9330 | Fluor Federal Solutions | 1256881 | P-Fluor Federal-1256881-P - Fluor Federal 1256881 Line 24 | 10843 | POC | USD |  | 25407.67 | 2017-07-19 | 2018-10-30 |  | 31351.08 |  | 22096.4 |  | 0 | [10 empty] | 0 | US | OE
IPO | RU1405 | 9330 | Fluor Federal Solutions | 1256881 | P-Fluor Federal-1256881-P - Fluor Federal 1256881 Line 25 | 10844 | POC | USD |  | 21999.85 | 2017-07-19 | 2018-10-30 |  | 27238.24 |  | 19908.35 |  | 0 | [10 empty] | 0 | US | OE
IPO | RU1405 | 10501 | Samsung Heavy Ind. | 1269119 | P - Samsung Heavy Ind, 1269119 Line 1 | 12455 | POC | USD | 474000.36 | 71083.52 | 2017-09-11 | 2018-07-23 |  | 67391.7 |  | 56820.66 |  | 7572.42 | [10 empty] | 0 | US | OE
IPO | RU1405 | 10501 | Samsung Heavy Ind. | 1269119 | P - Samsung Heavy Ind, 1269119 Line 2 | 12470 | POC | USD |  | 137990.03 | 2017-09-11 | 2018-07-23 |  | 134464.61 |  | 104030.94 |  | 13286.7 | [10 empty] | 0 | US | OE
IPO | RU1405 | 10501 | Samsung Heavy Ind. | 1269119 | P - Samsung Heavy Ind, 1269119 Line 3 | 12471 | POC | USD |  | 130036.55 | 2017-09-11 | 2018-07-23 |  | 126491.35 |  | 90848.16 |  | 15779.76 | [10 empty] | 0 | US | OE
IPO | RU1405 | 10501 | Samsung Heavy Ind. | 1269119 | P - Samsung Heavy Ind, 1269119 Line 4 | 12472 | POC | USD |  | 93472.65 | 2017-09-11 | 2018-07-23 |  | 93705.12 |  | 71478.08 |  | 19751.34 | [10 empty] | 0 | US | OE
IPO | RU1405 | 10501 | Samsung Heavy Ind. | 1269119 | P - Samsung Heavy Ind, 1269119 Line 5 | 12473 | POC | USD |  | 30523.53 | 2017-09-11 | 2018-07-23 |  | 28664.58 |  | 29562 |  | 3563.1 | [10 empty] | 0 | US | OE
IPO | RU1405 | 10501 | Samsung Heavy Ind. | 1269119 | P - Samsung Heavy Ind, 1269119 Warranty | 12474 | SL | USD |  | 26603.72 | 2017-09-11 | 2018-07-23 |  | 23283 | [14 empty] | 0 | US | OE | 2019-11-16 | 2022-02-03
IPO | RU1405 | 17322 | CB&I, LLC | 1279083 | P - CB&I, LLC - 1279083 -191058E-PO-110111-02-MARK 111 PUMPS | 18504 | POC | USD | 287692.56 | 266382 | 2017-12-01 | 2018-05-29 |  | 287692.56 | 18647 | 207778 |  | 164922.6 | [10 empty] | 0 | US | OE
IPO | RU1405 | 19313 | Suez Treatment Solutions Inc. | 1279339 | P - Suez Treatment Solutions Inc. - 1279339/410020174500250743 (10) Centrifugal Pumps | 20219 | POC | USD | 289883.55 | 284199.57 | 2017-12-14 | 2018-06-04 |  | 289883.55 | 0 | 265421.01 |  | 260085.2 | [10 empty] | 0 | US | OE
IPO | RU1405 | 19314 | Suez Treatment Solutions Inc. | 1279354 | P - Suez Treatment Solutions Inc. - 1279354/410020174500250575 (10) Centrifugal Pumps | 20195 | POC | USD | 289883.56 | 284199.57 | 2017-12-14 | 2018-07-28 |  | 289883.56 | 0 | 264549.15 |  | 257004 |  |  |  |  | 257004.09 |  | 218468.02 |  | 2018-05-31 | 138795/8/2378909 | 0 | US | OE
IPO | RU1405 | 19323 | Qaiwan Global Energy DMCC | 1254878 | P - Qaiwan Global Energy DMCC - 1254878/QGE201700036/2 (6) Self Priming Pumps with motors | 19985 | POC | USD | 250003 | 188308 | 2017-03-31 | 2018-01-31 |  | 188308 |  | 100851 |  | 100851 |  |  |  | 2018-03-29 | [6 empty] | 0 | IRAQ | OE
IPO | RU1405 | 19323 | Qaiwan Global Energy DMCC | 1254878 | P - Qaiwan Global Energy DMCC - 1254878/QGE201700036/2 (2) Self Priming Pumps with motors and Spare | 20669 | POC | USD |  | 61063 | 2017-03-31 | 2018-01-31 |  | 61063 |  | 29579 |  | 29579 |  |  |  | 2018-03-29 | [6 empty] | 0 | IRAQ | OE
IPO | RU1405 | 19323 | Qaiwan Global Energy DMCC | 1254878 | P - Qaiwan Global Energy DMCC - 1254878/QGE201700036/2 (1) Start-Up Spare (GM=96%) | 20670 | POC | USD |  | 632 | 2017-03-31 | 2018-01-31 |  | 632 |  | 1584 |  | 1584 |  |  |  | 2018-03-29 | [6 empty] | 0 | IRAQ | OE
IPO | RU1405 | 19328 | Celanese LTD | 1253732 | P - Celanese LTD - 1253732/4501730886 TAG P-0342/0343 | 20175 | POC | USD | 550609 | 51072.25 | 2017-03-22 | 2018-03-31 |  | 51072.25 |  | 56684 |  | 56684 |  |  |  | 2018-01-24 | [6 empty] | 0 | US | OE
IPO | RU1405 | 19328 | Celanese LTD | 1253732 | P - Celanese LTD - 1253732/4501730886 TAG: P-2925/2926 | 20751 | POC | USD |  | 84134.81 | 2017-03-22 | 2018-03-31 |  | 84134.81 |  | 62791 |  | 62791 |  |  |  | 2017-11-25 | [6 empty] | 0 | US | OE
IPO | RU1405 | 19328 | Celanese LTD | 1253732 | P - Celanese LTD - 1253732/4501730886 TAG: P-0319/0320 | 20752 | POC | USD |  | 22496.45 | 2017-03-22 | 2018-03-31 |  | 22496.45 |  | 19076.35 |  | 19076.35 |  |  |  | 2017-11-25 | [6 empty] | 0 | US | OE
IPO | RU1405 | 19328 | Celanese LTD | 1253732 | P - Celanese LTD - 1253732/4501730886 TAG: P-2920/2921 | 20753 | POC | USD |  | 87877.55 | 2017-03-22 | 2018-03-31 |  | 87877.55 |  | 59153.75 |  | 59153.75 |  |  |  | 2018-01-24 | [6 empty] | 0 | US | OE
IPO | RU1405 | 19328 | Celanese LTD | 1253732 | P - Celanese LTD - 1253732/4501730886 TAG: P-1258/1259 | 20754 | POC | USD |  | 60286.67 | 2017-03-22 | 2018-03-31 |  | 60286.67 |  | 67555.9 |  | 67555.9 |  |  |  | 2018-01-30 | [6 empty] | 0 | US | OE
IPO | RU1405 | 19328 | Celanese LTD | 1253732 | P - Celanese LTD - 1253732/4501730886 (2) ANSI Pumps TAG: P-0483/1012 | 20755 | POC | USD |  | 127559.03 | 2017-03-22 | 2018-03-31 |  | 127559.03 |  | 88962.46 |  | 88962.46 |  |  |  | 2018-01-22 | [6 empty] | 0 | US | OE
IPO | RU1405 | 19328 | Celanese LTD | 1253732 | P - Celanese LTD - 1253732/4501730886 (2) ANSI Pumps TAG: P-2658/2659 | 20756 | POC | USD |  | 77838.6 | 2017-03-22 | 2018-03-31 |  | 77838.6 |  | 66414.84 |  | 66414.84 |  |  |  | 2018-01-30 | [6 empty] | 0 | US | OE
IPO | RU1405 | 19328 | Celanese LTD | 1253732 | P - Celanese LTD - 1253732/4501730886 (1) ANSI Pump TAG: P-2660 | 20757 | POC | USD |  | 39343.64 | 2017-03-22 | 2018-03-31 |  | 39343.64 |  | 33197.57 |  | 33197.57 |  |  |  | 2018-01-30 | [6 empty] | 0 | US | OE
IPO | RU1405 | 19329 | Amec Foster Wheeler Kamtech, Inc | 1250503 | P - AMEC Foster Wheeler Kamtech, Inc. - 1250503/081018 | 20475 | POC | USD | 275537 | 19358 | 2017-02-17 | 2018-01-31 |  | 19358 |  | 10441.44 |  | 10441.44 |  |  |  | 2017-09-07 | [6 empty] | 0 | US | OE
IPO | RU1405 | 19329 | Amec Foster Wheeler Kamtech, Inc | 1250503 | P - AMEC Foster Wheeler Kamtech, Inc. - 1250503/081018 | 20580 | POC | USD |  | 55626 | 2017-02-17 | 2018-01-31 |  | 55626 |  | 35652.31 |  | 35652.31 |  |  |  | 2017-09-07 | [6 empty] | 0 | US | OE
IPO | RU1405 | 19329 | Amec Foster Wheeler Kamtech, Inc | 1250503 | P - AMEC Foster Wheeler Kamtech, Inc. - 1250503/081018 | 20581 | POC | USD |  | 28270 | 2017-02-17 | 2018-01-31 |  | 28270 |  | 21325.81 |  | 21325.81 |  |  |  | 2017-12-07 | [6 empty] | 0 | US | OE
IPO | RU1405 | 19329 | Amec Foster Wheeler Kamtech, Inc | 1250503 | P - AMEC Foster Wheeler Kamtech, Inc. - 1250503/081018 | 20582 | POC | USD |  | 33654 | 2017-02-17 | 2018-01-31 |  | 33654 |  | 26673.56 |  | 26673.56 |  |  |  | 2018-01-15 | [6 empty] | 0 | US | OE
IPO | RU1405 | 19329 | Amec Foster Wheeler Kamtech, Inc | 1250503 | P - AMEC Foster Wheeler Kamtech, Inc. - 1250503/081018 | 20583 | POC | USD |  | 138629 | 2017-02-17 | 2018-01-31 |  | 138629 |  | 145505.85 |  | 145505.85 |  |  |  | 2018-02-14 | [6 empty] | 0 | US | OE
IPO | RU1405 | 22876 | Air Products | 1285152 | P - Air Products - 1285152 - Item 1, 2, 3, 4, & 5 Pumps | 23292 | POC | USD | 411391 | 411391 | 2018-02-26 | 2018-06-19 |  | 411391 |  | 253394 |  | 13436.51 | [10 empty] | 0 | US | OE
IPO | RU1405 | 24537 | McCarthy | 1289277 | P - McCarthy - 1289277 - Pump: PO line 1: Tag: G-6242 | 26020 | POC | USD | 353382 | 6130.41 | 2018-03-29 | 2018-06-29 |  | 6130.41 |  | 4691.47 |  | 4691.47 | [10 empty] | 0 | US | OE
IPO | RU1405 | 24537 | McCarthy | 1289277 | P - McCarthy - 1289277 - Two Pumps: PO line 2: Tag: G-6871-2 | 26033 | POC | USD |  | 56831.09 | 2018-03-29 | 2018-06-29 |  | 56831.09 |  | 69427.9 |  | 0 | [10 empty] | 0 | US | OE
IPO | RU1405 | 24537 | McCarthy | 1289277 | P - McCarthy - 1289277 - Two Pumps: PO line 3: Tag: G-7711-2 | 26034 | POC | USD |  | 22480.18 | 2018-03-29 | 2018-06-29 |  | 22480.18 |  | 13036.92 |  | 13036.92 | [10 empty] | 0 | US | OE
IPO | RU1405 | 24537 | McCarthy | 1289277 | P - McCarthy - 1289277 - Two Pumps: PO line 4: Tag: G-6918/25 | 26035 | POC | USD |  | 16144.43 | 2018-03-29 | 2018-06-29 |  | 16144.43 |  | 9499.64 |  | 9499.64 | [10 empty] | 0 | US | OE
IPO | RU1405 | 24537 | McCarthy | 1289277 | P - McCarthy - 1289277 - Two Pumps: PO line 5: Tag: G-6915-6 | 26036 | POC | USD |  | 46543.72 | 2018-03-29 | 2018-06-29 |  | 46543.72 |  | 29410.5 |  | 0 | [10 empty] | 0 | US | OE
IPO | RU1405 | 24537 | McCarthy | 1289277 | P - McCarthy - 1289277 - Two Pumps: PO line 6: Tag: G-6923-4 | 26037 | POC | USD |  | 15040.6 | 2018-03-29 | 2018-06-29 |  | 15040.6 |  | 8743.68 |  | 8146.16 | [10 empty] | 0 | US | OE
IPO | RU1405 | 24537 | McCarthy | 1289277 | P - McCarthy - 1289277 - Two Pumps: PO line 7: Tag: G-7623-4 | 26038 | POC | USD |  | 45860.06 | 2018-03-29 | 2018-06-29 |  | 45860.06 |  | 28978.5 |  | 10993.51 | [10 empty] | 0 | US | OE
IPO | RU1405 | 24537 | McCarthy | 1289277 | P - McCarthy - 1289277 - One Pump: PO line 8: Tag: G-7625 | 26039 | POC | USD |  | 9026.49 | 2018-03-29 | 2018-06-29 |  | 9026.49 |  | 5247.45 |  | 1341.68 | [10 empty] | 0 | US | OE
IPO | RU1405 | 24537 | McCarthy | 1289277 | P - McCarthy - 1289277 - Two Pumps: PO line 9: Tag: G-7615-6 | 26040 | POC | USD |  | 107508.46 | 2018-03-29 | 2018-06-29 |  | 107508.46 |  | 65216.16 |  | 0 | [10 empty] | 0 | US | OE
IPO | RU1405 | 24537 | McCarthy | 1289277 | P - McCarthy - 1289277 - One Pump: PO line 10: Tag: G-7617 | 26041 | POC | USD |  | 7520.3 | 2018-03-29 | 2018-06-29 |  | 7520.3 |  | 4371.84 |  | 1114.2 | [10 empty] | 0 | US | OE
IPO | RU1405 | 24537 | McCarthy | 1289277 | P - McCarthy - 1289277 - Technical field services | 26042 | POC | USD |  | 20296.26 | 2018-03-29 | 2018-06-29 |  | 20296.26 |  | 25650 |  | 0 | [10 empty] | 0 | US | OE
IPO | RU1405 | 28169 | General Electric | 1293495 | P - General Electric - 1293495 | 28194 | POC | USD | 286981.5 | 286981.5 | 2018-05-09 | 2018-10-15 |  | 286981.5 |  | 243572.8 |  | 0 | [10 empty] | 0 | US | OE
IPO | RU1405 | 28170 | General Electric | 1293530 | P - General Electric - 1293530 | 28269 | POC | USD | 278643.3 | 278643.3 | 2018-05-09 | 2018-10-15 |  | 278643.3 |  | 236560.16 |  | 0 | [10 empty] | 0 | US | OE
IPO | RU1405 | 28267 | Valero Terminaling and Distribution Co. | 1293366 | P - Valero Terminaling - 1293366 - POB1 | 28591 | POC | USD | 360868 | 232508.23 | 2018-05-03 | 2018-09-26 |  | 232508.23 |  | 212680.64 |  | 0 | [10 empty] | 0 | US | OE
IPO | RU1405 | 28267 | Valero Terminaling and Distribution Co. | 1293366 | P - Valero Terminaling - 1293366 - POB2 | 28596 | POC | USD |  | 128359.77 | 2018-05-03 | 2018-09-26 |  | 128359.77 |  | 65989.44 |  | 0 | [10 empty] | 0 | US | OE
AMSS | RU1600 | 8537 | Huntsman | CGP170184, CGP170185, CGP170186, CGP170116 | P-Huntsman Corporation-CGP170184, CGP170185, CGP170186, CGP170116- 4805082545 - Rotor repair/ New Case | 9284 | POC | USD | 896073 | 228121 | 2017-07-18 | 2018-03-30 | [9 empty] | 2017-12-29 | [6 empty] | 0 | US | AM
AMSS | RU1600 | 8537 | Huntsman | CGP170184, CGP170185, CGP170186, CGP170116 | P-Huntsman Corporation-CGP170184, CGP170185, CGP170186, CGP170116-4805082545-Rotor repair/ New Case | 9285 | POC | USD |  | 298641 | 2017-07-18 | 2018-03-30 |  | 298641 |  | 184300.62 | [5 empty] | 2018-04-30 | [6 empty] | 0 | US | AM
AMSS | RU1600 | 8537 | Huntsman | CGP170184, CGP170185, CGP170186, CGP170116 | P-Huntsman Corporation-CGP170184, CGP170185, CGP170186, CGP170116-4805082545- Rotor repair/ New Case | 9286 | POC | USD |  | 298641 | 2017-07-18 | 2018-03-30 |  | 298791 | [7 empty] | 2018-02-28 | [6 empty] | 0 | US | AM
AMSS | RU1600 | 8537 | Huntsman | CGP170184, CGP170185, CGP170186, CGP170116 | P-Huntsman Corporation-CGP170184, CGP170185, CGP170186, CGP170116-4805082545 | 9287 | POC | USD |  | 298641 | 2017-07-18 | 2018-03-30 |  | 298641 | [7 empty] | 2018-03-21 | [6 empty] | 0 | US | AM
AMSS | RU1610 | 12034 | Dynegy Moss Landing | CJP170139, CJP170140, CJP140141, CJP170142 | P-Dynegy-CJP170139, CJP170140, CJP170141, CJP170142-Discharge Head Pump 1 | 13948 | POC | USD | 1044404.82 | 298422.88 | 2017-10-20 | 2018-06-30 |  | 300707.88 |  | 173749.77 |  | 173749.77 |  |  |  | 2018-04-12 | [6 empty] | 0 | US | AM
AMSS | RU1610 | 12034 | Dynegy Moss Landing | CJP170139, CJP170140, CJP140141, CJP170142 | P-Dynegy-CJP170139, CJP170140, CJP170141, CJP170142-Discharge Head Pump 2 | 13949 | POC | USD |  | 236339 | 2017-10-20 | 2018-06-30 |  | 350438.94 |  | 190848.53 |  | 113491.25 | [10 empty] | 0 | US | AM
AMSS | RU1610 | 12034 | Dynegy Moss Landing | CJP170139, CJP170140, CJP140141, CJP170142 | P-Dynegy-CJP170139, CJP170140, CJP170141, CJP170142-Discharge Head Pump 3 | 13950 | POC | USD |  | 196629 | 2017-10-20 | 2018-06-30 |  | 196629 |  | 88892 |  | 88892 | [10 empty] | 0 | US | AM
AMSS | RU1610 | 12034 | Dynegy Moss Landing | CJP170139, CJP170140, CJP140141, CJP170142 | P-Dynegy-CJP170139, CJP170140, CJP170141, CJP170142-Discharge Head Pump 4 | 13951 | POC | USD |  | 196629 | 2017-10-20 | 2018-06-30 |  | 196629 |  | 88892 |  | 88892 | [10 empty] | 0 | US | AM
AMSS | RU1615 | 12522 | BP Whiting | CK1700441 | P - BP Whiting - CK1700441 - 3000670488 | 12534 | POC | USD | 399661.7 | 399661.7 | 2017-10-31 | 2018-04-26 |  | 399661.7 |  | 361101.71 |  | 178739.06 | [10 empty] | 0 | US | AM
AMSS | RU1615 | 24132 | Lima Refining Company | CK1800027 | P - Lima Refining - CK1800027 - PO#8401241348 | 24134 | POC | USD | 469734 | 469734 | 2018-03-19 | 2018-12-26 |  | 469734 |  | 352768.9 |  | 145850.14 | [10 empty] | 0 | US | AM
AMSS | RU1705 | 8014 | Marathon Petroleum | CF0160355 | P-Marathon Petroleum-CF0160355-4100910852 Repair-1 impeller, Ln12 | 9249 | POC | USD | 941767.77 | 110942.95 | 2017-04-07 | 2018-04-30 |  | 111040.45 | [7 empty] | 2018-01-19 |  |  | 765752.32 |  | 2018-05-31 | 20006349-55 | 0 | US | AM
AMSS | RU1705 | 8014 | Marathon Petroleum | CF0160355 | P-Marathon Petroleum-CF0160355- 4100910852- New 1 impeller/1 shaft, Ln11 | 9250 | PIT | USD |  | 64877.36 | 2017-04-07 | 2018-04-30 |  | 64975 | [7 empty] | 2018-01-16 | [6 empty] | 0 | US | AM
AMSS | RU1705 | 8014 | Marathon Petroleum | CF0160355 | P-Marathon Petroleum-CF0160355-4100910852-Repair 1 Cover, Ln3 | 20166 | POC | USD |  | 156761.23 | 2017-04-07 | 2018-04-30 |  | 156843.23 |  | 84235.25 |  | 84235.25 |  |  |  | 2018-05-31 | [6 empty] | 0 | US | AM
AMSS | RU1705 | 8014 | Marathon Petroleum | CF0160355 | P-Marathon Petroleum-CF0160355-4100910852-Repair 1 Case, Ln7 | 20167 | POC | USD |  | 102807.78 | 2017-04-07 | 2018-04-30 |  | 102889.78 |  | 218455.63 |  | 218455.63 |  |  |  | 2018-05-31 | [6 empty] | 0 | US | AM
AMSS | RU1705 | 8014 | Marathon Petroleum | CF0160355 | P-Marathon Petroleum-CF0160355-4100910852-Repair 1 Case, Ln6 | 20168 | POC | USD |  | 102807.78 | 2017-04-07 | 2018-04-30 |  | 102889.78 |  | 207613.2 |  | 207613.2 |  |  |  | 2018-05-31 | [6 empty] | 0 | US | AM
AMSS | RU1705 | 8014 | Marathon Petroleum | CF0160355 | P-Marathon Petroleum-CF0160355-4100910852-Repair 1 Cover, Ln8 | 20169 | POC | USD |  | 156761.23 | 2017-04-07 | 2018-04-30 |  | 156843.23 |  | 83961.6 |  | 83961.6 |  |  |  | 2018-05-31 | [6 empty] | 0 | US | AM
AMSS | RU1705 | 8014 | Marathon Petroleum | CF0160355 | P-Marathon Petroleum-CF0160355-4100910852-New-1 Cover, Ln2 | 20170 | PIT | USD |  | 123061.15 | 2017-04-07 | 2018-04-30 |  | 123143.15 |  | 131857.31 |  | 131857.31 |  |  |  | 2018-05-31 | [6 empty] | 0 | US | AM
AMSS | RU1705 | 8014 | Marathon Petroleum | CF0160355 | P-Marathon Petroleum-CF0160355-4100910852-New 1 Cover, Ln9 | 20171 | PIT | USD |  | 123061.15 | 2017-04-07 | 2018-04-30 |  | 123143.15 |  | 130901.61 |  | 130901.61 |  |  |  | 2018-05-31 | [6 empty] | 0 | US | AM
AMSS | RU1705 | 14037 | Entergy/Louisiana Station | CF0170223(DCI only completed and invoiced) and CF0170224 (in process) | P - Entergy - CF0170224 - 10521490-001 | 14043 | POC | USD | 325000 | 325000 | 2017-11-29 | 2018-04-11 |  | 325000 |  | 283090.22 |  | 37976.42 | 105262 | [9 empty] | 0 | US | AM
AMSS | RU1705 | 14037 | Entergy/Louisiana Station | CF0170223(DCI only completed and invoiced) and CF0170224 (in process) | P - Entergy - CF0170224 - 10521490-001 | 16668 | PIT | USD |  | 19500 | 2017-11-29 | 2018-04-11 | [9 empty] | 2017-11-30 | [6 empty] | 0 | US | AM
AMSS | RU1705 | 16760 | Equilon Enterprises LLC | CF0170159 | P - Equilon - CF0170159 - #4522314269 | 16763 | POC | USD | 794682 | 794681.8 | 2017-08-31 | 2018-03-30 |  | 794682 | [7 empty] | 2018-03-22 | [6 empty] | 0 | US | AM
AMSS | RU1705 | 19377 | Jacobs Engineering Group, Inc. | CF0170380/CF0170381/CF0170382/CF0170383/CF0170384 | P-Jacobs Engineering-CF0170380-Desalter Pump Ln1-58FF25C6 | 19670 | POC | USD | 529289 | 114970 | 2018-01-22 | 2018-07-06 |  | 114970 |  | 63691.66 |  | 0 | [10 empty] | 0 | US | AM
AMSS | RU1705 | 19377 | Jacobs Engineering Group, Inc. | CF0170380/CF0170381/CF0170382/CF0170383/CF0170384 | P-Jacobs Engineering-CF0170381-Desalter Pump Ln2-58FF25C6 | 19671 | POC | USD |  | 114970 | 2018-01-22 | 2018-07-06 |  | 114970 |  | 63691.66 |  | 0 | [10 empty] | 0 | US | AM
AMSS | RU1705 | 19377 | Jacobs Engineering Group, Inc. | CF0170380/CF0170381/CF0170382/CF0170383/CF0170384 | P-Jacobs Engineering-CF0170382-Desalter Pump/Motor Lns3/4-58FF25C6 | 19673 | POC | USD |  | 219117 | 2018-01-22 | 2018-07-06 |  | 219117 |  | 162143 |  | 0 | [10 empty] | 0 | US | AM
AMSS | RU1705 | 19377 | Jacobs Engineering Group, Inc. | CF0170380/CF0170381/CF0170382/CF0170383/CF0170384 | P-Jacobs Engineering-CF0170383-DIP Reflux Pump Ln5-58FF25C6 | 19674 | POC | USD |  | 40116 | 2018-01-22 | 2018-07-06 |  | 40116 |  | 28311.36 |  | 4980.27 | [10 empty] | 0 | US | AM
AMSS | RU1705 | 19377 | Jacobs Engineering Group, Inc. | CF0170380/CF0170381/CF0170382/CF0170383/CF0170384 | P-Jacobs Engineering-CF0170384-DIP Reflux Pump Ln6-58FF25C6 | 19675 | POC | USD |  | 40116 | 2018-01-22 | 2018-07-06 |  | 40116 |  | 28315.67 |  | 4980.27 | [10 empty] | 0 | US | AM
AMSS | RU1710 | 8144 | Valero Refining-Texas, LP | CN0170364 | P - Valero - CN0170364 - #4504021830 | 8153 | POC | USD | 284479 | 284479 | 2017-08-11 | 2018-01-21 |  | 284479 |  | 191051.28 |  | 191051.28 | [10 empty] | 0 | US | AM
AMSS | RU1710 | 9064 | Valero Refining-Texas, L.P. | CN0130240 | P - Valero - CN0130240 - #4502728127 | 9069 | POC | USD | 311573 | 311573 | 2013-07-15 | 2018-01-21 |  | 311573 |  | 220866 |  | 220866 | [10 empty] | 0 | US | AM
AMSS | RU1710 | 16482 | St. Paul Park Refining Co. | CN0170203 | P - St Paul Park - CN0170203 - #93378 | 16675 | POC | USD | 256120.98 | 256120.98 | 2017-08-11 | 2018-01-15 |  | 256120.98 |  | 235653.09 |  | 234025.6 | [10 empty] | 0 | US | AM
AMSS | RU1710 | 26269 | Phillips 66 Company | CN0170968 | P - Phillips 66 - CN0170968 - 4524553183 | 26272 | POC | USD | 437004.18 | 437004.18 | 2018-03-15 | 2018-05-21 |  | 437004.18 |  | 298704.98 |  | 298704.98 | [10 empty] | 0 | US | AM
AMSS | RU1710 | 27125 | Seadrift Coke, LP | CN0180174 | P - Seadrift Coke - CN0180174 - 44916 | 27130 | POC | USD | 750000 | 750000 | 2018-04-11 | 2018-11-12 |  | 750000 |  | 540266.7 |  | 0 | [6 empty] | 225000 |  | 2018-04-12 | 330/10007514 | 0 | US | AM
AMSS | RU1710 | 27630 | Valero Refining-Texas, L.P. | CN0180220 | P Valero CN0180220 4504253916 | 27639 | POC | USD | 497236 | 497236 | 2018-04-30 | 2018-09-17 |  | 497236 |  |  |  | 0 | [10 empty] | 0 | US | AM
AMSS | RU1710 | 27645 | Ascend Performance Materials | CN0180072 | P Ascend CN0180072 4504396793 | 27653 | POC | USD | 264265.37 | 260765.37 | 2018-04-16 | 2018-07-02 |  | 264265.37 |  | 183963.05 |  | 91302.61 | [10 empty] | 0 | US | AM
AMSS | RU1725 | 7992 | BP West Coast Products | CW0160112 | P-BP West Coast Products-CW0160112-C244581 | 7997 | POC | USD | 384458 | 383058.48 | 2016-06-16 | 2018-03-31 |  | 384458 | [7 empty] | 2018-03-28 | [6 empty] | 0 | US | AM
AMSS | RU1725 | 11482 | BP West Coast Products LLC | CW0170126 | P-BP West Coast Products-CW0170126-C264987 | 11492 | POC | USD | 860104.22 | 860104.22 | 2018-01-26 | 2019-05-03 |  | 860104.22 |  | 486602.65 |  | 162409.29 | [6 empty] | 94789.95 |  | 2018-05-21 | 330/30002929 | 0 | US | AM
AMSS | RU1725 | 12966 | Salt River Project | CW0170107 | P-Salt River Project-CW0170107-4500135672 | 12975 | POC | USD | 296270 | 286720 | 2017-10-12 | 2018-03-01 |  | 296270 |  | 239016 |  | 239016 | 0 |  |  | 2018-05-21 |  |  | 296270 |  | 2018-05-31 | 330/30002942 | 0 | US | AM
AMSS | RU1725 | 13678 | Sutter Mutual | CW0170115/CW0170140 | P-Sutter Mutual-CW0170115,CW0170140-Horizontal pump repair | 13915 | POC | USD | 272950 | 213406.55 | 2017-11-07 | 2018-04-06 |  | 216356.55 |  | 141239.09 |  | 141239.09 |  |  |  | 2018-04-19 | [6 empty] | 0 | US | AM
AMSS | RU1725 | 13678 | Sutter Mutual | CW0170115/CW0170140 | P-Sutter Mutual-CW0170115,CW0170140-Horizontal pump repair Field Service | 13916 | POC | USD |  | 56593.45 | 2017-11-07 | 2018-04-06 |  | 56593.45 |  | 40812.93 |  | 40812.93 | [10 empty] | 0 | US | AM
AMSS | RU1725 | 24088 | Nova Group, Inc. | CW0180027/CW01800XX/CW01800XY | P - Nova Group, Inc. - CW0180027 - 1503.00009 | 24231 | POC | USD | 1183462 | 394487.34 | 2018-03-29 | 2019-06-28 |  | 394487.34 |  | 203316 |  | 11781.52 | [10 empty] | 0 | US | AM
AMSS | RU1725 | 24088 | Nova Group, Inc. | CW0180027/CW01800XX/CW01800XY | P - Nova Group, Inc. - CW0180049 - 1503.00009 | 24232 | POC | USD |  | 394487.33 | 2018-03-29 | 2019-06-28 |  | 394487.33 |  | 200656 |  | 834.76 | [10 empty] | 0 | US | AM
AMSS | RU1725 | 24088 | Nova Group, Inc. | CW0180027/CW01800XX/CW01800XY | P - Nova Group, Inc. - CW0180050 - 1503.00009 | 24233 | POC | USD |  | 394487.33 | 2018-03-29 | 2019-06-28 |  | 394487.33 |  | 200656 |  | 707.76 | [10 empty] | 0 | US | AM
AMSS | RU3041 | 6163 | Dresser-Rand | 730084 | P-Dresser-Rand Co.-730084-Panel & Spares | 7633 | POC | USD | 1070319 | 1070319 | 2017-10-19 | 2018-06-08 |  | 1070319 | 0 | 954892.23 |  | 831841.33 | 0 | 0 |  | 2018-05-10 |  |  | 524433.26 |  | 2018-05-22 | 16J164551 | 0 | US | OE
AMSS | RU3041 | 9077 | Dresser-Rand Co. | 735783 | P-Dresser-Rand Co.-735783-Product | 9130 | POC | USD | 1185852 | 1132162 | 2016-11-15 | 2018-04-20 |  | 1185852 | 0 | 955587.88 |  | 955587.88 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | US | OE
AMSS | RU3041 | 9077 | Dresser-Rand Co. | 735783 | P-Dresser-Rand Co.-735783-Spare Parts | 9131 | POC | USD |  | 53690 | 2016-11-15 | 2018-04-20 |  |  | 0 |  |  | 0 | 0 | 0 | [8 empty] | 0 | US | OE
AMSS | RU3041 | 11034 | Dresser-Rand | 713280 | P-Dresser-Rand-713280-LOC | 11487 | POC | USD | 831674.22 | 554146 | 2016-08-01 | 2018-05-01 |  | 554146 | 0 | 526438.7 |  | 109137.52 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | US | OE
AMSS | RU3041 | 11034 | Dresser-Rand | 713280 | P - Dresser-Rand - 713280 - Panel & Spares | 20681 | PIT | USD |  | 277528.22 | 2016-08-01 | 2018-05-01 |  | 277528.22 | 0 |  |  | 0 | 0 | 0 | [8 empty] | 0 | US | OE
AMSS | RU3041 | 17294 | Houston Refining LP | 816520 | P - Lyondellbasell - 816520 - Seal Support System | 18484 | POC | USD | 1924581.05 | 1924581.05 | 2017-12-27 | 2018-08-10 |  | 1924581.05 | 0 | 1539665 |  | 16222.41 | 0 | 0 |  | 2018-04-10 |  |  | 0 |  |  |  | 0 | US | AM
AMSS | RU3041 | 26330 | E.I. du Pont de Numours and Company | 823373 | P-DuPont-823373/3501898005-Reserviors | 27619 | POC | USD | 409585.12 | 409585.12 | 2018-04-09 | 2018-08-17 |  | 409585.12 | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | US | AM
FCO | RU5000 | 3957 | Shell Chemical Appalachia LLC | 8004932 | P-Shell Chemical Appalachia LLC-8004932-Valves (Qty 10) + Docs + Testing/Inspection Plan | 4095 | POC | USD | 2645743 | 2079093.12 | 2016-03-24 | 2019-01-03 |  | 2079093.12 |  | 2005141 |  | 2005141 |  |  |  | 2018-03-31 | [6 empty] | 0 | US | OE
FCO | RU5000 | 3957 | Shell Chemical Appalachia LLC | 8004932 | P-Shell Chemical Appalachia LLC-8004932-Valves (Qty 11) + Docs + Testing/Inspection Plan | 4098 | POC | USD |  | 432913.88 | 2016-03-24 | 2019-01-03 |  | 432913.88 |  | 214777 |  | 66492 |  |  |  |  | 46151 | [5 empty] | 0 | US | OE
FCO | RU5000 | 3957 | Shell Chemical Appalachia LLC | 8004932 | P-Shell Chemical Appalachia LLC-8004932-Extension of Warranty by 36 months | 4099 | SL | USD |  | 133736 | 2016-03-24 | 2019-01-03 |  | 133736 |  |  |  | 0 | [10 empty] | 0 | US | OE | 2019-01-01 | 2022-01-31
FCO | RU5000 | 4182 | SEPCO Electric Power Corporation | 8006141 | P-SEPCO-8006141-VALVE 10" | 4296 | POC | USD | 653328 | 147189.28 | 2016-04-29 | 2018-03-31 |  | 147189.28 |  | 131376 |  | 131376 | [6 empty] | 130666 |  | 2018-05-17 | 8006141-002 | 19599.84 | ASIA | OE
FCO | RU5000 | 4182 | SEPCO Electric Power Corporation | 8006141 | P-SEPCO-8006141-HEADER 4" #1 | 4297 | POC | USD |  | 140188.45 | 2016-04-29 | 2018-03-31 |  | 140188.45 |  | 84309 |  | 82834 | [10 empty] | 0 | ASIA | OE
FCO | RU5000 | 4182 | SEPCO Electric Power Corporation | 8006141 | P-SEPCO-8006141-HEADER 4" #2 | 4298 | POC | USD |  | 132395.69 | 2016-04-29 | 2018-03-31 |  | 132395.69 |  | 84309 |  | 82575 | [10 empty] | 0 | ASIA | OE
FCO | RU5000 | 4182 | SEPCO Electric Power Corporation | 8006141 | P-SEPCO-8006141-HEADER 14" #1 | 4299 | POC | USD |  | 116777.29 | 2016-04-29 | 2018-03-31 |  | 116777.29 |  | 114563 |  | 114563 | [10 empty] | 0 | ASIA | OE
FCO | RU5000 | 4182 | SEPCO Electric Power Corporation | 8006141 | P-SEPCO-8006141-HEADER 14" #2 | 4300 | POC | USD |  | 116777.29 | 2016-04-29 | 2018-03-31 |  | 116777.29 |  | 114563 |  | 114563 | [10 empty] | 0 | ASIA | OE
FCO | RU5000 | 4219 | Hengli Petrochemicals Refinery Co. | 8013823 | P-HENGLI PETROCHEMICAL (DALIAN) REFINERY CO LTD-8013823.006 | 4349 | POC | USD | 1069000 | 10914 | 2017-03-31 | 2018-02-05 |  | 10914 |  | 12765 |  | 12765 |  |  |  | 2018-01-31 | [6 empty] | 10690 | CHINA | OE
FCO | RU5000 | 4219 | Hengli Petrochemicals Refinery Co. | 8013823 | P-HENGLI PETROCHEMICAL (DALIAN) REFINERY CO LTD-8013823.005 | 4354 | POC | USD |  | 93102 | 2017-03-31 | 2018-02-05 |  | 93102 |  | 54325 |  | 54325 |  |  |  | 2018-01-31 | [6 empty] | 0 | CHINA | OE
FCO | RU5000 | 4219 | Hengli Petrochemicals Refinery Co. | 8013823 | P-HENGLI PETROCHEMICAL (DALIAN) REFINERY CO LTD-8013823.004 | 7340 | POC | USD |  | 31600 | 2017-03-31 | 2018-02-05 |  | 31600 |  | 54325 |  | 54325 |  |  |  | 2018-02-28 | [6 empty] | 0 | CHINA | OE
FCO | RU5000 | 4219 | Hengli Petrochemicals Refinery Co. | 8013823 | P-HENGLI PETROCHEMICAL (DALIAN) REFINERY CO LTD-8013823.003 | 7343 | POC | USD |  | 353136 | 2017-03-31 | 2018-02-05 |  | 353136 |  | 398843 |  | 398843 |  |  |  | 2018-03-31 | [6 empty] | 0 | CHINA | OE
FCO | RU5000 | 4219 | Hengli Petrochemicals Refinery Co. | 8013823 | P-HENGLI PETROCHEMICAL (DALIAN) REFINERY CO LTD-8013823.002 | 7344 | POC | USD |  | 330888 | 2017-03-31 | 2018-02-05 |  | 330888 |  | 357707 |  | 357707 |  |  |  | 2018-03-31 | [6 empty] | 0 | CHINA | OE
FCO | RU5000 | 4219 | Hengli Petrochemicals Refinery Co. | 8013823 | P-HENGLI PETROCHEMICAL (DALIAN) REFINERY CO LTD-8013823.001 | 7345 | POC | USD |  | 249360 | 2017-03-31 | 2018-02-05 |  | 249360 |  | 249899 |  | 249899 |  |  |  | 2018-03-31 | [6 empty] | 0 | CHINA | OE
FCO | RU5000 | 4774 | Hengli Petrochemical (Dallan) Refinery Co., Ltd. | 8014788 | P-Hengli Petrochemical (Dallan) Refinery Co., Ltd.-8014788-Mark One 6" 600# Valve Tag #48181PV0034A | 5155 | POC | USD | 990000 | 77195 | 2017-04-26 | 2018-01-30 |  | 77195 |  | 63027 |  | 63027 | [10 empty] | 9900 | CHINA | OE
FCO | RU5000 | 4774 | Hengli Petrochemical (Dallan) Refinery Co., Ltd. | 8014788 | P-Hengli Petrochemical (Dallan) Refinery Co., Ltd.-8014788-Mark One 8" 600# Valve Tag #48181TV0031B1 | 5156 | POC | USD |  | 115244 | 2017-04-26 | 2018-01-30 |  | 115244 |  | 93351 |  | 90019 | [10 empty] | 0 | CHINA | OE
FCO | RU5000 | 4774 | Hengli Petrochemical (Dallan) Refinery Co., Ltd. | 8014788 | P-Hengli Petrochemical (Dallan) Refinery Co., Ltd.-8014788-Mark One 8" 600# Valve Tag #48181TV0031B2 | 5157 | POC | USD |  | 114981 | 2017-04-26 | 2018-01-30 |  | 114981 |  | 93048 |  | 89721 | [10 empty] | 0 | CHINA | OE
FCO | RU5000 | 4774 | Hengli Petrochemical (Dallan) Refinery Co., Ltd. | 8014788 | P-Hengli Petrochemical (Dallan) Refinery Co., Ltd.-8014788-Mark One 3" 600# Valve Tag #48181FV0017 | 5158 | POC | USD |  | 39546 | 2017-04-26 | 2018-01-30 |  | 39546 |  | 28287 |  | 28287 | [10 empty] | 0 | CHINA | OE
FCO | RU5000 | 4774 | Hengli Petrochemical (Dallan) Refinery Co., Ltd. | 8014788 | P-Hengli Petrochemical (Dallan) Refinery Co., Ltd.-8014788-Mark One 3" 600# Valve Tag #48181FV0018 | 5159 | POC | USD |  | 39546 | 2017-04-26 | 2018-01-30 |  | 39546 |  | 28287 |  | 19765 | [10 empty] | 0 | CHINA | OE
FCO | RU5000 | 4774 | Hengli Petrochemical (Dallan) Refinery Co., Ltd. | 8014788 | P-Hengli Petrochemical (Dallan) Refinery Co., Ltd.-8014788-Mark One 8" 600# Valve Tag #48181TV0001B3 | 5160 | POC | USD |  | 112022 | 2017-04-26 | 2018-01-30 |  | 112022 |  | 92288 |  | 92288 | [10 empty] | 0 | CHINA | OE
FCO | RU5000 | 4774 | Hengli Petrochemical (Dallan) Refinery Co., Ltd. | 8014788 | P-Hengli Petrochemical (Dallan) Refinery Co., Ltd.-8014788-Mark One 8" 600# Valve Tag #48181TV0001B4 | 5161 | POC | USD |  | 111907 | 2017-04-26 | 2018-01-30 |  | 111907 |  | 91354 |  | 91354 | [10 empty] | 0 | CHINA | OE
FCO | RU5000 | 4774 | Hengli Petrochemical (Dallan) Refinery Co., Ltd. | 8014788 | P-Hengli Petrochemical (Dallan) Refinery Co., Ltd.-8014788-Mark One 6" 600# Valve Tag #48181LV0004 | 5162 | POC | USD |  | 83365 | 2017-04-26 | 2018-01-30 |  | 83365 |  | 72050 |  | 68556 | [10 empty] | 0 | CHINA | OE
FCO | RU5000 | 4774 | Hengli Petrochemical (Dallan) Refinery Co., Ltd. | 8014788 | P-Hengli Petrochemical (Dallan) Refinery Co., Ltd.-8014788-Mark One 3" 150# Valve Tag #48181PV0030A1 | 5163 | POC | USD |  | 13443 | 2017-04-26 | 2018-01-30 |  | 13443 |  | 8427 |  | 8427 | [10 empty] | 0 | CHINA | OE
FCO | RU5000 | 4774 | Hengli Petrochemical (Dallan) Refinery Co., Ltd. | 8014788 | P-Hengli Petrochemical (Dallan) Refinery Co., Ltd.-8014788-Mark One 1" 300# Valve Tag #48181PV0030A2 | 5164 | POC | USD |  | 4600 | 2017-04-26 | 2018-01-30 |  | 4600 |  | 2976 |  | 2976 | [10 empty] | 0 | CHINA | OE
FCO | RU5000 | 4774 | Hengli Petrochemical (Dallan) Refinery Co., Ltd. | 8014788 | P-Hengli Petrochemical (Dallan) Refinery Co., Ltd.-8014788-Mark One 3" 150# Valve Tag #48181PV0030B1 | 5165 | POC | USD |  | 13443 | 2017-04-26 | 2018-01-30 |  | 13443 |  | 8427 |  | 8427 | [10 empty] | 0 | CHINA | OE
FCO | RU5000 | 4774 | Hengli Petrochemical (Dallan) Refinery Co., Ltd. | 8014788 | P-Hengli Petrochemical (Dallan) Refinery Co., Ltd.-8014788-Mark One 1" 300# Valve Tag #48181PV0030B2 | 5166 | POC | USD |  | 4600 | 2017-04-26 | 2018-01-30 |  | 4600 |  | 3151 |  | 3151 | [10 empty] | 0 | CHINA | OE
FCO | RU5000 | 4774 | Hengli Petrochemical (Dallan) Refinery Co., Ltd. | 8014788 | P-Hengli Petrochemical (Dallan) Refinery Co., Ltd.-8014788-Mark One 3" 150# Valve Tag #48182FV0039 | 5167 | POC | USD |  | 21065 | 2017-04-26 | 2018-01-30 |  | 21065 |  | 15427 |  | 15427 | [10 empty] | 0 | CHINA | OE
FCO | RU5000 | 4774 | Hengli Petrochemical (Dallan) Refinery Co., Ltd. | 8014788 | P-Hengli Petrochemical (Dallan) Refinery Co., Ltd.-8014788-Mark One 4" 150# Valve Tag #48182LV0006 | 5168 | POC | USD |  | 17494 | 2017-04-26 | 2018-01-30 |  | 17494 |  | 12449 |  | 12449 | [10 empty] | 0 | CHINA | OE
FCO | RU5000 | 4774 | Hengli Petrochemical (Dallan) Refinery Co., Ltd. | 8014788 | P-Hengli Petrochemical (Dallan) Refinery Co., Ltd.-8014788-Mark One 1" 150# Valve Tag #48182FV0004B | 5169 | POC | USD |  | 10567 | 2017-04-26 | 2018-01-30 |  | 10567 |  | 8545 |  | 8545 | [10 empty] | 0 | CHINA | OE
FCO | RU5000 | 4774 | Hengli Petrochemical (Dallan) Refinery Co., Ltd. | 8014788 | P-Hengli Petrochemical (Dallan) Refinery Co., Ltd.-8014788-Mark One 4" 150# Valve Tag #48182LV0001 | 5170 | POC | USD |  | 35633 | 2017-04-26 | 2018-01-30 |  | 35633 |  | 27386 |  | 27386 | [10 empty] | 0 | CHINA | OE
FCO | RU5000 | 4774 | Hengli Petrochemical (Dallan) Refinery Co., Ltd. | 8014788 | P-Hengli Petrochemical (Dallan) Refinery Co., Ltd.-8014788-Mark One 2" 150# Valve Tag #48182LV0002 | 5171 | POC | USD |  | 14406 | 2017-04-26 | 2018-01-30 |  | 14406 |  | 11864 |  | 11864 | [10 empty] | 0 | CHINA | OE
FCO | RU5000 | 4774 | Hengli Petrochemical (Dallan) Refinery Co., Ltd. | 8014788 | P-Hengli Petrochemical (Dallan) Refinery Co., Ltd.-8014788-Mark One 1" 150# Valve Tag #48182TV0044 | 5172 | POC | USD |  | 5391 | 2017-04-26 | 2018-01-30 |  | 5391 |  | 4300 |  | 4300 | [10 empty] | 0 | CHINA | OE
FCO | RU5000 | 4774 | Hengli Petrochemical (Dallan) Refinery Co., Ltd. | 8014788 | P-Hengli Petrochemical (Dallan) Refinery Co., Ltd.-8014788-Mark One 1" 150# Valve Tag #48182TV0053 | 5173 | POC | USD |  | 6196 | 2017-04-26 | 2018-01-30 |  | 6196 |  | 4917 |  | 4917 | [10 empty] | 0 | CHINA | OE
FCO | RU5000 | 4774 | Hengli Petrochemical (Dallan) Refinery Co., Ltd. | 8014788 | P-Hengli Petrochemical (Dallan) Refinery Co., Ltd.-8014788-Mark One 1" 150# Valve Tag #48182LV0013 | 5174 | POC | USD |  | 8200 | 2017-04-26 | 2018-01-30 |  | 8200 |  | 4433 |  | 4433 | [10 empty] | 0 | CHINA | OE
FCO | RU5000 | 4774 | Hengli Petrochemical (Dallan) Refinery Co., Ltd. | 8014788 | P-Hengli Petrochemical (Dallan) Refinery Co., Ltd.-8014788-Mark One 2" 150# Valve Tag #48184LV-0005 | 5175 | POC | USD |  | 9325 | 2017-04-26 | 2018-01-30 |  | 9325 |  | 6564 |  | 6564 | [10 empty] | 0 | CHINA | OE
FCO | RU5000 | 4774 | Hengli Petrochemical (Dallan) Refinery Co., Ltd. | 8014788 | P-Hengli Petrochemical (Dallan) Refinery Co., Ltd.-8014788-Mark One 1" 150# Valve Tag #48184FV-0001 | 5176 | POC | USD |  | 7955 | 2017-04-26 | 2018-01-30 |  | 7955 |  | 5728 |  | 5728 | [10 empty] | 0 | CHINA | OE
FCO | RU5000 | 4774 | Hengli Petrochemical (Dallan) Refinery Co., Ltd. | 8014788 | P-Hengli Petrochemical (Dallan) Refinery Co., Ltd.-8014788-Mark One 1" 150# Valve Tag #48184PV-0002 | 5177 | POC | USD |  | 6224 | 2017-04-26 | 2018-01-30 |  | 6224 |  | 4541 |  | 4541 | [10 empty] | 0 | CHINA | OE
FCO | RU5000 | 4774 | Hengli Petrochemical (Dallan) Refinery Co., Ltd. | 8014788 | P-Hengli Petrochemical (Dallan) Refinery Co., Ltd.-8014788-Mark One 1" 300# Valve Tag #48184HV-0002 | 5178 | POC | USD |  | 22861 | 2017-04-26 | 2018-01-30 |  | 22861 |  | 9336 |  | 9224 | [10 empty] | 0 | CHINA | OE
FCO | RU5000 | 4774 | Hengli Petrochemical (Dallan) Refinery Co., Ltd. | 8014788 | P-Hengli Petrochemical (Dallan) Refinery Co., Ltd.-8014788-Mark One 1" 150# Valve Tag #48184PV-0001 | 5179 | POC | USD |  | 6224 | 2017-04-26 | 2018-01-30 |  | 6224 |  | 4541 |  | 4541 | [10 empty] | 0 | CHINA | OE
FCO | RU5000 | 4774 | Hengli Petrochemical (Dallan) Refinery Co., Ltd. | 8014788 | P-Hengli Petrochemical (Dallan) Refinery Co., Ltd.-8014788-Survivor 6" 600# Valve Tag #48181FV0014 | 5180 | POC | USD |  | 88567 | 2017-04-26 | 2018-01-30 |  | 88567 |  | 63329 |  | 60927 | [10 empty] | 0 | CHINA | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661 - WARRANTY | 7332 | SL | USD | 4086823.83 | 95471 | 2015-10-16 | 2018-04-29 |  | 95471 |  | 95471 |  | 0 | [10 empty] | 30651.17 | US | OE | 2019-10-01 | 2021-06-30
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661 - COMPLETE | 7346 | POC | USD |  | 1420049.09 | 2015-10-16 | 2018-04-29 |  | 1420049.09 |  | 841304 |  | 841304 |  |  |  | 2017-08-30 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661 - LOC | 7361 | PIT | USD |  | 5456 | 2015-10-16 | 2018-04-29 |  | 5456 |  | 5456 |  | 0 | [10 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661 - LINE 143, 142, 141, 164, 120, 118 and 185 | 7431 | POC | USD |  | 54431 | 2015-10-16 | 2018-04-29 |  | 54431 |  | 45058 |  | 45058 |  |  |  | 2018-03-29 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661 - LINE 233 AND 177 | 7444 | POC | USD |  | 251987 | 2015-10-16 | 2018-04-29 |  | 251987 |  | 99917 |  | 99917 |  |  |  | 2018-03-29 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661 - LINE 049, 036 AND 189 | 7446 | POC | USD |  | 108494 | 2015-10-16 | 2018-04-29 |  | 108494 |  | 63027 |  | 63027 |  |  |  | 2018-02-05 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661 - LINE 248, 054, 078, 079 AND 173 | 7448 | POC | USD |  | 118522.98 | 2015-10-16 | 2018-04-29 |  | 118522.98 |  | 112305 |  | 112305 |  |  |  | 2018-04-30 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661 - LINE 190, 234, 052, 304, 303, 221, 217, 218, 220 AND 240 | 7449 | POC | USD |  | 234209.58 | 2015-10-16 | 2018-04-29 |  | 234209.58 |  | 169529 |  | 169529 |  |  |  | 2018-04-30 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661 - LINE 051, 192, 158, 157 AND 163 | 7450 | POC | USD |  | 350999.1 | 2015-10-16 | 2018-04-29 |  | 350999 |  | 231170 |  | 231170 |  |  |  | 2018-03-29 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661 - LINE 162, 035, 212, 081 AND 006 | 7452 | POC | USD |  | 197740.18 | 2015-10-16 | 2018-04-29 |  | 197740.18 |  | 120041 |  | 120041 |  |  |  | 2018-04-30 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661 - LINE 202, 302, 301, 208, 297, 129, 127, 128, 126 and 153 | 7455 | POC | USD |  | 161654.82 | 2015-10-16 | 2018-04-29 |  | 161655 |  | 109353 |  | 109353 |  |  |  | 2018-03-29 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661 - LINE 043 | 7458 | POC | USD |  | 3455.27 | 2015-10-16 | 2018-04-29 |  | 3455 |  | 4378 |  | 4378 |  |  |  | 2018-03-29 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661 - LINE 065, 132 and 242 | 7459 | POC | USD |  | 30824.19 | 2015-10-16 | 2018-04-29 |  | 30824 |  | 23908 |  | 23908 |  |  |  | 2018-03-29 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661 - LINE 182, 183 and 070 | 7462 | POC | USD |  | 76081 | 2015-10-16 | 2018-04-29 |  | 76081 |  | 68014 |  | 68014 |  |  |  | 2018-02-27 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661 - LINE 204, 309, 124, 122, 116, 178, 105, 147 and 072 | 7464 | POC | USD |  | 67605.58 | 2015-10-16 | 2018-04-29 |  | 67606 |  | 61125 |  | 61125 |  |  |  | 2018-03-29 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661- LINE 064, 201, 211, 169, 225, 205, 150, 029, 032, 030 and 241 | 7465 | POC | USD |  | 100831.89 | 2015-10-16 | 2018-04-29 |  | 100832 |  | 82276 |  | 82276 |  |  |  | 2018-03-29 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661- LINE 047, 180, 170, 056, 176 and 227 | 7468 | POC | USD |  | 28761.63 | 2015-10-16 | 2018-04-29 |  | 28762 |  | 26741 |  | 26741 |  |  |  | 2018-02-27 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661- LINE 080, 038, 181, 224 and 117 | 7471 | POC | USD |  | 31951.28 | 2015-10-16 | 2018-04-29 |  | 31951 |  | 26389 |  | 26389 |  |  |  | 2018-03-29 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661- LINE 041, 219, 216, 125, 123, 195, 196, 012, 226, 223, 034, 033 and 031 | 7474 | POC | USD |  | 94248.89 | 2015-10-16 | 2018-04-29 |  | 94249 |  | 86498 |  | 86498 |  |  |  | 2018-02-27 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661- LINE 236, 013, 042 and 174 | 7476 | POC | USD |  | 32311.55 | 2015-10-16 | 2018-04-29 |  | 32312 |  | 29928 |  | 29928 |  |  |  | 2018-02-27 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661- LINE 210, 228, 188, 067, 249, 149, 039 and 186 | 7482 | POC | USD |  | 80264.42 | 2015-10-16 | 2018-04-29 |  | 80264 |  | 72662 |  | 72662 |  |  |  | 2018-02-27 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661- LINE 213, 247, 121, 119, 148, 086, 085 and 135 | 7483 | POC | USD |  | 53625.62 | 2015-10-16 | 2018-04-29 |  | 53626 |  | 57835 |  | 57835 |  |  |  | 2017-12-31 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661- LINE 060, 306, 305 and 037 | 7484 | POC | USD |  | 46418.77 | 2015-10-16 | 2018-04-29 |  | 46419 |  | 47972 |  | 47972 |  |  |  | 2017-12-31 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661- LINE 225 and 184 | 7485 | POC | USD |  | 20299.27 | 2015-10-16 | 2018-04-29 |  | 20299 |  | 19452 |  | 19452 |  |  |  | 2017-12-31 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661- LINE 209, 187 and 045 | 7486 | POC | USD |  | 24195.24 | 2015-10-16 | 2018-04-29 |  | 24195 |  | 27074 |  | 27074 |  |  |  | 2017-12-31 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661- LINE 168 and 166 | 7487 | POC | USD |  | 10454.54 | 2015-10-16 | 2018-04-29 |  | 10455 |  | 13289 |  | 13289 |  |  |  | 2017-12-31 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661- LINE 167 | 7488 | POC | USD |  | 4609.43 | 2015-10-16 | 2018-04-29 |  | 4609 |  | 5533 |  | 5533 |  |  |  | 2017-12-31 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661- LINE 194, 193, 112, 111, 110, 109, 100 and 099 | 7489 | POC | USD |  | 35049.28 | 2015-10-16 | 2018-04-29 |  | 35049 |  | 46732 |  | 46732 |  |  |  | 2018-02-05 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661- LINE 040 | 7490 | POC | USD |  | 2940 | 2015-10-16 | 2018-04-29 |  | 2940 |  | 4262 |  | 4262 |  |  |  | 2017-11-30 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661- LINE 068 | 7491 | POC | USD |  | 4760.61 | 2015-10-16 | 2018-04-29 |  | 4761 |  | 7628 |  | 7628 |  |  |  | 2017-11-30 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661- LINE 069 | 7492 | POC | USD |  | 6594.61 | 2015-10-16 | 2018-04-29 |  | 6595 |  | 11060 |  | 11060 |  |  |  | 2017-11-30 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661- LINE 179,229 AND 061 | 7571 | POC | USD |  | 86883.07 | 2015-10-16 | 2018-04-29 |  | 86883 |  | 46891 |  | 46891 |  |  |  | 2018-03-29 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661- LINE 063, 203, 340, 339, AND 191 | 7572 | POC | USD |  | 232432.31 | 2015-10-16 | 2018-04-29 |  | 232432 |  | 113425 |  | 113425 |  |  |  | 2017-12-31 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661- LINE 044 | 7754 | POC | USD |  | 2566 | 2015-10-16 | 2018-04-29 |  | 2566 |  | 4262 |  | 4262 |  |  |  | 2017-12-31 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661- LINE 071 | 7755 | POC | USD |  | 4501 | 2015-10-16 | 2018-04-29 |  | 4501 |  | 9190 |  | 9190 |  |  |  | 2017-12-31 | [6 empty] | 0 | US | OE
FCO | RU5000 | 7092 | Bechtel Oil, Gas and Chemicals, Inc. | 8001661 | P - BECHTEL - 8001661- LINE 066 | 7756 | POC | USD |  | 6142.89 | 2015-10-16 | 2018-04-29 |  | 6143 |  | 9766 |  | 9766 |  |  |  | 2017-12-31 | [6 empty] | 0 | US | OE
FCO | RU5000 | 9072 | Westinghouse Electrical Company | 246752, 246754, 258558, 258559, 263679, 263772, 272973, 272974, 275406, 275407, 277730, 277731, 284876, 284877, 289865, 289866, 290531, 290536, 291425, 291426, 298851, 298852, 299524, 299523, 8010267, 8012091 | P-Westinghouse Electric Co LLC-PO 4500332337 & 4500332338 284877.001-.002 Mark One 1.00 CL 300 | 7621 | POC | USD | 16222058.73 | 57726 | 2010-02-05 | 2019-12-27 |  | 57726 |  | 45039 |  | 45039 | [10 empty] | 0 | US | OE
FCO | RU5000 | 9072 | Westinghouse Electrical Company | 246752, 246754, 258558, 258559, 263679, 263772, 272973, 272974, 275406, 275407, 277730, 277731, 284876, 284877, 289865, 289866, 290531, 290536, 291425, 291426, 298851, 298852, 299524, 299523, 8010267, 8012091 | P-Westinghouse Electric Co LLC-PO 4500332337 & 4500332338 284877.005-.012 Mark One 4.00 CL 600 | 7624 | POC | USD |  | 147864 | 2010-02-05 | 2019-12-27 |  | 147864 |  | 80560 |  | 80560 |  |  |  | 2017-10-31 | [6 empty] | 0 | US | OE
FCO | RU5000 | 9072 | Westinghouse Electrical Company | 246752, 246754, 258558, 258559, 263679, 263772, 272973, 272974, 275406, 275407, 277730, 277731, 284876, 284877, 289865, 289866, 290531, 290536, 291425, 291426, 298851, 298852, 299524, 299523, 8010267, 8012091 | P-Westinghouse Electric Co LLC-PO 4500332337 & 4500332338 298852.019-.020, .041-.042 Mark One 2.00 CL 600 | 7626 | POC | USD |  | 27712 | 2010-02-05 | 2019-12-27 |  | 27712 |  | 38115 |  | 38115 |  |  |  | 2018-05-30 | [6 empty] | 0 | US | OE
FCO | RU5000 | 9072 | Westinghouse Electrical Company | 246752, 246754, 258558, 258559, 263679, 263772, 272973, 272974, 275406, 275407, 277730, 277731, 284876, 284877, 289865, 289866, 290531, 290536, 291425, 291426, 298851, 298852, 299524, 299523, 8010267, 8012091 | P-Westinghouse Electric Co LLC-PO 4500332337 & 4500332338 298852.045-.046 Mark One 6.00 CL 300 | 7628 | POC | USD |  | 46042 | 2010-02-05 | 2019-12-27 |  | 46042 |  | 27205 |  | 23071 | [10 empty] | 0 | US | OE
FCO | RU5000 | 9072 | Westinghouse Electrical Company | 246752, 246754, 258558, 258559, 263679, 263772, 272973, 272974, 275406, 275407, 277730, 277731, 284876, 284877, 289865, 289866, 290531, 290536, 291425, 291426, 298851, 298852, 299524, 299523, 8010267, 8012091 | P-Westinghouse Electric Co LLC-PO 4500332337 & 4500332338 298852.047-.054 Mark One 1.00 CL 600 | 7630 | POC | USD |  | 63656 | 2010-02-05 | 2019-12-27 |  | 63656 |  | 37192 |  | 0 | [10 empty] | 0 | US | OE
FCO | RU5000 | 9072 | Westinghouse Electrical Company | 246752, 246754, 258558, 258559, 263679, 263772, 272973, 272974, 275406, 275407, 277730, 277731, 284876, 284877, 289865, 289866, 290531, 290536, 291425, 291426, 298851, 298852, 299524, 299523, 8010267, 8012091 | P-Westinghouse Electric Co LLC-PO 4500332337 & 4500332338 298852.055-.058 Mark One 2.00 CL 600 | 7632 | POC | USD |  | 33712 | 2010-02-05 | 2019-12-27 |  | 33712 |  | 24282 |  | 24282 |  |  |  | 2018-05-30 | [6 empty] | 0 | US | OE
FCO | RU5000 | 9072 | Westinghouse Electrical Company | 246752, 246754, 258558, 258559, 263679, 263772, 272973, 272974, 275406, 275407, 277730, 277731, 284876, 284877, 289865, 289866, 290531, 290536, 291425, 291426, 298851, 298852, 299524, 299523, 8010267, 8012091 | P-Westinghouse Electric Co LLC-PO 4500332337 & 4500332338 298852.059-.062 Mark One 1.00 CL 600 | 7636 | POC | USD |  | 31828 | 2010-02-05 | 2019-12-27 |  | 31828 |  | 18697 |  | 18697 |  |  |  | 2018-05-30 | [6 empty] | 0 | US | OE
FCO | RU5000 | 9072 | Westinghouse Electrical Company | 246752, 246754, 258558, 258559, 263679, 263772, 272973, 272974, 275406, 275407, 277730, 277731, 284876, 284877, 289865, 289866, 290531, 290536, 291425, 291426, 298851, 298852, 299524, 299523, 8010267, 8012091 | P-Westinghouse Electric Co LLC-PO 4500332337 & 4500332338 298852.063-.066 Mark One 2.00 CL 600 | 7644 | POC | USD |  | 33968 | 2010-02-05 | 2019-12-27 |  | 33968 |  | 20491 |  | 0 | [10 empty] | 0 | US | OE
FCO | RU5000 | 9072 | Westinghouse Electrical Company | 246752, 246754, 258558, 258559, 263679, 263772, 272973, 272974, 275406, 275407, 277730, 277731, 284876, 284877, 289865, 289866, 290531, 290536, 291425, 291426, 298851, 298852, 299524, 299523, 8010267, 8012091 | P-Westinghouse Electric Co LLC-PO 4500332337 & 4500332338 298852.067-.070 Mark One 1.00 CL 600 | 7651 | POC | USD |  | 28368 | 2010-02-05 | 2019-12-27 |  | 28368 |  | 17539 |  | 17539 |  |  |  | 2018-04-30 | [6 empty] | 0 | US | OE
FCO | RU5000 | 9072 | Westinghouse Electrical Company | 246752, 246754, 258558, 258559, 263679, 263772, 272973, 272974, 275406, 275407, 277730, 277731, 284876, 284877, 289865, 289866, 290531, 290536, 291425, 291426, 298851, 298852, 299524, 299523, 8010267, 8012091 | P-Westinghouse Electric Co LLC-PO 4500332337 & 4500332338 298852.071-.080 Mark One 2.00 CL 600 | 7653 | POC | USD |  | 98560 | 2010-02-05 | 2019-12-27 |  | 98560 |  | 53467 |  | 53467 |  |  |  | 2018-04-30 | [6 empty] | 0 | US | OE
FCO | RU5000 | 9072 | Westinghouse Electrical Company | 246752, 246754, 258558, 258559, 263679, 263772, 272973, 272974, 275406, 275407, 277730, 277731, 284876, 284877, 289865, 289866, 290531, 290536, 291425, 291426, 298851, 298852, 299524, 299523, 8010267, 8012091 | P-Westinghouse Electric Co LLC-PO 4500332337 & 4500332338 298852.081-.088 Mark One 2.00 CL 600 | 7655 | POC | USD |  | 60864 | 2010-02-05 | 2019-12-27 |  | 60864 |  | 43370 |  | 21275 |  |  |  | 2018-05-30 | 21275 | [5 empty] | 0 | US | OE
FCO | RU5000 | 9072 | Westinghouse Electrical Company | 246752, 246754, 258558, 258559, 263679, 263772, 272973, 272974, 275406, 275407, 277730, 277731, 284876, 284877, 289865, 289866, 290531, 290536, 291425, 291426, 298851, 298852, 299524, 299523, 8010267, 8012091 | P-Westinghouse Electric Co LLC-PO 4500332337 & 4500332338 299524.005-.021 Valve Modifications | 7658 | POC | USD |  | 350209.73 | 2010-02-05 | 2019-12-27 |  | 350209.73 |  | 128469 |  | 0 | [10 empty] | 0 | US | OE
FCO | RU5000 | 9072 | Westinghouse Electrical Company | 246752, 246754, 258558, 258559, 263679, 263772, 272973, 272974, 275406, 275407, 277730, 277731, 284876, 284877, 289865, 289866, 290531, 290536, 291425, 291426, 298851, 298852, 299524, 299523, 8010267, 8012091 | P-Westinghouse Electric Co LLC-PO 4500332337 & 4500332338 Shipped Items | 7659 | POC | USD |  | 15241548.53 | 2010-02-05 | 2019-12-27 |  | 15241549 |  | 7310805 |  | 7310805 |  |  |  | 2017-12-31 | [6 empty] | 0 | US | OE
FCO | RU5000 | 10927 | United Launch Alliance | 8018508 | P-United Launch Alliance-8018508-PO lines 1 thru 8 | 11479 | POC | USD | 492545 | 64511 | 2017-10-09 | 2018-04-02 |  | 64511 |  | 28947 |  | 28947 |  |  |  | 2018-04-30 | [6 empty] | 96566.6 | US | OE
FCO | RU5000 | 10927 | United Launch Alliance | 8018508 | P-United Launch Alliance-8018508-PO Lines 9 thru 17 | 11480 | POC | USD |  | 413614 | 2017-10-09 | 2018-04-02 |  | 413614 |  | 174047 |  | 174047 |  |  |  | 2018-04-30 | [6 empty] | 0 | US | OE
FCO | RU5000 | 10927 | United Launch Alliance | 8018508 | P-United Launch Alliance-8018508-PO Line 18 | 26024 | PIT | USD |  | 14420 | 2017-10-09 | 2018-04-02 |  | 14420 |  | 5092 |  | 5092 |  |  |  | 2018-04-30 | [6 empty] | 0 | US | OE
FCO | RU5000 | 12559 | SaBon Water Technology | 8018973 | P-SafBon Water Tech-8018973-PO Line 1 | 12798 | POC | USD | 784280 | 162135 | 2017-10-30 | 2018-06-05 |  | 162135 |  | 114187 |  | 0 | [10 empty] | 35292.6 | US | OE
FCO | RU5000 | 12559 | SaBon Water Technology | 8018973 | P-SafBon Water Tech-8018973-PO Line 2 | 12799 | POC | USD |  | 237995 | 2017-10-30 | 2018-06-05 |  | 237995 |  | 159512 |  | 0 | [10 empty] | 0 | US | OE
FCO | RU5000 | 12559 | SaBon Water Technology | 8018973 | P-SafBon Water Tech-8018973-PO Line 3 | 12800 | POC | USD |  | 220290 | 2017-10-30 | 2018-06-05 |  | 220290 |  | 138085 |  | 11527.05 | [10 empty] | 0 | US | OE
FCO | RU5000 | 12559 | SaBon Water Technology | 8018973 | P-SafBon Water Tech-8018973-PO Line 4 | 12801 | POC | USD |  | 76060 | 2017-10-30 | 2018-06-05 |  | 76060 |  | 34271 |  | 0 | [10 empty] | 0 | US | OE
FCO | RU5000 | 12559 | SaBon Water Technology | 8018973 | P-SafBon Water Tech-8018973-PO Line 5 | 12802 | POC | USD |  | 31062 | 2017-10-30 | 2018-06-05 |  | 31062 |  | 18121 |  | 0 | [10 empty] | 0 | US | OE
FCO | RU5000 | 12559 | SaBon Water Technology | 8018973 | P-SafBon Water Tech-8018973-PO Line 6 | 12803 | POC | USD |  | 27468 | 2017-10-30 | 2018-06-05 |  | 27468 |  | 13029 |  | 0 | [10 empty] | 0 | US | OE
FCO | RU5000 | 12559 | SaBon Water Technology | 8018973 | P-SafBon Water Tech-8018973-PO Line 7 | 12804 | POC | USD |  | 29270 | 2017-10-30 | 2018-06-05 |  | 29270 |  | 20427 |  | 0 | [10 empty] | 0 | US | OE
FCO | RU5000 | 12575 | The Chemours Company | 8004630 | P-The Chemours Company-8004630-PO Line 79 | 12840 | POC | USD | 818932 | 10904 | 2016-02-16 | 2018-04-30 |  | 10904 |  | 7948 |  | 7948 | [10 empty] | 47777.19 | LA | OE
FCO | RU5000 | 12575 | The Chemours Company | 8004630 | P-The Chemours Company-8004630-PO Line 83 | 12841 | POC | USD |  | 5266 | 2016-02-16 | 2018-04-30 |  | 5266 |  | 2383 |  | 2383 | [10 empty] | 0 | LA | OE
FCO | RU5000 | 12575 | The Chemours Company | 8004630 | P-The Chemours Company-8004630-PO Line 84 | 12842 | POC | USD |  | 5944 | 2016-02-16 | 2018-04-30 |  | 5944 |  | 6190 |  | 6190 | [10 empty] | 0 | LA | OE
FCO | RU5000 | 12575 | The Chemours Company | 8004630 | P-The Chemours Company-8004630-PO Line 88 | 12843 | POC | USD |  | 6847 | 2016-02-16 | 2018-04-30 |  | 6847 |  | 3991 |  | 3991 | [10 empty] | 0 | LA | OE
FCO | RU5000 | 12575 | The Chemours Company | 8004630 | P-The Chemours Company-8004630-PO Lines 91 thru 94 | 12844 | POC | USD |  | 19317 | 2016-02-16 | 2018-04-30 |  | 19317 |  | 11705 |  | 11705 | [10 empty] | 0 | LA | OE
FCO | RU5000 | 12575 | The Chemours Company | 8004630 | P-The Chemours Company-8004630-PO Lines 95 | 12845 | POC | USD |  | 4695 | 2016-02-16 | 2018-04-30 |  | 4695 |  | 4875 |  | 4875 | [10 empty] | 0 | LA | OE
FCO | RU5000 | 12575 | The Chemours Company | 8004630 | P-The Chemours Company-8004630-PO Lines 98 & 99 | 12846 | POC | USD |  | 36728 | 2016-02-16 | 2018-04-30 |  | 36728 |  | 14697 |  | 14697 | [10 empty] | 0 | LA | OE
FCO | RU5000 | 12575 | The Chemours Company | 8004630 | P-The Chemours Company-8004630-PO Lines 1 thru 47 Modifications | 12847 | POC | USD |  | 27333 | 2016-02-16 | 2018-04-30 |  | 48312 |  | 30570 |  | 0 | [10 empty] | 0 | LA | OE
FCO | RU5000 | 12575 | The Chemours Company | 8004630 | P-The Chemours Company-8004630-PO Line 81 | 12848 | POC | USD |  | 82143 | 2016-02-16 | 2018-04-30 |  | 82143 |  | 47861 |  | 47229 | [10 empty] | 0 | LA | OE
FCO | RU5000 | 12575 | The Chemours Company | 8004630 | P-The Chemours Company-8004630-PO Line 85 | 12849 | POC | USD |  | 74400 | 2016-02-16 | 2018-04-30 |  | 74400 |  | 47209 |  | 47209 | [10 empty] | 0 | LA | OE
FCO | RU5000 | 12575 | The Chemours Company | 8004630 | P-The Chemours Company-8004630-PO Line 101 | 12850 | POC | USD |  | 8242 | 2016-02-16 | 2018-04-30 |  | 8242 |  | 14448 |  | 14448 | [10 empty] | 0 | LA | OE
FCO | RU5000 | 12575 | The Chemours Company | 8004630 | P-The Chemours Company-8004630-PO Line 77 | 12851 | POC | USD |  | 10489 | 2016-02-16 | 2018-04-30 |  | 10489 |  | 6010 |  | 0 | [10 empty] | 0 | LA | OE
FCO | RU5000 | 12575 | The Chemours Company | 8004630 | P-The Chemours Company-8004630-PO Line 21 & 41 | 12852 | POC | USD |  | 16311 | 2016-02-16 | 2018-04-30 |  | 16311 |  | 9587 |  | 9587 | [10 empty] | 0 | LA | OE
FCO | RU5000 | 12575 | The Chemours Company | 8004630 | P-The Chemours Company-8004630-PO Line 32 | 12853 | POC | USD |  | 7411 | 2016-02-16 | 2018-04-30 |  | 7411 |  | 2205 |  | 2205 | [10 empty] | 0 | LA | OE
FCO | RU5000 | 12575 | The Chemours Company | 8004630 | P-The Chemours Company-8004630-PO Line 68, 69, 71, 73 | 12854 | POC | USD |  | 22026 | 2016-02-16 | 2018-04-30 |  | 22026 |  | 18085 |  | 18085 | [10 empty] | 0 | LA | OE
FCO | RU5000 | 12575 | The Chemours Company | 8004630 | P-The Chemours Company-8004630-PO Lines 1, 2, 4 -20, 22-26, 28-31, 34-40, 42-46 | 12855 | POC | USD |  | 322069 | 2016-02-16 | 2018-04-30 |  | 322069 |  | 204424 |  | 204424 |  |  |  | 2017-12-31 | [6 empty] | 0 | LA | OE
FCO | RU5000 | 12575 | The Chemours Company | 8004630 | P-The Chemours Company-8004630-PO Line 33 | 12856 | POC | USD |  | 26484 | 2016-02-16 | 2018-04-30 |  | 26484 |  | 21024 |  | 21204 | [10 empty] | 0 | LA | OE
FCO | RU5000 | 12575 | The Chemours Company | 8004630 | P-The Chemours Company-8004630-PO Line 80 | 12857 | POC | USD |  | 3508 | 2016-02-16 | 2018-04-30 |  | 3508 |  | 3158 |  | 3158 | [10 empty] | 0 | LA | OE
FCO | RU5000 | 12575 | The Chemours Company | 8004630 | P-The Chemours Company-8004630-PO Line 90 & 100 | 12858 | POC | USD |  | 8038 | 2016-02-16 | 2018-04-30 |  | 8038 |  | 4712 |  | 4712 | [10 empty] | 0 | LA | OE
FCO | RU5000 | 12575 | The Chemours Company | 8004630 | P-The Chemours Company-8004630-PO Lines 102,105-113 | 12859 | POC | USD |  | 99798 | 2016-02-16 | 2018-04-30 |  | 99798 |  | 44721 |  | 40989 | [10 empty] | 0 | LA | OE
FCO | RU5000 | 14284 | Chevron Products Company | 8019962 | P-Chevron Products Company-8019962-Valves 4 Mark One types and 11 Qty | 18468 | POC | USD | 294228 | 294228 | 2017-11-17 | 2018-05-31 |  | 294228 |  | 155950.03 |  | 10948.89 | [10 empty] | 0 | US | OE
FCO | RU5000 | 17199 | DFAS | 81020263 | P-DFAS-8020263-Control Valve for Rocket Propellant Run Tank | 17540 | POC | USD | 273766 | 121419 | 2017-12-19 | 2018-07-02 |  | 121419 |  | 40260 |  | 0 | [10 empty] | 22350.99 | US | OE
FCO | RU5000 | 17199 | DFAS | 81020263 | P-DFAS-8020263-Control Valve for Liquid Oxygen Run Tank | 17541 | POC | USD |  | 152347 | 2017-12-19 | 2018-07-02 |  | 152347 |  | 44180 |  | 0 | [10 empty] | 0 | US | OE
FCO | RU5000 | 17296 | Bechtel Oil, Gas And Chemicals, Inc. | 8020151 | P – Bechtel – 8020151/25959-140-POA-JV01-0000 Initial Order (5) Cryogenic Cold Box Valves | 17504 | POC | USD | 851835 | 851835.34 | 2017-12-22 | 2018-09-07 |  | 851835 |  | 429715 |  | 0 | [10 empty] | 0 | US | OE
FCO | RU5000 | 18243 | United Launch Alliance | 8020455 | P-United Launch Alliance-8020455-25 Various Valves 150PSI 316SS | 18418 | POC | USD | 555793 | 555793 | 2017-12-29 | 2018-06-26 |  | 555793 |  | 209047.22 |  | 185802.34 |  |  |  |  | 142679.37 | [5 empty] | 101423.5 | US | OE
FCO | RU5000 | 21677 | C B & I LLC | 8021163 | P - CB & I LLC - 8021163 - PO Lines 1 2 4 thru 8 10 thru 12 | 21924 | POC | USD | 281708.35 | 200677.76 | 2018-01-19 | 2018-11-28 |  | 200677.76 |  | 127270 |  | 0 | [10 empty] | 12677 | US | OE
FCO | RU5000 | 21677 | C B & I LLC | 8021163 | P - CB & I LLC - 8021163 - PO Lines 3 and 9 | 21925 | POC | USD |  | 30229.65 | 2018-01-19 | 2018-11-28 |  | 30229.65 |  | 19175 |  | 0 | [10 empty] | 0 | US | OE
FCO | RU5000 | 21677 | C B & I LLC | 8021163 | P - CB & I LLC - 8021163 - Hydroflush Kits | 21926 | POC | USD |  | 50800.94 | 2018-01-19 | 2018-11-28 |  | 50800.94 |  | 32218 |  | 0 | [10 empty] | 0 | US | OE
FCO | RU5000 | 24470 | Shell Offshore Inc. | 8022590 | P-Shell Pipeline Co.-8022590 | 27094 | POC | USD | 1484549 | 1484549 | 2018-03-27 | 2019-04-01 |  | 1484549 |  | 1080593 |  | 0 | [10 empty] | 0 | US | OE
FCO | RU5000 | 26129 | Bechtel Oil, Gas and Chemicals, Inc. | 8020151 | P-Bechtel – 8020151/25959-140-POA-JV01-00001 Change Order for (202) Standard Control Valves | 26245 | POC | USD | 2782039.3 | 2782039.3 | 2018-02-15 | 2019-10-12 |  | 2782039.3 |  | 1441096 |  | 0 | [10 empty] | 0 | US | OE
FCO | RU5050 | 3644 | Shell Chemical Appalachia LLC | SO # 828304 | P-Shell Chemical Appalachia LLC-828304- (60%+) Control valves | 14514 | POC | USD | 5980809 | 1344607.96 | 2015-11-18 | 2018-09-30 |  | 1344608 | 0 | 42224097 |  | 35004830 | 0 | 0 |  |  | 4172578 |  |  | 0 |  |  | 0 | US | OE
FCO | RU5050 | 3644 | Shell Chemical Appalachia LLC | SO # 828304 | P-Shell Chemical Appalachia LLC-828304- (Less than 5%) Control valves | 25933 | POC | USD |  | 150865 | 2015-11-18 | 2018-09-30 |  | 150865 | 0 | 4326899 |  | 3820399 | 0 | 0 | [8 empty] | 0 | US | OE
FCO | RU5050 | 3644 | Shell Chemical Appalachia LLC | SO # 828304 | P-Shell Chemical Appalachia LLC-828304- (10%) Control valves | 25934 | POC | USD |  | 1111379 | 2015-11-18 | 2018-09-30 |  | 1111379 | 0 | 72900651 |  | 650211 | 20099159 | 0 | [8 empty] | 0 | US | OE
FCO | RU5050 | 3644 | Shell Chemical Appalachia LLC | SO # 828304 | P-Shell Chemical Appalachia LLC-828304- (20%) Control valves | 25935 | POC | USD |  | 107589 | 2015-11-18 | 2018-09-30 |  | 107589 | 0 | 4929245 |  | 3769176 | 0 | 0 |  |  | 2594905 | [5 empty] | 0 | US | OE
FCO | RU5050 | 3644 | Shell Chemical Appalachia LLC | SO # 828304 | P-Shell Chemical Appalachia LLC-828304- (30%) Control valves | 25936 | POC | USD |  | 591481 | 2015-11-18 | 2018-09-30 |  | 591481 | 0 | 24215805 |  | 12537798 | 0 | 0 |  |  | 1428418 | [5 empty] | 0 | US | OE
FCO | RU5050 | 3644 | Shell Chemical Appalachia LLC | SO # 828304 | P-Shell Chemical Appalachia LLC-828304- (40%) Control valves | 25937 | POC | USD |  | 700849 | 2015-11-18 | 2018-09-30 |  | 700849 | 0 | 26587150 |  | 22130813 | 0 | 0 |  |  | 5917483 | [5 empty] | 0 | US | OE
FCO | RU5050 | 3644 | Shell Chemical Appalachia LLC | SO # 828304 | P-Shell Chemical Appalachia LLC-828304- (50%) Control valves | 25938 | POC | USD |  | 1974038 | 2015-11-18 | 2018-09-30 |  | 1974038 | 0 | 68291155 |  | 61143748 | 0 | 0 |  |  | 17928206 | [5 empty] | 0 | US | OE
FCO | RU5050 | 4015 | JGC CORPORATION | 832026 | P-JGC CORPORATION-832026-Supply of control valves - 184 nos. | 14289 | POC | USD | 834514 | 834514 | 2017-05-11 | 2019-01-15 |  | 834514 | 0 | 45727214 |  | 39976301 | 0 | 0 |  |  | 29350904 |  |  | 0 |  |  | 59446 | OTHERAFRICA | OE
FCO | RU5050 | 5456 | HYUNDAI HEAVY INDUSTRIES CO., LTD. | 830101,832523,832524 | P-HYUNDAI HEAVY INDUSTRIES CO., LTD-830101- (55%+)Control Valves | 13911 | POC | USD | 11904580 | 2543396.95 | 2016-09-12 | 2018-08-30 |  | 2543397 | 9169.62 | 67869272 |  | 52768747 | 0 | 0 |  |  | 14783804 |  |  | 0 |  |  | 1328118 | ASIA | OE
FCO | RU5050 | 5456 | HYUNDAI HEAVY INDUSTRIES CO., LTD. | 830101,832523,832524 | P-HYUNDAI HEAVY INDUSTRIES CO., LTD-830101 - (-5%) Control Valves | 24527 | POC | USD |  | 458485.49 | 2016-09-12 | 2018-08-30 |  | 458485 | 0 | 31369735 |  | 30332049 | 0 | 0 |  |  | 29950810 | [5 empty] | 0 | ASIA | OE
FCO | RU5050 | 5456 | HYUNDAI HEAVY INDUSTRIES CO., LTD. | 830101,832523,832524 | P-HYUNDAI HEAVY INDUSTRIES CO., LTD-830101- (5%) Control Valves | 24528 | POC | USD |  | 442442.85 | 2016-09-12 | 2018-08-30 |  | 442443 | 0 | 28884282 |  | 26747433 | 0 | 0 |  |  | 26747433 | [5 empty] | 0 | ASIA | OE
FCO | RU5050 | 5456 | HYUNDAI HEAVY INDUSTRIES CO., LTD. | 830101,832523,832524 | P-HYUNDAI HEAVY INDUSTRIES CO., LTD-830101- (15%) Control Valves | 24529 | POC | USD |  | 2509857.26 | 2016-09-12 | 2018-08-30 |  | 2509857 | 0 | 136445070 |  | 135700196 | 0 | 0 |  |  | 135681526 | [5 empty] | 0 | ASIA | OE
FCO | RU5050 | 5456 | HYUNDAI HEAVY INDUSTRIES CO., LTD. | 830101,832523,832524 | P-HYUNDAI HEAVY INDUSTRIES CO., LTD-830101- (25%) Control Valves | 24530 | POC | USD |  | 3365185.86 | 2016-09-12 | 2018-08-30 |  | 3365186 | 0 | 158262426 |  | 143460019 | 0 | 0 |  |  | 140551003 | [5 empty] | 0 | ASIA | OE
FCO | RU5050 | 5456 | HYUNDAI HEAVY INDUSTRIES CO., LTD. | 830101,832523,832524 | P-HYUNDAI HEAVY INDUSTRIES CO., LTD-830101- (35%) Control Valves | 24531 | POC | USD |  | 1937467.96 | 2016-09-12 | 2018-08-30 |  | 1937468 | 0 | 85321411 |  | 76755859 | 0 | 0 |  |  | 70599443 | [5 empty] | 0 | ASIA | OE
FCO | RU5050 | 5456 | HYUNDAI HEAVY INDUSTRIES CO., LTD. | 830101,832523,832524 | P-HYUNDAI HEAVY INDUSTRIES CO., LTD-830101- (45%) Control Valves | 24532 | POC | USD |  | 647744.03 | 2016-09-12 | 2018-08-30 |  | 647744 | 0 | 21367478 |  | 20702903 | 0 | 0 |  |  | 17345485 | [5 empty] | 0 | ASIA | OE
FCO | RU5050 | 5864 | TECNICAS REUNIDAS | 832479 | P-TECNICAS REUNIDAS-832479-Control Valves | 6211 | POC | USD | 3260622 | 3210932 | 2017-06-30 | 2018-09-26 |  | 3210932 | 0 | 141887857 |  | 94979004 | 0 | 0 |  |  | 94953895 |  |  | 0 |  |  | 2281751 | ASIA | OE
FCO | RU5050 | 5864 | TECNICAS REUNIDAS | 832479 | P-TECNICAS REUNIDAS-832479-Commissioning Spare parts | 6212 | POC | USD |  | 19904 | 2017-06-30 | 2018-09-26 |  | 19904 | 0 | 954137 |  | 0 | 0 | 0 | [8 empty] | 0 | ASIA | OE
FCO | RU5050 | 5864 | TECNICAS REUNIDAS | 832479 | P-TECNICAS REUNIDAS-832479-Extnded warranty | 6213 | SL | USD |  | 29786 | 2017-06-30 | 2018-09-26 |  | 29786 | 0 | 19 |  | 0 | 0 | 0 | [8 empty] | 0 | ASIA | AM | 2018-08-20 | 2022-08-20
FCO | RU5050 | 6003 | Shell Chemical Appalachia LLC | SO # 828378 | P-Shell Chemical Appalachia LLC-828378- (More than 30% margin)Supply of Control Valves | 15032 | POC | USD | 1434773 | 223338 | 2015-11-18 | 2018-09-30 |  | 223338 | 0 | 8583720 |  | 7989654 | 0 | 0 | [5 empty] | 0 |  |  | 0 | US | OE
FCO | RU5050 | 6003 | Shell Chemical Appalachia LLC | SO # 828378 | P-Shell Chemical Appalachia LLC-828378-(Less than 20% Margin)Supply of Control Valves | 25941 | POC | USD |  | 71519 | 2015-11-18 | 2018-09-30 |  | 71519 | 0 | 3822520 |  | 3639590 | 0 | 0 | [8 empty] | 0 | US | OE
FCO | RU5050 | 6003 | Shell Chemical Appalachia LLC | SO # 828378 | P-Shell Chemical Appalachia LLC-828378-(25% + or - 5% margin)Supply of Control Valves | 25942 | POC | USD |  | 1139916 | 2015-11-18 | 2018-09-30 |  | 1139916 | 0 | 48471538 |  | 15432388 | 0 | 0 | [8 empty] | 0 | US | OE
FCO | RU5050 | 6125 | Shell Chemical Appalachia LLC | 830030 | P-Shell Chemical Appalachia LLC-830030-(65%+) Various valves | 6272 | POC | USD | 1513092 | 197396 | 2016-07-29 | 2019-02-10 |  | 197396 | 0 | 4498359 |  | 3160376 | 0 | 0 | [5 empty] | 0 |  |  | 0 | US | OE
FCO | RU5050 | 6125 | Shell Chemical Appalachia LLC | 830030 | P-Shell Chemical Appalachia LLC-830030- (35%) Various valves | 25947 | POC | USD |  | 731226 | 2016-07-29 | 2019-02-10 |  | 731226 | 0 | 30951326 |  | 16329610 | 0 | 0 |  |  | 1249457 | [5 empty] | 0 | US | OE
FCO | RU5050 | 6125 | Shell Chemical Appalachia LLC | 830030 | P-Shell Chemical Appalachia LLC-830030- (45%) Various valves | 25948 | POC | USD |  | 195883 | 2016-07-29 | 2019-02-10 |  | 195883 | 0 | 6978194 |  | 3883497 | 0 | 0 |  |  | 861557 | [5 empty] | 0 | US | OE
FCO | RU5050 | 6125 | Shell Chemical Appalachia LLC | 830030 | P-Shell Chemical Appalachia LLC-830030- (55%) Various valves | 25949 | POC | USD |  | 189442 | 2016-07-29 | 2019-02-10 |  | 189442 | 0 | 5431735 |  | 4256785 | 0 | 0 |  |  | 677693 | [5 empty] | 0 | US | OE
FCO | RU5050 | 6125 | Shell Chemical Appalachia LLC | 830030 | P-Shell Chemical Appalachia LLC-830030- (25%) Various valves | 25950 | POC | USD |  | 199145 | 2016-07-29 | 2019-02-10 |  | 199145 | 0 | 6183440 |  | 5282979 | 0 | 0 |  |  | 1754656 | [5 empty] | 0 | US | OE
FCO | RU5050 | 6727 | JOLAC ENGINEERING SDN BHD | 832503 | P-JOLAC ENGINEERING SDN BHD-832503-Valves | 6792 | POC | USD | 479880 | 479880 | 2017-06-30 | 2018-04-18 |  | 479880 | 0 | 24439524 |  | 24439524 | 0 | 0 |  |  | 24438686 |  |  | 0 |  |  | 0 | ASIA | OE
FCO | RU5050 | 6728 | Shell Chemical Appalachia LLC | SO # 830057 | P-SHELL CHEMICAL APPALACHIA LLC-830057-1st lot out of 94 Valves | 6739 | POC | USD | 512411 | 509643 | 2016-07-25 | 2018-06-25 |  | 509643 | 0 | 25218970 |  | 20325543 | 0 | 0 | [5 empty] | 0 |  |  | 0 | US | OE
FCO | RU5050 | 6728 | Shell Chemical Appalachia LLC | SO # 830057 | P-SHELL CHEMICAL APPALACHIA LLC-830057-Extnded warranty up to 36/48 months | 6740 | SL | USD |  | 2768 | 2016-07-25 | 2018-06-25 |  | 2768 | 0 | 2 |  | 0 | 0 | 0 | [8 empty] | 0 | US | AM | 2018-06-25 | 2022-06-25
FCO | RU5050 | 6733 | BECHTEL OIL, GAS AND CHEMICALS, INC | 832274 | P-BECHTEL OIL, GAS AND CHEMICALS, INC-832274-Supply of control valves 181 nos. | 13909 | POC | USD | 1338284 | 1372470 | 2017-06-09 | 2018-06-22 |  | 1331029 | 0 | 67507097 |  | 63655108 | 0 | 0 |  |  | 62810955 |  |  | 0 |  |  | 0 | US | OE
FCO | RU5050 | 6733 | BECHTEL OIL, GAS AND CHEMICALS, INC | 832274 | P-BECHTEL OIL, GAS AND CHEMICALS, INC-832274-Commissioning Spares | 13910 | POC | USD |  | 7595 | 2017-06-09 | 2018-06-22 |  | 7255 | 0 | 568687 |  | 568413 | 0 | 0 | [8 empty] | 0 | US | OE
FCO | RU5050 | 8571 | CB&l Nederland B.V. | 832709 | P-CB&l Nederland B.V.-832709-Single lot of 26 nos. control valves - Mar 2018 | 12636 | POC | USD | 525317 | 487381 | 2017-08-01 | 2018-03-07 |  | 487381 | 0 | 23025855 |  | 1950069 | 0 | 0 | [5 empty] | 0 |  |  | 0 | EUROPE | OE
FCO | RU5050 | 8571 | CB&l Nederland B.V. | 832709 | P-CB&l Nederland B.V.-832709-Extended Warranty charges | 12637 | SL | USD |  | 5764 | 2017-08-01 | 2018-03-07 |  | 5764 | 0 |  |  | 0 | 0 | 0 | [8 empty] | 0 | EUROPE | AM | 2018-06-07 | 2021-06-07
FCO | RU5050 | 8571 | CB&l Nederland B.V. | 832709 | P-CB&l Nederland B.V.-832709-Spares | 12638 | POC | USD |  | 32172 | 2017-08-01 | 2018-03-07 |  | 32172 | 0 | 290275 |  | 0 | 0 | 0 | [8 empty] | 0 | EUROPE | OE
FCO | RU5050 | 8931 | HYUNDAI ENGINEERING CO., LTD | 832926 | P-HYUNDAI ENGINEERING CO LTD-832926-Supply of Control Valves 96 nos. | 13922 | POC | USD | 3200000 | 3104967 | 2017-08-30 | 2018-07-31 |  | 3104967 | 57110 | 150917158 |  | 78159541 | 0 | 0 |  |  | 7701193 |  |  | 0 |  |  | 0 | ASIA | OE
FCO | RU5050 | 8931 | HYUNDAI ENGINEERING CO., LTD | 832926 | P-HYUNDAI ENGINEERING CO LTD-832926-Extended Warranty charges | 13923 | SL | USD |  | 40373 | 2017-08-30 | 2018-07-31 |  | 40373 | 0 | 3 |  | 0 | 0 | 0 | [8 empty] | 0 | ASIA | OE | 2017-08-30 | 2019-08-30
FCO | RU5050 | 8931 | HYUNDAI ENGINEERING CO., LTD | 832926 | P-HYUNDAI ENGINEERING CO LTD-832926-Spares | 13925 | POC | USD |  | 54660 | 2017-08-30 | 2018-07-31 |  | 54660 | 0 | 2615801 |  | 0 | 0 | 0 | [8 empty] | 0 | ASIA | OE
FCO | RU5050 | 10222 | Meglobal Americas, Inc | 833161 | P-Meglobal Americas, Inc.-833161-CONTROL VALVE ASSEMBLY - GLOBE TYPE | 15750 | POC | USD | 1362956 | 1362955.58 | 2017-09-29 | 2018-04-27 |  | 1362956 | 0 | 54282552 |  | 51713524 | 0 | 0 |  |  | 39409116 |  |  | 0 |  |  | 0 | US | OE
FCO | RU5050 | 14950 | Hyundai Engineering & Construction Co. Ltd. | 833579 | P-Hyundai Engineering & Construction Co. Ltd., - OA # 833579 | 18239 | POC | USD | 1540446 | 1540446 | 2017-11-30 | 2018-11-01 |  | 1540446 | 0 | 86643751 |  | 1241292 | 0 | 0 | [5 empty] | 0 |  |  | 0 | ASIA | OE
FCO | RU5050 | 15388 | UOP INDIA PRIVATE LIMITED | 833442 | P-UOP INDIA PRIVATE LIMITED-833442-Auto Valves | 15511 | POC | INR | 26588699 | 420746.31 | 2017-11-30 | 2018-03-22 |  | 26588699 | 0 | 19990924 |  | 19990924 | 0 | 0 |  | 2018-04-30 | 19994577 | [5 empty] | 0 | INDIA | OE
FCO | RU5050 | 16195 | TECNIMONT SpA | 832273 | P - TECNIMONT SpA-SO # 832273 | 16994 | POC | USD | 674310 | 674309.8 | 2017-06-06 | 2018-07-20 |  | 674310 | 0 | 46654554 |  | 34326717 | 0 | 0 |  |  | 25983238 |  |  | 0 |  |  | 0 | ASIA | OE
FCO | RU5050 | 18551 | JGC CORPORATION | 833654 | P-JGC CORPORATION - SO # 833654 | 19857 | POC | USD | 374027 | 374027 | 2018-01-09 | 2019-01-31 |  | 374027 | 0 | 20122125 |  | 1383623 | 0 | 0 | [5 empty] | 0 |  |  | 0 | JAPAN | OE
FCO | RU5050 | 22531 | Construction Development Company Limited | 834083 | P-Construction Development Company-834083-Mark One control valves (4 units) | 22537 | POC | USD | 460000 | 460000 | 2018-02-20 | 2018-09-15 |  | 460000 | 0 | 23100898 |  | 5034233 | 0 | 0 | [5 empty] | 0 |  |  | 0 | MIDEAST | OE
FCO | RU5050 | 24147 | TECHNIP BENELUX B.V | 834098 | P - Technip Benelux B.V. - 834098 | 24191 | POC | USD | 301160 | 301160 | 2018-03-13 | 2018-09-15 |  | 301160 | 0 | 15622114 |  | 1466430 | 0 | 0 | [5 empty] | 0 |  |  | 0 | EUROPE | OE
FCO | RU5050 | 24450 | Belayim Petroleum CO. (PETROBEL) | 834216 | P - Belayim Petroleum Co. (PETROBEL) - 834216 (5% margin) | 26082 | POC | USD | 1035958 | 53243.19 | 2018-03-08 | 2018-11-07 |  | 53243 | 0 | 3293331 |  | 684386 | 0 | 0 | [5 empty] | 0 |  |  | 0 | NAFRICA | OE
FCO | RU5050 | 24450 | Belayim Petroleum CO. (PETROBEL) | 834216 | P - Belayim Petroleum Co. (PETROBEL) - 834216 (15% margin) | 26085 | POC | USD |  | 192515.16 | 2018-03-08 | 2018-11-07 |  | 192515 | 0 | 10654463 |  | 821025 | 0 | 0 | [8 empty] | 0 | NAFRICA | OE
FCO | RU5050 | 24450 | Belayim Petroleum CO. (PETROBEL) | 834216 | P - Belayim Petroleum Co. (PETROBEL) - 834216 (25% margin) | 26086 | POC | USD |  | 332579.57 | 2018-03-08 | 2018-11-07 |  | 332580 | 0 | 16240692 |  | 2244140 | 0 | 0 | [8 empty] | 0 | NAFRICA | OE
FCO | RU5050 | 24450 | Belayim Petroleum CO. (PETROBEL) | 834216 | P - Belayim Petroleum Co. (PETROBEL) - 834216 (35% margin) | 26087 | POC | USD |  | 413424.29 | 2018-03-08 | 2018-11-07 |  | 413424 | 0 | 17496736 |  | 1449130 | 0 | 0 | [8 empty] | 0 | NAFRICA | OE
FCO | RU5050 | 24450 | Belayim Petroleum CO. (PETROBEL) | 834216 | P - Belayim Petroleum Co. (PETROBEL) - 834216 (45% margin) | 26088 | POC | USD |  | 44195.58 | 2018-03-08 | 2018-11-07 |  | 44196 | 0 | 1582666 |  | 10336 | 0 | 0 | [8 empty] | 0 | NAFRICA | OE
FCO | RU5050 | 24451 | MATHESON TRI-GAS | 834292 | P-MATHESON TRI-GAS-834292-Various Valves | 26066 | POC | USD | 967365 | 771615 | 2018-03-27 | 2018-08-16 |  | 771615 | 0 | 39207181 |  | 7757284 | 0 | 0 | [5 empty] | 0 |  |  | 0 | US | OE
FCO | RU5050 | 24451 | MATHESON TRI-GAS | 834292 | P-MATHESON TRI-GAS-834292-DDP Charges | 26067 | PIT | USD |  | 376974 | 2018-03-27 | 2018-08-16 |  | 195750 | 0 | 9275471 |  | 0 | 0 | 0 | [8 empty] | 0 | US | OE
FCO | RU5050 | 24514 | EAGLE PROCESS SERVICE LIMITED | 834467 | P-EAGLE PROCESS SERVICE LIMITED-834467-Various Valves | 26089 | POC | USD | 900000 | 900000 | 2018-03-30 | 2020-08-31 |  | 900000 | 0 | 38089350 |  | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | ASIA | OE
FCO | RU5050 | 26375 | Air Liquide Global E&C Solutions Singapore Pte Ltd | 834163 | P-Air Liquide Global-834163-(5%) Control Valves | 26412 | POC | EUR | 210823 | 60418.02 | 2018-04-05 | 2018-08-15 |  | 49038 | 0 | 3905153 |  | 1480870 | 0 | 0 | [5 empty] | 0 |  |  | 0 | ASIA | OE
FCO | RU5050 | 26375 | Air Liquide Global E&C Solutions Singapore Pte Ltd | 834163 | P-Air Liquide Global-834163-(15%) Control Valves | 26413 | POC | EUR |  | 38669.35 | 2018-04-05 | 2018-08-15 |  | 31386 | 0 | 2232121 |  | 775156 | 0 | 0 | [8 empty] | 0 | ASIA | OE
FCO | RU5050 | 26375 | Air Liquide Global E&C Solutions Singapore Pte Ltd | 834163 | P-Air Liquide Global-834163-(25%) Control Valves | 26414 | POC | EUR |  | 94872.13 | 2018-04-05 | 2018-08-15 |  | 77002 | 0 | 4931998 |  | 2068436 | 0 | 0 | [8 empty] | 0 | ASIA | OE
FCO | RU5050 | 26375 | Air Liquide Global E&C Solutions Singapore Pte Ltd | 834163 | P-Air Liquide Global-834163-(45%) Control Valves | 26415 | POC | EUR |  | 65788.95 | 2018-04-05 | 2018-08-15 |  | 53397 | 0 | 3737884 |  | 606526 | 0 | 0 | [8 empty] | 0 | ASIA | OE
FCO | RU5050 | 28092 | Air Liquide Global E&C Solutions Singapore Pte Ltd | 834807 | P-Air Liquide Global E&C Solutions Singapore Pte Ltd-834807-POB-1 (11%-20%) | 28151 | POC | EUR | 275323.705 | 87041.96 | 2018-05-08 | 2018-09-20 |  | 72073.9968 |  | 4817207 |  | 81854 | 0 | 0 | [5 empty] | 0 |  |  | 0 | ASIA | OE
FCO | RU5050 | 28092 | Air Liquide Global E&C Solutions Singapore Pte Ltd | 834807 | P-Air Liquide Global E&C Solutions Singapore Pte Ltd-834807-POB-2 (21%-30%) | 28152 | POC | EUR |  | 92226.51 | 2018-05-08 | 2018-09-20 |  | 76366.998 |  | 4503651 |  | 102907 | 0 | 0 | [8 empty] | 0 | ASIA | OE
FCO | RU5050 | 28092 | Air Liquide Global E&C Solutions Singapore Pte Ltd | 834807 | P-Air Liquide Global E&C Solutions Singapore Pte Ltd-834807-POB-3 (31%-40%) | 28153 | POC | EUR |  | 118983.41 | 2018-05-08 | 2018-09-20 |  | 98522.7114 |  | 5035556 |  | 10298 | 0 | 0 | [8 empty] | 0 | ASIA | OE
FCO | RU5050 | 28092 | Air Liquide Global E&C Solutions Singapore Pte Ltd | 834807 | P-Air Liquide Global E&C Solutions Singapore Pte Ltd-834807-POB-4 (41%-50%) | 28154 | POC | EUR |  | 34249.66 | 2018-05-08 | 2018-09-20 |  | 28359.9988 |  | 1226497 |  | 2879 | 0 | 0 | [8 empty] | 0 | ASIA | OE
FCO | RU5062 | 14876 | S&B Engineering and Constructors, LTD | 5000619 | P - S&B Engineers and Constructors, LTD- 5000619 5/18 | 17057 | POC | USD | 405660 | 177995 | 2017-10-19 | 2018-06-29 |  | 177995 |  | 140814 |  | 132184 | - | - |  |  |  |  | 227665 |  | 2018-05-17 | 50215249 | 0 | US | OE
FCO | RU5062 | 14876 | S&B Engineering and Constructors, LTD | 5000619 | P - S&B Engineers and Constructors, LTD- 5000619 6.18 | 17058 | POC | USD |  | 227665 | 2017-10-19 | 2018-06-29 |  | 227665 |  | 247576 |  | 247576 | - | - |  | 2018-05-17 | [6 empty] | 0 | US | OE
FCO | RU5062 | 19367 | Consumers Energy Company | 5000651 | P- Consumers Energy Company - 5000651 | 19910 | POC | USD | 2404855 | 2404855 | 2017-12-21 | 2020-05-29 |  | 2404855 |  | 1515059 |  | 0 | - | - | [8 empty] | 72146 | US | OE
FCO | RU5062 | 24093 | Chevron USA Inc | 5000715 | P-Chevron USA Inc-5000715-PO Lines 1 10 11 | 27095 | POC | USD | 1344212 | 143280 | 2018-03-21 | 2018-09-17 |  | 143280 |  | 138982 |  | 0 | - | - | [8 empty] | 21282 | US | OE
FCO | RU5062 | 24093 | Chevron USA Inc | 5000715 | P-Chevron USA Inc-5000715-PO Lines 2 3 12 13 14 15 20 21 22 23 | 27096 | POC | USD |  | 382864 | 2018-03-21 | 2018-09-17 |  | 382864 |  | 371378 |  | 0 | - | - | [8 empty] | 0 | US | OE
FCO | RU5062 | 24093 | Chevron USA Inc | 5000715 | P-Chevron USA Inc-5000715-PO Lines 4 5 6 7 8 16 24 | 27097 | POC | USD |  | 237664 | 2018-03-21 | 2018-09-17 |  | 237664 |  | 230534 |  | 0 | - | - | [8 empty] | 0 | US | OE
FCO | RU5062 | 24093 | Chevron USA Inc | 5000715 | P-Chevron USA Inc-5000715-PO Line 9 | 27099 | POC | USD |  | 73218 | 2018-03-21 | 2018-09-17 |  | 73218 |  | 71021 |  | 0 | - | - | [8 empty] | 0 | US | OE
FCO | RU5062 | 24093 | Chevron USA Inc | 5000715 | P-Chevron USA Inc-5000715-PO Line 18 19 | 27100 | POC | USD |  | 137790 | 2018-03-21 | 2018-09-17 |  | 137790 |  | 133656 |  | 0 | - | - | [8 empty] | 0 | US | OE
FCO | RU5062 | 24093 | Chevron USA Inc | 5000715 | P-Chevron USA Inc-5000715-PO Line 17 | 27101 | POC | USD |  | 87726 | 2018-03-21 | 2018-09-17 |  | 87726 |  | 85094 |  | 0 | - | - | [8 empty] | 0 | US | OE
FCO | RU5062 | 24093 | Chevron USA Inc | 5000715 | P-Chevron USA Inc-5000715-PO Lines 25 thru 30 | 27102 | POC | USD |  | 281670 | 2018-03-21 | 2018-09-17 |  | 281670 |  | 273220 |  | 0 | - | - | [8 empty] | 0 | US | OE
FCO | RU5085 | 10181 | United Refining Inc | 641835 | P-United Refining Inc-641835 | 10236 | POC | USD | 287010.83 | 305851 | 2017-09-25 | 2018-04-30 | [5 empty] | 0 |  |  |  | 2018-01-31 | [6 empty] | 42112.91 | US | AM
FCO | RU5085 | 10181 | United Refining Inc | 641835 | P-United Refining Inc-641835 | 10237 | POC | USD |  | 285397.91 | 2017-09-25 | 2018-04-30 |  | 287010.83 |  | 137356.79 |  | 137357 |  |  |  | 2018-04-30 | [6 empty] | 0 | US | AM
FCO | RU5115 | 7313 | CB&I Areva Mox Services LLC | 1718674 | P - CB&I Areva Mox Services LLC - 1718674 | 7315 | POC | USD | 868823.35 | 868823.35 | 2012-06-28 | 2018-12-31 |  | 868823.35 | 0 | 817731 |  | 817731 | [10 empty] | 0 | US | OE
FCO | RU5115 | 22094 | Hengli Petrochemical (Dalian) Refinery Co. Ltd. | 1619444 | P-Hengli Petrochemical-1619444-POb1 | 22295 | POC | USD | 4283400 | 7778 | 2018-01-19 | 2018-09-19 |  | 7778 | 0 | 20682.9 |  | 1831.24 | 0 | 551.7 |  |  |  |  | 856680 |  | 2018-05-07 | INV01-1619444-R0 | 42834 | CHINA | OE
FCO | RU5115 | 22094 | Hengli Petrochemical (Dalian) Refinery Co. Ltd. | 1619444 | P-Hengli Petrochemical-1619444-POb2 | 22296 | POC | USD |  | 4956 | 2018-01-19 | 2018-09-19 |  | 4956 | 0 | 12124.35 |  | 4862.12 | 0 | 1436.81 | [8 empty] | 0 |  | OE
FCO | RU5115 | 22094 | Hengli Petrochemical (Dalian) Refinery Co. Ltd. | 1619444 | P-Hengli Petrochemical-1619444-POb3 | 22297 | POC | USD |  | 16523 | 2018-01-19 | 2018-09-19 |  | 16523 | 0 | 15830.25 |  | 4185.89 | 0 | 5045.1 | [8 empty] | 0 |  | OE
FCO | RU5115 | 22094 | Hengli Petrochemical (Dalian) Refinery Co. Ltd. | 1619444 | P-Hengli Petrochemical-1619444-POb4 | 22298 | POC | USD |  | 478360 | 2018-01-19 | 2018-09-19 |  | 478360 | 0 | 408720.49 |  | 113100.22 | 10583.38 | 22937.69 | [8 empty] | 0 |  | OE
FCO | RU5115 | 22094 | Hengli Petrochemical (Dalian) Refinery Co. Ltd. | 1619444 | P-Hengli Petrochemical-1619444-POb5 | 22299 | POC | USD |  | 2537901 | 2018-01-19 | 2018-09-19 |  | 2537901 | 0 | 2102330.74 |  | 138055.38 | 2250.77 | 66617.11 | [8 empty] | 0 |  | OE
FCO | RU5115 | 22094 | Hengli Petrochemical (Dalian) Refinery Co. Ltd. | 1619444 | P-Hengli Petrochemical-1619444-POb6 | 22300 | POC | USD |  | 777005 | 2018-01-19 | 2018-09-19 |  | 777005 | 0 | 587083.37 |  | 354115.01 | 13042.74 | 49977.67 | [8 empty] | 0 |  | OE
FCO | RU5115 | 22094 | Hengli Petrochemical (Dalian) Refinery Co. Ltd. | 1619444 | P-Hengli Petrochemical-1619444-POb7 | 22301 | POC | USD |  | 169070 | 2018-01-19 | 2018-09-19 |  | 169070 | 0 | 120338.66 |  | 89174.76 | 915.93 | 26013.16 | [8 empty] | 0 |  | OE
FCO | RU5115 | 22094 | Hengli Petrochemical (Dalian) Refinery Co. Ltd. | 1619444 | P-Hengli Petrochemical-1619444-POb8 | 22302 | POC | USD |  | 84593 | 2018-01-19 | 2018-09-19 |  | 84593 | 0 | 56176.66 |  | 47996.88 | 0 | 13857.53 | [8 empty] | 0 |  | OE
FCO | RU5115 | 22094 | Hengli Petrochemical (Dalian) Refinery Co. Ltd. | 1619444 | P-Hengli Petrochemical-1619444-POb9 | 22303 | POC | USD |  | 188122 | 2018-01-19 | 2018-09-19 |  | 188122 | 0 | 61581.7 |  | 0 | 0 | 0 | [8 empty] | 0 |  | OE
FCO | RU5115 | 22094 | Hengli Petrochemical (Dalian) Refinery Co. Ltd. | 1619444 | P-Hengli Petrochemical-1619444-POb10 | 22304 | POC | USD |  | 9682 | 2018-01-19 | 2018-09-19 |  | 9682 | 0 | 2095.93 |  | 0 | 0 | 0 | [8 empty] | 0 |  | OE
FCO | RU5115 | 22094 | Hengli Petrochemical (Dalian) Refinery Co. Ltd. | 1619444 | P-Hengli Petrochemical-1619444-POb11 | 22305 | POC | USD |  | 9410 | 2018-01-19 | 2018-09-19 |  | 9410 | 0 | 713.13 |  | 7422.97 | 0 | 2108.57 | [8 empty] | 0 |  | OE
FCO | RU5200 | 3867 | State Nuclear Power Engr Corp | 110408 | P-State Nuclear Power Engr Corp Ltd-110408-38" Main Steam Isolation Valve- Unit 1- Valve 1 &2 and Portable filtering unit | 4036 | POC | USD | 3631048 | 1821134 | 2015-10-08 | 2019-08-31 |  | 1821134 |  | 1337398 |  | 41352 | [10 empty] | 0 | CHINA | AM
FCO | RU5200 | 3867 | State Nuclear Power Engr Corp | 110408 | P-State Nuclear Power Engr Corp Ltd-110408-38" Main Steam Isolation Valve- Unit 2- Valve 1 &2 | 4037 | POC | USD |  | 1809914 | 2015-10-08 | 2019-08-31 |  | 1809914 |  | 1329158 |  | 14105 | [10 empty] | 0 |  | AM
FCO | RU5200 | 4381 | Westinghouse Electric Company | 91170 | P-Westinghouse Electric Company-91170-POB1 | 12805 | POC | USD | 0 | 16542495.61 | 2017-07-05 | 2018-07-30 | [16 empty] | 0 | US | OE
FCO | RU5200 | 4392 | Hengli Petro Refinery Co. Ltd. | 120801 & 120794 | P-Hengli Petrochemical Refinery Co. Ltd-120801 & 120794-POB1 PACKAGE 1 HCK2A | 9123 | POC | USD | 9441339 | 1503648.99 | 2017-06-13 | 2018-01-31 |  | 1605910 | 102261.3 | 1603819 |  | 693390 |  |  |  |  | 224028 |  | 6214756 |  | 2018-05-07 | 338406 | 0 | CHINA | OE
FCO | RU5200 | 4392 | Hengli Petro Refinery Co. Ltd. | 120801 & 120794 | P-Hengli Petrochemical Refinery Co. Ltd-120801 & 120794-POB2 PACKAGE 2 HCK2B | 15137 | POC | USD |  | 2267412.62 | 2017-06-13 | 2018-01-31 |  | 2421617 | 154203.92 | 2560948 |  | 842049 |  |  |  |  | 443998 | [5 empty] | 0 |  | OE
FCO | RU5200 | 4392 | Hengli Petro Refinery Co. Ltd. | 120801 & 120794 | P-Hengli Petrochemical Refinery Co. Ltd-120801 & 120794-POB3 PACKAGE 3 HOIL | 15140 | POC | USD |  | 1181701.85 | 2017-06-13 | 2018-01-31 |  | 1262068 | 80366.08 | 1493603 |  | 811676 |  |  |  |  | 537886 | [5 empty] | 0 |  | OE
FCO | RU5200 | 4392 | Hengli Petro Refinery Co. Ltd. | 120801 & 120794 | P-Hengli Petrochemical Refinery Co. Ltd-120801 & 120794-POB4 PACKAGE 4 DIESAL | 15142 | POC | USD |  | 769505.18 | 2017-06-13 | 2018-01-31 |  | 821838 | 52333.09 | 808354 |  | 472668 |  |  |  |  | 94887 | [5 empty] | 0 |  | OE
FCO | RU5200 | 4392 | Hengli Petro Refinery Co. Ltd. | 120801 & 120794 | P-Hengli Petrochemical Refinery Co. Ltd-120801 & 120794-POB5 STEAM LINE VALVES AND PARTS | 16772 | POC | USD |  | 2026773.53 | 2017-06-13 | 2018-01-31 |  | 2111065 | 84291.54 | 2773755 |  | 2641671 |  |  |  |  | 2204470 | [5 empty] | 0 |  | OE
FCO | RU5200 | 4392 | Hengli Petro Refinery Co. Ltd. | 120801 & 120794 | P-Hengli Petrochemical Refinery Co. Ltd-120801 & 120794-POB6 FEEDWAATER LINE VALVES AND PARTS | 16773 | POC | USD |  | 1182657.91 | 2017-06-13 | 2018-01-31 |  | 1218841 | 36183.01 | 1576023 |  | 1500975 |  |  |  |  | 1157966 | [5 empty] | 0 |  | OE
FCO | RU5200 | 4449 | State Nuclear Power Engr Corp | 110410 | P - State Nuclear Power Engr Corp Ltd-110410-38" Main Steam Isolation Valve- Unit 1- Valve 1 &2 and Portable filtering unit | 4454 | POC | USD | 3631048 | 1821134 | 2015-10-08 | 2019-08-31 |  | 1821134 |  | 1337398 |  | 0 | [10 empty] | 0 | CHINA | OE
FCO | RU5200 | 4449 | State Nuclear Power Engr Corp | 110410 | P - State Nuclear Power Engr Corp Ltd-110410-38" Main Steam Isolation Valve- Unit 2- Valve 1 &2 | 4455 | POC | USD |  | 1809914 | 2015-10-08 | 2019-08-31 |  | 1809914 |  | 1329158 |  | 0 | [10 empty] | 0 |  | OE
FCO | RU5200 | 4458 | State Nuclear Power Engr Corp | 110403 | P-State Nuclear Power Engr Corp Ltd-110403-38" Main Steam Isolation Valve- Unit 1- Valve 1 &2 and Portable filtering unit | 4591 | POC | USD | 3631048 | 1821134 | 2015-10-08 | 2019-08-31 |  | 1821134 |  | 1337398 |  | 83456 | [10 empty] | 0 | CHINA | OE
FCO | RU5200 | 4458 | State Nuclear Power Engr Corp | 110403 | P-State Nuclear Power Engr Corp Ltd-110403-38” Main Steam Isolation Valve-Unit 2 – Valve 1 &2 | 4592 | POC | USD |  | 1809914 | 2015-10-08 | 2019-08-31 |  | 1809914 |  | 1329158 |  | 48555 | [10 empty] | 0 |  | OE
FCO | RU5200 | 4645 | Westinghouse Electric Company | 91172 | P - WESTINGHOUSE ELECTRIC CO LTD - POB1 91172 | 15054 | POC | USD | 0 | 3429923.5 | 2017-06-14 | 2018-12-31 | [16 empty] | 0 | US | OE
FCO | RU5200 | 4650 | Westinghouse Electric Co LLC | 91175 | P-Westinghouse Electric Co LLC-91175-POB#1 10 FIG 1515-FW (CF3M) W/SB-3 DS 116 | 7944 | POC | USD | 17399203 | 1853438.11 | 2010-10-01 | 2018-10-31 |  | 1853438 |  | 1270439 |  | 1270438 |  |  |  | 2017-11-30 | [6 empty] | 0 | US | OE
FCO | RU5200 | 4650 | Westinghouse Electric Co LLC | 91175 | P-Westinghouse Electric Co LLC-91175-POB#2 10-1500-FW (CF3M) W/SB-3 DS 120 | 7945 | POC | USD |  | 438532.19 | 2010-10-01 | 2018-10-31 |  | 438532 |  | 309993 |  | 309993 |  |  |  | 2017-11-30 | [6 empty] | 0 |  | OE
FCO | RU5200 | 4650 | Westinghouse Electric Co LLC | 91175 | P-Westinghouse Electric Co LLC-91175-POB#4 10-1515-FW (CF3M) W/SB-2 | 7947 | POC | USD |  | 351871.08 | 2010-10-01 | 2018-10-31 |  | 351871 |  | 260827 |  | 260827 |  |  |  | 2017-11-30 | [6 empty] | 0 |  | OE
FCO | RU5200 | 4650 | Westinghouse Electric Co LLC | 91175 | P-Westinghouse Electric Co LLC-91175-POB#5 14-1515-FW (CF3M) W/SB-3 DS 118 | 7948 | POC | USD |  | 519540.58 | 2010-10-01 | 2018-10-31 |  | 519541 |  | 436605 |  | 258430 |  |  |  |  | 204677 | [5 empty] | 0 |  | OE
FCO | RU5200 | 4650 | Westinghouse Electric Co LLC | 91175 | P-Westinghouse Electric Co LLC-91175-POB#6 14-1515-FW (CF3M) W/SB-3 DS 117 | 7949 | POC | USD |  | 2116135.24 | 2010-10-01 | 2018-10-31 |  | 2116135 |  | 2367017 |  | 554343 |  |  |  |  | 320121 | [5 empty] | 0 |  | OE
FCO | RU5200 | 4650 | Westinghouse Electric Co LLC | 91175 | P-Westinghouse Electric Co LLC-91175-POB#7 3 -1530-FW (CF3M) W/SB-0 DS 100 | 7950 | POC | USD |  | 184997.11 | 2010-10-01 | 2018-10-31 |  | 184997 |  | 194124 |  | 84811 |  |  |  |  | 84811 | [5 empty] | 0 |  | OE
FCO | RU5200 | 4650 | Westinghouse Electric Co LLC | 91175 | P-Westinghouse Electric Co LLC-91175-POB#8 3-1530-FW (CF3M) W/SB-1 DS 104 | 7951 | POC | USD |  | 237259.1 | 2010-10-01 | 2018-10-31 |  | 237259 |  | 207539 |  | 207539 |  |  |  | 2017-11-30 | [6 empty] | 0 |  | OE
FCO | RU5200 | 4650 | Westinghouse Electric Co LLC | 91175 | P-Westinghouse Electric Co LLC-91175-POB#9 3 FIG B2016(CF3M)JMTY | 7952 | POC | USD |  | 256988.01 | 2010-10-01 | 2018-10-31 |  | 256988 |  | 172411 |  | 172411 |  |  |  | 2017-11-30 | [6 empty] | 0 |  | OE
FCO | RU5200 | 4650 | Westinghouse Electric Co LLC | 91175 | P-Westinghouse Electric Co LLC-91175-POB#12 3-1890-FW (CF3M) W/SB-1 | 7955 | POC | USD |  | 475630.69 | 2010-10-01 | 2018-10-31 |  | 475631 |  | 485199 |  | 377690 |  |  |  |  | 346814 | [5 empty] | 0 |  | OE
FCO | RU5200 | 4650 | Westinghouse Electric Co LLC | 91175 | P-Westinghouse Electric Co LLC-91175-POB#13 4 -1530-FW (CF3M) W/SB-0 | 7956 | POC | USD |  | 353185.08 | 2010-10-01 | 2018-10-31 |  | 353185 |  | 317458 |  | 317458 |  |  |  | 2017-11-30 | [6 empty] | 0 |  | OE
FCO | RU5200 | 4650 | Westinghouse Electric Co LLC | 91175 | P-Westinghouse Electric Co LLC-91175-POB#14 4 FIG BD2026(CF3M)JMTY DS 131 | 7957 | POC | USD |  | 650368.38 | 2010-10-01 | 2018-10-31 |  | 650368 |  | 510335 |  | 432824 |  |  |  |  | 432824 | [5 empty] | 0 |  | OE
FCO | RU5200 | 4650 | Westinghouse Electric Co LLC | 91175 | P-Westinghouse Electric Co LLC-91175-POB#15 8-1530-FW (CF3M) W/SB-3 dS 113 | 7958 | POC | USD |  | 1881477.59 | 2010-10-01 | 2018-10-31 |  | 1881478 |  | 1629763 |  | 1338538 |  |  |  |  | 1290875 | [5 empty] | 0 |  | OE
FCO | RU5200 | 4650 | Westinghouse Electric Co LLC | 91175 | P-Westinghouse Electric Co LLC-91175-POB#16 4-1530-FW (CF3M) W/SB-1 DS 103 | 7959 | POC | USD |  | 777075.03 | 2010-10-01 | 2018-10-31 |  | 777075 |  | 631179 |  | 508964 |  |  |  |  | 508964 | [5 empty] | 0 |  | OE
FCO | RU5200 | 4650 | Westinghouse Electric Co LLC | 91175 | P-Westinghouse Electric Co LLC-91175-POB#17 6 FIG 900-FW (WC6) W/SB-2-2 DS 108 | 7960 | POC | USD |  | 542182.96 | 2010-10-01 | 2018-10-31 |  | 542183 |  | 499777 |  | 222050 |  |  |  |  | 222050 | [5 empty] | 0 |  | OE
FCO | RU5200 | 4650 | Westinghouse Electric Co LLC | 91175 | P-Westinghouse Electric Co LLC-91175-POB#18 6-1500-FW (CF3M) w/SB-2 DS 107 | 7961 | POC | USD |  | 270083.95 | 2010-10-01 | 2018-10-31 |  | 270084 |  | 231787 |  | 231787 |  |  |  | 2018-03-31 | [6 empty] | 0 |  | OE
FCO | RU5200 | 4650 | Westinghouse Electric Co LLC | 91175 | P-Westinghouse Electric Co LLC-91175-POB#19 6-150-FW (CF3M) W/SB-00 DS 110 | 7962 | POC | USD |  | 800680.18 | 2010-10-01 | 2018-10-31 |  | 800680 |  | 743598 |  | 689590 |  |  |  |  | 547291 | [5 empty] | 0 |  | OE
FCO | RU5200 | 4650 | Westinghouse Electric Co LLC | 91175 | P-Westinghouse Electric Co LLC-91175-POB#20 6-900-FW W/SB-2 DS 109 | 7963 | POC | USD |  | 555709.21 | 2010-10-01 | 2018-10-31 |  | 555709 |  | 484239 |  | 212726 |  |  |  |  | 212726 | [5 empty] | 0 |  | OE
FCO | RU5200 | 4650 | Westinghouse Electric Co LLC | 91175 | P-Westinghouse Electric Co LLC-91175-POB#21 8 FIG BD2026(CF3M)JMTY DS 132 | 7964 | POC | USD |  | 1834565.28 | 2010-10-01 | 2018-10-31 |  | 1834565 |  | 1212214 |  | 1068911 |  |  |  |  | 1068911 | [5 empty] | 0 |  | OE
FCO | RU5200 | 4650 | Westinghouse Electric Co LLC | 91175 | P-Westinghouse Electric Co LLC-91175-POB#22 8-1500-FW (CF3M) W/SB-1 DS 111 | 7965 | POC | USD |  | 287403.15 | 2010-10-01 | 2018-10-31 |  | 287403 |  | 240197 |  | 240197 |  |  |  | 2017-11-30 | [6 empty] | 0 |  | OE
FCO | RU5200 | 4650 | Westinghouse Electric Co LLC | 91175 | P-Westinghouse Electric Co LLC-91175-POB#23 8-150-FW (CF3M) W/SB-00 DS 115 | 7966 | POC | USD |  | 556306.4 | 2010-10-01 | 2018-10-31 |  | 556306 |  | 500697 |  | 205633 |  |  |  |  | 205582 | [5 empty] | 0 |  | OE
FCO | RU5200 | 4650 | Westinghouse Electric Co LLC | 91175 | P-Westinghouse Electric Co LLC-91175-POB#24 8-1515-FW (CF3M) W/SB-2 DS 106 | 7967 | POC | USD |  | 1352373.14 | 2010-10-01 | 2018-10-31 |  | 1352373 |  | 803027 |  | 590832 |  |  |  |  | 491948 | [5 empty] | 0 |  | OE
FCO | RU5200 | 4650 | Westinghouse Electric Co LLC | 91175 | P-Westinghouse Electric Co LLC-91175-POB#25 8-1530-FW (CF3M) W/SB-3 DS 114 | 7968 | POC | USD |  | 762758.87 | 2010-10-01 | 2018-10-31 |  | 762759 |  | 639239 |  | 639239 |  |  |  | 2018-03-31 | [6 empty] | 0 |  | OE
FCO | RU5200 | 4650 | Westinghouse Electric Co LLC | 91175 | P-Westinghouse Electric Co LLC-91175-POB#26 8-900-FW (CF3M) W/SB-0 | 7969 | POC | USD |  | 232469.08 | 2010-10-01 | 2018-10-31 |  | 232469 |  | 190715 |  | 80846 |  |  |  |  | 80846 | [5 empty] | 0 |  | OE
FCO | RU5200 | 4650 | Westinghouse Electric Co LLC | 91175 | P-Westinghouse Electric Co LLC-91175-POB#27 Spare Parts Misc | 7970 | POC | USD |  | 108174.45 | 2010-10-01 | 2018-10-31 |  | 108174 |  | 30505 |  | 30310 |  |  |  |  | 28917 | [5 empty] | 0 |  | OE
FCO | RU5200 | 4656 | Westinghouse Electric Co LLC | 91177 | P-Westinghouse Electric Co LLC-91177-POB1-MSIV Unit 3 (QTY 2) - 1st Valve-Documentation and Engineering | 7646 | POC | USD | 3429923 | 1727589.01 | 2017-08-28 | 2018-03-31 |  | 1727589 |  | 2002930 |  | 1050441 |  |  |  |  | 978232 | [5 empty] | 0 | US | OE
FCO | RU5200 | 4656 | Westinghouse Electric Co LLC | 91177 | P-Westinghouse Electric Co LLC-91177-MSIV Unit 4 (QTY 1) - 1st Valve-Documentation and Engineering | 7648 | POC | USD |  | 1692794.49 | 2017-08-28 | 2018-03-31 |  | 1692794 |  | 2045687 |  | 1506835 | [10 empty] | 0 |  | OE
FCO | RU5200 | 4656 | Westinghouse Electric Co LLC | 91177 | P-Westinghouse Electric Co LLC-91177- POB3-Portable Hydralic Filtering Unit | 7650 | POC | USD |  | 9540 | 2017-08-28 | 2018-03-31 |  | 9540 |  | 5220 |  | 5220 |  |  |  | 2018-03-30 | [6 empty] | 0 |  | OE
FCO | RU5200 | 4669 | China Nuclear Energy Industry Corporation | 91247 | P-CHINA NUCLEAR ENERGY INDUSTRY CORPORATION-91247-MSIV Unit 1 (QTY 3) | 7303 | POC | USD | 4650001 | 1763310.68 | 2016-04-12 | 2018-06-30 |  | 1763311 |  | 1629375 |  | 1551786 | [10 empty] | 0 | CHINA | OE
FCO | RU5200 | 4669 | China Nuclear Energy Industry Corporation | 91247 | P-CHINA NUCLEAR ENERGY INDUSTRY CORPORATION-91247-MSIV Unit 2 (QTY 3) | 7304 | POC | USD |  | 1734611.65 | 2016-04-12 | 2018-06-30 |  | 1734612 |  | 1385308 |  | 603250 | [10 empty] | 0 |  | OE
FCO | RU5200 | 4669 | China Nuclear Energy Industry Corporation | 91247 | P-CHINA NUCLEAR ENERGY INDUSTRY CORPORATION-91247-Spare Parts Standard & Special Tools | 7305 | POC | USD |  | 803048.54 | 2016-04-12 | 2018-06-30 |  | 803049 |  | 602286 |  | 172034 | [10 empty] | 0 |  | OE
FCO | RU5200 | 4669 | China Nuclear Energy Industry Corporation | 91247 | P-CHINA NUCLEAR ENERGY INDUSTRY CORPORATION-91247-Spare Parts Strategic | 7306 | POC | USD |  | 213592.23 | 2016-04-12 | 2018-06-30 |  | 213592 |  | 160194 |  | 36205 | [10 empty] | 0 |  | OE
FCO | RU5200 | 4669 | China Nuclear Energy Industry Corporation | 91247 | P-CHINA NUCLEAR ENERGY INDUSTRY CORPORATION-91247-Extended Warranty | 7307 | SL | USD |  | 135436.89 | 2016-04-12 | 2018-06-30 |  | 135437 |  |  |  | 0 | [10 empty] | 0 |  | OE | 2018-10-01 | 2023-09-30
FCO | RU5200 | 5088 | China Nuclear Power Engineering Company LTD. | 119209 | P-GUANGXI FANGCHENGGANG NUCLEAR POWER CO. LT-119209-Main Steam Isolation Valve (3) Unit 3 | 5134 | POC | USD | 8138647 | 1817381.59 | 2016-12-22 | 2019-08-30 |  | 1817382 |  | 1412105 |  | 1190 | [10 empty] | 0 | CHINA | OE
FCO | RU5200 | 5088 | China Nuclear Power Engineering Company LTD. | 119209 | P-GUANGXI FANGCHENGGANG NUCLEAR POWER CO. LT-119209-Main Steam Isolation Valve (3) Unit 4 | 5135 | POC | USD |  | 1815693.33 | 2016-12-22 | 2019-08-30 |  | 1815693 |  | 1410794 |  | 813 | [10 empty] | 0 |  | OE
FCO | RU5200 | 5088 | China Nuclear Power Engineering Company LTD. | 119209 | P-GUANGXI FANGCHENGGANG NUCLEAR POWER CO. LT-119209-FLLIV (6) Unit 3 | 5136 | POC | USD |  | 1938534.2 | 2016-12-22 | 2019-08-30 |  | 1938534 |  | 1506241 |  | 50697 | [10 empty] | 0 |  | OE
FCO | RU5200 | 5088 | China Nuclear Power Engineering Company LTD. | 119209 | P-GUANGXI FANGCHENGGANG NUCLEAR POWER CO. LT-119209-FLLIV (6) Unit 4 | 5137 | POC | USD |  | 1936283.19 | 2016-12-22 | 2019-08-30 |  | 1936283 |  | 1504492 |  | 27336 | [10 empty] | 0 |  | OE
FCO | RU5200 | 5088 | China Nuclear Power Engineering Company LTD. | 119209 | P-GUANGXI FANGCHENGGANG NUCLEAR POWER CO. LT-119209-Parts MSIV | 5138 | POC | USD |  | 276521.38 | 2016-12-22 | 2019-08-30 |  | 276521 |  | 214857 |  | 1101 | [10 empty] | 0 |  | OE
FCO | RU5200 | 5088 | China Nuclear Power Engineering Company LTD. | 119209 | P-GUANGXI FANGCHENGGANG NUCLEAR POWER CO. LT-119209-Parts FFLIV | 5139 | POC | USD |  | 209526.48 | 2016-12-22 | 2019-08-30 |  | 209526 |  | 162802 |  | 14958 | [10 empty] | 0 |  | OE
FCO | RU5200 | 5088 | China Nuclear Power Engineering Company LTD. | 119209 | P-GUANGXI FANGCHENGGANG NUCLEAR POWER CO. LT -119209-Warranty | 5140 | SL | USD |  | 144707.83 | 2016-12-22 | 2019-08-30 |  | 144708 |  |  |  | 0 | [10 empty] | 0 |  | OE | 2019-02-28 | 2022-08-27
FCO | RU5200 | 5348 | CB&I Areva Mox Services LLC | 115898 | P-CB&I AREVA MOX Services LLC-115898-Base Contract POB1 | 5947 | POC | USD | 1425019 | 276573.51 | 2015-12-16 | 2025-05-08 |  | 276574 |  | 186309 |  | 186309 |  |  |  | 2018-05-31 | [6 empty] | 0 | US | OE
FCO | RU5200 | 5348 | CB&I Areva Mox Services LLC | 115898 | P - CB&I AREVA MOX Services LLC - 115898 POB2 Option | 5948 | POC | USD |  | 1148445.49 | 2015-12-16 | 2025-05-08 |  | 1148445 |  | 859560 |  | 0 | [10 empty] | 0 |  | OE
FCO | RU5200 | 6147 | NOOTER/ERIKSEN | 113555 | P-NOOTER/ERIKSEN-113555-Valves 1 | 6158 | POC | USD | 0 | 275472 | 2016-03-16 | 2018-03-31 | [16 empty] | 0
FCO | RU5200 | 6147 | NOOTER/ERIKSEN | 113555 | P-NOOTER/ERIKSEN-113555-Valves 2 | 6159 | POC | USD |  | 147258 | 2016-03-16 | 2018-03-31 | [16 empty] | 0
FCO | RU5200 | 6286 | STATE NUCLEAR POWER ENGR CORP LTD | 110261 | P-STATE NUCLEAR POWER ENGR CORP LTD -110261-PV 68 MFIV (QTY4) | 7439 | POC | USD | 645352 | 645286.27 | 2015-10-08 | 2019-08-31 |  | 642513 |  | 488311 |  | 0 | [10 empty] | 0 | CHINA | OE
FCO | RU5200 | 6286 | STATE NUCLEAR POWER ENGR CORP LTD | 110261 | P - STATE NUCLEAR POWER ENGR CORP LTD SNPEC - 110261 - SPARE PARTS | 7440 | POC | USD |  | 2838.73 | 2015-10-08 | 2019-08-31 |  | 2839 |  | 2157 |  | 0 | [10 empty] | 0 |  | OE
FCO | RU5200 | 6291 | STATE NUCLEAR POWER ENGR CORP LTD SNPEC | 110262 | P-STATE NUCLEAR POWER ENGR CORP LTD -110262-PV 68 MFIV (QTY4) | 7435 | POC | USD | 645352 | 645286.27 | 2015-10-08 | 2019-08-31 |  | 642513 |  | 488311 |  | 0 | [10 empty] | 0 | CHINA | OE
FCO | RU5200 | 6291 | STATE NUCLEAR POWER ENGR CORP LTD SNPEC | 110262 | P-STATE NUCLEAR POWER ENGR CORP LTD -110262-Spare Parts | 7436 | POC | USD |  | 2838.73 | 2015-10-08 | 2019-08-31 |  | 2839 |  | 2157 |  | 0 | [10 empty] | 0 |  | OE
FCO | RU5200 | 6296 | STATE NUCLEAR POWER ENGR CORP LTD | 110263 | P-STATE NUCLEAR POWER ENGR CORP LTD -110263-PV 68 MFIV (QTY4) | 7549 | POC | USD | 645352 | 645286.27 | 2015-10-08 | 2019-08-30 |  | 642513 |  | 488311 |  | 1281 | [10 empty] | 0 | CHINA | OE
FCO | RU5200 | 6296 | STATE NUCLEAR POWER ENGR CORP LTD | 110263 | P - STATE NUCLEAR POWER ENGR CORP LTD SNPEC - 110263 - SPARE PARTS | 7550 | POC | USD |  | 2838.73 | 2015-10-08 | 2019-08-30 |  | 2839 |  | 2157 |  | 0 | [10 empty] | 0 |  | OE
FCO | RU5200 | 6301 | STATE NUCLEAR POWER ENGR CORP LTD (CNPEC) | 110407 | P-STATE NUCLEAR POWER ENGR CORP LTD -110407-PV 67 MFIV (QTY4) | 8080 | POC | USD | 1495448 | 1441645.58 | 2014-12-01 | 2019-08-30 |  | 1441646 |  | 1095651 |  | 22672 | [10 empty] | 0 | CHINA | OE
FCO | RU5200 | 6301 | STATE NUCLEAR POWER ENGR CORP LTD (CNPEC) | 110407 | P-STATE NUCLEAR POWER ENGR CORP LTD -110407-Extended Warranty | 8081 | SL | USD |  | 53802.42 | 2014-12-01 | 2019-08-30 |  | 53802 |  |  |  | 0 | [10 empty] | 0 |  | OE | 2019-06-03 | 2024-06-02
FCO | RU5200 | 6313 | STATE NUCLEAR POWER ENGR CORP LTD (SNPEC) | 110409 | P-STATE NUCLEAR POWER ENGR CORP LTD -110409-PV 67 MFIV (QTY4) | 8000 | POC | USD | 1495448 | 1441645.58 | 2014-12-01 | 2019-05-17 |  | 1441646 |  | 1095651 |  | 43471 | [10 empty] | 0 | CHINA | OE
FCO | RU5200 | 6313 | STATE NUCLEAR POWER ENGR CORP LTD (SNPEC) | 110409 | P-STATE NUCLEAR POWER ENGR CORP LTD -110409-Extended Warranty | 8001 | SL | USD |  | 53802.42 | 2014-12-01 | 2019-05-17 |  | 53802 |  |  |  | 0 | [10 empty] | 0 |  | OE | 2019-06-03 | 2024-06-02
FCO | RU5200 | 6533 | AMSEC LLC | 114117 | P- AMSEC LLC -114117-12" 600 FW-GATE VALVE (QTY 2) | 8154 | POC | USD | 503874 | 503874 | 2015-09-24 | 2025-12-31 |  | 503874 |  | 269573 |  | 2388 | [10 empty] | 0 | US | OE
FCO | RU5200 | 6799 | Westinghouse Electric Co. LLC | 115654 | P-Westinghouse Electric Co. LLC-115654-Spare Parts | 6858 | POC | USD | 335736 | 335736 | 2016-02-25 | 2018-06-30 |  | 335736 |  | 142493 |  | 115061 |  |  |  |  | 115061 | [5 empty] | 0 | US | AM
FCO | RU5200 | 6814 | CHINA HK JIAMING ENGINEERING LTD. | 120030 | P-CHINA HK JIAMING ENGINEERING LTD -120030-SUPPLIMENTAL VALVES | 8023 | POC | USD | 695258 | 695258 | 2017-03-15 | 2018-11-08 |  | 695258 |  | 743663 |  | 743663 |  |  |  | 2018-03-30 | [6 empty] | 0 | US | OE
FCO | RU5200 | 6819 | STATE NUCLEAR POWER ENGR CORP LTD (SNPEC) | 120153 | P-STATE NUCLEAR POWER ENGR CORP LTD -120153-PV 64 MSIV (QTY2) | 7987 | POC | USD | 2347591 | 2347591.27 | 2014-03-17 | 2019-08-30 |  | 2347591 |  | 1849667 |  | 0 | [6 empty] | 845112 |  | 2018-05-07 | 338724 | 0 | CHINA | OE
FCO | RU5200 | 6819 | STATE NUCLEAR POWER ENGR CORP LTD (SNPEC) | 120153 | P-STATE NUCLEAR POWER ENGR CORP LTD -120153-Extended Warranty | 7988 | SL | USD |  | 67014.73 | 2014-03-17 | 2019-08-30 | [5 empty] | 0 | [10 empty] | 0 |  | OE | 2020-01-01 | 2024-12-31
FCO | RU5200 | 6831 | AREVA NP | 120216 | P-AREVA NP-120216-Main Steam Isolation Valves QTY 4 | 10223 | POC | USD | 10357970 | 10357970 | 2017-04-03 | 2020-12-28 |  | 10357970 |  | 8962644 |  | 0 | [10 empty] | 0 | EUROPE | OE
FCO | RU5200 | 6853 | CHINA NUCLEAR POWER ENGINEERING COMPANY LTD | 120832 | P- CHINA NUCLEAR POWER ENGINEERING COMPANY LTD -120832-SPARE PARTS LOT | 8608 | POC | USD | 417064 | 417064 | 2017-05-11 | 2018-06-25 |  | 417064 |  | 250238 |  | 4390 |  |  |  |  | 69330 | [5 empty] | 0 | CHINA | OE
FCO | RU5200 | 6864 | KOREA HYDRO & NUCLEAR POWER CO LTD | 121153 | P-KOREA HYDRO & NUCLEAR POWER CO-121153-SPARE PARTS & CFSI CHARGE | 7789 | POC | USD | 2362172 | 2338172 | 2017-06-26 | 2018-03-05 |  | 2362172 | 24000 | 480929 |  | 480929 |  |  |  | 2018-04-30 | [6 empty] | 177163 | ASIA | OE
FCO | RU5200 | 7131 | STATE NUCLEAR POWER ENGR CORP LTD (SNPEC) | 110411 | P-STATE NUCLEAR POWER ENGR CORP LTD -110411-PV 67 MFIV (QTY4) | 7998 | POC | USD | 1441646 | 1441645.58 | 2014-12-01 | 2019-08-30 |  | 1441646 |  | 1095641 |  | 0 | [10 empty] | 0 | CHINA | OE
FCO | RU5200 | 7131 | STATE NUCLEAR POWER ENGR CORP LTD (SNPEC) | 110411 | P-STATE NUCLEAR POWER ENGR CORP LTD -110411-Extended Warranty | 7999 | SL | USD |  | 53802.42 | 2014-12-01 | 2019-08-30 | [5 empty] | 0 | [10 empty] | 0 |  | OE | 2020-01-01 | 2024-12-31
FCO | RU5200 | 7157 | STATE NUCLEAR ENGR CORP LTD (SNPEC) | 118007 | P-STATE NUCLEAR POWER ENGR CORP LTD -118007-PV 68 MFIV (QTY2) | 7790 | POC | USD | 873708 | 873708 | 2016-08-24 | 2019-02-06 |  | 873708 |  | 675376 |  | 14209 | [10 empty] | 0 | CHINA | OE
FCO | RU5200 | 7163 | STATE NUCLEAR POWER ENGR CORP LTD (SNPEC) | 118012 | P-STATE NUCLEAR POWER ENGR CORP LTD -118012-PV 68 Check Valve (QTY2) | 8138 | POC | USD | 364874 | 364874 | 2016-08-24 | 2018-11-30 |  | 364874 |  | 235308 |  | 0 | [10 empty] | 0 | CHINA | OE
FCO | RU5200 | 7227 | STATE NUCLEAR POWER ENGR CORP LTD (SNPEC) | 118703 | P-STATE NUCLEAR POWER ENGR CORP LTD -118703-POB1 3-1910-FW w/ SB-1 (DS 099) | 7603 | POC | USD | 14834407 | 237685.72 | 2016-10-27 | 2025-05-08 |  | 237686 |  | 178264 |  | 72 | [10 empty] | 0 | CHINA | OE
FCO | RU5200 | 7227 | STATE NUCLEAR POWER ENGR CORP LTD (SNPEC) | 118703 | P-STATE NUCLEAR POWER ENGR CORP LTD -118703-POB2 3-1515-FW w/ SB-0 (DS 100) | 7604 | POC | USD |  | 190568.86 | 2016-10-27 | 2025-05-08 |  | 190569 |  | 142927 |  | 0 | [10 empty] | 0 |  | OE
FCO | RU5200 | 7227 | STATE NUCLEAR POWER ENGR CORP LTD (SNPEC) | 118703 | P-STATE NUCLEAR POWER ENGR CORP LTD -118703-POB3 3-1910-FW w/ SB-1 (DS 101) | 7605 | POC | USD |  | 237685.72 | 2016-10-27 | 2025-05-08 |  | 237686 |  | 178264 |  | 0 | [10 empty] | 0 |  | OE
FCO | RU5200 | 7227 | STATE NUCLEAR POWER ENGR CORP LTD (SNPEC) | 118703 | P-STATE NUCLEAR POWER ENGR CORP LTD -118703-POB4 3-1515-FW w/ SB-1 (DS 104) | 7606 | POC | USD |  | 237182.17 | 2016-10-27 | 2025-05-08 |  | 237182 |  | 177887 |  | 0 | [10 empty] | 0 |  | OE
FCO | RU5200 | 7227 | STATE NUCLEAR POWER ENGR CORP LTD (SNPEC) | 118703 | P-STATE NUCLEAR POWER ENGR CORP LTD -118703-POB5 10-1530-FW w/ SB-3 (DS 106) | 7607 | POC | USD |  | 1583418.33 | 2016-10-27 | 2025-05-08 |  | 1583418 |  | 1187564 |  | 3400 | [10 empty] | 0 |  | OE
FCO | RU5200 | 7227 | STATE NUCLEAR POWER ENGR CORP LTD (SNPEC) | 118703 | P-STATE NUCLEAR POWER ENGR CORP LTD -118703-POB6 10-1500-FW w/ SB-1 (DS 111) | 7608 | POC | USD |  | 412802.85 | 2016-10-27 | 2025-05-08 |  | 412803 |  | 309602 |  | 0 | [10 empty] | 0 |  | OE
FCO | RU5200 | 7227 | STATE NUCLEAR POWER ENGR CORP LTD (SNPEC) | 118703 | P-STATE NUCLEAR POWER ENGR CORP LTD -118703-POB7 8-1535-FW w/ SB-3 (DS 113) | 7609 | POC | USD |  | 1413534.79 | 2016-10-27 | 2025-05-08 |  | 1413535 |  | 1060151 |  | 5257 | [10 empty] | 0 |  | OE
FCO | RU5200 | 7227 | STATE NUCLEAR POWER ENGR CORP LTD (SNPEC) | 118703 | P-STATE NUCLEAR POWER ENGR CORP LTD -118703-POB8 10-1530-FW w/ SB-4 (DS 114) | 7610 | POC | USD |  | 717738.12 | 2016-10-27 | 2025-05-08 |  | 717738 |  | 538304 |  | 0 | [10 empty] | 0 |  | OE
FCO | RU5200 | 7227 | STATE NUCLEAR POWER ENGR CORP LTD (SNPEC) | 118703 | P-STATE NUCLEAR POWER ENGR CORP LTD -118703-POB9 12-1530-FW w/ SB-3 (DS 116) | 7611 | POC | USD |  | 2220325.75 | 2016-10-27 | 2025-05-08 |  | 2220326 |  | 1665244 |  | 0 | [10 empty] | 0 |  | OE
FCO | RU5200 | 7227 | STATE NUCLEAR POWER ENGR CORP LTD (SNPEC) | 118703 | P-STATE NUCLEAR POWER ENGR CORP LTD -118703-POB10 18-1530-FW w/ SB-4 (DS 117) | 7612 | POC | USD |  | 3297358.31 | 2016-10-27 | 2025-05-08 |  | 3297358 |  | 2473019 |  | 0 | [10 empty] | 0 |  | OE
FCO | RU5200 | 7227 | STATE NUCLEAR POWER ENGR CORP LTD (SNPEC) | 118703 | P-STATE NUCLEAR POWER ENGR CORP LTD -118703-POB11 16-1530-FW w/ SB-4 (DS 118) | 7613 | POC | USD |  | 794616.82 | 2016-10-27 | 2025-05-08 |  | 794617 |  | 595963 |  | 0 | [10 empty] | 0 |  | OE
FCO | RU5200 | 7227 | STATE NUCLEAR POWER ENGR CORP LTD (SNPEC) | 118703 | P-STATE NUCLEAR POWER ENGR CORP LTD -118703-POB12 12-1530-FW w/ SB-2 (DS 119) | 7614 | POC | USD |  | 521959.3 | 2016-10-27 | 2025-05-08 |  | 521959 |  | 391469 |  | 0 | [10 empty] | 0 |  | OE
FCO | RU5200 | 7227 | STATE NUCLEAR POWER ENGR CORP LTD (SNPEC) | 118703 | P-STATE NUCLEAR POWER ENGR CORP LTD -118703-POB13 12-1530-FW w/ SB-3 (DS 120) | 7615 | POC | USD |  | 573091.79 | 2016-10-27 | 2025-05-08 |  | 573092 |  | 429819 |  | 0 | [10 empty] | 0 |  | OE
FCO | RU5200 | 7227 | STATE NUCLEAR POWER ENGR CORP LTD (SNPEC) | 118703 | P-STATE NUCLEAR POWER ENGR CORP LTD -118703-POB14 3 FIG 2016(CF3M)JMTY w/ SMB-1 (DS 130) | 7616 | POC | USD |  | 246147.81 | 2016-10-27 | 2025-05-08 |  | 246148 |  | 184611 |  | 660 | [10 empty] | 0 |  | OE
FCO | RU5200 | 7227 | STATE NUCLEAR POWER ENGR CORP LTD (SNPEC) | 118703 | P-STATE NUCLEAR POWER ENGR CORP LTD -118703-POB15 4 FIG BD2026(CF3M)Y w/ SMB-0(DS 131) | 7617 | POC | USD |  | 246147.81 | 2016-10-27 | 2025-05-08 |  | 246148 |  | 184611 |  | 4193 | [10 empty] | 0 |  | OE
FCO | RU5200 | 7227 | STATE NUCLEAR POWER ENGR CORP LTD (SNPEC) | 118703 | P-STATE NUCLEAR POWER ENGR CORP LTD -118703-POB16 8 FIG BD2026(CF3M)Y w/ SMB-1(DS 132) | 7618 | POC | USD |  | 1364807.32 | 2016-10-27 | 2025-05-08 |  | 1364807 |  | 1023605 |  | 3879 | [10 empty] | 0 |  | OE
FCO | RU5200 | 7227 | STATE NUCLEAR POWER ENGR CORP LTD (SNPEC) | 118703 | P-STATE NUCLEAR POWER ENGR CORP LTD -118703-POB17 Extended Warranty | 7619 | SL | USD |  | 539334.53 | 2016-10-27 | 2025-05-08 |  | 539335 |  |  |  | 0 | [10 empty] | 0 |  | OE | 2020-01-01 | 2024-12-31
FCO | RU5200 | 7279 | HENGLI PETROCHEMICAL | 121628 | P-HENGLI PETROCHEMICAL-121628-MOTOR GATE VALVES | 9063 | POC | USD | 371020 | 352469 | 2017-09-12 | 2018-05-15 |  | 371020 | 18551 | 285685 |  | 2723 | [10 empty] | 0 | CHINA | OE
FCO | RU5200 | 8733 | ENTERGY NUCLEAR INDIAN POINT 2 LLC | 121762 | P-ENTERGY NUCLEAR INDIAN POINT 2 LLC-121762-POB #1 Stem & Wedge Assembly | 8871 | POC | USD | 915564 | 78028 | 2017-08-28 | 2018-02-27 |  | 78028 |  | 47480 |  | 16535 |  |  |  |  | 16535 | [5 empty] | 0 | US | OE
FCO | RU5200 | 8733 | ENTERGY NUCLEAR INDIAN POINT 2 LLC | 121762 | P-ENTERGY NUCLEAR INDIAN POINT 2 LLC-121762-POB #2 Stem & Wedge Assembly | 8872 | POC | USD |  | 110347 | 2017-08-28 | 2018-02-27 |  | 110347 |  | 67146 |  | 18985 |  |  |  |  | 18985 | [5 empty] | 0 |  | OE
FCO | RU5200 | 8733 | ENTERGY NUCLEAR INDIAN POINT 2 LLC | 121762 | P-ENTERGY NUCLEAR INDIAN POINT 2 LLC-121762-POB #3 Stem & Wedge Assembly | 8873 | POC | USD |  | 83787 | 2017-08-28 | 2018-02-27 |  | 83787 |  | 50984 |  | 16583 |  |  |  |  | 16583 | [5 empty] | 0 |  | OE
FCO | RU5200 | 8733 | ENTERGY NUCLEAR INDIAN POINT 2 LLC | 121762 | P-ENTERGY NUCLEAR INDIAN POINT 2 LLC-121762-POB #4 Stem & Wedge Assembly | 8874 | POC | USD |  | 78028 | 2017-08-28 | 2018-02-27 |  | 78028 |  | 47480 |  | 17594 |  |  |  |  | 17594 | [5 empty] | 0 |  | OE
FCO | RU5200 | 8733 | ENTERGY NUCLEAR INDIAN POINT 2 LLC | 121762 | P-ENTERGY NUCLEAR INDIAN POINT 2 LLC-121762-POB #5 Stem & Wedge Assembly | 8875 | POC | USD |  | 155356 | 2017-08-28 | 2018-02-27 |  | 155356 |  | 94534 |  | 10159 | [10 empty] | 0 |  | OE
FCO | RU5200 | 8733 | ENTERGY NUCLEAR INDIAN POINT 2 LLC | 121762 | P-ENTERGY NUCLEAR INDIAN POINT 2 LLC-121762-POB #6 Stem & Wedge Assembly | 8876 | POC | USD |  | 273112 | 2017-08-28 | 2018-02-27 |  | 273112 |  | 166189 |  | 36371 |  |  |  |  | 36371 | [5 empty] | 0 |  | OE
FCO | RU5200 | 8733 | ENTERGY NUCLEAR INDIAN POINT 2 LLC | 121762 | P-ENTERGY NUCLEAR INDIAN POINT 2 LLC-121762-POB #7 Stem & Wedge Assembly | 8877 | POC | USD |  | 136906 | 2017-08-28 | 2018-02-27 |  | 136906 |  | 83307 |  | 18588 |  |  |  |  | 18588 | [5 empty] | 0 |  | OE
FCO | RU5200 | 10257 | ALABAMA POWER COMPANY | 122072 | P-ALABAMA POWER COMPANY-122072-CHECK VALVES 20" QTY 10 (POB1) | 10266 | POC | USD | 1801920 | 1801920 | 2017-10-04 | 2021-01-15 |  | 1801920 |  | 1057727 |  | 2313 | [10 empty] | 0 | US | OE
FCO | RU5200 | 10274 | ALABAMA POWER COMPANY | 122073 | P-ALABAMA POWER COMPANY-122073-CHECK VALVES 20" QTY 10 (POB1) | 10284 | POC | USD | 1190810 | 1190810 | 2017-10-05 | 2021-01-15 |  | 1190810 |  | 699055 |  | 8342 | [10 empty] | 0 | US | OE
FCO | RU5200 | 10289 | HUAYOU LIHUA (HK) TECHNICAL DEVELOPMENT CO | 122066 | P-HUAYOU LIHUA (HK) TECHNICAL DEVELOPMENT CO-122066-POB1-Y Stop Check B7502HHPTY | 10300 | POC | USD | 783217 | 114401 | 2017-10-05 | 2018-05-25 |  | 114401 |  | 89888 |  | 0 | [10 empty] | 0 | CHINA | OE
FCO | RU5200 | 10289 | HUAYOU LIHUA (HK) TECHNICAL DEVELOPMENT CO | 122066 | P-HUAYOU LIHUA (HK) TECHNICAL DEVELOPMENT CO-122066-POB2-Y Stop Check B7502(WC6)FHHPTY | 10316 | POC | USD |  | 121684 | 2017-10-05 | 2018-05-25 |  | 121684 |  | 100739 |  | 0 | [10 empty] | 0 |  | OE
FCO | RU5200 | 10289 | HUAYOU LIHUA (HK) TECHNICAL DEVELOPMENT CO | 122066 | P-HUAYOU LIHUA (HK) TECHNICAL DEVELOPMENT CO-122066-POB3-Y Stop Check B7502FJHHPTY | 10317 | POC | USD |  | 133044 | 2017-10-05 | 2018-05-25 |  | 133044 |  | 119574 |  | 1394 | [10 empty] | 0 |  | OE
FCO | RU5200 | 10289 | HUAYOU LIHUA (HK) TECHNICAL DEVELOPMENT CO | 122066 | P-HUAYOU LIHUA (HK) TECHNICAL DEVELOPMENT CO-122066-POB4-Y Stop Check B4014FJHHPTY | 10318 | POC | USD |  | 414088 | 2017-10-05 | 2018-05-25 |  | 414088 |  | 337640 |  | 0 | [10 empty] | 0 |  | OE
FCO | RU5200 | 10705 | CHINA NUCLEAR POWER ENGINEERING COMPANY LTD | 91296 | P-CHINA NUCLEAR POWER ENGINEERING COMPANY LTD-91296-POB1 Unit 1 MFIV | 10722 | POC | USD | 2119498 | 883018.87 | 2017-10-19 | 2018-12-31 |  | 883019 |  | 1074624 |  | 1074624 |  |  |  | 2018-01-31 | [6 empty] | 0 | CHINA | OE
FCO | RU5200 | 10705 | CHINA NUCLEAR POWER ENGINEERING COMPANY LTD | 91296 | P-CHINA NUCLEAR POWER ENGINEERING COMPANY LTD-91296-POB2 Unit 2 MFIV | 10737 | POC | USD |  | 654112.17 | 2017-10-19 | 2018-12-31 |  | 883020 | 228907 | 1074304 |  | 729496 | [10 empty] | 0 |  | OE
FCO | RU5200 | 10705 | CHINA NUCLEAR POWER ENGINEERING COMPANY LTD | 91296 | P-CHINA NUCLEAR POWER ENGINEERING COMPANY LTD-91296-POB3 Spare Parts | 10742 | POC | USD |  | 353459.43 | 2017-10-19 | 2018-12-31 |  | 353459 |  | 113505 |  | 113368 |  |  |  | 2018-01-31 | [6 empty] | 0 |  | OE
FCO | RU5200 | 10705 | CHINA NUCLEAR POWER ENGINEERING COMPANY LTD | 91296 | P-CHINA NUCLEAR POWER ENGINEERING COMPANY LTD-91296-POB4 Warranty | 10747 | SL | USD |  | 127169.83 | 2017-10-19 | 2018-12-31 | [5 empty] | 0 | [10 empty] | 0 |  | OE | 2018-10-23 | 2022-10-22
FCO | RU5200 | 10753 | CHINA HUADIAN LOGISTICS CO LTD | 119587 | P - CHINA HUADIAN LOGISTICS CO LTD - 119857-POB1 All Lines | 10755 | POC | USD | 486000 | 461700 | 2017-10-20 | 2018-12-31 |  | 486000 | 24300 | 570975 |  | 361419 | [10 empty] | 0 | CHINA | OE
FCO | RU5200 | 10915 | Westinghouse Electric Co LLC | 91174 | P-WESTINGHOUSE ELECTRIC CO LLC-91174- POB1 | 15065 | POC | USD | 0 | 433427.37 | 2017-12-05 | 2018-12-31 | [16 empty] | 0 | US | OE
FCO | RU5200 | 12612 | CHINA HK JIAMING ENGINEERING LTD. | 115210 | P-CHINA HK JIAMING ENGINEERING LTD-POB1-115210 | 12623 | POC | USD | 488799 | 488799 | 2017-11-03 | 2018-12-31 |  | 488799 |  | 399048 |  | 395988 |  |  |  |  | 395640 | [5 empty] | 19372 | ASIA | OE
FCO | RU5200 | 12613 | CHINA HK JIAMING ENGINEERING LTD. | 115215 | P-CHINA HK JIAMING ENGINEERING LTD-POB1-115215 | 12643 | POC | USD | 627791 | 627791.2 | 2017-11-03 | 2018-12-31 |  | 627791 |  | 888074 |  | 888074 |  |  |  | 2018-03-30 | [6 empty] | 37771 | ASIA | OE
FCO | RU5200 | 12614 | CHINA HK JIAMING ENGINEERING LTD. | 115217 | P-CHINA HK JIAMING ENGINEERING LTD.-POB1-115217 | 12648 | POC | USD | 1761135 | 1761134.8 | 2017-11-03 | 2018-12-31 |  | 1761135 |  | 2512633 |  | 2512633 |  |  |  | 2018-03-30 | [6 empty] | 70557 | ASIA | OE
FCO | RU5200 | 14407 | ENTERGY ARKANSAS INC | 122475 | P - ENTERGY ARKANSAS INC- POB1- 122475 | 14475 | POC | USD | 997159 | 997159 | 2017-11-30 | 2018-05-11 |  | 997159 |  | 86205 |  | 86205 |  |  |  | 2018-04-30 | [6 empty] | 0 | US | OE
FCO | RU5200 | 14781 | KOREA HYDRO & NUCLEAR POWER CO LTD | 121351 | P- KOREA HYDRO & NUCLEAR POWER CO LTD- 121351- POB 1 | 14846 | POC | USD | 4209731 | 4209731.18 | 2017-12-01 | 2018-12-28 |  | 4209731 |  | 1473406 |  | 142600 |  |  |  |  | 121938 | [5 empty] | 315730 | ASIA | OE
FCO | RU5200 | 15056 | WESTINGHOUSE ELECTRIC CO LLC | 91178 | P - WESTINGHOUSE ELECTRIC CO LLC - 91178 - POB1 | 15057 | POC | USD | 1567151 | 1567150.57 | 2017-12-05 | 2018-05-23 |  | 1567151 |  | 1480800 |  | 1185893 |  |  |  |  | 585636 | [5 empty] | 0 | US | OE
FCO | RU5200 | 16415 | AREVA NP | 122216 | P-AREVA NP-122216- POB 1 MFFLIV Unit 1 & Spares | 16465 | POC | USD | 7303015 | 3924711 | 2017-10-16 | 2022-05-12 |  | 3924711 |  | 2707266 |  | 0 | [10 empty] | 0 | EUROPE | OE
FCO | RU5200 | 16415 | AREVA NP | 122216 | P-AREVA NP-122216- POB 2 MFFLIV Unit 2 | 16469 | POC | USD |  | 3378304 | 2017-10-16 | 2022-05-12 |  | 3378304 |  | 2330345 |  | 0 | [10 empty] | 0 |  | OE
FCO | RU5200 | 17822 | ENTERGY NUCLEAR PALISADES | 122884 | P - ENTERGY NUCLEAR PALISADES - POB1- 122884 | 17823 | POC | USD | 593893 | 593893 | 2017-12-28 | 2018-07-18 |  | 593893 |  | 372549 |  | 123118 | [10 empty] | 0 | US | OE
FCO | RU5200 | 18185 | NOOTER / ERIKSEN | 122902 | P-NOOTER/ERIKSEN-122902-POB1 | 18843 | POC | USD | 297414 | 297414 | 2018-01-04 | 2018-08-27 |  | 297414 |  | 223061 |  | 36029 | [10 empty] | 0 | US | OE
FCO | RU5200 | 18820 | KOREA HYDRO & NUCLEAR POWER CO LTD | 122954 | P- KOREA HYDRO & NUCLEAR POWER CO LTD- 122954- POB 1 | 18829 | POC | USD | 3654407 | 3654407 | 2018-01-11 | 2018-09-07 |  | 3654407 |  | 913602 |  | 299419 |  |  |  |  | 54254 | [5 empty] | 274081 | ASIA | OE
FCO | RU5200 | 21034 | Duke Energy | 123113 | P-DUKE ENERGY-123113-POB1 | 21349 | POC | USD | 520157 | 520157 | 2018-01-29 | 2019-01-11 |  | 520157 |  | 274591 |  | 0 | [10 empty] | 0 | US | OE
FCO | RU5200 | 22895 | Duke Energy | 123393 | P-DUKE ENERGY-123393-POB1 | 22896 | POC | USD | 489482 | 489482 | 2018-02-23 | 2018-09-30 |  | 489482 |  | 264320 |  | 0 | [10 empty] | 0 | US | OE
FCO | RU5200 | 22994 | Taiwan Power Company | Various | P-TAIWAN POWER COMPANY-POB1-123431/123433/123434/123435/123436/123448 | 23994 | POC | USD | 2462460 | 62488 | 2018-02-27 | 2018-12-31 |  | 62488 |  | 33744 |  | 0 | [10 empty] | 0 | ASIA | OE
FCO | RU5200 | 22994 | Taiwan Power Company | Various | P-TAIWAN POWER COMPANY-POB2-123431/123433/123434/123435/123436/123448 | 24001 | POC | USD |  | 151413 | 2018-02-27 | 2018-12-31 |  | 151413 |  | 81763 |  | 0 | [10 empty] | 0 | ASIA | OE
FCO | RU5200 | 22994 | Taiwan Power Company | Various | P-TAIWAN POWER COMPANY-POB3-123431/123433/123434/123435/123436/123448 | 24004 | POC | USD |  | 232225 | 2018-02-27 | 2018-12-31 |  | 232225 |  | 125402 |  | 0 | [10 empty] | 0 | ASIA | OE
FCO | RU5200 | 22994 | Taiwan Power Company | Various | P-TAIWAN POWER COMPANY-POB4-123431/123433/123434/123435/123436/123448 | 24005 | POC | USD |  | 161925 | 2018-02-27 | 2018-12-31 |  | 161925 |  | 87440 |  | 0 | [10 empty] | 0 | ASIA | OE
FCO | RU5200 | 22994 | Taiwan Power Company | Various | P-TAIWAN POWER COMPANY-POB5-123431/123433/123434/123435/123436/123448 | 24007 | POC | USD |  | 277379 | 2018-02-27 | 2018-12-31 |  | 277379 |  | 149785 |  | 0 | [10 empty] | 0 | ASIA | OE
FCO | RU5200 | 22994 | Taiwan Power Company | Various | P-TAIWAN POWER COMPANY-POB6-123431/123433/123434/123435/123436/123448 | 24008 | POC | USD |  | 1577030 | 2018-02-27 | 2018-12-31 |  | 1577030 |  | 851596 |  | 727 | [10 empty] | 0 | ASIA | OE
FCO | RU5200 | 25648 | KOREA HYDRO & NUCLEAR POWER CO LTD | 123806 | P-KOREA HYDRO & NUCLEAR POWER CO-123806-SPARE PARTS & CFSI CHARGE | 25649 | POC | USD | 285865 | 285865 | 2018-03-30 | 2018-08-30 |  | 285865 |  | 85760 |  | 0 | [10 empty] | 0 | ASIA | OE
FCO | RU5200 | 25846 | ENTERGY NUCLEAR RIVER BEND | 123812 | P - ENTERGY NUCLEAR RIVER BEND -POB1- 123812 | 25853 | POC | USD | 291218 | 291218 | 2018-03-30 | 2018-10-31 |  | 291218 |  | 100645 |  | 3 | [10 empty] | 0 | US | OE
FCO | RU5200 | 25856 | Dominion Engergy | 123797 | P-DOMINION-123797-POB1 | 25869 | POC | USD | 640250 | 126166 | 2018-03-30 | 2018-09-12 |  | 126166 |  | 104718 |  | 0 | [10 empty] | 0 | US | OE
FCO | RU5200 | 25856 | Dominion Engergy | 123797 | P-DOMINION-123797-POB2 | 25870 | PIT | USD |  | 514084 | 2018-03-30 | 2018-09-12 |  | 514084 |  | 426690 |  | 0 | [10 empty] | 0 | US | OE
FCO | RU5200 | 26335 | XCEL ENERGY | 123858 | P-XCEL ENERGY-POB1-123858 | 26340 | POC | USD | 362490 | 362490 | 2018-04-06 | 2019-01-07 |  | 362490 |  | 151245 |  | 0 | [10 empty] | 0 | US | OE
FCO | RU5200 | 26705 | KOREA HYDRO & NUCLEAR POWER CO LTD | 123965 | P- KOREA HYDRO & NUCLEAR POWER CO LTD- 123965- POB 1 | 26706 | POC | USD | 439863 | 439863 | 2018-04-16 | 2018-12-17 |  | 439863 |  | 131959 |  | 0 | [10 empty] | 0 | ASIA | OE
FCO | RU5200 | 27357 | Westinghouse Electric Company | 124095 | P -Westinghouse Electric Company - 124095 | 27363 | POC | USD | 533682 | 533682 | 2018-04-30 | 2018-11-02 |  | 533682 |  | 373577 |  | 0 | [10 empty] | 0 | US | OE
FCO | RU5200 | 28059 | KOREA HYDRO & NUCLEAR POWER CO LTD | 123806 | P-KOREA HYDRO & NUCLEAR POWER CO-124291-SPARE PARTS & CFSI CHARGE | 28060 | POC | USD | 928023 | 928023 | 2018-05-15 | 2019-01-18 |  | 928023 |  | 232006 |  | 0 | [10 empty] | 69602 | ASIA | OE
FCO | RU5220 | 5127 | Newport News Ship Building | 162876 | P-Newport News Ship Building-162876-SMB-1 | 6797 | POC | USD | 561484 | 391528 | 2017-05-30 | 2018-04-16 |  | 391528 |  | 233334.03 |  | 233334.03 |  |  |  | 2018-05-31 |  |  | 518995 |  | 2018-05-30 | 291663 | 0 | US | OE
FCO | RU5220 | 5127 | Newport News Ship Building | 162876 | P-Newport News Ship Building-162876-SMB-2 | 6798 | POC | USD |  | 169956 | 2017-05-30 | 2018-04-16 |  | 169956 |  | 133488.16 |  | 114025.38 |  |  |  |  | 99997.73 | [5 empty] | 0 | US | OE
FCO | RU5220 | 5644 | Newport News Ship Building | 146648 | P-Newport News Ship Building-146648-NM120-420 | 5668 | POC | USD | 3614992 | 3079437 | 2014-12-15 | 2018-01-29 | [9 empty] | 2018-01-31 | [6 empty] | 0 | US | OE
FCO | RU5220 | 5644 | Newport News Ship Building | 146648 | P-Newport News Ship Building-146648-NM120-120 | 5669 | POC | USD |  | 3614992 | 2014-12-15 | 2018-01-29 |  | 3614992 |  | 2478814.89 |  | 1807715.32 |  |  |  |  | 2337237 | [5 empty] | 0 | US | OE
FCO | RU5220 | 5644 | Newport News Ship Building | 146648 | P-Newport News Ship Building-146648-Patterns, Modeling & Tooling | 21754 | POC | USD |  | 468726 | 2014-12-15 | 2018-01-29 | [9 empty] | 2017-01-01 | [6 empty] | 0 | US | OE
FCO | RU5220 | 12502 | Newport News Ship Building | 163420 | P - Newport News Ship Building - 163420 - SMB-00 | 12624 | POC | USD | 9560 | 701920 | 2017-06-09 | 2018-01-15 | [9 empty] | 2018-01-31 | [6 empty] | 0 | US | OE
FCO | RU5220 | 12502 | Newport News Ship Building | 163420 | P - Newport News Ship Building - 163420 - 60-224-0401-2 | 12627 | POC | USD |  | 9560 | 2017-06-09 | 2018-01-15 |  | 9560 | [7 empty] | 2018-02-28 | [6 empty] | 0 | US | OE
IPO | RU7803 | 9812 | GE Power & Water - Canada | 4000050014 | P-GE Power Water-4502931560-Triplex Vacuum Pump System | 18879 | POC | CAD | 340000 | 276420 | 2017-09-29 | 2018-02-23 |  | 340000 | [7 empty] | 2018-02-28 | [6 empty] | 0 | OTHER | OE
IPO | RU7830 | 15031 | Tianjin Dexin Weiye Technology | 1204355 | P-Tianjin Dexin Weiye-1204355-1253-PU01 | 18250 | POC | CNY | 5333289.2737 | 300032 | 2017-11-27 | 2018-07-31 |  | 1982896.0412 | 0 | 1675215 |  | 39144.12 | [10 empty] | 0 | CHINA | OE
IPO | RU7830 | 15031 | Tianjin Dexin Weiye Technology | 1204355 | P-Tianjin Dexin Weiye-1204355-1253-PU02 | 18251 | POC | CNY |  | 106045 | 2017-11-27 | 2018-07-31 |  | 700845.9454 | 0 | 588000 |  | 862.06 | [10 empty] | 0 | CHINA | OE
IPO | RU7830 | 15031 | Tianjin Dexin Weiye Technology | 1204355 | P-Tianjin Dexin Weiye-1204355-1250-PU01 | 18252 | POC | CNY |  | 116391 | 2017-11-27 | 2018-07-31 |  | 769222.1268 | 0 | 711098 |  | 102410.36 | [10 empty] | 0 | CHINA | OE
IPO | RU7830 | 15031 | Tianjin Dexin Weiye Technology | 1204355 | P-Tianjin Dexin Weiye-1204355-1250-PU02 | 18253 | POC | CNY |  | 103459 | 2017-11-27 | 2018-07-31 |  | 683755.2045 | 0 | 576770 |  | 0 | [10 empty] | 0 | CHINA | OE
IPO | RU7830 | 15031 | Tianjin Dexin Weiye Technology | 1204355 | P-Tianjin Dexin Weiye-1204355-1255-PU01 | 18254 | POC | CNY |  | 181053 | 2017-11-27 | 2018-07-31 |  | 1196569.9557 | 0 | 883108 |  | 85540.1 | [10 empty] | 0 | CHINA | OE
IPO | RU7830 | 18247 | Zhejiang Petroleum Chemical Co., Ltd. | 1206169 | P-Zhejiang Petroleum Chemical-1206169-1210-P-3006A/B LPH 50523 pump system 1 unit | 19439 | POC | CNY | 3721367.5141 | 90361.29 | 2017-12-12 | 2018-07-30 |  | 592521.393 | 0 | 499790 |  | 0 | [10 empty] | 0 | CHINA | OE
IPO | RU7830 | 18247 | Zhejiang Petroleum Chemical Co., Ltd. | 1206169 | P-Zhejiang Petroleum Chemical-1206169-1210-P-3012A/B LPH 50523 pump system 1 unit | 19440 | POC | CNY |  | 90361.29 | 2017-12-12 | 2018-07-30 |  | 592521.393 | 0 | 499790 |  | 0 | [10 empty] | 0 | CHINA | OE
IPO | RU7830 | 18247 | Zhejiang Petroleum Chemical Co., Ltd. | 1206169 | P-Zhejiang Petroleum Chemical-1206169-1210-P-3022A/B LPH 50115 pump system 1 unit | 19441 | POC | CNY |  | 84399.33 | 2017-12-12 | 2018-07-30 |  | 553427.3424 | 0 | 503992 |  | 0 | [10 empty] | 0 | CHINA | OE
IPO | RU7830 | 18247 | Zhejiang Petroleum Chemical Co., Ltd. | 1206169 | P-Zhejiang Petroleum Chemical-1206169-1210-P-5010A/B LPH 55320 pump system 1 unit | 19445 | POC | CNY |  | 63046.3 | 2017-12-12 | 2018-07-30 |  | 413410.228 | 0 | 374422 |  | 0 | [10 empty] | 0 | CHINA | OE
IPO | RU7830 | 18247 | Zhejiang Petroleum Chemical Co., Ltd. | 1206169 | P-Zhejiang Petroleum Chemical-1206169-1210-P-7150A/B LPH 50115 pump system 1 unit | 19447 | POC | CNY |  | 77896.45 | 2017-12-12 | 2018-07-30 |  | 510786.3452 | 0 | 469032 |  | 0 | [10 empty] | 0 | CHINA | OE
IPO | RU7830 | 18247 | Zhejiang Petroleum Chemical Co., Ltd. | 1206169 | P-Zhejiang Petroleum Chemical-1206169-1210-P-8016A/B LPH 55316 pump system 1 unit | 19448 | POC | CNY |  | 92925.16 | 2017-12-12 | 2018-07-30 |  | 609333.3246 | 0 | 504415 |  | 0 | [10 empty] | 0 | CHINA | OE
IPO | RU7830 | 18247 | Zhejiang Petroleum Chemical Co., Ltd. | 1206169 | P-Zhejiang Petroleum Chemical-1206169-Spare parts for 1210-P-3006A/B LPH 50523 | 19449 | POC | CNY |  | 11423.38 | 2017-12-12 | 2018-07-30 |  | 74905.9363 | 0 | 42708 |  | 0 | [10 empty] | 0 | CHINA | AM
IPO | RU7830 | 18247 | Zhejiang Petroleum Chemical Co., Ltd. | 1206169 | P-Zhejiang Petroleum Chemical-1206169-Spare parts for 1210-P-3012A/B LPH 50523 | 19452 | POC | CNY |  | 11423.39 | 2017-12-12 | 2018-07-30 |  | 74906.0018 | 0 | 42880 |  | 0 | [10 empty] | 0 | CHINA | AM
IPO | RU7830 | 18247 | Zhejiang Petroleum Chemical Co., Ltd. | 1206169 | P-Zhejiang Petroleum Chemical-1206169-Spare parts for 1210-P-3022A/B LPH 50115 | 19458 | POC | CNY |  | 11418.17 | 2017-12-12 | 2018-07-30 |  | 74871.773 | 0 | 41993 |  | 0 | [10 empty] | 0 | CHINA | AM
IPO | RU7830 | 18247 | Zhejiang Petroleum Chemical Co., Ltd. | 1206169 | P-Zhejiang Petroleum Chemical-1206169-Spare parts for 1210-P-5010A/B LPH 55320 | 19461 | POC | CNY |  | 11423.39 | 2017-12-12 | 2018-07-30 |  | 74906.0018 | 0 | 41683 |  | 0 | [10 empty] | 0 | CHINA | AM
IPO | RU7830 | 18247 | Zhejiang Petroleum Chemical Co., Ltd. | 1206169 | P-Zhejiang Petroleum Chemical-1206169-Spare parts for 1210-P-7150A/B LPH 50115 | 19462 | POC | CNY |  | 11418.17 | 2017-12-12 | 2018-07-30 |  | 74871.773 | 0 | 41993 |  | 0 | [10 empty] | 0 | CHINA | AM
IPO | RU7830 | 18247 | Zhejiang Petroleum Chemical Co., Ltd. | 1206169 | P-Zhejiang Petroleum Chemical-1206169-Spare parts for 1210-P-8016A/B LPH 55316 | 19463 | POC | CNY |  | 11423.39 | 2017-12-12 | 2018-07-30 |  | 74906.0018 | 0 | 42707 |  | 0 | [10 empty] | 0 | CHINA | AM
IPO | RU7830 | 18248 | Zhejiang Petroleum Chemical Co., Ltd. | 1208210 | P-Zhejiang Petroleum Chemical-1208210-4x booster8k-2xH1k system/PK-2611 1 unit | 19524 | POC | CNY | 12774358.9962 | 681701.45 | 2017-12-07 | 2018-09-30 |  | 4470085.5065 | 0 | 3424932 |  | 0 | [10 empty] | 0 | CHINA | OE
IPO | RU7830 | 18248 | Zhejiang Petroleum Chemical Co., Ltd. | 1208210 | P-Zhejiang Petroleum Chemical-1208210-5x booster8k-3xH1k system/PK-2612 1 unit | 19525 | POC | CNY |  | 886081.54 | 2017-12-07 | 2018-09-30 |  | 5810256.454 | 0 | 4397582 |  | 0 | [10 empty] | 0 | CHINA | OE
IPO | RU7830 | 18248 | Zhejiang Petroleum Chemical Co., Ltd. | 1208210 | P-Zhejiang Petroleum Chemical-1208210-H630/K-2613AS | 19526 | POC | CNY |  | 177268.44 | 2017-12-07 | 2018-09-30 |  | 1162393.1332 | 0 | 864226 |  | 0 | [10 empty] | 0 | CHINA | OE
IPO | RU7830 | 18248 | Zhejiang Petroleum Chemical Co., Ltd. | 1208210 | P-Zhejiang Petroleum Chemical-1208210-spare parts for PK-2611 | 19527 | POC | CNY |  | 37799.89 | 2017-12-07 | 2018-09-30 |  | 247863.2551 | 0 | 245131 |  | 0 | [10 empty] | 0 | CHINA | AM
IPO | RU7830 | 18248 | Zhejiang Petroleum Chemical Co., Ltd. | 1208210 | P-Zhejiang Petroleum Chemical-1208210-spare parts for PK-2612 | 19528 | POC | CNY |  | 145203.71 | 2017-12-07 | 2018-09-30 |  | 952136.7449 | 0 | 941371 |  | 0 | [10 empty] | 0 | CHINA | AM
IPO | RU7830 | 18248 | Zhejiang Petroleum Chemical Co., Ltd. | 1208210 | P-Zhejiang Petroleum Chemical-1208210-spare parts for K-2613AS | 19529 | POC | CNY |  | 20073.04 | 2017-12-07 | 2018-09-30 |  | 131623.9025 | 0 | 125487 |  | 0 | [10 empty] | 0 | CHINA | AM
IPO | RU7866 | 3885 | JV of Tecnicas Reunidas S.A., Sinopec Engineering (group) Co. Ltd. and Hanhwa Engineering and Construction Corporation (KNPC) | 40004597 | P-KNPC Al Zour-40004597-Pump Package 03 incl.Techn.Ass. Doc. And Spares | 3934 | POC | EUR | 6501987 | 1345857.72 | 2016-11-02 | 2018-05-07 |  | 1307377 | 103892 | 1444578 |  | 1172185 | [10 empty] | 0 | ASIA | OE
IPO | RU7866 | 3885 | JV of Tecnicas Reunidas S.A., Sinopec Engineering (group) Co. Ltd. and Hanhwa Engineering and Construction Corporation (KNPC) | 40004597 | P-KNPC Al Zour-40004597-Pump Package 13 incl.Techn.Ass. Doc. And Spares | 3935 | POC | EUR |  | 1277266.88 | 2016-11-02 | 2018-05-07 |  | 1240748 | 98597 | 1372349 |  | 1113577 | [10 empty] | 0 | ASIA | OE
IPO | RU7866 | 3885 | JV of Tecnicas Reunidas S.A., Sinopec Engineering (group) Co. Ltd. and Hanhwa Engineering and Construction Corporation (KNPC) | 40004597 | P-KNPC Al Zour-40004597-Pump Package 23 incl. Techn.Ass. Doc. And Spares | 3936 | POC | EUR |  | 1277266.88 | 2016-11-02 | 2018-05-07 |  | 1240748 | 98597 | 1372349 |  | 1113577 | [10 empty] | 0 | ASIA | OE
IPO | RU7866 | 3885 | JV of Tecnicas Reunidas S.A., Sinopec Engineering (group) Co. Ltd. and Hanhwa Engineering and Construction Corporation (KNPC) | 40004597 | P-KNPC Al Zour-40004597-Vacuum Dryer 05 incl. Techn.Ass.Doc. Spares. | 3937 | POC | EUR |  | 1396485.26 | 2016-11-02 | 2018-05-07 |  | 1356557 | 107800 | 1516808 |  | 1230795 | [10 empty] | 0 | ASIA | OE
IPO | RU7866 | 3885 | JV of Tecnicas Reunidas S.A., Sinopec Engineering (group) Co. Ltd. and Hanhwa Engineering and Construction Corporation (KNPC) | 40004597 | P-KNPC Al Zour-40004597-Vacuum Dryer 25 incl. Techn.Ass.Doc. Spares. | 3938 | POC | EUR |  | 1396485.26 | 2016-11-02 | 2018-05-07 |  | 1356557 | 107800 | 1516808 |  | 1230795 | [10 empty] | 0 | ASIA | OE
IPO | RU7866 | 4467 | PJSC Power Machines | 40004637 | P - PJSC Power Machines - 40004637 - Unit 1 | 4608 | POC | USD | 1614246.5384 | 798377 | 2016-09-21 | 2019-01-31 |  | 807123.2692 | 120302 | 498972 |  | 382873 | [7 empty] | 0 |  |  | 0 | RUSCIS | OE
IPO | RU7866 | 4467 | PJSC Power Machines | 40004637 | P - PJSC Power Machines - 40004637 - Unit 2 | 4660 | POC | USD |  | 798377 | 2016-09-21 | 2019-01-31 |  | 807123.2692 | 120302 | 498972 |  | 382872 | [10 empty] | 0 | RUSCIS | OE
IPO | RU7866 | 5536 | InfraServ Gendorf Technik GmbH | 40004716 | P-InfraServ Gendorf-40004716-Compressor Units incl.Spares and Documentation | 7321 | POC | EUR | 358590 | 374529 | 2017-05-04 | 2018-01-26 |  | 358590 | [7 empty] | 2018-03-15 | [6 empty] | 0 | EUROPE | OE
IPO | RU7866 | 7698 | NAFTA INDUSTRIJA SRBIJE j.s.c. (NIS) | 40004730 | P-NIS-40004730-Water Ring Compressor Package | 7836 | POC | EUR | 508000 | 571043 | 2017-06-14 | 2018-03-28 |  | 508000 | 50800 | 525614 | [12 empty] | 0 | EUROPE | OE
IPO | RU7866 | 7972 | SNC Butachimie | 40004735 | Pob - Butachimie - 40004735 | 8097 | POC | EUR | 756013 | 850399 | 2017-07-20 | 2018-06-08 |  | 756013 | 56517 | 870826 |  | 359946 | [6 empty] | 80738 |  | 2018-05-09 | 96025177 | 0 | EUROPE | OE
IPO | RU7866 | 8585 | BASF SE | 40004699 | POB - BASF - 40004699 | 8595 | POC | EUR | 720496 | 761561 | 2017-04-27 | 2018-01-18 |  | 720496 |  | 978256 |  | 913420 | [10 empty] | 0 | EUROPE | OE
IPO | RU7866 | 8676 | TecnimontHQC S.c.a.r.l. Italy | 40004712 | Pob - Tecnimont - 40004712 | 9141 | POC | EUR | 1222388 | 1363568 | 2017-06-16 | 2018-02-28 |  | 1222388 | 99112 | 2107573 |  | 722726 | [10 empty] | 0 | EUROPE | OE
IPO | RU7866 | 8952 | Allmaster Enterprise Co. Ltd. | 40004721 | POB - Allmaster - PLGW500/1 - 40004721 | 10478 | POC | EUR | 546000 | 221876.08 | 2017-06-06 | 2018-01-03 |  | 207480 |  | 294952 | [5 empty] | 2018-04-30 | [6 empty] | 0 | ASIA | OE
IPO | RU7866 | 8952 | Allmaster Enterprise Co. Ltd. | 40004721 | POB - Allmaster - PLGW250/1 - 40004721 | 10479 | POC | EUR |  | 369070.84 | 2017-06-06 | 2018-01-03 |  | 338520 |  | 481237 | [5 empty] | 2018-04-20 | [6 empty] | 0 | ASIA | OE
IPO | RU7866 | 9154 | Mineraloelraffinerie Oberrhein GmbH&Co.KG (MiRo) | 40004745 | P-MiRo-40004745-Liquid Ring Compressor | 9218 | POC | EUR | 916231 | 957182 | 2017-08-30 | 2018-08-31 |  | 760231 |  | 689865 |  | 335438 | [10 empty] | 0 | EUROPE | OE
IPO | RU7866 | 9154 | Mineraloelraffinerie Oberrhein GmbH&Co.KG (MiRo) | 40004745 | P-MiRo-40004745-Spare Compressor | 9219 | POC | EUR |  | 184704 | 2017-08-30 | 2018-08-31 |  | 156000 |  | 131403 |  | 63893 | [10 empty] | 0 | EUROPE | OE
IPO | RU7866 | 9160 | BASF SE | 40004753 | P-BASF SE-40004753-Vacuum Pump Unit | 9288 | POC | EUR | 370405.1689 | 353419.53 | 2017-08-30 | 2018-04-27 |  | 295205 | 19495 | 211645 | [12 empty] | 0 | EUROPE | OE
IPO | RU7866 | 9160 | BASF SE | 40004753 | P-BASF SE-40004753-Spare pump | 9289 | POC | EUR |  | 84452.47 | 2017-08-30 | 2018-04-27 |  | 75200.1689 |  | 20852 | [12 empty] | 0 | EUROPE | OE
IPO | RU7866 | 9296 | Tecnicas Reunidas UTE TR Fadhili Project (Fadhili) | 40004585 | Pob- Tecnicas Reunidas Fadhili - 40004585 | 12788 | POC | EUR | 2950211 | 3246162.94 | 2016-08-11 | 2018-01-13 |  | 2950211 | 222059 | 3477765 |  | 3170644 | [10 empty] | 0 | EUROPE | OE
IPO | RU7866 | 9301 | BASF SE | 1175997 | Pob - BASF SE - 1175997 | 9910 | POC | EUR | 392180 | 422104.8 | 2017-06-12 | 2018-03-08 |  | 392180 | 19609 | 162373 | [5 empty] | 2018-04-30 | [6 empty] | 0 | EUROPE | OE
IPO | RU7866 | 10301 | Bayer AG | 1194701 | POB - Bayer AG - 1194701 | 10477 | POC | EUR | 349000 | 415589 | 2017-09-28 | 2018-02-07 |  | 349000 | [7 empty] | 2018-02-27 | [6 empty] | 0 | EUROPE | OE
IPO | RU7866 | 12482 | ORLEN Projekt S.A. (Orlen) | 40004762 | P - Orlen - 40004762 | 13904 | POC | EUR | 1100000 | 1299320 | 2017-10-23 | 2018-10-30 |  | 1100000 |  | 947877 |  | 124082 | [10 empty] | 0 | EUROPE | OE
IPO | RU7866 | 14290 | Formosa Chemicals & Fibre Corporation (Formosa) | 40004761 | P - Allmaster Formosa - 40004761 | 15564 | POC | EUR | 559000.3435 | 650900 | 2017-11-28 | 2018-07-31 |  | 559000.3435 |  | 529180 |  | 168423 | [10 empty] | 11180 | CHINA | OE
IPO | RU7866 | 15528 | Dairen Chemical (M) SDN BHD | 40004638 | P - Dairen Chemical - 40004638 | 16949 | POC | EUR | 249245 | 277916 | 2017-01-17 | 2018-06-26 |  | 249245 |  | 216025 |  | 210058 | [10 empty] | 0 | ASIA | OE
IPO | RU7866 | 18426 | Petrobel Belayim Petroleum Company | 40004646 | P-Petrobel Belayim Petroleum Company-40004646-MEG Compressor Package | 18776 | POC | EUR | 1071570 | 1140651.57 | 2016-11-10 | 2018-01-03 |  | 1071570 | [7 empty] | 2018-01-30 | [6 empty] | 0 | OTHERAFRICA | OE
IPO | RU7866 | 18427 | Evonik Industries AG | 40004672 | P-Evonik-40004672-Vacuum pump stand | 18794 | POC | EUR | 249000 | 263566.5 | 2016-12-20 | 2018-03-31 |  | 249000 |  | 240000 |  | 219600 | [10 empty] | 0 | EUROPE | OE
IPO | RU7866 | 23986 | China Nuclear Power Engineering Company Ltd. | 1217748 | P-China Nuclear-1217748-Equipment Pob | 27688 | POC | EUR | 4808673.8292 | 5309342 | 2018-03-27 | 2019-10-15 |  | 4354418.1088 |  | 2723887 |  | 35457 | [6 empty] | 1202168 |  | 2018-05-16 | 96025204 | 0 | CHINA | OE
IPO | RU7866 | 23986 | China Nuclear Power Engineering Company Ltd. | 1217748 | P-China Nuclear-1217748-Spare Parts Pob | 27689 | POC | EUR |  | 553874 | 2018-03-27 | 2019-10-15 |  | 454255.7205 |  | 211192 | [12 empty] | 0 | CHINA | OE
IPO | RU7866 | 26424 | Formosa Chemicals & Fibre Corporation | 40004807 | P-Formosa Chemicals -40004807-Liquid Ring Compressor | 27917 | POC | EUR | 585000.4058 | 720779 | 2018-03-28 | 2018-11-06 |  | 585000.4058 |  | 498689 |  | 0 | [6 empty] | 175500 |  | 2018-05-29 | 96025177 | 0 | ASIA | OE
IPO | RU7866 | 27690 | Bayer AG | 40004815 | P - Bayer - 40004815 | 27923 | POC | EUR | 245885.8859 | 302956 | 2018-04-19 | 2019-02-28 |  | 245885.8859 |  | 189884 |  | 0 | [10 empty] | 0 | EUROPE | OE
IPO | RU7881 | 10219 | NNB GENERATION COMPANY LTD | 102376 | P - NNB GENERATION COMPANY, LTD – 102376 - POb1: Interface studies – TEG Compressors, erection services documents and commissioning services | 19889 | POC | EUR | 1050609.9962 | 1119319.89 | 2016-12-19 | 2018-06-30 |  | 1050609.9962 | [14 empty] | 0 | EUROPE | OE
IPO | RU7887 | 18265 | Teijin Aramid BV | 85409840 | P- Teijin Aramid B.V. - 85409840 | 20251 | POC | EUR | 395239.9967 | 474129.9 | 2017-12-20 | 2018-08-10 |  | 395239.9967 |  | 305090 |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0 | EUROPE | OE
IPO | RU7890 | 8750 | NIS j.s.c. Novi Sad | 1191467 | P-NIS-1191467-Pob CB&I NIS LOT 1, 2, 3, 4, spares and supervision | 11558 | POC | EUR | 820931 | 909133 | 2017-08-22 | 2018-03-15 |  | 820931 | 70600 | 681293 |  | 544250 | [10 empty] | 0 | EUROPE | OE
IPO | RU7890 | 8935 | Adisseo España, S.A. | 1170014 | P-Adisseo-1170014-Group of pumps: A B C D F G | 10311 | POC | EUR | 87824 | 425436 | 2017-03-21 | 2018-01-28 |  |  | 25511 | [6 empty] | 2017-09-30 |  |  | 45824 |  | 2018-05-28 | 1190177252 | 0 | EUROPE | OE
IPO | RU7890 | 8935 | Adisseo España, S.A. | 1170014 | P-Adisseo-1170014-Group of pumps: ZA | 10312 | PIT | EUR |  | 8670 | 2017-03-21 | 2018-01-28 |  |  | 549 | [6 empty] | 2018-04-30 | [6 empty] | 0 | EUROPE | OE
IPO | RU7890 | 8935 | Adisseo España, S.A. | 1170014 | P-Adisseo-1170014-Group of pumps: Z | 10313 | POC | EUR |  | 27264 | 2017-03-21 | 2018-01-28 |  |  | 1634 | [6 empty] | 2017-11-30 | [6 empty] | 0 | EUROPE | OE
IPO | RU7890 | 8935 | Adisseo España, S.A. | 1170014 | P-Adisseo-1170014-Group of pumps: W | 17194 | POC | EUR |  | 46745 | 2017-03-21 | 2018-01-28 |  | 42000 | 2520 | 42267 |  | 38719 |  |  |  | 2018-03-21 | [6 empty] | 0 | EUROPE | OE
IPO | RU7890 | 8935 | Adisseo España, S.A. | 1170014 | P-Adisseo-1170014-Group of pumps: X | 17273 | POC | EUR |  | 35154 | 2017-03-21 | 2018-01-28 |  |  | 1905 | [6 empty] | 2018-01-12 | [6 empty] | 0 | EUROPE | OE
IPO | RU7890 | 8935 | Adisseo España, S.A. | 1170014 | P-Adisseo-1170014-Group of pumps: Y | 17275 | POC | EUR |  | 20147 | 2017-03-21 | 2018-01-28 |  |  | 1076 | [6 empty] | 2018-01-12 | [6 empty] | 0 | EUROPE | OE
IPO | RU7890 | 8935 | Adisseo España, S.A. | 1170014 | P-Adisseo-1170014-Group of pumps: ZB | 18760 | PIT | EUR |  | 49752 | 2017-03-21 | 2018-01-28 |  | 45824 | 1833 | 21248 |  | 0 | 0 | 0 |  | 2018-05-28 | [6 empty] | 0 | EUROPE | OE
IPO | RU7890 | 9026 | Desmet Ballestra S.p.A. | 1181989 | P-Desmet Ballestra-1181989-Pumps Unit 34 and Commissioning & 2-years spares | 10268 | POC | EUR | 475285 | 299778 | 2017-09-15 | 2018-01-01 |  | 291593 | 29159 | 254216 |  | 254216 |  |  |  | 2018-05-30 | 254216 |  | 362122 |  | 2018-05-21 | 1600007005 | 0 | MIDEAST | OE
IPO | RU7890 | 9026 | Desmet Ballestra S.p.A. | 1181989 | P-Desmet Ballestra-1181989-Pumps Unit 38 | 14308 | POC | EUR |  | 135833 | 2017-09-15 | 2018-01-01 |  | 132124 | 13212 | 125831 |  | 125831 |  |  |  | 2018-05-30 | 125831 | [5 empty] | 0 | MIDEAST | OE
IPO | RU7890 | 9026 | Desmet Ballestra S.p.A. | 1181989 | P-Desmet Ballestra-1181989-Pumps Unit 36 | 14318 | POC | EUR |  | 53016 | 2017-09-15 | 2018-01-01 |  | 51568 | 5157 | 42301 |  | 42301 |  |  |  | 2018-05-30 | 42301 | [5 empty] | 0 | MIDEAST | OE
IPO | RU7890 | 9043 | INTECSA INGENIERIA INDUSTRIAL S.A. - ABU DHABI | 1180182 | P-Intecsa-1180182-Grupo 300 | 20531 | POC | EUR | 258024 | 46888 | 2017-07-21 | 2018-01-01 |  | 45608 | 4561 | 39690 |  | 39690 |  |  |  | 2018-05-30 | 39690 |  | 210434 |  | 2018-05-24 | 1190177161 | 0 | MIDEAST | OE
IPO | RU7890 | 9043 | INTECSA INGENIERIA INDUSTRIAL S.A. - ABU DHABI | 1180182 | P-Intecsa-1180182-Grupo 500 | 20532 | POC | EUR |  | 37305 | 2017-07-21 | 2018-01-01 |  | 36286 | 3629 | 30471 |  | 30471 |  |  |  | 2018-05-30 | 30471 | [5 empty] | 0 | MIDEAST | OE
IPO | RU7890 | 9043 | INTECSA INGENIERIA INDUSTRIAL S.A. - ABU DHABI | 1180182 | P-Intecsa-1180182-Grupo 600 | 20533 | POC | EUR |  | 48926 | 2017-07-21 | 2018-01-01 |  | 47590 | 4759 | 43507 |  | 40866 | [10 empty] | 0 | MIDEAST | OE
IPO | RU7890 | 9043 | INTECSA INGENIERIA INDUSTRIAL S.A. - ABU DHABI | 1180182 | P-Intecsa-1180182-Grupo 700 | 20534 | POC | EUR |  | 22772 | 2017-07-21 | 2018-01-01 |  | 22150 | 2215 | 19952 |  | 19952 |  |  |  | 2018-05-30 | 19952 | [5 empty] | 0 | MIDEAST | OE
IPO | RU7890 | 9043 | INTECSA INGENIERIA INDUSTRIAL S.A. - ABU DHABI | 1180182 | P-Intecsa-1180182-Grupo 100 | 20535 | POC | EUR |  | 36768 | 2017-07-21 | 2018-01-01 |  | 35764 | 3576 | 29278 |  | 29278 |  |  |  | 2018-05-30 | 29278 | [5 empty] | 0 | MIDEAST | OE
IPO | RU7890 | 9043 | INTECSA INGENIERIA INDUSTRIAL S.A. - ABU DHABI | 1180182 | P-Intecsa-1180182-Grupo 200 | 20536 | POC | EUR |  | 36496 | 2017-07-21 | 2018-01-01 |  | 35500 | 3550 | 29256 |  | 29256 |  |  |  | 2018-05-30 | 29256 | [5 empty] | 0 | MIDEAST | OE
IPO | RU7890 | 9043 | INTECSA INGENIERIA INDUSTRIAL S.A. - ABU DHABI | 1180182 | P-Intecsa-1180182-Grupo 400 | 20537 | POC | EUR |  | 36111 | 2017-07-21 | 2018-01-01 |  | 35126 | 3513 | 31067 |  | 31067 |  |  |  | 2018-05-30 | 31067 | [5 empty] | 0 | MIDEAST | OE
IPO | RU7890 | 21343 | HPD PROCESS ENGINEERING SA | 1212164 | P-Veolia HD-1212164 | 21972 | POC | EUR | 233440 | 273584 | 2018-01-25 | 2018-06-15 |  | 233440 | 9338 | 180599 |  | 0 | [10 empty] | 0 | LA | OE
IPO | RU7905 | 17161 | EXERGY SPA | 126794 | P-Exergy-126794-Supply of 2 HP pumps | 18940 | POC | EUR | 261999.8333 | 172022.53 | 2017-12-28 | 2018-05-14 |  | 143399.9083 | [13 empty] | 5 | 0 | OTHER | OE
IPO | RU7905 | 17161 | EXERGY SPA | 126794 | P-Exergy-126794-Supply of 2 LP pumps | 18941 | POC | EUR |  | 142272.47 | 2017-12-28 | 2018-05-14 |  | 118599.925 | [14 empty] | 0 | OTHER | OE
IPO | RU7908 | 18267 | Lanxess N.V. | 20815301 | P- Lanxess- 1207407 | 18634 | POC | EUR | 230726.8006 | 276779.87 | 2017-12-07 | 2018-05-07 |  | 230726.8006 |  | 173949 |  | 173949 |  |  |  | 2018-05-23 |  |  | 146026.8 |  | 2018-05-28 | 290052860 | 0 | EUROPE | AM
IPO | RU7926 | 22558 | OMV Petrom S.A. | 8460005441 | P - OMV Petrom S.A. - 8460005441 | 22561 | POC | EUR | 825000 | 989670 | 2018-01-31 | 2018-10-05 |  | 825000 | [11 empty] | 0 |  |  | 0 | EUROPE | OE
IPO | RU7932 | 10314 | GRUPA AZOTY Zakłady Azotowe „Puławy” Spółka Akcyjna | PL/17/278 | P - Pulawy PL/17/278 | 12487 | POC | EUR | 547200.427 | 615108 | 2017-06-30 | 2018-02-28 |  | 547200.427 | 0 | 1641311 |  |  | 58840 | [6 empty] | 0 |  |  | 0 | EUROPE | OE
EPO | RU8000 | 3858 | SHELL CHEMICAL APPALACHIA LLC CO TECHNIP FRANCE | 16AE0018/20 | P-SHELL CHEMICAL APPALACHIA LLC CO TECHNIP FRANCE-064340C006-U40000-PO-0910-005-0-O3085 | 4080 | POC | USD | 1499452 | 1287242.63 | 2016-01-29 | 2018-11-26 |  | 1351604.63 | 64362 | 34038768 | [9 empty] | 0 |  |  | 0 | US | OE
EPO | RU8000 | 3858 | SHELL CHEMICAL APPALACHIA LLC CO TECHNIP FRANCE | 16AE0018/20 | P-SHELL CHEMICAL APPALACHIA LLC CO TECHNIP FRANCE-064340C006-U40000-PO-0910-005-0-O3085 | 4083 | POC | USD |  | 140807.37 | 2016-01-29 | 2018-11-26 |  | 147847.37 | 7040 | 3730099 | [12 empty] | 0 | US | OE
EPO | RU8000 | 4202 | SHELL CHEMICAL APPALACHIA LLC | 15AE0100/102 | P- SHELL CHEMICAL APPALACHIA LLC PO 25873-100-POA-MPGB-00001 | 4307 | POC | USD | 4201763.81 | 3499601.1 | 2015-12-23 | 2018-05-14 |  | 3674581.1 | 174980 | 76762486 | [9 empty] | 0 |  |  | 0 | US | OE
EPO | RU8000 | 4202 | SHELL CHEMICAL APPALACHIA LLC | 15AE0100/102 | P- SHELL CHEMICAL APPALACHIA LLC PO 25873-100-POA-MPGB-00001 | 4348 | POC | USD |  | 502078.71 | 2015-12-23 | 2018-05-14 |  | 527182.71 | 25104 | 11095432 | [12 empty] | 0 | US | OE
EPO | RU8000 | 5959 | CAMERON ARGENTINA SAIC | 17AB0614/17 | P- CAMERON ARGENTINA SAIC- PO 4511538551 | 5970 | POC | USD | 272440 | 45932.4 | 2017-06-26 | 2018-01-31 |  | 48478.4 | 2546 | 1152384 | [9 empty] | 0 |  |  | 0 | LA | OE
EPO | RU8000 | 5959 | CAMERON ARGENTINA SAIC | 17AB0614/17 | P- CAMERON ARGENTINA SAIC- PO 4511538551 | 6186 | POC | USD |  | 137797.19 | 2017-06-26 | 2018-01-31 |  | 145436.19 | 7639 | 3752707 | [12 empty] | 0 | LA | OE
EPO | RU8000 | 5959 | CAMERON ARGENTINA SAIC | 17AB0614/17 | P- CAMERON ARGENTINA SAIC- PO 4511538551 | 6188 | POC | USD |  | 75088.41 | 2017-06-26 | 2018-01-31 |  | 78525.41 | 3437 | 760003 | [12 empty] | 0 | LA | OE
EPO | RU8000 | 6312 | Joint Venture of Tecnicas Reunidas S.A. (JV Leader)/ Sinopec Engineering (Group) Co. Ltd and Hanwha Engineering and Construction | 16AE0037/75 | P - Joint Venture of Tecnicas Reunidas/Sinopec and Hanwha - Al Jour Refinery Project PO 1003005160/16AE0037/42 | 9991 | POC | USD | 22706380.77 | 2850729.06 | 2016-10-19 | 2018-05-30 |  | 3017366.06 | 166637 | 55970380 | [9 empty] | 0 |  |  | 0 | OTHER | OE
EPO | RU8000 | 6312 | Joint Venture of Tecnicas Reunidas S.A. (JV Leader)/ Sinopec Engineering (Group) Co. Ltd and Hanwha Engineering and Construction | 16AE0037/75 | P - Joint Venture of Tecnicas Reunidas/Sinopec and Hanwha - Al Jour Refinery Project PO 1003005160/16AE0070/75 | 20592 | POC | USD |  | 3228511.74 | 2016-10-19 | 2018-05-30 |  | 3882654.74 | 654143 | 155074487 | [12 empty] | 0 | OTHER | OE
EPO | RU8000 | 6312 | Joint Venture of Tecnicas Reunidas S.A. (JV Leader)/ Sinopec Engineering (Group) Co. Ltd and Hanwha Engineering and Construction | 16AE0037/75 | P - Joint Venture of Tecnicas Reunidas/Sinopec and Hanwha - Al Jour Refinery Project PO 1003005160/16AE0043/51 | 20593 | POC | USD |  | 7323226.17 | 2016-10-19 | 2018-05-30 |  | 7832938.17 | 509712 | 141996615 | [12 empty] | 0 | OTHER | OE
EPO | RU8000 | 6312 | Joint Venture of Tecnicas Reunidas S.A. (JV Leader)/ Sinopec Engineering (Group) Co. Ltd and Hanwha Engineering and Construction | 16AE0037/75 | P - Joint Venture of Tecnicas Reunidas/Sinopec and Hanwha - Al Jour Refinery Project PO 1003005160/16AE0052/60 | 20594 | POC | USD |  | 7772785.8 | 2016-10-19 | 2018-05-30 |  | 7973421.8 | 200636 | 61341165 | [12 empty] | 0 | OTHER | OE
EPO | RU8000 | 7094 | CB&I LLC | 17AE0047/57 | P- CB&I LLC- 191058E-PO-110110-01 | 7317 | POC | USD | 9106509.01 | 955097.69 | 2017-06-16 | 2018-10-23 |  | 955097.69 |  | 18393408 | [9 empty] | 0 |  |  | 0 | US | OE
EPO | RU8000 | 7094 | CB&I LLC | 17AE0047/57 | P- CB&I LLC- 191058E-PO-110110-01 | 7428 | POC | USD |  | 1594947.45 | 2017-06-16 | 2018-10-23 |  | 1594947.45 |  | 30655207 | [12 empty] | 0 | US | OE
EPO | RU8000 | 7094 | CB&I LLC | 17AE0047/57 | P- CB&I LLC- 191058E-PO-110110-01 | 7429 | POC | USD |  | 511836.47 | 2017-06-16 | 2018-10-23 |  | 511836.47 |  | 9838781 | [12 empty] | 0 | US | OE
EPO | RU8000 | 7094 | CB&I LLC | 17AE0047/57 | P- CB&I LLC- 191058E-PO-110110-01 | 7430 | POC | USD |  | 1489566.02 | 2017-06-16 | 2018-10-23 |  | 1489566.02 |  | 28719435 | [12 empty] | 0 | US | OE
EPO | RU8000 | 7094 | CB&I LLC | 17AE0047/57 | P- CB&I LLC- 191058E-PO-110110-01 | 7432 | POC | USD |  | 496522.01 | 2017-06-16 | 2018-10-23 |  | 496522.01 |  | 9573145 | [12 empty] | 0 | US | OE
EPO | RU8000 | 7094 | CB&I LLC | 17AE0047/57 | P- CB&I LLC- 191058E-PO-110110-01 | 7438 | POC | USD |  | 2707578.81 | 2017-06-16 | 2018-10-23 |  | 2707578.81 |  | 52054790 | [12 empty] | 0 | US | OE
EPO | RU8000 | 7094 | CB&I LLC | 17AE0047/57 | P- CB&I LLC- 191058E-PO-110110-01 | 7453 | POC | USD |  | 1350960.56 | 2017-06-16 | 2018-10-23 |  | 1350960.56 |  | 26047066 | [12 empty] | 0 | US | OE
EPO | RU8000 | 7541 | PROSERNAT | 17AE0029/46 | P-PROSERNAT- PO 41572/02361 | 7543 | POC | USD | 1358523.16 | 1249841.16 | 2017-06-08 | 2018-02-12 |  | 1358523.16 | 108682 | 27059301 | [9 empty] | 0 |  |  | 532377 | LA | OE
EPO | RU8000 | 8555 | AXION ENERGY ARGENTINA SA | 17AB0621/30 | P- AXION ENERGY ARGENTINA SA- 4500006936 | 9356 | POC | USD | 843233 | 110909.9 | 2017-07-14 | 2018-04-18 |  | 110909.9 |  | 2289011 | [9 empty] | 0 |  |  | 0 | LA | OE
EPO | RU8000 | 8555 | AXION ENERGY ARGENTINA SA | 17AB0621/30 | P- AXION ENERGY ARGENTINA SA- 4500006936 | 9397 | POC | USD |  | 158903.3 | 2017-07-14 | 2018-04-18 |  | 158903.3 |  | 2784782 | [12 empty] | 0 | LA | OE
EPO | RU8000 | 8555 | AXION ENERGY ARGENTINA SA | 17AB0621/30 | P- AXION ENERGY ARGENTINA SA- 4500006936 | 9398 | POC | USD |  | 70806.6 | 2017-07-14 | 2018-04-18 |  | 70806.6 |  | 1289269 | [12 empty] | 0 | LA | OE
EPO | RU8000 | 8555 | AXION ENERGY ARGENTINA SA | 17AB0621/30 | P- AXION ENERGY ARGENTINA SA- 4500006936 | 9399 | POC | USD |  | 44503.3 | 2017-07-14 | 2018-04-18 |  | 44503.3 |  | 820104 | [12 empty] | 0 | LA | OE
EPO | RU8000 | 8555 | AXION ENERGY ARGENTINA SA | 17AB0621/30 | P- AXION ENERGY ARGENTINA SA- 4500006936 | 9400 | POC | USD |  | 160803.3 | 2017-07-14 | 2018-04-18 |  | 160803.3 |  | 2813010 | [12 empty] | 0 | LA | OE
EPO | RU8000 | 8555 | AXION ENERGY ARGENTINA SA | 17AB0621/30 | P- AXION ENERGY ARGENTINA SA- 4500006936 | 9401 | POC | USD |  | 32603.3 | 2017-07-14 | 2018-04-18 |  | 32603.3 |  | 638451 | [12 empty] | 0 | LA | OE
EPO | RU8000 | 8555 | AXION ENERGY ARGENTINA SA | 17AB0621/30 | P- AXION ENERGY ARGENTINA SA- 4500006936 | 9402 | POC | USD |  | 264703.3 | 2017-07-14 | 2018-04-18 |  | 264703.3 |  | 4979871 | [12 empty] | 0 | LA | OE
EPO | RU8000 | 10207 | ENGINEERING FOR THE PETROLEUM AND PROCESS INDUSTRIES | 17AE0021/28 | P - ENGINEERING FOR THE PETROLEUM AND PROCESS INDUSTRIES-17AE0021/28 - Manufacture and Delivery of API Centrifugal Pumps | 20091 | POC | USD | 822793.7 | 800487.7 | 2017-06-02 | 2018-03-05 |  | 822793.7 | 29906 | 14861070 | [9 empty] | 0 |  |  | 102656 | NAFRICA | OE
EPO | RU8000 | 10207 | ENGINEERING FOR THE PETROLEUM AND PROCESS INDUSTRIES | 17AE0021/28 | P - ENGINEERING FOR THE PETROLEUM AND PROCESS INDUSTRIES-17AE0021/28 - Manufacture and Delivery of API Centrifugal Pumps | 20747 | POC | USD |  | 144313 | 2017-06-02 | 2018-03-05 | [9 empty] | 2017-11-30 | [6 empty] | 0 | NAFRICA | OE
EPO | RU8000 | 10207 | ENGINEERING FOR THE PETROLEUM AND PROCESS INDUSTRIES | 17AE0021/28 | P - ENGINEERING FOR THE PETROLEUM AND PROCESS INDUSTRIES-17AE0021/28 - Manufacture and Delivery of API Centrifugal Pumps | 20748 | POC | USD |  | 137079 | 2017-06-02 | 2018-03-05 | [9 empty] | 2017-11-30 | [6 empty] | 0 | NAFRICA | OE
EPO | RU8000 | 10208 | SHELL CIA. ARGENTINA DE PETROLEO S.A. | 17AB6261 | P- SHELL CIA. ARGENTINA DE PETROLEO S.A.- PO 17000125 000 00121 | 16097 | POC | USD | 365760 | 365760 | 2017-06-19 | 2018-03-12 |  | 365760 |  | 4848034 | [9 empty] | 0 |  |  | 0 | LA | AM
EPO | RU8000 | 10208 | SHELL CIA. ARGENTINA DE PETROLEO S.A. | 17AB6261 | P- SHELL CIA. ARGENTINA DE PETROLEO S.A.- PO 17000125 000 00121 | 21332 | PIT | USD |  | 37900 | 2017-06-19 | 2018-03-12 | [9 empty] | 2017-12-31 | [6 empty] | 0 | LA | AM
EPO | RU8000 | 10210 | SHELL OFFSHORE INC. | 17AE0064 | P-SHELL OFFSHORE INC- PO 4513031199-200HP Pump | 16637 | POC | USD | 400400 | 400400 | 2017-07-13 | 2018-04-09 |  | 400400 |  | 7028811 | [9 empty] | 0 |  |  | 0 | US | OE
EPO | RU8000 | 16059 | ADVANSIX INC. | 17AE0070 | P- ADVANSIX INC- PO 4520040769 | 16358 | POC | USD | 464000 | 464000 | 2017-11-21 | 2018-07-27 |  | 464000 |  | 7531072 | [9 empty] | 0 |  |  | 0 | US | OE
EPO | RU8000 | 16347 | SHELL CANADA PRODUCTS | 16AE0329 | P-SHELL CANADA PRODUCTS - PO 4520387441 - PO 4520511442 - 1st Stage Reactor Feed Pump | 16367 | POC | CAD | 2559311.7569 | 1491651.34 | 2016-10-24 | 2018-02-16 |  | 1923335.2911 |  | 33289532 | [9 empty] | 0 |  |  | 0 | US | OE
EPO | RU8000 | 16347 | SHELL CANADA PRODUCTS | 16AE0329 | P-SHELL CANADA PRODUCTS - PO 4520387441 - PO 4520511442 - 1st Stage Capital Spares | 16494 | POC | CAD |  | 493234.41 | 2016-10-24 | 2018-02-16 |  | 635976.4659 |  | 11114693 | [12 empty] | 0 | US | OE
EPO | RU8000 | 16350 | SHELL CANADA PRODUCTS | 16AE0328 | P-SHELL CANADA PRODUCTS - PO 4520257996 - PO 4520511487 - 2nd Stage Reactor Feed Pump | 16368 | POC | CAD | 2691133.1441 | 1566948.55 | 2016-10-24 | 2018-02-16 |  | 2020423.5163 |  | 39899249 | [9 empty] | 0 |  |  | 0 | US | OE
EPO | RU8000 | 16350 | SHELL CANADA PRODUCTS | 16AE0328 | P-SHELL CANADA PRODUCTS - PO 4520257996 - PO 4520511487 - 2nd Stage Capital Spares | 16499 | POC | CAD |  | 520171.87 | 2016-10-24 | 2018-02-16 |  | 670709.6278 |  | 13448502 | [12 empty] | 0 | US | OE
EPO | RU8000 | 16493 | VALERO REFINIG TEXAS, LP | 16AE0089/90 | P - VALERO REFINING TEXAS, LP - 16AE0089/90 | 19475 | POC | USD | 1352358 | 1352358 | 2016-10-31 | 2018-01-15 |  | 1352358 |  | 22630566 | [9 empty] | 0 |  |  | 509736 | US | OE
EPO | RU8000 | 16495 | PLAINS MIDSTREAM CANADA | 17AE0004/5 | P - PLAINS MIDSTREAM CANADA - 17AE0004/5 - Pump1 | 19573 | POC | USD | 0 | 350443 | 2017-07-04 | 2018-02-05 | [9 empty] | 2017-12-31 |  |  |  | 0 |  |  | 0 | US | OE
EPO | RU8000 | 16495 | PLAINS MIDSTREAM CANADA | 17AE0004/5 | P - PLAINS MIDSTREAM CANADA - 17AE0004/5 - Pump2 | 20750 | POC | USD |  | 331275 | 2017-07-04 | 2018-02-05 | [9 empty] | 2018-02-28 | [6 empty] | 0 | US | OE
EPO | RU8000 | 16641 | TECPETROL S.A. | 17AB0565/92-600/05-608/13 | P - TECPETROL S.A. - 160002799-3 - POb1: 1K3X1.5-82RV M3 ST/1 - T AG: FPBATTIBH-001 A/B/C & Spare parts | 20865 | POC | USD | 1320274.09 | 81329.54 | 2017-05-22 | 2018-03-15 | [9 empty] | 2017-12-31 |  |  |  | 0 |  |  | 0 | LA | OE
EPO | RU8000 | 16641 | TECPETROL S.A. | 17AB0565/92-600/05-608/13 | P - TECPETROL S.A. - 160002799-3 - POb2: 300 VLT / 1 ETAPA - TAG: FPBATTIPBH-003 A/B & Spare parts | 20866 | POC | USD |  | 336278.79 | 2017-05-22 | 2018-03-15 |  | 336278.79 |  | 5402191 | [12 empty] | 0 | LA | OE
EPO | RU8000 | 16641 | TECPETROL S.A. | 17AB0565/92-600/05-608/13 | P - TECPETROL S.A. - 160002799-3 - POb3: 2K4X3-10RV M3 ST - TAG: FPPTA1-BA-001 A/B & Spare parts | 20867 | POC | USD |  | 28292.9 | 2017-05-22 | 2018-03-15 | [9 empty] | 2017-12-31 | [6 empty] | 0 | LA | OE
EPO | RU8000 | 16641 | TECPETROL S.A. | 17AB0565/92-600/05-608/13 | P - TECPETROL S.A. - 160002799-3 - POb4: 2K3X2-82RV M3 ST - TAG: FPPTG1-BH-004 A/B & Spare parts | 20868 | POC | USD |  | 25271.9 | 2017-05-22 | 2018-03-15 | [9 empty] | 2017-12-31 | [6 empty] | 0 | LA | OE
EPO | RU8000 | 16641 | TECPETROL S.A. | 17AB0565/92-600/05-608/13 | P - TECPETROL S.A. - 160002799-3 - POb5: 100 VLT / 3 ETAPAS TAG: FPPTG1-BH -081 A/B & Spare parts | 20869 | POC | USD |  | 62515.8 | 2017-05-22 | 2018-03-15 | [9 empty] | 2017-12-31 | [6 empty] | 0 | LA | OE
EPO | RU8000 | 16641 | TECPETROL S.A. | 17AB0565/92-600/05-608/13 | P - TECPETROL S.A. - 160002799-3 - POb6: 1K1.5X1-62RV M3 ST TAG: FPPTG1-BA-001 A/B & Spare parts | 20870 | POC | USD |  | 16066.68 | 2017-05-22 | 2018-03-15 | [9 empty] | 2017-12-31 | [6 empty] | 0 | LA | OE
EPO | RU8000 | 16641 | TECPETROL S.A. | 17AB0565/92-600/05-608/13 | P - TECPETROL S.A. - 160002799-3 - POb7: 40 NM / 9 ETAPAS - TAG: FPSAF-BA-004 & Spare parts | 20871 | POC | USD |  | 21204 | 2017-05-22 | 2018-03-15 | [9 empty] | 2017-12-31 | [6 empty] | 0 | LA | OE
EPO | RU8000 | 16641 | TECPETROL S.A. | 17AB0565/92-600/05-608/13 | P - TECPETROL S.A. - 160002799-3 - POb8: 3X12DMX/12 ETAPAS DESTAGEADA A 5 & Spare parts | 20872 | POC | USD |  | 983995.3 | 2017-05-22 | 2018-03-15 |  | 983995.3 |  | 18200875 | [12 empty] | 0 | LA | OE
EPO | RU8000 | 16641 | TECPETROL S.A. | 17AB0565/92-600/05-608/13 | P - TECPETROL S.A. - 160002799-3 - POb9: MODELO 16 GM/ 5 ETAPAS & Spare parts | 20873 | POC | USD |  | 235341 | 2017-05-22 | 2018-03-15 | [9 empty] | 2018-01-31 | [6 empty] | 0 | LA | OE
EPO | RU8000 | 16641 | TECPETROL S.A. | 17AB0565/92-600/05-608/13 | P - TECPETROL S.A. - 160002799-3 - POb10: 100 VLT / 28 ETAPAS & Spare parts | 20874 | POC | USD |  | 118044 | 2017-05-22 | 2018-03-15 | [9 empty] | 2018-02-28 | [6 empty] | 0 | LA | OE
EPO | RU8000 | 17376 | KIEWIT OFFSHORE SERVICES LTD. C/O WOOD GROUP MUSTANG INC. | 16AE0086/87 | P - KIEWIT OFFSHORE SERVICES LTD. C/O WOOD GROUP MUSTANG INC. - PO# 106663-302.0 - POb2: Complete 6X11 DMX- 9 STG | 17395 | POC | USD | 0 | 1138366.57 | 2016-08-25 | 2018-01-15 | [9 empty] | 2018-01-31 |  |  |  | 0 |  |  | 0 | US | OE
EPO | RU8000 | 17376 | KIEWIT OFFSHORE SERVICES LTD. C/O WOOD GROUP MUSTANG INC. | 16AE0086/87 | P - KIEWIT OFFSHORE SERVICES LTD. C/O WOOD GROUP MUSTANG INC. - PO# 106663-302.0 - POb1: Complete 6X11 DMX-9 STG (Pump A) | 20142 | POC | USD |  | 1138366.58 | 2016-08-25 | 2018-01-15 | [9 empty] | 2018-01-31 | [6 empty] | 0 | US | OE
EPO | RU8000 | 18180 | AXION ENERGY ARGENTINA S.A. | 17AB0606/07 | P- AXION ENERGY ARGENTINA S.A.- PO #4500006794 | 18209 | POC | USD | 580570.32 | 580570.32 | 2017-06-12 | 2018-01-17 |  | 580570.32 |  | 14108469 | [9 empty] | 0 |  |  | 174358 | LA | OE
EPO | RU8000 | 18218 | YACIMIENTO ENTRE LOMAS S.A. | 17AB6312/13 | P- YACIMIENTO ENTRE LOMAS S.A.- PO #046042 | 18227 | POC | USD | 0 | 150730 | 2017-08-02 | 2018-01-10 | [9 empty] | 2018-01-31 |  |  |  | 0 |  |  | 0 | LA | AM
EPO | RU8000 | 18218 | YACIMIENTO ENTRE LOMAS S.A. | 17AB6312/13 | P- YACIMIENTO ENTRE LOMAS S.A.- PO #046042 | 20603 | POC | USD |  | 150924 | 2017-08-02 | 2018-01-10 | [9 empty] | 2018-01-31 | [6 empty] | 0 | LA | AM
EPO | RU8000 | 18655 | FLUOR CHILE INGENIERIA Y CONSTRUCCION S.A. | 17AE0060/61 | P-FLUOR CHILE INGENIERIA Y CONSTRUCCION S.A. PO- 4500120969 | 18653 | POC | USD | 376753 | 183160.04 | 2017-06-12 | 2018-01-30 | [9 empty] | 2018-02-28 |  |  |  | 0 |  |  | 0 | LA | OE
EPO | RU8000 | 18655 | FLUOR CHILE INGENIERIA Y CONSTRUCCION S.A. | 17AE0060/61 | P-FLUOR CHILE INGENIERIA Y CONSTRUCCION S.A. PO- 4500120969 | 20851 | POC | USD |  | 296191.26 | 2017-06-12 | 2018-01-30 |  | 376753 | 40281 | 7371982 | [12 empty] | 0 | LA | OE
EPO | RU8000 | 23218 | AIR PRODUCTS AND CHEMICALS | 18AE0002/03 | P- AIR PRODUCTS AND CHEMICALS INC- PO 4504337750- Multi stage lean solvent pumps | 23233 | POC | USD | 585592 | 585592 | 2018-02-28 | 2018-09-25 |  | 585592 |  | 10009817 | [9 empty] | 0 |  |  | 0 | US | OE
EPO | RU8000 | 27620 | VALERO TERMINALING AND DISTRIBUTION CO. | 18AE0010/11 | P-VALERO TERMINALING AND DISTRIBUTION CO- #4504238511 | 27636 | POC | USD | 667558 | 667558 | 2018-04-18 | 2019-01-08 |  | 667558 | [11 empty] | 0 |  |  | 0
EPO | RU8000 | 27746 | YPF ENERGIA ELECTRICA S.A. | 18AB6270/73 | P- YPF ENERGIA ELECTRICA S.A.- #4700391499- 18AB6270 | 27749 | POC | USD | 480935.6 | 120233.9 | 2018-04-26 | 2018-12-27 |  | 120233.9 | [11 empty] | 0 |  |  | 0
EPO | RU8000 | 27746 | YPF ENERGIA ELECTRICA S.A. | 18AB6270/73 | P- YPF ENERGIA ELECTRICA S.A.- #4700391499- 18AB6271 | 27750 | POC | USD |  | 120233.9 | 2018-04-26 | 2018-12-27 |  | 120233.9 | [14 empty] | 0
EPO | RU8000 | 27746 | YPF ENERGIA ELECTRICA S.A. | 18AB6270/73 | P- YPF ENERGIA ELECTRICA S.A.- #4700391499- 18AB6272 | 27751 | POC | USD |  | 120233.9 | 2018-04-26 | 2018-12-27 |  | 120233.9 | [14 empty] | 0
EPO | RU8000 | 27746 | YPF ENERGIA ELECTRICA S.A. | 18AB6270/73 | P- YPF ENERGIA ELECTRICA S.A.- #4700391499- 18AB6273 | 27752 | POC | USD |  | 120233.9 | 2018-04-26 | 2018-12-27 |  | 120233.9 | [14 empty] | 0
EPO | RU8000 | 27792 | OLEODUCTO DEL VALLE S.A. | 18AB6209-18AB6280/83 | P-OLEODUCTO DEL VALLE S.A.-PO# 5300000033-18AB6209 | 27811 | POC | USD | 891440 | 147529.4 | 2018-04-27 | 2018-08-20 |  | 147529.4 | [11 empty] | 0 |  |  | 0
EPO | RU8000 | 27792 | OLEODUCTO DEL VALLE S.A. | 18AB6209-18AB6280/83 | P-OLEODUCTO DEL VALLE S.A.-PO# 5300000033-18AB6280 | 27818 | POC | USD |  | 142692 | 2018-04-27 | 2018-08-20 |  | 142692 | [14 empty] | 0
EPO | RU8000 | 27792 | OLEODUCTO DEL VALLE S.A. | 18AB6209-18AB6280/83 | P-OLEODUCTO DEL VALLE S.A.-PO# 5300000033-18AB6281 | 27819 | POC | USD |  | 234899.3 | 2018-04-27 | 2018-08-20 |  | 234899.3 | [14 empty] | 0
EPO | RU8000 | 27792 | OLEODUCTO DEL VALLE S.A. | 18AB6209-18AB6280/83 | P-OLEODUCTO DEL VALLE S.A.-PO# 5300000033-18AB6282 | 27821 | POC | USD |  | 234899.3 | 2018-04-27 | 2018-08-20 |  | 234899.3 | [14 empty] | 0
EPO | RU8000 | 27792 | OLEODUCTO DEL VALLE S.A. | 18AB6209-18AB6280/83 | P-OLEODUCTO DEL VALLE S.A.-PO# 5300000033-18AB6283 | 27822 | POC | USD |  | 131420 | 2018-04-27 | 2018-08-20 |  | 131420 | [14 empty] | 0
EPO | RU8000 | 27865 | TECPETROL S.A. | 18AB6218/20 | P-TECPETROL- PO# 450-009.003 | 27889 | POC | USD | 533514.15 | 533514.15 | 2018-04-30 | 2018-08-13 |  | 533514.15 | [11 empty] | 0 |  |  | 0
EPO | RU8000 | 27930 | ECOPETROL S.A. | 18AE0004/8 | P-ECOPETROL S.A.- PO#1500004-COMPLETE 8X15 DVMXDH-B PUMP + SPARE PARTS (GROUPED) | 27934 | POC | USD | 3040585 | 3040585 | 2018-03-30 | 2018-12-12 |  | 3040585 | [11 empty] | 0 |  |  | 0
IPO | RU8002 | 10211 | SHELL CIA. ARGENTINA DE PETROLEO S.A. | 17AB0642/47 | P- SHELL CIA. ARGENTINA DE PETROLEO S.A.- PO OA17000886 000 00121 Pob 3 | 15948 | POC | USD | 292540 | 94467.64 | 2017-08-14 | 2018-03-30 |  | 94467.64 | [11 empty] | 0 |  |  | 0 | LA | OE
IPO | RU8002 | 10211 | SHELL CIA. ARGENTINA DE PETROLEO S.A. | 17AB0642/47 | P- SHELL CIA. ARGENTINA DE PETROLEO S.A.- PO OA17000886 000 00121 POb 1 | 20179 | POC | USD |  | 54602.98 | 2017-08-14 | 2018-03-30 |  | 54602.98 | [14 empty] | 0 | LA | OE
IPO | RU8002 | 10211 | SHELL CIA. ARGENTINA DE PETROLEO S.A. | 17AB0642/47 | P- SHELL CIA. ARGENTINA DE PETROLEO S.A.- PO OA17000886 000 00121 POb 4 | 20180 | POC | USD |  | 107489.25 | 2017-08-14 | 2018-03-30 |  | 107489.25 | [14 empty] | 0 | LA | OE
IPO | RU8002 | 10211 | SHELL CIA. ARGENTINA DE PETROLEO S.A. | 17AB0642/47 | P- SHELL CIA. ARGENTINA DE PETROLEO S.A.- PO OA17000886 000 00121 POb 2 | 20943 | POC | USD |  | 35980.13 | 2017-08-14 | 2018-03-30 |  | 35980.13 | [14 empty] | 0 | LA | OE
AMSS | RU8010 | 27904 | CENTRAL DOCK SUD S.A. | 18AB6274/78 | P-CENTRAL DOCK SUD+ PO# 1400730299- CCR | 27910 | POC | USD | 262844 | 39891 | 2018-04-30 | 2019-04-26 |  | 39891 | [11 empty] | 0 |  |  | 0
AMSS | RU8010 | 27904 | CENTRAL DOCK SUD S.A. | 18AB6274/78 | P-CENTRAL DOCK SUD+ PO# 1400730299- Alimentacion MP | 27911 | POC | USD |  | 23228 | 2018-04-30 | 2019-04-26 |  | 23228 | [14 empty] | 0
AMSS | RU8010 | 27904 | CENTRAL DOCK SUD S.A. | 18AB6274/78 | P-CENTRAL DOCK SUD+ PO# 1400730299- Alimentacion AP | 27912 | POC | USD |  | 57167 | 2018-04-30 | 2019-04-26 |  | 57167 | [14 empty] | 0
AMSS | RU8010 | 27904 | CENTRAL DOCK SUD S.A. | 18AB6274/78 | P-CENTRAL DOCK SUD+ PO# 1400730299- Agua circulacion | 27913 | PIT | USD |  | 112578 | 2018-04-30 | 2019-04-26 |  | 112578 | [14 empty] | 0
AMSS | RU8010 | 27904 | CENTRAL DOCK SUD S.A. | 18AB6274/78 | P-CENTRAL DOCK SUD+ PO# 1400730299- extraccion y condensado | 28014 | PIT | USD |  | 29980 | 2018-04-30 | 2019-04-26 |  | 29980 | [14 empty] | 0
AMSS | RU8020 | 17066 | Woodside | S75705 | P - Woodside GasPac - 4650000561 | 17073 | POC | AUD | 735459.9524 | 556449 | 2017-10-02 | 2017-11-15 |  | 735459.9524 | [14 empty] | 0 | ASIA | AM
EPO | RU8025 | 5569 | SHELL CHEMICAL APPALACHIA | 234512615 | P - SHELL CHEMICAL APPALACHIA - 234512615 - Comonomer Charge Pumps - TAG-No: P-31002 | 5592 | POC | USD | 749471 | 137088.16 | 2015-12-02 | 2019-04-30 |  | 137088 | 6854.41 | 104103.93 |  | 79358 | [7 empty] | 0 |  |  | 0 | US | OE
EPO | RU8025 | 5569 | SHELL CHEMICAL APPALACHIA | 234512615 | P - SHELL CHEMICAL APPALACHIA - 234512615 - Comonomer Charge Pumps - TAG-No: P-31003 | 5593 | POC | USD |  | 130451.81 | 2015-12-02 | 2019-04-30 |  | 130452 | 6522.59 | 104103.93 |  | 79358 | [10 empty] | 0 |  | OE
EPO | RU8025 | 5569 | SHELL CHEMICAL APPALACHIA | 234512615 | P - SHELL CHEMICAL APPALACHIA - 234512615 - Comonomer Charge Pumps - TAG-No: P-31014 | 5594 | POC | USD |  | 129620.69 | 2015-12-02 | 2019-04-30 |  | 129621 | 6481.03 | 99861.83 |  | 42728 | [10 empty] | 0 |  | OE
EPO | RU8025 | 5569 | SHELL CHEMICAL APPALACHIA | 234512615 | P - SHELL CHEMICAL APPALACHIA - 234512615 - High Pressure Condensate Return Pumps - TAG No: P-25215 A-B | 5595 | POC | USD |  | 176155.45 | 2015-12-02 | 2019-04-30 |  | 176155 | 8807.77 | 123966.75 |  | 206229 | [10 empty] | 0 |  | OE
EPO | RU8025 | 5569 | SHELL CHEMICAL APPALACHIA | 234512615 | P - SHELL CHEMICAL APPALACHIA - 234512615 - High Pressure Condensate Return Pumps - TAG No: P-35215 A-B | 5596 | POC | USD |  | 176155.45 | 2015-12-02 | 2019-04-30 |  | 176155 | 8807.77 | 123966.75 |  | 206229 | [10 empty] | 0 |  | OE
EPO | RU8025 | 5632 | NESTE SINGAPORE PTE LTD | 234515294 | P - NESTE SINGAPORE PTE LTD - 234515294 - Hydrotreating Reactor Feed Pump / TAG-No: 20GA-01/S | 5666 | POC | EUR | 826924.3484 | 442393.46 | 2017-04-25 | 2018-05-16 |  | 393553.4739 |  | 303356.2 |  | 493462 | [10 empty] | 0 | ASIA | OE
EPO | RU8025 | 5632 | NESTE SINGAPORE PTE LTD | 234515294 | P - NESTE SINGAPORE PTE LTD - 234515294 - Hydrotreating Reactor Feed Pump / TAG-No: 20GA-01 | 5667 | POC | EUR |  | 446138.96 | 2017-04-25 | 2018-05-16 |  | 396885.4728 |  | 303356.2 |  | 493462 | [10 empty] | 0 |  | OE
EPO | RU8025 | 5632 | NESTE SINGAPORE PTE LTD | 234515294 | P - NESTE SINGAPORE PTE LTD - 234515294 - Spare Parts for 2 years operation | 6800 | POC | EUR |  | 41013.24 | 2017-04-25 | 2018-05-16 |  | 36485.4017 |  | 33177.54 |  | 27976 | [10 empty] | 0 |  | AM
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Amine Sump Pump / Tag-No. 31-P-0003 | 5878 | POC | USD | 4771288.45 | 57938.35 | 2016-12-22 | 2018-08-03 |  | 57938.35 | 1159 | 109492.63 |  | 107598 | [7 empty] | 0 |  |  | 0 | MIDEAST | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Wet Slops Sump Pumps / Tag-No. 31-P-0004 | 5879 | POC | USD |  | 44239.76 | 2016-12-22 | 2018-08-03 |  | 44239.76 | 885 | 52030.39 |  | 52030 |  |  |  | 2018-03-31 | [6 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Wet Slops Sump Pumps / Tag-No. 31-P-0004S | 5880 | POC | USD |  | 36098.89 | 2016-12-22 | 2018-08-03 |  | 36098.89 | 722 | 36194.32 |  | 36194 |  |  |  | 2018-03-31 | [6 empty] | 0 |  | AM
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Wet Slops Sump Pump / Tag-No. 32-P-1101 | 5881 | POC | USD |  | 46535.93 | 2016-12-22 | 2018-08-03 |  | 46535.93 | 931 | 51318.79 |  | 51319 |  |  |  | 2018-01-31 | [6 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Wet Slops Sump Pump / Tag-No. 33-P-0208 | 5882 | POC | USD |  | 44382.42 | 2016-12-22 | 2018-08-03 |  | 44382.42 | 888 | 48461.86 |  | 48462 |  |  |  | 2018-01-31 | [6 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Wet Slops Sump Pump / Tag-No. 33-P-0408 | 5883 | POC | USD |  | 44382.42 | 2016-12-22 | 2018-08-03 |  | 44382.42 | 888 | 50748.13 |  | 50748 |  |  |  | 2018-03-31 | [6 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Naphtha Drain Drum Pumps / Tag-No. 33-P-0209 | 5884 | POC | USD |  | 44529.22 | 2016-12-22 | 2018-08-03 |  | 44529.22 | 891 | 48483.19 |  | 48483 |  |  |  | 2018-01-31 | [6 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Naphtha Drain Drum Pumps / Tag-No. 33-P-0209S | 5885 | POC | USD |  | 37498.93 | 2016-12-22 | 2018-08-03 |  | 37498.93 | 750 | 35952.21 |  | 35952 |  |  |  | 2018-01-31 | [6 empty] | 0 |  | AM
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Naphtha Drain Drum Pump / Tag-No. 33-P-0409 | 5886 | POC | USD |  | 44529.22 | 2016-12-22 | 2018-08-03 |  | 44529.22 | 891 | 49646.68 |  | 49647 |  |  |  | 2018-03-31 | [6 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Blowdown Condesate Pumps / Tag-No. 33-P-0510 A/B | 5887 | POC | USD |  | 134602.14 | 2016-12-22 | 2018-08-03 |  | 134602.14 | 2692 | 125608.88 |  | 125609 |  |  |  | 2018-01-31 | [6 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Wet Slops Sump Pump / Tag-No. 35-P-0108 | 5888 | POC | USD |  | 43664.48 | 2016-12-22 | 2018-08-03 |  | 43664.48 | 873 | 52038.72 |  | 52039 |  |  |  | 2018-01-31 | [6 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Wet Slops Sump Pump / Tag-No. 35-P-0208 | 5889 | POC | USD |  | 43664.48 | 2016-12-22 | 2018-08-03 |  | 43664.48 | 873 | 40758.87 |  | 40759 |  |  |  | 2018-03-31 | [6 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Wet Slops Sump Pump / Tag-No. 35-P-0308 | 5890 | POC | USD |  | 43664.48 | 2016-12-22 | 2018-08-03 |  | 43664.48 | 873 | 40758.87 |  | 40759 |  |  |  | 2018-03-31 | [6 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Sour Water Drain Drum Pumps / Tag-No. 35-P-0110 | 5891 | POC | USD |  | 63174.34 | 2016-12-22 | 2018-08-03 |  | 63174.34 | 1263 | 59863.45 |  | 58894 | [10 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Sour Water Drain Drum Pumps / Tag-No. 35-P-0110S | 5892 | POC | USD |  | 50411.69 | 2016-12-22 | 2018-08-03 |  | 50411.69 | 1008 | 39022.99 |  | 38462 | [10 empty] | 0 |  | AM
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Sour Water Drain Drum Pump / Tag-No. 35-P-0210 | 5893 | POC | USD |  | 63174.34 | 2016-12-22 | 2018-08-03 |  | 63174.34 | 1263 | 49675.96 |  | 92489 | [10 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Sour Water Drain Drum Pump / Tag-No. 35-P-0310 | 5894 | POC | USD |  | 63174.34 | 2016-12-22 | 2018-08-03 |  | 63174.34 | 1263 | 49675.96 |  | 92489 | [10 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Amine Drain Pumps / Tag-No. 39-P-0105 | 5895 | POC | USD |  | 68766.02 | 2016-12-22 | 2018-08-03 |  | 68766.02 | 1375 | 59254.98 |  | 58297 | [10 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Amine Drain Pumps / Tag-No. 39-P-0105S | 5896 | POC | USD |  | 57308.63 | 2016-12-22 | 2018-08-03 |  | 57308.63 | 1146 | 45785.48 |  | 45092 | [10 empty] | 0 |  | AM
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Amine Drain Pump / Tag-No. 39-P-0205 | 5897 | POC | USD |  | 68766.03 | 2016-12-22 | 2018-08-03 |  | 68766.03 | 1375 | 50178.23 |  | 98593 | [10 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Amine Drain Pump / Tag-No. 39-P-0305 | 5898 | POC | USD |  | 68766.03 | 2016-12-22 | 2018-08-03 |  | 68766.03 | 1375 | 50178.23 |  | 98593 | [10 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Wet Slops Sump Pump / Tag-No. 39-P-0108 | 5899 | POC | USD |  | 43664.5 | 2016-12-22 | 2018-08-03 |  | 43664.5 | 873 | 41373.36 |  | 41373 |  |  |  | 2018-01-31 | [6 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Wet Slops Sump Pump / Tag-No. 39-P-0208 | 5900 | POC | USD |  | 43664.5 | 2016-12-22 | 2018-08-03 |  | 43664.5 | 873 | 41373.36 |  | 41373 |  |  |  | 2018-01-31 | [6 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Wet Slops Sump Pump / Tag-No. 39-P-0308 | 5901 | POC | USD |  | 43664.49 | 2016-12-22 | 2018-08-03 |  | 43664.49 | 873 | 48708.86 |  | 48709 |  |  |  | 2018-01-31 | [6 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Solvent Drain Return Pumps / Tag-No. 43-P-0125 | 5902 | POC | USD |  | 53803.87 | 2016-12-22 | 2018-08-03 |  | 53803.87 | 1076 | 51320 |  | 50518 | [10 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Solvent Drain Return Pumps / Tag-No. 43-P-0125S | 5903 | POC | USD |  | 45977.9 | 2016-12-22 | 2018-08-03 |  | 45977.9 | 920 | 37285.76 |  | 36759 | [10 empty] | 0 |  | AM
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Solvent Drain Return Pumps / Tag-No. 43-P-0225 | 5904 | POC | USD |  | 53803.88 | 2016-12-22 | 2018-08-03 |  | 53803.88 | 1076 | 42962.48 |  | 84444 | [10 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Solvent Drain Return Pumps / Tag-No. 43-P-0325 | 5905 | POC | USD |  | 53803.88 | 2016-12-22 | 2018-08-03 |  | 53803.88 | 1076 | 42962.48 |  | 84444 | [10 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Sour Water Drains Pump / Tag-No. 43-P-0127 | 5906 | POC | USD |  | 43451.96 | 2016-12-22 | 2018-08-03 |  | 43451.96 | 869 | 52045.8 |  | 52046 |  |  |  | 2018-01-31 | [6 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Sour Water Drains Pump / Tag-No. 43-P-0127S | 5907 | POC | USD |  | 35600.88 | 2016-12-22 | 2018-08-03 |  | 35600.88 | 712 | 35364.14 |  | 35364 |  |  |  | 2018-01-31 | [6 empty] | 0 |  | AM
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Sour Water Drains Pump / Tag-No. 43-P-0227 | 5908 | POC | USD |  | 43451.97 | 2016-12-22 | 2018-08-03 |  | 43451.97 | 869 | 41776.97 |  | 41777 |  |  |  | 2018-03-31 | [6 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Sour Water Drains Pump / Tag-No. 43-P-0327 | 5909 | POC | USD |  | 43451.97 | 2016-12-22 | 2018-08-03 |  | 43451.97 | 869 | 41776.97 |  | 41777 |  |  |  | 2018-03-31 | [6 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Sulfur Cooler Pump / Tag-No. 43-P-0141 A/B | 5910 | POC | USD |  | 67945.5 | 2016-12-22 | 2018-08-03 |  | 67945.5 | 1359 | 77427.81 |  | 77428 |  |  |  | 2018-03-31 | [6 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Sulfur Cooler Pump / Tag-No. 43-P-0241 A/B | 5911 | POC | USD |  | 67945.5 | 2016-12-22 | 2018-08-03 |  | 67945.5 | 1359 | 54706.2 |  | 54706 |  |  |  | 2018-03-31 | [6 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Sulfur Cooler Pump / Tag-No. 43-P-0341 A/B | 5912 | POC | USD |  | 67945.5 | 2016-12-22 | 2018-08-03 |  | 67945.5 | 1359 | 54706.2 |  | 54706 |  |  |  | 2018-03-31 | [6 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Sulfur Cooler Pump / Tag-No. 43-P-0142 A/B | 5913 | POC | USD |  | 124854.76 | 2016-12-22 | 2018-08-03 |  | 124854.76 | 2497 | 82225.96 |  | 82226 |  |  |  | 2018-01-31 | [6 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Sulfur Cooler Pump / Tag-No. 43-P-0242 A/B | 5914 | POC | USD |  | 124854.76 | 2016-12-22 | 2018-08-03 |  | 124854.76 | 2497 | 64289.27 |  | 64289 |  |  |  | 2018-03-31 | [6 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Sulfur Cooler Pump / Tag-No. 43-P-0342 A/B | 5915 | POC | USD |  | 124854.76 | 2016-12-22 | 2018-08-03 |  | 124854.76 | 2497 | 64289.27 |  | 64289 |  |  |  | 2018-03-31 | [6 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Fresh Water Sump Pump / Tag-No. 62-P-0202 A/B and Automatic Re-Circulation Valve | 5916 | POC | USD |  | 244208.44 | 2016-12-22 | 2018-08-03 |  | 244208.44 | 4884 | 216816.63 |  | 216817 |  |  |  | 2018-01-31 | [6 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Desalinated Water Sump Pump / Tag- No. 62-P-0702 A/B/C and Automatic Re-Circulation Valve | 5917 | POC | USD |  | 613765.17 | 2016-12-22 | 2018-08-03 |  | 613765.17 | 12275 | 589388.62 |  | 513232 | [10 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - AOC Dry Weather Pump / Tag-No. 76-P-0101 A/B | 5918 | POC | USD |  | 88437.34 | 2016-12-22 | 2018-08-03 |  | 88437.34 | 1769 | 89596.47 |  | 89596 |  |  |  | 2018-03-31 | [6 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Clean Water Pump / Tag-No. 76-P-0102 A/B | 5919 | POC | USD |  | 111037.16 | 2016-12-22 | 2018-08-03 |  | 111037.16 | 2221 | 108911.69 |  | 108912 |  |  |  | 2018-03-31 | [6 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Off-Spec Pump / Tag-No. 76-P-0103 A/B | 5920 | POC | USD |  | 87770.9 | 2016-12-22 | 2018-08-03 |  | 87770.9 | 1755 | 85859.75 |  | 85860 |  |  |  | 2018-03-31 | [6 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Flow Diverter Pump / Tag-No. 76-P-0201 A/B | 5921 | POC | USD |  | 76504.06 | 2016-12-22 | 2018-08-03 |  | 76504.06 | 1530 | 68699.02 |  | 68699 |  |  |  | 2018-03-31 | [6 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Utility Water Pump / Tag-No. 76-P-1904 A/B | 5922 | POC | USD |  | 82488.65 | 2016-12-22 | 2018-08-03 |  | 82488.65 | 1650 | 103841.58 |  | 103842 |  |  |  | 2018-03-31 | [6 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Cooling Water Pump / Tag-No. 78-P-0001 A/B/C/D/E/F/G/H | 5923 | POC | USD |  | 763882.32 | 2016-12-22 | 2018-08-03 |  | 763882.32 | 15278 | 662151.18 |  | 534507 | [10 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Cooling Water Pump / Tag-No. 78-P-0001S | 5924 | POC | USD |  | 95485.29 | 2016-12-22 | 2018-08-03 |  | 95485.29 | 1910 | 95213.12 |  | 86100 | [10 empty] | 0 |  | AM
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - Emergency Overflow Pumps / Tag-No. 76-P-0104 A/B | 5925 | POC | USD |  | 207873.2 | 2016-12-22 | 2018-08-03 |  | 207873.2 | 4157 | 150766.84 |  | 136161 | [10 empty] | 0 |  | OE
EPO | RU8025 | 5858 | FLUOR LIMITED | 234514543 | P - FLUOR LIMITED - 234514543 - SSF Backwash Pump / Tag-No. 63-P-0102 A/B | 5926 | POC | USD |  | 147823.2 | 2016-12-22 | 2018-08-03 |  | 147823.2 | 2956 | 113252.32 |  | 82496 | [10 empty] | 0 |  | OE
EPO | RU8025 | 5938 | SP OLEFINS (TAIXING) CO LTD | 234515487 | P - SP OLEFINS (TAIXING) CO LTD - 234515487 - SHP Ethylene Pumps (G217045) | 5999 | POC | EUR | 658130.0046 | 695275.32 | 2017-06-02 | 2018-06-30 |  | 638160 | 6382 | 553713.73 |  | 434509 | [10 empty] | 0 | CHINA | OE
EPO | RU8025 | 5938 | SP OLEFINS (TAIXING) CO LTD | 234515487 | P - SP OLEFINS (TAIXING) CO LTD - 234515487 - Startup & 2 Years Operation Spare Parts (IS217045) | 6000 | POC | EUR |  | 21757.32 | 2017-06-02 | 2018-06-30 |  | 19970.0046 | 200 | 19379.63 |  | 19122 | [10 empty] | 0 |  | AM
EPO | RU8025 | 6004 | CB&I NEDERLAND B.V. | 234515596 | P - CB&I NEDERLAND B.V. - 234515596 - Amine Drain Pump inkl motor shaft seal system mechanical seal & spare parts (G217052) | 6060 | POC | EUR | 1631106.0119 | 68596.01 | 2017-05-31 | 2018-08-23 |  | 62961.0005 |  | 62629.07 |  | 33494 | [10 empty] | 0 | EUROPE | OE
EPO | RU8025 | 6004 | CB&I NEDERLAND B.V. | 234515596 | P - CB&I NEDERLAND B.V. - 234515596 - Amine Drain Pump inkl motor & mechanical seal (G217053) | 6061 | POC | EUR |  | 55926.21 | 2017-05-31 | 2018-08-23 |  | 51331.9963 |  | 59698.87 |  | 25964 | [10 empty] | 0 |  | AM
EPO | RU8025 | 6004 | CB&I NEDERLAND B.V. | 234515596 | P - CB&I NEDERLAND B.V. - 234515596 - Sour Water Drain Pump inkl motor shaft seal system mechanical seal & spare parts (G217054) | 6062 | POC | EUR |  | 65315.53 | 2017-05-31 | 2018-08-23 |  | 59950.0046 |  | 59644.85 |  | 26479 | [10 empty] | 0 |  | OE
EPO | RU8025 | 6004 | CB&I NEDERLAND B.V. | 234515596 | P - CB&I NEDERLAND B.V. - 234515596 - Sour Water Drain Pump inkl mechanical seal (G217055) | 6063 | POC | EUR |  | 52644.64 | 2017-05-31 | 2018-08-23 |  | 48320 |  | 53234.65 |  | 25775 | [10 empty] | 0 |  | AM
EPO | RU8025 | 6004 | CB&I NEDERLAND B.V. | 234515596 | P - CB&I NEDERLAND B.V. - 234515596 - HC Drain Drum Pump inkl motor shaft seal system mechanical seal & spare parts (G217056) | 6064 | POC | EUR |  | 92544.31 | 2017-05-31 | 2018-08-23 |  | 84942.0009 |  | 84546.64 |  | 28467 | [10 empty] | 0 |  | OE
EPO | RU8025 | 6004 | CB&I NEDERLAND B.V. | 234515596 | P - CB&I NEDERLAND B.V. - 234515596 - HC Drain Drum Pump inkl motor & mechanical seal (G217057) | 6065 | POC | EUR |  | 79506.26 | 2017-05-31 | 2018-08-23 |  | 72974.9977 |  | 80256.62 |  | 26297 | [10 empty] | 0 |  | OE
EPO | RU8025 | 6004 | CB&I NEDERLAND B.V. | 234515596 | P - CB&I NEDERLAND B.V. - 234515596 - Emergency Drain Drum Pump inkl motor shaft seal system mechanical seal & spare parts (G217058) | 6066 | POC | EUR |  | 138084.32 | 2017-05-31 | 2018-08-23 |  | 126741.0005 |  | 116636.7 |  | 52949 | [10 empty] | 0 |  | OE
EPO | RU8025 | 6004 | CB&I NEDERLAND B.V. | 234515596 | P - CB&I NEDERLAND B.V. - 234515596 - HC Drain Drum Pump inkl motor shaft seal system mechanical seal & spare parts (G217059) | 6067 | POC | EUR |  | 54909.71 | 2017-05-31 | 2018-08-23 |  | 50398.9995 |  | 55579.63 |  | 17665 | [10 empty] | 0 |  | OE
EPO | RU8025 | 6004 | CB&I NEDERLAND B.V. | 234515596 | P - CB&I NEDERLAND B.V. - 234515596 - HC Drain Drum Pump inkl motor & mechanical seal (G217060) | 6068 | POC | EUR |  | 42238.83 | 2017-05-31 | 2018-08-23 |  | 38769.0041 |  | 51412.94 |  | 16774 | [10 empty] | 0 |  | AM
EPO | RU8025 | 6004 | CB&I NEDERLAND B.V. | 234515596 | P - CB&I NEDERLAND B.V. - 234515596 - Emergency Drain Drum Pump inkl motor shaft seal system mechanical seal & spare parts (G217061) | 6069 | POC | EUR |  | 69718.19 | 2017-05-31 | 2018-08-23 |  | 63990.9959 |  | 60793.67 |  | 18677 | [10 empty] | 0 |  | OE
EPO | RU8025 | 6004 | CB&I NEDERLAND B.V. | 234515596 | P - CB&I NEDERLAND B.V. - 234515596 - Amine Sump Pump inkl motor shaft seal system mechanical seal & spare parts (G217062) | 6070 | POC | EUR |  | 61178.69 | 2017-05-31 | 2018-08-23 |  | 56152.9968 |  | 58677.97 |  | 27138 | [10 empty] | 0 |  | OE
EPO | RU8025 | 6004 | CB&I NEDERLAND B.V. | 234515596 | P - CB&I NEDERLAND B.V. - 234515596 - Amine Sump Pump inkl mechanical seal (G217063) | 6071 | POC | EUR |  | 49005.71 | 2017-05-31 | 2018-08-23 |  | 44980 |  | 52160.81 |  | 24719 | [10 empty] | 0 |  | AM
EPO | RU8025 | 6004 | CB&I NEDERLAND B.V. | 234515596 | P - CB&I NEDERLAND B.V. - 234515596 - Sour Water Drain Pump inkl motor shaft seal system mechanical seal & spare parts (G217064) | 6072 | POC | EUR |  | 73824.52 | 2017-05-31 | 2018-08-23 |  | 67760 |  | 70987.51 |  | 26911 | [10 empty] | 0 |  | OE
EPO | RU8025 | 6004 | CB&I NEDERLAND B.V. | 234515596 | P - CB&I NEDERLAND B.V. - 234515596 - Sour Water Drain Pump inkl motor & mechanical seal (G217065) | 6073 | POC | EUR |  | 64473.34 | 2017-05-31 | 2018-08-23 |  | 59176.9986 |  | 55428.78 |  | 26702 | [10 empty] | 0 |  | AM
EPO | RU8025 | 6004 | CB&I NEDERLAND B.V. | 234515596 | P - CB&I NEDERLAND B.V. - 234515596 - Amine Drain Pump inkl motor shaft seal system mechanical seal & spare parts (G217066) | 6074 | POC | EUR |  | 59470.36 | 2017-05-31 | 2018-08-23 |  | 54585.0023 |  | 55587.16 |  | 21975 | [10 empty] | 0 |  | OE
EPO | RU8025 | 6004 | CB&I NEDERLAND B.V. | 234515596 | P - CB&I NEDERLAND B.V. - 234515596 - Amine Drain Pump inkl motor & mechanical seal (G217067) | 6075 | POC | EUR |  | 47313.72 | 2017-05-31 | 2018-08-23 |  | 43427.0032 |  | 40633.83 |  | 20734 | [10 empty] | 0 |  | AM
EPO | RU8025 | 6004 | CB&I NEDERLAND B.V. | 234515596 | P - CB&I NEDERLAND B.V. - 234515596 - Hydrocarbon Drain Pump inkl motor shaft seal system mechanical seal & spare parts (G217068) | 6076 | POC | EUR |  | 88238.61 | 2017-05-31 | 2018-08-23 |  | 80990.0046 |  | 81459.7 |  | 28023 | [10 empty] | 0 |  | OE
EPO | RU8025 | 6004 | CB&I NEDERLAND B.V. | 234515596 | P - CB&I NEDERLAND B.V. - 234515596 - Hydrocarbon Drain Pump inkl mechanical seal (G217069) | 6077 | POC | EUR |  | 75199.47 | 2017-05-31 | 2018-08-23 |  | 69022.0009 |  | 62517.79 |  | 26952 | [10 empty] | 0 |  | AM
EPO | RU8025 | 6004 | CB&I NEDERLAND B.V. | 234515596 | P - CB&I NEDERLAND B.V. - 234515596 - Amine Drain Pump inkl motor shaft seal system mechanical seal & spare parts (G217070) | 6078 | POC | EUR |  | 76079.79 | 2017-05-31 | 2018-08-23 |  | 69830.0046 |  | 65337.88 |  | 30305 | [10 empty] | 0 |  | OE
EPO | RU8025 | 6004 | CB&I NEDERLAND B.V. | 234515596 | P - CB&I NEDERLAND B.V. - 234515596 - Amine Drain Pump inkl mechanical seal (G217071) | 6079 | POC | EUR |  | 63409.99 | 2017-05-31 | 2018-08-23 |  | 58201.0005 |  | 47255.15 |  | 28190 | [10 empty] | 0 |  | AM
EPO | RU8025 | 6004 | CB&I NEDERLAND B.V. | 234515596 | P - CB&I NEDERLAND B.V. - 234515596 - Hydrocarbon Drain Pump inkl motor shaft seal system mechanical seal & spare parts (G217072) | 6080 | POC | EUR |  | 92709.91 | 2017-05-31 | 2018-08-23 |  | 85093.9972 |  | 86244.31 |  | 32417 | [10 empty] | 0 |  | OE
EPO | RU8025 | 6004 | CB&I NEDERLAND B.V. | 234515596 | P - CB&I NEDERLAND B.V. - 234515596 - Hydrocarbon Drain Pump inkl mechanical seal (G217073) | 6081 | POC | EUR |  | 80018.33 | 2017-05-31 | 2018-08-23 |  | 73445.0023 |  | 66378.2 |  | 31311 | [10 empty] | 0 |  | AM
EPO | RU8025 | 6004 | CB&I NEDERLAND B.V. | 234515596 | P - CB&I NEDERLAND B.V. - 234515596 - Sour Water Drain Pump inkl motor shaft seal system mechanical seal & spare parts (G217074) | 6082 | POC | EUR |  | 79907.2 | 2017-05-31 | 2018-08-23 |  | 73343.0014 |  | 74203.41 |  | 26341 | [10 empty] | 0 |  | OE
EPO | RU8025 | 6004 | CB&I NEDERLAND B.V. | 234515596 | P - CB&I NEDERLAND B.V. - 234515596 - Hydrocarbon Drain Pump inkl motor shaft seal system mechanical seal & spare parts (G217075) | 6083 | POC | EUR |  | 79907.2 | 2017-05-31 | 2018-08-23 |  | 73343.0014 |  | 74290.72 |  | 26199 | [10 empty] | 0 |  | OE
EPO | RU8025 | 6004 | CB&I NEDERLAND B.V. | 234515596 | P - CB&I NEDERLAND B.V. - 234515596 - Hydrocarbon Drain Pump inkl motor & mechanical seal (G217076) | 6084 | POC | EUR |  | 66869.15 | 2017-05-31 | 2018-08-23 |  | 61375.9982 |  | 58573.48 |  | 25423 | [10 empty] | 0 |  | AM
EPO | RU8025 | 6120 | CHEMOPROJEKT A.S. | 234515722 | P - CHEMOPROJEKT AS - 234515722 - Condensate pumps Tag No 4-P03 A/B | 6127 | POC | EUR | 1780290.9972 | 72969.83 | 2017-08-02 | 2018-04-23 |  | 64914.0023 |  | 68230.64 |  | 57186 | [10 empty] | 0 | EUROPE | OE
EPO | RU8025 | 6120 | CHEMOPROJEKT A.S. | 234515722 | P - CHEMOPROJEKT AS - 234515722 - Total Naphta Pump Tag No 4-P07 A/B | 6128 | POC | EUR |  | 71729.95 | 2017-08-02 | 2018-04-23 |  | 63811.0044 |  | 66701.25 |  | 48478 | [10 empty] | 0 |  | OE
EPO | RU8025 | 6120 | CHEMOPROJEKT A.S. | 234515722 | P - CHEMOPROJEKT AS - 234515722 - Stabilizer Reflux Pump Tag No 4-P10 A | 6129 | POC | EUR |  | 56099.33 | 2017-08-02 | 2018-04-23 |  | 49905.9959 |  | 77999.87 |  | 39580 | [10 empty] | 0 |  | OE
EPO | RU8025 | 6120 | CHEMOPROJEKT A.S. | 234515722 | P - CHEMOPROJEKT AS - 234515722 - Stabilizer Reflux Pump Tag No 4-P10 BT | 6130 | POC | EUR |  | 206245.37 | 2017-08-02 | 2018-04-23 |  | 183475.9986 |  | 175179.32 |  | 191936 | [10 empty] | 0 |  | OE
EPO | RU8025 | 6120 | CHEMOPROJEKT A.S. | 234515722 | P - CHEMOPROJEKT AS - 234515722 - RO Water Pump Tag No 4-P13 A/B | 6131 | POC | EUR |  | 59646.99 | 2017-08-02 | 2018-04-23 |  | 53061.9963 |  | 56997.59 |  | 45666 | [10 empty] | 0 |  | OE
EPO | RU8025 | 6120 | CHEMOPROJEKT A.S. | 234515722 | P - CHEMOPROJEKT AS - 234515722 - Blow Down Pump Tag No 4-P19 A/B | 6132 | POC | EUR |  | 52421.28 | 2017-08-02 | 2018-04-23 |  | 46634.0005 |  | 71687.1 |  | 35699 | [10 empty] | 0 |  | OE
EPO | RU8025 | 6120 | CHEMOPROJEKT A.S. | 234515722 | P - CHEMOPROJEKT AS - 234515722 - Caustic Soda Circulation Pump Tag No 4-P20 A/B | 6133 | POC | EUR |  | 35556.41 | 2017-08-02 | 2018-04-23 |  | 31631.0026 |  | 38490.82 |  | 24938 | [10 empty] | 0 |  | OE
EPO | RU8025 | 6120 | CHEMOPROJEKT A.S. | 234515722 | P - CHEMOPROJEKT AS - 234515722 - Lean DEA Pump Tag No 4-P29 A/B | 6134 | POC | EUR |  | 96333.12 | 2017-08-02 | 2018-04-23 |  | 85697.9984 |  | 72671.84 |  | 60240 | [10 empty] | 0 |  | OE
EPO | RU8025 | 6120 | CHEMOPROJEKT A.S. | 234515722 | P - CHEMOPROJEKT AS - 234515722 - Desulfurized LPG pump Tag No 4-P33 A/B | 6135 | POC | EUR |  | 203700.41 | 2017-08-02 | 2018-04-23 |  | 181212.0007 |  | 188961.8 |  | 151599 | [10 empty] | 0 |  | OE
EPO | RU8025 | 6120 | CHEMOPROJEKT A.S. | 234515722 | P - CHEMOPROJEKT AS - 234515722 - Lift Pump Tag No 2-P01 AT | 6136 | POC | EUR |  | 242708.93 | 2017-08-02 | 2018-04-23 |  | 215914.0023 |  | 215616.37 |  | 96493 | [10 empty] | 0 |  | OE
EPO | RU8025 | 6120 | CHEMOPROJEKT A.S. | 234515722 | P - CHEMOPROJEKT AS - 234515722 - Lift Pump Tag No 2-P01 B/C | 6137 | POC | EUR |  | 67159.35 | 2017-08-02 | 2018-04-23 |  | 59744.996 |  | 72045.38 |  | 44095 | [10 empty] | 0 |  | OE
EPO | RU8025 | 6120 | CHEMOPROJEKT A.S. | 234515722 | P - CHEMOPROJEKT AS - 234515722 - FW pump Tag No 2-P02 AT | 6138 | POC | EUR |  | 389047.64 | 2017-08-02 | 2018-04-23 |  | 346097.002 |  | 326898.55 |  | 143595 | [10 empty] | 0 |  | OE
EPO | RU8025 | 6120 | CHEMOPROJEKT A.S. | 234515722 | P - CHEMOPROJEKT AS - 234515722 - FW pump Tag No 2P-02 B/C | 6139 | POC | EUR |  | 447606.5 | 2017-08-02 | 2018-04-23 |  | 398190.9972 |  | 381112.37 |  | 225634 | [10 empty] | 0 |  | OE
EPO | RU8025 | 6148 | International Development Company | 234515641 | P - INTERNATIONAL DEVELOPMENT COMPANY - 234515641 - Crude Oil Pumps / Tag No 442-P-0007 A/B | 6226 | POC | EUR | 695829.9973 | 782182.5 | 2017-06-30 | 2018-05-15 |  | 695829.9973 | 34792 | 646497.35 |  | 331857 | [10 empty] | 0 | MIDEAST | OE
EPO | RU8025 | 6200 | ZHEJIANG PETROLEUM & CHEMICAL CO LTD | 234515723 | P - ZHEJIANG PETROLEUM & CHEMICAL CO LTD - 234515723 - DEMETHANIZER REFLUX PUMP Tag No 1201-P-1425 A/S | 6214 | POC | EUR | 1160000 | 280614.7 | 2017-08-03 | 2018-04-30 |  | 249635 | 6240.87 | 348811.43 |  | 182533 | [10 empty] | 0 | CHINA | OE
EPO | RU8025 | 6200 | ZHEJIANG PETROLEUM & CHEMICAL CO LTD | 234515723 | P - ZHEJIANG PETROLEUM & CHEMICAL CO LTD - 234515723 - DEMETHANIZER REFLUX PUMP Tag No 1201-P-1435 A/S | 6215 | POC | EUR |  | 255157.21 | 2017-08-03 | 2018-04-30 |  | 226988 | 5674.7 | 279684.51 |  | 164222 | [10 empty] | 0 |  | OE
EPO | RU8025 | 6200 | ZHEJIANG PETROLEUM & CHEMICAL CO LTD | 234515723 | P - ZHEJIANG PETROLEUM & CHEMICAL CO LTD - 234515723 - ETHANE RECYCLE PUMP Tag No 1201-P-1445 A/S | 6216 | POC | EUR |  | 239736.81 | 2017-08-03 | 2018-04-30 |  | 213270 | 5331.75 | 252322.51 |  | 149713 | [10 empty] | 0 |  | OE
EPO | RU8025 | 6200 | ZHEJIANG PETROLEUM & CHEMICAL CO LTD | 234515723 | P - ZHEJIANG PETROLEUM & CHEMICAL CO LTD - 234515723 - ETHYLENE PRODUCT PUMP Tag No 1201-P-1690 A/S | 6217 | POC | EUR |  | 282729.14 | 2017-08-03 | 2018-04-30 |  | 251516 | 6287.9 | 296867.46 |  | 202721 | [10 empty] | 0 |  | OE
EPO | RU8025 | 6200 | ZHEJIANG PETROLEUM & CHEMICAL CO LTD | 234515723 | P - ZHEJIANG PETROLEUM & CHEMICAL CO LTD - 234515723 - Spare Parts Commissioning & 3 Years Operation | 6218 | POC | EUR |  | 79097.3 | 2017-08-03 | 2018-04-30 |  | 70365 | 1759.13 | 33859.55 |  | 34854 | [10 empty] | 0 |  | AM
EPO | RU8025 | 6200 | ZHEJIANG PETROLEUM & CHEMICAL CO LTD | 234515723 | P - ZHEJIANG PETROLEUM & CHEMICAL CO LTD - 234515723 - Spare Parts Commissioning & 3 Years Operation | 6219 | POC | EUR |  | 59590.79 | 2017-08-03 | 2018-04-30 |  | 53012 | 1325.3 | 30198.51 |  | 22115 | [10 empty] | 0 |  | AM
EPO | RU8025 | 6200 | ZHEJIANG PETROLEUM & CHEMICAL CO LTD | 234515723 | P - ZHEJIANG PETROLEUM & CHEMICAL CO LTD - 234515723 - Spare Parts Commissioning & 3 Years Operation | 6220 | POC | EUR |  | 63770.19 | 2017-08-03 | 2018-04-30 |  | 56730 | 1418.25 | 18109.81 |  | 17543 | [10 empty] | 0 |  | AM
EPO | RU8025 | 6200 | ZHEJIANG PETROLEUM & CHEMICAL CO LTD | 234515723 | P - ZHEJIANG PETROLEUM & CHEMICAL CO LTD - 234515723 - Spare Parts Commissioning & 3 Years Operation | 6221 | POC | EUR |  | 43259.86 | 2017-08-03 | 2018-04-30 |  | 38484 | 962.1 | 18738.59 |  | 16395 | [10 empty] | 0 |  | AM
EPO | RU8025 | 6228 | PROFIT MAKING INTERNATIONAL LIMITED | 234515676 | P - PROFIT MAKING INTERNATIONAL LIMITED - 234515676 - Condensate pumps (G217086) | 6255 | POC | EUR | 803320 | 779527.38 | 2017-07-25 | 2018-05-31 |  | 693468 | 13869 | 687774.46 |  | 489356 | [10 empty] | 0 | CHINA | OE
EPO | RU8025 | 6228 | PROFIT MAKING INTERNATIONAL LIMITED | 234515676 | P - PROFIT MAKING INTERNATIONAL LIMITED - 234515676 - Spare Parts for Commissioning & 2 Years Operation (IS217086) | 6256 | POC | EUR |  | 123484.63 | 2017-07-25 | 2018-05-31 |  | 109852 | 2197 | 68136.1 |  | 35447 | [10 empty] | 0 |  | AM
EPO | RU8025 | 7382 | Sinopec Europa GmbH | 234515823 | P - SINOPEC EUROPA GMBH - 234515823 | 7395 | POC | USD | 408000 | 408000 | 2017-08-04 | 2018-04-16 |  | 408000 | 14280 | 335507.87 |  | 282096 | [7 empty] | 0 |  |  | 0 | CHINA | OE
EPO | RU8025 | 7706 | ENPPI (ENGINEERING FOR THE PETROLEUM AND PROCESS INDUSTRIES) | 234516031 | P - ENPPI - 234516031 - Potable Water Pumps & Spare Parts | 7727 | POC | EUR | 300650 | 355969.6 | 2017-08-31 | 2018-05-31 |  | 300650 | 15032.5 | 230307.24 |  | 203202 | [10 empty] | 4509.75 | NAFRICA | OE
EPO | RU8025 | 7842 | DANGOTE OIL REFINING COMPANY LIMITED | 234515934 | P - DANGOTE - 234515934 - HSD Booster Pumps (G217120) | 11463 | POC | USD | 952278 | 609096 | 2017-07-31 | 2018-10-17 |  | 609096 |  | 579979.22 |  | 35305 | [7 empty] | 0 |  |  | 8000.99 | OTHERAFRICA | OE
EPO | RU8025 | 7842 | DANGOTE OIL REFINING COMPANY LIMITED | 234515934 | P - DANGOTE - 234515934 - Slurry Sump Vessel Pumps (G217121/G217122) | 11464 | POC | USD |  | 82602 | 2017-07-31 | 2018-10-17 |  | 82602 |  | 110619.6 |  | 24425 | [10 empty] | 0 |  | OE
EPO | RU8025 | 7842 | DANGOTE OIL REFINING COMPANY LIMITED | 234515934 | P - DANGOTE - 234515934 - Slop Transfer Pump (G217123) | 11465 | POC | USD |  | 71305 | 2017-07-31 | 2018-10-17 |  | 71305 |  | 60960.28 |  | 24502 | [10 empty] | 0 |  | OE
EPO | RU8025 | 7842 | DANGOTE OIL REFINING COMPANY LIMITED | 234515934 | P - DANGOTE - 234515934 - Propylene Reprocess Pump (G217124) | 11466 | POC | USD |  | 37764 | 2017-07-31 | 2018-10-17 |  | 37764 |  | 95848.1 |  | 43278 | [10 empty] | 0 |  | OE
EPO | RU8025 | 7842 | DANGOTE OIL REFINING COMPANY LIMITED | 234515934 | P - DANGOTE - 234515934 - Mandatory and 2 Years Operation Spare Parts (IS217120-IS217124) | 11467 | POC | USD |  | 151511 | 2017-07-31 | 2018-10-17 |  | 151511 |  | 15791.64 |  | 29 | [10 empty] | 0 |  | AM
EPO | RU8025 | 7850 | DANGOTE OIL REFINING COMPANY LIMITED | 234515935 | P - DANGOTE - 234515935 - Crude Sump Pump (G217125) | 11964 | POC | USD | 3208588 | 31179 | 2017-07-31 | 2018-10-17 |  | 31179 |  | 49210.97 |  | 13909 | [7 empty] | 0 |  |  | 26958.3935 | OTHERAFRICA | OE
EPO | RU8025 | 7850 | DANGOTE OIL REFINING COMPANY LIMITED | 234515935 | P - DANGOTE - 234515935 - SAT C4 Feed Pumps (G217126) | 11965 | POC | USD |  | 180820 | 2017-07-31 | 2018-10-17 |  | 180820 |  | 144892.59 |  | 25208 | [10 empty] | 0 |  | OE
EPO | RU8025 | 7850 | DANGOTE OIL REFINING COMPANY LIMITED | 234515935 | P - DANGOTE - 234515935 - Intermediate Sump Vessel Pumps B2/B3 (G217127/G217128) | 11966 | POC | USD |  | 120459 | 2017-07-31 | 2018-10-17 |  | 120459 |  | 106724.22 |  | 35109 | [10 empty] | 0 |  | OE
EPO | RU8025 | 7850 | DANGOTE OIL REFINING COMPANY LIMITED | 234515935 | P - DANGOTE - 234515935 - Blending Sump Vessel Pump B5/B6 (G217129/G217130) | 11968 | POC | USD |  | 99830 | 2017-07-31 | 2018-10-17 |  | 99830 |  | 96583.95 |  | 20029 | [10 empty] | 0 |  | OE
EPO | RU8025 | 7850 | DANGOTE OIL REFINING COMPANY LIMITED | 234515935 | P - DANGOTE - 234515935 - Ethanol UG Vessel Pump (G217131) | 11970 | POC | USD |  | 51069 | 2017-07-31 | 2018-10-17 |  | 51069 |  | 55943.87 |  | 9535 | [10 empty] | 0 |  | OE
EPO | RU8025 | 7850 | DANGOTE OIL REFINING COMPANY LIMITED | 234515935 | P - DANGOTE - 234515935 - Ethanol UG Vessel (unloading) Pump (G217132) | 11971 | POC | USD |  | 54539 | 2017-07-31 | 2018-10-17 |  | 54539 |  | 52168.9 |  | 10203 | [10 empty] | 0 |  | OE
EPO | RU8025 | 7850 | DANGOTE OIL REFINING COMPANY LIMITED | 234515935 | P - DANGOTE - 234515935 - LP flare KOD Pumps A4 (G217133) | 11972 | POC | USD |  | 231642 | 2017-07-31 | 2018-10-17 |  | 231642 |  | 117904.81 |  | 36370 | [10 empty] | 0 |  | OE
EPO | RU8025 | 7850 | DANGOTE OIL REFINING COMPANY LIMITED | 234515935 | P - DANGOTE - 234515935 - LP flare KOD Pumps B5 (G217134) | 11973 | POC | USD |  | 238900 | 2017-07-31 | 2018-10-17 |  | 238900 |  | 122134.64 |  | 39137 | [10 empty] | 0 |  | OE
EPO | RU8025 | 7850 | DANGOTE OIL REFINING COMPANY LIMITED | 234515935 | P - DANGOTE - 234515935 - HP flare KOD Pumps B6 (G217135) | 11974 | POC | USD |  | 246302 | 2017-07-31 | 2018-10-17 |  | 246302 |  | 145086.89 |  | 39382 | [10 empty] | 0 |  | OE
EPO | RU8025 | 7850 | DANGOTE OIL REFINING COMPANY LIMITED | 234515935 | P - DANGOTE - 234515935 - LP flare KOD Pumps B7 (G217136) | 11975 | POC | USD |  | 171820 | 2017-07-31 | 2018-10-17 |  | 171820 |  | 138210.31 |  | 38278 | [10 empty] | 0 |  | OE
EPO | RU8025 | 7850 | DANGOTE OIL REFINING COMPANY LIMITED | 234515935 | P - DANGOTE - 234515935 - HP flare KOD Pumps C2 (G217137) | 11976 | POC | USD |  | 347508 | 2017-07-31 | 2018-10-17 |  | 347508 |  | 227902.37 |  | 33289 | [10 empty] | 0 |  | OE
EPO | RU8025 | 7850 | DANGOTE OIL REFINING COMPANY LIMITED | 234515935 | P - DANGOTE - 234515935 - CBD Pumps C3 (G217138/G217139) | 11977 | POC | USD |  | 159478 | 2017-07-31 | 2018-10-17 |  | 159478 |  | 123159.42 |  | 43742 | [10 empty] | 0 |  | OE
EPO | RU8025 | 7850 | DANGOTE OIL REFINING COMPANY LIMITED | 234515935 | P - DANGOTE - 234515935 - CBD Pumps C9 (G217140/G217141) | 11978 | POC | USD |  | 159938 | 2017-07-31 | 2018-10-17 |  | 159938 |  | 122819.17 |  | 42600 | [10 empty] | 0 |  | OE
EPO | RU8025 | 7850 | DANGOTE OIL REFINING COMPANY LIMITED | 234515935 | P - DANGOTE - 234515935 - Neutralization Basin Pumps (G217142) | 11979 | POC | USD |  | 325600 | 2017-07-31 | 2018-10-17 |  | 325600 |  | 261839.2 |  | 54689 | [10 empty] | 0 |  | OE
EPO | RU8025 | 7850 | DANGOTE OIL REFINING COMPANY LIMITED | 234515935 | P - DANGOTE - 234515935 - Neutralisatzion Basin Slop Oil Pump (G217143) | 11980 | POC | USD |  | 162732 | 2017-07-31 | 2018-10-17 |  | 162732 |  | 130505.48 |  | 41978 | [10 empty] | 0 |  | OE
EPO | RU8025 | 7850 | DANGOTE OIL REFINING COMPANY LIMITED | 234515935 | P - DANGOTE - 234515935 - Slop Vessel Pumps (G217144) | 11981 | POC | USD |  | 151698 | 2017-07-31 | 2018-10-17 |  | 151698 |  | 112698.11 |  | 24186 | [10 empty] | 0 |  | OE
EPO | RU8025 | 7850 | DANGOTE OIL REFINING COMPANY LIMITED | 234515935 | P - DANGOTE - 234515935 - SAR neutralization basin Pumps (G217145) | 11982 | POC | USD |  | 295013 | 2017-07-31 | 2018-10-17 |  | 295013 |  | 217517.09 |  | 42142 | [10 empty] | 0 |  | OE
EPO | RU8025 | 7850 | DANGOTE OIL REFINING COMPANY LIMITED | 234515935 | P - DANGOTE - 234515935 - Mandatory and 2 Years Operation Spare Parts (IS217125-IS217145) | 11984 | POC | USD |  | 180061 | 2017-07-31 | 2018-10-17 |  | 180061 |  | 64219.2 |  | 11903 | [10 empty] | 0 |  | AM
EPO | RU8025 | 8073 | NIS j.s.c. Novi Sad | 234516055 | P - NIS j.s.c. Novi Sad - 234516055 - LCGO Flushing Oil HP Pumps (G217150) | 9418 | POC | EUR | 290000 | 343360 | 2017-08-31 | 2018-05-31 |  | 290000 | 29000 | 238206.71 |  | 120903 | [6 empty] | 28987 |  | 2018-05-08 | 8025039060 | 0 | EUROPE | OE
EPO | RU8025 | 8681 | PIELDS ENGINEERING CO. LTD. | 234516056 | P - PIELDS ENGINEERING CO. LTD. - 234516056 - Strat Up Naphtha Recovery Pump (Tag No P-192) G217151 / IS217151 | 9958 | POC | EUR | 410301.9924 | 37867.45 | 2017-11-17 | 2018-06-30 |  | 32520.9979 | 20515 | 34866.06 |  | 34816 | [10 empty] | 0 | ASIA | OE
EPO | RU8025 | 8681 | PIELDS ENGINEERING CO. LTD. | 234516056 | P - PIELDS ENGINEERING CO. LTD. - 234516056 - BFW Pump (Tag No P-601A/B) G217152 / IS217152 | 9959 | POC | EUR |  | 295846.09 | 2017-11-17 | 2018-06-30 |  | 254075.9962 |  | 210521.71 |  | 186959 | [10 empty] | 0 |  | OE
EPO | RU8025 | 8681 | PIELDS ENGINEERING CO. LTD. | 234516056 | P - PIELDS ENGINEERING CO. LTD. - 234516056 - Process Condensate pump (Tag No P-651A/B) G217153 / IS217153 | 9960 | POC | EUR |  | 144042.1 | 2017-11-17 | 2018-06-30 |  | 123704.9983 |  | 118637.32 |  | 96061 | [10 empty] | 0 |  | OE
EPO | RU8025 | 8844 | JGC GULF INTERNATIONAL LTD. | 234516094 | P - JGC GULF INTERNATIONAL LTD. - 234516094 - Drain Sump Pumps - Refinery | 9841 | POC | EUR | 236110 | 112060.86 | 2017-08-29 | 2018-06-30 |  | 94645.9966 |  | 112232.18 |  | 60253 | [10 empty] | 0 | MIDEAST | OE
EPO | RU8025 | 8844 | JGC GULF INTERNATIONAL LTD. | 234516094 | P - JGC GULF INTERNATIONAL LTD. - 234516094 - Drain Sump Pumps - SITRA | 9842 | POC | EUR |  | 167493.38 | 2017-08-29 | 2018-06-30 |  | 141464.0034 |  | 119218.27 |  | 69374 | [10 empty] | 0 |  | OE
EPO | RU8025 | 10279 | FABRICOM NV | 234516162 | P - FABRICOM NV - 234516162 - Geothermal Brine Reinjection Pump (Tag No AP001/2) | 10452 | POC | EUR | 475000 | 479177.92 | 2017-09-29 | 2018-06-30 |  | 402400 | 20120 | 397492.58 |  | 339268 | [10 empty] | 0 | EUROPE | OE
EPO | RU8025 | 10279 | FABRICOM NV | 234516162 | P - FABRICOM NV - 234516162 - Geothermal Brine Reinjection Pump (Tag No AP003) | 10453 | POC | EUR |  | 86452.08 | 2017-09-29 | 2018-06-30 |  | 72600 | 3630 | 62454.95 |  | 55389 | [10 empty] | 0 |  | OE
EPO | RU8025 | 12436 | SINGLE BUOY MOORINGS INC | 234516301 | P - SINGLE BUOY MOORINGS INC - 234516301 - Methanol Pumps (G217168) | 13381 | POC | EUR | 525000 | 374312.9 | 2017-10-31 | 2018-06-04 |  | 301100 | 22582.5 | 261900.34 |  | 142635 | [6 empty] | 80017 |  | 2018-05-28 | 8025039179 | 0 | EUROPE | OE
EPO | RU8025 | 12436 | SINGLE BUOY MOORINGS INC | 234516301 | P - SINGLE BUOY MOORINGS INC - 234516301 - Xylene Pumps (G217169) | 13382 | POC | EUR |  | 276110.49 | 2017-10-31 | 2018-06-04 |  | 223900 | 16792.5 | 192508.27 |  | 86031 | [10 empty] | 0 |  | OE
EPO | RU8025 | 13120 | CHINA PETROLEUM PIPELINE MATERIAL AND EQUIPMENT COMPANY LIMITED | 234515094 | P - CHINA PETROLEUM PIPELINE MATERIAL AND EQUIPMENT COMPANY LIMITED - 234515094 - Slop Transfer Pumps (G217020) | 13187 | POC | EUR | 1343776 | 81987.98 | 2017-04-28 | 2018-07-31 |  | 77530.0047 |  | 67320.71 |  | 23047 | [10 empty] | 0 | CHINA | OE
EPO | RU8025 | 13120 | CHINA PETROLEUM PIPELINE MATERIAL AND EQUIPMENT COMPANY LIMITED | 234515094 | P - CHINA PETROLEUM PIPELINE MATERIAL AND EQUIPMENT COMPANY LIMITED - 234515094 - Slop Transfer Pumps (G217021) | 13188 | POC | EUR |  | 77506.29 | 2017-04-28 | 2018-07-31 |  | 73292 |  | 64630.7 |  | 20120 | [10 empty] | 0 |  | OE
EPO | RU8025 | 13120 | CHINA PETROLEUM PIPELINE MATERIAL AND EQUIPMENT COMPANY LIMITED | 234515094 | P - CHINA PETROLEUM PIPELINE MATERIAL AND EQUIPMENT COMPANY LIMITED - 234515094 - Slop Transfer Pumps (G217022) | 13189 | POC | EUR |  | 91716.97 | 2017-04-28 | 2018-07-31 |  | 86729.9953 |  | 78411.72 |  | 27540 | [10 empty] | 0 |  | OE
EPO | RU8025 | 13120 | CHINA PETROLEUM PIPELINE MATERIAL AND EQUIPMENT COMPANY LIMITED | 234515094 | P - CHINA PETROLEUM PIPELINE MATERIAL AND EQUIPMENT COMPANY LIMITED - 234515094 - Slop Transfer Pumps (G217023) | 13190 | POC | EUR |  | 106949.21 | 2017-04-28 | 2018-07-31 |  | 101134.0047 |  | 89596.12 |  | 35210 | [10 empty] | 0 |  | OE
EPO | RU8025 | 13120 | CHINA PETROLEUM PIPELINE MATERIAL AND EQUIPMENT COMPANY LIMITED | 234515094 | P - CHINA PETROLEUM PIPELINE MATERIAL AND EQUIPMENT COMPANY LIMITED - 234515094 - Slop Transfer Pumps (G217024) | 13191 | POC | EUR |  | 143437.18 | 2017-04-28 | 2018-07-31 |  | 135637.9953 |  | 136810.43 |  | 75630 | [10 empty] | 0 |  | OE
EPO | RU8025 | 13120 | CHINA PETROLEUM PIPELINE MATERIAL AND EQUIPMENT COMPANY LIMITED | 234515094 | P - CHINA PETROLEUM PIPELINE MATERIAL AND EQUIPMENT COMPANY LIMITED - 234515094 - Slop Transfer Pumps (G217025) | 13192 | POC | EUR |  | 95756.63 | 2017-04-28 | 2018-07-31 |  | 90550.0047 |  | 86089.19 |  | 30125 | [10 empty] | 0 |  | OE
EPO | RU8025 | 13120 | CHINA PETROLEUM PIPELINE MATERIAL AND EQUIPMENT COMPANY LIMITED | 234515094 | P - CHINA PETROLEUM PIPELINE MATERIAL AND EQUIPMENT COMPANY LIMITED - 234515094 - Slop Transfer Pumps (G217026) | 13193 | POC | EUR |  | 101613.06 | 2017-04-28 | 2018-07-31 |  | 96088 |  | 86957.17 |  | 27360 | [10 empty] | 0 |  | OE
EPO | RU8025 | 13120 | CHINA PETROLEUM PIPELINE MATERIAL AND EQUIPMENT COMPANY LIMITED | 234515094 | P - CHINA PETROLEUM PIPELINE MATERIAL AND EQUIPMENT COMPANY LIMITED - 234515094 - Oily Water Transfer Pumps (G217027) | 13194 | POC | EUR |  | 70734.06 | 2017-04-28 | 2018-07-31 |  | 66888 |  | 62805.24 |  | 18985 | [10 empty] | 0 |  | OE
EPO | RU8025 | 13120 | CHINA PETROLEUM PIPELINE MATERIAL AND EQUIPMENT COMPANY LIMITED | 234515094 | P - CHINA PETROLEUM PIPELINE MATERIAL AND EQUIPMENT COMPANY LIMITED - 234515094 - Oily Water Transfer Pumps (G217028) | 13195 | POC | EUR |  | 68356.8 | 2017-04-28 | 2018-07-31 |  | 64640 |  | 59242.46 |  | 19490 | [10 empty] | 0 |  | OE
EPO | RU8025 | 13120 | CHINA PETROLEUM PIPELINE MATERIAL AND EQUIPMENT COMPANY LIMITED | 234515094 | P - CHINA PETROLEUM PIPELINE MATERIAL AND EQUIPMENT COMPANY LIMITED - 234515094 - Oily Water Transfer Pumps (G217029) | 13196 | POC | EUR |  | 107230.5 | 2017-04-28 | 2018-07-31 |  | 101400 |  | 94463.94 |  | 31865 | [10 empty] | 0 |  | OE
EPO | RU8025 | 13120 | CHINA PETROLEUM PIPELINE MATERIAL AND EQUIPMENT COMPANY LIMITED | 234515094 | P - CHINA PETROLEUM PIPELINE MATERIAL AND EQUIPMENT COMPANY LIMITED - 234515094 - Oily Water Transfer Pumps (G217030) | 13197 | POC | EUR |  | 104874.39 | 2017-04-28 | 2018-07-31 |  | 99172 |  | 95296.15 |  | 31560 | [10 empty] | 0 |  | OE
EPO | RU8025 | 13120 | CHINA PETROLEUM PIPELINE MATERIAL AND EQUIPMENT COMPANY LIMITED | 234515094 | P - CHINA PETROLEUM PIPELINE MATERIAL AND EQUIPMENT COMPANY LIMITED - 234515094 - Oily Water Transfer Pumps (G217031) | 13198 | POC | EUR |  | 104544.45 | 2017-04-28 | 2018-07-31 |  | 98860 |  | 95419.64 |  | 33115 | [10 empty] | 0 |  | OE
EPO | RU8025 | 13120 | CHINA PETROLEUM PIPELINE MATERIAL AND EQUIPMENT COMPANY LIMITED | 234515094 | P - CHINA PETROLEUM PIPELINE MATERIAL AND EQUIPMENT COMPANY LIMITED - 234515094 - Oily Water Transfer Pumps (G217032) | 13199 | POC | EUR |  | 107657.73 | 2017-04-28 | 2018-07-31 |  | 101804 |  | 96809.99 |  | 33784 | [10 empty] | 0 |  | OE
EPO | RU8025 | 13120 | CHINA PETROLEUM PIPELINE MATERIAL AND EQUIPMENT COMPANY LIMITED | 234515094 | P - CHINA PETROLEUM PIPELINE MATERIAL AND EQUIPMENT COMPANY LIMITED - 234515094 - Diesel Oil Filling Pump Unload (G217033) | 13200 | POC | EUR |  | 45882.81 | 2017-04-28 | 2018-07-31 |  | 43388 |  | 40103.62 |  | 17793 | [10 empty] | 0 |  | OE
EPO | RU8025 | 13120 | CHINA PETROLEUM PIPELINE MATERIAL AND EQUIPMENT COMPANY LIMITED | 234515094 | P - CHINA PETROLEUM PIPELINE MATERIAL AND EQUIPMENT COMPANY LIMITED - 234515094 - Commissioning & 2 Years Spare Parts (IS217020-33) | 13201 | POC | EUR |  | 112795.06 | 2017-04-28 | 2018-07-31 |  | 106661.9953 |  | 60202.44 |  | 49113 | [10 empty] | 0 |  | AM
EPO | RU8025 | 13514 | SABIC Petrochemicals B.V. | 234514666 | P - SABIC Petrochemicals BV - 234514666 - C3/C4 Pumps (G216213) | 13624 | POC | EUR | 352271 | 422584.29 | 2016-12-16 | 2018-02-16 |  | 352271 |  | 286812.61 |  | 286813 |  |  |  | 2018-02-28 |  |  | 17614 |  | 2018-05-28 | 8025039178 | 0 | EUROPE | OE
EPO | RU8025 | 13798 | HONG KONG JIAXIN INDUSTRIAL EQUIPMENT CO LTD | 234508572 | P - HONG KONG JIAXIN INDUSTRIAL EQUIPMENT CO LTD - 234508572 - C2 Splitter Reflux Pumps (G213301) | 13840 | POC | EUR | 347150 | 189339.28 | 2014-01-07 | 2018-05-31 |  | 139302.0012 |  | 110438.51 |  | 117798 |  |  |  | 2018-05-28 |  |  | 277720 |  | 2018-05-08 | 8025039058 | 12150.25 | CHINA | OE
EPO | RU8025 | 13798 | HONG KONG JIAXIN INDUSTRIAL EQUIPMENT CO LTD | 234508572 | P - HONG KONG JIAXIN INDUSTRIAL EQUIPMENT CO LTD - 234508572 - C3R Pumpout Pump (G213302) | 13841 | POC | EUR |  | 282507 | 2014-01-07 | 2018-05-31 |  | 207847.9988 |  | 146664.86 |  | 135738 |  |  |  | 2018-05-28 | [6 empty] | 0 |  | OE
EPO | RU8025 | 13852 | HONG KONG JIAXIN INDUSTRIAL EQUIPMENT CO LTD | 234508772 | P - HONG KONG JIAXIN INDUSTRIAL EQUIPMENT CO LTD - 234508772 - Centrifugal Pumps (G214006) | 13862 | POC | EUR | 610000 | 425598.12 | 2014-01-31 | 2018-08-31 |  | 309638.5013 |  | 217535.98 |  | 167644 | [6 empty] | 610001 |  | 2018-05-09 | 8025039087 | 21350 | CHINA | OE
EPO | RU8025 | 13852 | HONG KONG JIAXIN INDUSTRIAL EQUIPMENT CO LTD | 234508772 | P - HONG KONG JIAXIN INDUSTRIAL EQUIPMENT CO LTD - 234508772 - Centrifugal Pumps (G214007) | 13863 | POC | EUR |  | 412846.88 | 2014-01-31 | 2018-08-31 |  | 300361.4987 |  | 194138.96 |  | 137435 | [10 empty] | 0 |  | OE
EPO | RU8025 | 13899 | AMEC FOSTER WHEELER ASIA PACIFIC PTE LTD | 234516362 | P - AMEC FOSTER WHEELER ASIA PACIFIC PTE LTD - 234516362 - C5 Feed Pumps (G217170) | 15531 | POC | EUR | 1587411.9976 | 333404.98 | 2017-11-15 | 2018-09-30 |  | 286331.9993 |  | 220340.82 |  | 54809 | [6 empty] | 2376 |  | 2018-05-08 | 8025039059 | 15874 | ASIA | OE
EPO | RU8025 | 13899 | AMEC FOSTER WHEELER ASIA PACIFIC PTE LTD | 234516362 | P - AMEC FOSTER WHEELER ASIA PACIFIC PTE LTD - 234516362 - Naptha Transfer Pump (G217171) | 15532 | POC | EUR |  | 295403.62 | 2017-11-15 | 2018-09-30 |  | 253695.9979 |  | 207219.8 |  | 21307 | [10 empty] | 0 |  | OE
EPO | RU8025 | 13899 | AMEC FOSTER WHEELER ASIA PACIFIC PTE LTD | 234516362 | P - AMEC FOSTER WHEELER ASIA PACIFIC PTE LTD - 234516362 - LDBSCN + C4 Blending Pumps (G217172) | 15533 | POC | EUR |  | 576135.8 | 2017-11-15 | 2018-09-30 |  | 494791.9959 |  | 381963.44 |  | 21928 | [10 empty] | 0 |  | OE
EPO | RU8025 | 13899 | AMEC FOSTER WHEELER ASIA PACIFIC PTE LTD | 234516362 | P - AMEC FOSTER WHEELER ASIA PACIFIC PTE LTD - 234516362 - Mogas Transfer Pumps (G217173) | 15534 | POC | EUR |  | 643438.13 | 2017-11-15 | 2018-09-30 |  | 552592.0045 |  | 435032.56 |  | 25556 | [10 empty] | 0 |  | OE
EPO | RU8025 | 14734 | CSTS Joint Operation | 234516311 | P - CSTS Joint Operation - 234516311 - Recovered HC Closed Drain Pump (G217163) | 15881 | POC | EUR | 1141036.9976 | 107279.67 | 2017-11-27 | 2018-09-30 |  | 92133.0041 |  | 61753.89 |  | 34960 | [6 empty] | 285259 |  | 2018-05-09 | 8025039077 | 0 | ASIA | OE
EPO | RU8025 | 14734 | CSTS Joint Operation | 234516311 | P - CSTS Joint Operation - 234516311 - Amine Closed Drain Pump (G217164) | 15882 | POC | EUR |  | 83293.03 | 2017-11-27 | 2018-09-30 |  | 71533.0041 |  | 79571.29 |  | 30124 | [10 empty] | 0 |  | OE
EPO | RU8025 | 14734 | CSTS Joint Operation | 234516311 | P - CSTS Joint Operation - 234516311 - Propane Transfer Pump (G217165) | 15883 | POC | EUR |  | 282172.55 | 2017-11-27 | 2018-09-30 |  | 242333.0041 |  | 206993.45 |  | 38085 | [10 empty] | 0 |  | OE
EPO | RU8025 | 14734 | CSTS Joint Operation | 234516311 | P - CSTS Joint Operation - 234516311 - Depropanizer Reflux Pumps (G217166) | 15884 | POC | EUR |  | 487613.46 | 2017-11-27 | 2018-09-30 |  | 418768.0007 |  | 336237.5 |  | 54514 | [10 empty] | 0 |  | OE
EPO | RU8025 | 14734 | CSTS Joint Operation | 234516311 | P - CSTS Joint Operation - 234516311 - Debutanizer Reflux Pumps (G217167) | 15885 | POC | EUR |  | 368264.77 | 2017-11-27 | 2018-09-30 |  | 316269.9845 |  | 259302.55 |  | 69048 | [10 empty] | 0 |  | OE
EPO | RU8025 | 14742 | ROTARY ENGINEERING FUJAIRAH FZE | 234516433 | P - ROTARY ENGINEERING FUJAIRAH FZE - 234516433 - Centrifugal Pumps (G217176-179) | 15655 | POC | EUR | 486758.0041 | 566781.02 | 2017-11-29 | 2018-08-16 |  | 486758.0041 |  | 443107.38 |  | 91359 | [10 empty] | 0 | MIDEAST | OE
EPO | RU8025 | 14764 | Tecnimont SpA | 234516322 | P - Tecnimont SpA - 234516322 - Operating Spare Parts (R54380) | 16956 | POC | EUR | 872779.0965 | 1016263.98 | 2017-11-28 | 2018-05-20 |  | 872779.0965 |  | 208158.97 |  | 204655 | [6 empty] | 580398 |  | 2018-05-23 | 8025039144 | 0 | EUROPE | AM
EPO | RU8025 | 17877 | DANGOTE OIL REFINING COMPANY LIMITED | 234516662 | P - DANGOTE - 234516662 - Amine Blowdown Pumps (G217197) | 18698 | POC | USD | 1386883 | 192380 | 2017-12-27 | 2018-12-29 |  | 192380 |  | 154801.63 |  | 4444 | [7 empty] | 0 |  |  | 11653 | OTHERAFRICA | OE
EPO | RU8025 | 17877 | DANGOTE OIL REFINING COMPANY LIMITED | 234516662 | P - DANGOTE - 234516662 - Hot Oil Blowdown Pumps (G217198) | 18701 | POC | USD |  | 168808 | 2017-12-27 | 2018-12-29 |  | 168808 |  | 134900.73 |  | 4373 | [10 empty] | 0 |  | OE
EPO | RU8025 | 17877 | DANGOTE OIL REFINING COMPANY LIMITED | 234516662 | P - DANGOTE - 234516662 - CBD Pumps for Drum (G217199) | 18702 | POC | USD |  | 194642 | 2017-12-27 | 2018-12-29 |  | 194642 |  | 157003.82 |  | 4186 | [10 empty] | 0 |  | OE
EPO | RU8025 | 17877 | DANGOTE OIL REFINING COMPANY LIMITED | 234516662 | P - DANGOTE - 234516662 - Amine Blowdown Pumps (G217200) | 18703 | POC | USD |  | 197262 | 2017-12-27 | 2018-12-29 |  | 197262 |  | 160659.9 |  | 4186 | [10 empty] | 0 |  | OE
EPO | RU8025 | 17877 | DANGOTE OIL REFINING COMPANY LIMITED | 234516662 | P - DANGOTE - 234516662 - LP Flare KOD Pumps (G217201) | 18704 | POC | USD |  | 176798 | 2017-12-27 | 2018-12-29 |  | 176798 |  | 132916.85 |  | 5099 | [10 empty] | 0 |  | OE
EPO | RU8025 | 17877 | DANGOTE OIL REFINING COMPANY LIMITED | 234516662 | P - DANGOTE - 234516662 - Amine Sump Pumps (G217202 - G217203) | 18705 | POC | USD |  | 116380 | 2017-12-27 | 2018-12-29 |  | 116380 |  | 121911.42 |  | 8889 | [10 empty] | 0 |  | OE
EPO | RU8025 | 17877 | DANGOTE OIL REFINING COMPANY LIMITED | 234516662 | P - DANGOTE - 234516662 - CBD Pumps (G217204 - G217205) | 18706 | POC | USD |  | 174206 | 2017-12-27 | 2018-12-29 |  | 174206 |  | 146785.14 |  | 7820 | [10 empty] | 0 |  | OE
EPO | RU8025 | 17877 | DANGOTE OIL REFINING COMPANY LIMITED | 234516662 | P - DANGOTE - 234516662 - Spare Parts (IS217197 - IS217205) | 18708 | POC | USD |  | 166407 | 2017-12-27 | 2018-12-29 |  | 166407 |  | 65397.3 |  | 0 | [10 empty] | 0 |  | AM
EPO | RU8025 | 17883 | COMPAÑÍA ESPAÑOLA DE PETRÓLEOS, SAU - CEPSA | 234516651 | P - CEPSA - 234516651 - Waste Water Pump (G217195) | 18561 | POC | EUR | 255000 | 206023.62 | 2017-12-22 | 2018-08-03 |  | 173100 |  | 121375.32 |  | 35221 | [10 empty] | 0 | EUROPE | OE
EPO | RU8025 | 17883 | COMPAÑÍA ESPAÑOLA DE PETRÓLEOS, SAU - CEPSA | 234516651 | P - CEPSA - 234516651 - Waste Water Pump (G217196) | 18562 | POC | EUR |  | 97477.38 | 2017-12-22 | 2018-08-03 |  | 81900 |  | 55628.05 |  | 19061 | [10 empty] | 0 |  | OE
EPO | RU8025 | 22060 | SINOPEC EUROPA GMBH | 234516751 | P - SINOPEC EUROPA GMBH - 234516751 - Olefin Free Isobutane Pumps (G218003) | 22268 | POC | EUR | 940600 | 538716.37 | 2018-01-31 | 2018-10-23 |  | 449080.0017 |  | 313407.86 |  | 19349 | [10 empty] | 9406 | CHINA | OE
EPO | RU8025 | 22060 | SINOPEC EUROPA GMBH | 234516751 | P - SINOPEC EUROPA GMBH - 234516751 - Recycle Isobutane Pumps (G218004) | 22269 | POC | EUR |  | 547202.34 | 2018-01-31 | 2018-10-23 |  | 456154.0013 |  | 318471.24 |  | 19058 | [10 empty] | 0 |  | OE
EPO | RU8025 | 22060 | SINOPEC EUROPA GMBH | 234516751 | P - SINOPEC EUROPA GMBH - 234516751 - Commissioning & Start-Up Spare Parts (IS218003/4) | 22270 | POC | EUR |  | 42425.05 | 2018-01-31 | 2018-10-23 |  | 35365.997 |  | 27742.98 |  | 0 | [10 empty] | 0 |  | AM
EPO | RU8025 | 22079 | JACOBS ENGINEERING GROUP INC | 234516782 | P - JACOBS ENGINEERING GROUP INC - 234516782 - #1 Depropanizer O.H. Reflux Pumps (G218011) | 22263 | POC | USD | 390248 | 390248 | 2018-01-31 | 2018-09-20 |  | 390248 |  | 231507.48 |  | 54156 | [7 empty] | 0 |  |  | 0 | US | OE
EPO | RU8025 | 23885 | SINOPEC NANJING ENGINEERING CO LTD | 234516915 | P - SINOPEC NANJING ENGINEERING CO LTD - 234516915 - Ethylene Feed Pumps (G218015) | 23920 | POC | EUR | 634100 | 395053.2 | 2018-03-12 | 2018-08-23 |  | 324000 |  | 277076.88 |  | 6590 | [6 empty] | 63410 |  | 2018-05-18 | 8025039129 | 0 | CHINA | OE
EPO | RU8025 | 23885 | SINOPEC NANJING ENGINEERING CO LTD | 234516915 | P - SINOPEC NANJING ENGINEERING CO LTD - 234516915 - Propylene Feed Pumps (G218016) | 23921 | POC | EUR |  | 378104.93 | 2018-03-12 | 2018-08-23 |  | 310100 |  | 270134.76 |  | 7182 | [10 empty] | 0 |  | OE
EPO | RU8025 | 24472 | TECHNIP FRANCE ABU DHABI | 234516918 | P - TECHNIP FRANCE ABU DHABI - 234516918 - Organic Recovery Pumps (G218007 & G218008) | 26174 | POC | EUR | 714078.9961 | 287011.02 | 2018-03-19 | 2018-12-21 |  | 235389.9943 |  | 103231.83 |  | 7667 | [10 empty] | 0 | MIDEAST | OE
EPO | RU8025 | 24472 | TECHNIP FRANCE ABU DHABI | 234516918 | P - TECHNIP FRANCE ABU DHABI - 234516918 - Mineral Recovery Pump (G218009) | 26175 | POC | EUR |  | 139540.35 | 2018-03-19 | 2018-12-21 |  | 114443.0001 |  | 95720.13 |  | 3943 | [10 empty] | 0 |  | OE
EPO | RU8025 | 24472 | TECHNIP FRANCE ABU DHABI | 234516918 | P - TECHNIP FRANCE ABU DHABI - 234516918 - Effluent Pit Pumps (G218010) | 26176 | POC | EUR |  | 444125.15 | 2018-03-19 | 2018-12-21 |  | 364246.0018 |  | 304655.35 |  | 4781 | [10 empty] | 0 |  | OE
EPO | RU8025 | 25993 | Henghuan Refining Company Berhad | 234516967 | P - Henghuan Refining Company Berhad - 234516967 - UG Sump Oil Pump (G218023) | 26002 | POC | EUR | 264363.0034 | 162263.23 | 2018-03-29 | 2018-10-29 |  | 133079.0043 |  | 96862.26 |  | 12241 | [6 empty] | 26436 |  | 2018-05-29 | 8025039184 | 0 | ASIA | OE
EPO | RU8025 | 25993 | Henghuan Refining Company Berhad | 234516967 | P - Henghuan Refining Company Berhad - 234516967 - CDF Water Pump (G218024) | 26003 | POC | EUR |  | 160074.58 | 2018-03-29 | 2018-10-29 |  | 131283.999 |  | 124251.3 |  | 11456 | [10 empty] | 0 |  | OE
FCO | RU8031 | 6755 | Zarubezhneft - Production Kharyaga LLC | 1326702 | P-Zarubezhneft-1326702 V740 | 6769 | PIT | EUR | 133754.1301 | 733757.38 | 2013-11-28 | 2018-04-15 | [16 empty] | 0 | RUSCIS | OE
FCO | RU8031 | 6755 | Zarubezhneft - Production Kharyaga LLC | 1326702 | P-Zarubezhneft-1326702 MK1_Pressure Reducer | 7045 | POC | EUR |  | 158364.89 | 2013-11-28 | 2018-04-15 |  | 133754.1301 |  | 60512 |  | 60512 |  |  |  | 2018-05-15 | [6 empty] | 0 | RUSCIS | OE
FCO | RU8031 | 7534 | Linde | 1725133 | P-Linde AG-1725133-POb 1 - 1 Flow Pro CL 600 and 3 Flow Top CL 300 Valves | 9225 | POC | EUR | 357290 | 23950.73 | 2018-01-24 | 2018-11-12 |  | 19284 |  | 21861.61 |  | 21861.94 | [10 empty] | 0 | US | OE
FCO | RU8031 | 7534 | Linde | 1725133 | P-Linde AG-1725133-POb 2 - 9 Flow Pro CL 600 Valves | 27149 | POC | EUR |  | 47490.35 | 2018-01-24 | 2018-11-12 |  | 38237 |  | 41743.96 |  | 41514.84 | [10 empty] | 0 | US | OE
FCO | RU8031 | 7534 | Linde | 1725133 | P-Linde AG-1725133-POb 3 - 5 Flow Pro CL 600 and 1 Flow Top CL 300 Valves | 27150 | POC | EUR |  | 34455.56 | 2018-01-24 | 2018-11-12 |  | 27742 |  | 28908.88 |  | 28909.56 | [10 empty] | 0 | US | OE
FCO | RU8031 | 7534 | Linde | 1725133 | P-Linde AG-1725133-POb 4 - 14 Flow Pro CL 600 - 3 Flow Top CL 300 and 3 Flow Top CL 150 Valves | 27151 | POC | EUR |  | 105579.94 | 2018-01-24 | 2018-11-12 |  | 85008 |  | 81269.85 |  | 81270.41 | [10 empty] | 0 | US | OE
FCO | RU8031 | 7534 | Linde | 1725133 | P-Linde AG-1725133-POb 5 - 9 Flow Pro CL 600 - 11 Flow Top CL 150 and 1 Flow Top CL 300 Valves | 27157 | POC | EUR |  | 109020.28 | 2018-01-24 | 2018-11-12 |  | 87778 |  | 81520.33 |  | 81270.19 | [10 empty] | 0 | US | OE
FCO | RU8031 | 7534 | Linde | 1725133 | P-Linde AG-1725133-POb 6 - 7 Flow Pro CL 600 - 3 Flow Top CL 300 and 4 Flow Top CL 150 Valves | 27159 | POC | EUR |  | 71670.85 | 2018-01-24 | 2018-11-12 |  | 57706 |  | 52327.41 |  | 51913.69 | [10 empty] | 0 | US | OE
FCO | RU8031 | 7534 | Linde | 1725133 | P-Linde AG-1725133-POb 7 - 4 Flow Pro CL 600 - 2 Flow Top CL 150 and 1 Flow Top 300 Valves | 27160 | POC | EUR |  | 39970.04 | 2018-01-24 | 2018-11-12 |  | 32182 |  | 27272.41 |  | 27225.95 | [10 empty] | 0 | US | OE
FCO | RU8031 | 7534 | Linde | 1725133 | P-Linde AG-1725133-POb 8 - Spare Parts | 27161 | POC | EUR |  | 11616.43 | 2018-01-24 | 2018-11-12 |  | 9353 |  | 2908.14 |  | 1032.33 | [10 empty] | 0 | US | OE
FCO | RU8031 | 7837 | Amec Foster Wheeler Italiana Srl | 1BD0874E PIT014 | P-Amec-1722911 | 9263 | POC | EUR | 241849.0034 | 286349.22 | 2017-05-04 | 2018-01-15 |  | 241849.0034 |  | 174415 |  | 174415 | [10 empty] | 0 | EUROPE | OE
FCO | RU8031 | 9347 | Air Liquide Advanced Technologies | 1723280 | P-Air Liquide 1723280 C726 | 13180 | POC | EUR | 396433.0054 | 375479.7 | 2017-10-03 | 2018-05-09 |  | 317880 |  | 400997 |  | 294388 | [10 empty] | 0 | EUROPE | OE
FCO | RU8031 | 9347 | Air Liquide Advanced Technologies | 1723280 | P-Air Liquide 1723280 V726 | 13567 | PIT | EUR |  | 92786.81 | 2017-10-03 | 2018-05-09 |  | 78553.0054 | [14 empty] | 0 | EUROPE | OE
FCO | RU8031 | 10141 | Linde AG | 1726536 | P-Linde AG-1726536 | 10778 | POC | EUR | 374735 | 442636.98 | 2017-10-06 | 2018-04-13 |  | 374735 | 18057 | 328916 |  | 316964 | [10 empty] | 0 | CHINA | OE
FCO | RU8031 | 10784 | Score (Europe) Ltd. | 1726827 | P-Score 1726827 | 10789 | POC | EUR | 279955.3844 | 330683.3 | 2017-11-26 | 2018-04-17 |  | 279955.3844 |  | 148243 |  | 148243 |  |  |  | 2018-05-03 | [6 empty] | 0 | EUROPE | OE
FCO | RU8031 | 14263 | Tong Tai International (Hong Kong) Limited | 1727941 | P-Tong Tai-1727941 | 14306 | POC | EUR | 941810.9982 | 1120943.45 | 2017-12-15 | 2018-06-30 |  | 941810.9982 |  | 713977 |  | 27557 | [10 empty] | 0 | CHINA | OE
FCO | RU8031 | 20883 | Tong Tai International (Hong Kong) Limited | 1820248 | P-Tong Tai-1820248 | 20884 | POC | EUR | 294756.002 | 353589.3 | 2018-01-15 | 2018-08-15 |  | 294756.002 |  | 225369 | [12 empty] | 0 | CHINA | OE
FCO | RU8031 | 20889 | Hong Kong BSV Trading Limited | 1820627 | P-Hong Kong BSV-1820627-POb 1 - 14 Mark One CL 300 Valves | 21435 | POC | EUR | 1069883.2944 | 229943 | 2018-01-31 | 2018-08-31 |  | 191683.061 |  | 175039.38 |  | 1086.49 | [10 empty] | 0 | CHINA | OE
FCO | RU8031 | 20889 | Hong Kong BSV Trading Limited | 1820627 | P-Hong Kong BSV-1820627-POb 2 - 4 Mark One CL 300 Valves | 21661 | POC | EUR |  | 49142 | 2018-01-31 | 2018-08-31 |  | 40965.3218 |  | 34126.72 |  | 434.6 | [10 empty] | 0 | CHINA | OE
FCO | RU8031 | 20889 | Hong Kong BSV Trading Limited | 1820627 | P-Hong Kong BSV-1820627-POb 3 - 4 Mark One CL 300 Valves | 21662 | POC | EUR |  | 89706 | 2018-01-31 | 2018-08-31 |  | 74779.9266 |  | 57595.72 |  | 434.6 | [10 empty] | 0 | CHINA | OE
FCO | RU8031 | 20889 | Hong Kong BSV Trading Limited | 1820627 | P-Hong Kong BSV-1820627-POb 4 - 6 Mark One CL 300 Valves | 21663 | POC | EUR |  | 195775 | 2018-01-31 | 2018-08-31 |  | 163200.2334 |  | 152129.82 |  | 0 | [10 empty] | 0 | CHINA | OE
FCO | RU8031 | 20889 | Hong Kong BSV Trading Limited | 1820627 | P-Hong Kong BSV-1820627-POb 5 - 48 Flow Pro CL 600 Valves | 21664 | POC | EUR |  | 348359 | 2018-01-31 | 2018-08-31 |  | 290395.9653 |  | 252961.86 |  | 534.67 | [10 empty] | 0 | CHINA | OE
FCO | RU8031 | 20889 | Hong Kong BSV Trading Limited | 1820627 | P-Hong Kong BSV-1820627-POb 6 - 2 Mark One CL 300 Valves | 21665 | POC | EUR |  | 113032 | 2018-01-31 | 2018-08-31 |  | 94224.7416 |  | 64719.12 |  | 0 | [10 empty] | 0 | CHINA | OE
FCO | RU8031 | 20889 | Hong Kong BSV Trading Limited | 1820627 | P-Hong Kong BSV-1820627-POb 7 - 6 Mark One CL 300 Valves | 21666 | POC | EUR |  | 175649 | 2018-01-31 | 2018-08-31 |  | 146422.9743 |  | 96840.66 |  | 0 | [10 empty] | 0 | CHINA | OE
FCO | RU8031 | 20889 | Hong Kong BSV Trading Limited | 1820627 | P-Hong Kong BSV-1820627-POb 8 - 4 Mark One CL 300 Valves | 21667 | POC | EUR |  | 39547 | 2018-01-31 | 2018-08-31 |  | 32966.8223 |  | 29954.56 |  | 0 | [10 empty] | 0 | CHINA | OE
FCO | RU8031 | 20889 | Hong Kong BSV Trading Limited | 1820627 | P-Hong Kong BSV-1820627-POb 9 - 2 Mark One CL 300 Valves | 21668 | POC | EUR |  | 42279 | 2018-01-31 | 2018-08-31 |  | 35244.2481 |  | 26697.74 |  | 217.3 | [10 empty] | 0 | CHINA | OE
FCO | RU8031 | 20891 | Hong Kong BSV Trading Limited | 1820549 | P-Hong Kong BSV-1820549-POb 1 - 2 Mark One CL 300 Valves | 21310 | POC | EUR | 468398.6329 | 32788 | 2018-01-31 | 2018-08-31 |  | 27332.4441 |  | 26650.54 |  | 0 | [10 empty] | 0 | CHINA | OE
FCO | RU8031 | 20891 | Hong Kong BSV Trading Limited | 1820549 | P-Hong Kong BSV-1820549-POb 2 - 2 Mark One CL 300 Valves | 21371 | POC | EUR |  | 20885 | 2018-01-31 | 2018-08-31 |  | 17409.97 |  | 16835.24 |  | 340.07 | [10 empty] | 0 | CHINA | OE
FCO | RU8031 | 20891 | Hong Kong BSV Trading Limited | 1820549 | P-Hong Kong BSV-1820549-POb 3 - 2 Mark One CL 300 Valves | 21372 | POC | EUR |  | 28115 | 2018-01-31 | 2018-08-31 |  | 23436.979 |  | 23140.36 |  | 0 | [10 empty] | 0 | CHINA | OE
FCO | RU8031 | 20891 | Hong Kong BSV Trading Limited | 1820549 | P-Hong Kong BSV-1820549-POb 4 - 2 Mark One CL 300 Valves | 21373 | POC | EUR |  | 37621 | 2018-01-31 | 2018-08-31 |  | 31361.2871 |  | 27091.68 |  | 0 | [10 empty] | 0 | CHINA | OE
FCO | RU8031 | 20891 | Hong Kong BSV Trading Limited | 1820549 | P-Hong Kong BSV-1820549-POb 5 - 2 Mark One CL 300 Valves | 21374 | POC | EUR |  | 24685 | 2018-01-31 | 2018-08-31 |  | 20577.6926 |  | 20577.02 |  | 0 | [10 empty] | 0 | CHINA | OE
FCO | RU8031 | 20891 | Hong Kong BSV Trading Limited | 1820549 | P-Hong Kong BSV-1820549-POb 6 - 2 Mark One CL 300 Valves | 21375 | POC | EUR |  | 45348 | 2018-01-31 | 2018-08-31 |  | 37802.6009 |  | 28758.28 |  | 0 | [10 empty] | 0 | CHINA | OE
FCO | RU8031 | 20891 | Hong Kong BSV Trading Limited | 1820549 | P-Hong Kong BSV-1820549-POb 7 - 2 Mark One CL 300 Valves | 21376 | POC | EUR |  | 21986 | 2018-01-31 | 2018-08-31 |  | 18327.7759 |  | 17262.96 |  | 634.9 | [10 empty] | 0 | CHINA | OE
FCO | RU8031 | 20891 | Hong Kong BSV Trading Limited | 1820549 | P-Hong Kong BSV-1820549-POb 8 - 2 Mark One CL 300 Valves | 21377 | POC | EUR |  | 20568 | 2018-01-31 | 2018-08-31 |  | 17145.7152 |  | 17032.78 |  | 0 | [10 empty] | 0 | CHINA | OE
FCO | RU8031 | 20891 | Hong Kong BSV Trading Limited | 1820549 | P-Hong Kong BSV-1820549-POb 9 - 2 Mark One CL 300 Valves | 21378 | POC | EUR |  | 23884 | 2018-01-31 | 2018-08-31 |  | 19909.97 |  | 19543.56 |  | 0 | [10 empty] | 0 | CHINA | OE
FCO | RU8031 | 20891 | Hong Kong BSV Trading Limited | 1820549 | P-Hong Kong BSV-1820549-POb 10 - 2 Mark One CL 300 Valves | 21379 | POC | EUR |  | 16909 | 2018-01-31 | 2018-08-31 |  | 14095.5318 |  | 12399.2 |  | 340.07 | [10 empty] | 0 | CHINA | OE
FCO | RU8031 | 20891 | Hong Kong BSV Trading Limited | 1820549 | P-Hong Kong BSV-1820549-POb 11 - 2 Mark One CL 300 Valves | 21380 | POC | EUR |  | 20568 | 2018-01-31 | 2018-08-31 |  | 17145.7152 |  | 17137.04 |  | 0 | [10 empty] | 0 | CHINA | OE
FCO | RU8031 | 20891 | Hong Kong BSV Trading Limited | 1820549 | P-Hong Kong BSV-1820549-POb 12 - 2 Mark One CL 300 Valves | 21381 | POC | EUR |  | 31019 | 2018-01-31 | 2018-08-31 |  | 25857.7859 |  | 27912.48 |  | 0 | [10 empty] | 0 | CHINA | OE
FCO | RU8031 | 20891 | Hong Kong BSV Trading Limited | 1820549 | P-Hong Kong BSV-1820549-POb 13 - 2 Mark One CL 300 Valves | 21382 | POC | EUR |  | 88668 | 2018-01-31 | 2018-08-31 |  | 73914.6382 |  | 55080.26 |  | 0 | [10 empty] | 0 | CHINA | OE
FCO | RU8031 | 20891 | Hong Kong BSV Trading Limited | 1820549 | P-Hong Kong BSV-1820549-POb 14 - 4 Mark One CL 300 Valves | 21383 | POC | EUR |  | 148847 | 2018-01-31 | 2018-08-31 |  | 124080.5268 |  | 111163.32 |  | 0 | [10 empty] | 0 | CHINA | OE
FCO | RU8031 | 22542 | Linde AG | 1821128 | P-Linde Yantai Wanhua II-1821128-POb 1 - 2 Flow Top V726 Valves | 22544 | POC | EUR | 359000 | 9945.94 | 2018-03-06 | 2018-08-25 |  | 8159.0976 |  | 8589.71 | [12 empty] | 0 | CHINA | OE
FCO | RU8031 | 22542 | Linde AG | 1821128 | P-Linde Yantai Wanhua II-1821128-POb 2 - 2 Mark One Valves | 26183 | POC | EUR |  | 135513.32 | 2018-03-06 | 2018-08-25 |  | 111167.6128 |  | 68084.62 | [12 empty] | 0 | CHINA | OE
FCO | RU8031 | 22542 | Linde AG | 1821128 | P-Linde Yantai Wanhua II-1821128-POb 3 - 2 Mark One Valves | 26184 | POC | EUR |  | 147945.74 | 2018-03-06 | 2018-08-25 |  | 121366.4807 |  | 92737.18 | [12 empty] | 0 | CHINA | OE
FCO | RU8031 | 22542 | Linde AG | 1821128 | P-Linde Yantai Wanhua II-1821128-POb 4 - 2 Flow Pro V724 Valves | 26185 | POC | EUR |  | 27351.32 | 2018-03-06 | 2018-08-25 |  | 22437.5062 |  | 14461.68 | [12 empty] | 0 | CHINA | OE
FCO | RU8031 | 22542 | Linde AG | 1821128 | P-Linde Yantai Wanhua II-1821128-POb 5 - 2 Flow Pro V724 Valves | 26186 | POC | EUR |  | 39783.72 | 2018-03-06 | 2018-08-25 |  | 32636.3577 |  | 18263.66 | [12 empty] | 0 | CHINA | OE
FCO | RU8031 | 22542 | Linde AG | 1821128 | P-Linde Yantai Wanhua II-1821128-POb 6 - 2 Flow Top V726 Valves | 26188 | POC | EUR |  | 36054 | 2018-03-06 | 2018-08-25 |  | 29576.7022 |  | 14598.82 | [12 empty] | 0 | CHINA | OE
FCO | RU8031 | 22542 | Linde AG | 1821128 | P-Linde Yantai Wanhua II-1821128-POb 7 - 2 Flow Top V726 Valves | 26189 | POC | EUR |  | 41026.96 | 2018-03-06 | 2018-08-25 |  | 33656.2428 |  | 21545.78 | [12 empty] | 0 | CHINA | OE
FCO | RU8031 | 22556 | BP Exploration Limited | 1821451 | P-BP Shah Deniz-1821451-POb 1 - 1 Mark One Valve | 22587 | POC | EUR | 310027.6329 | 98015.87 | 2018-02-19 | 2018-09-26 |  | 78917.7697 |  | 51000 | [12 empty] | 0 | MIDEAST | OE
FCO | RU8031 | 22556 | BP Exploration Limited | 1821451 | P-BP Shah Deniz-1821451-POb 2 - 1 Mark One Valve | 22615 | POC | EUR |  | 103509.45 | 2018-02-19 | 2018-09-26 |  | 83340.942 |  | 54000 | [12 empty] | 0 | MIDEAST | OE
FCO | RU8031 | 22556 | BP Exploration Limited | 1821451 | P-BP Shah Deniz-1821451-POb 3 - 1 Mark One Valve | 22618 | POC | EUR |  | 53016.97 | 2018-02-19 | 2018-09-26 |  | 42686.7713 |  | 28000 | [12 empty] | 0 | MIDEAST | OE
FCO | RU8031 | 22556 | BP Exploration Limited | 1821451 | P-BP Shah Deniz-1821451-POb 4 - 1 Mark One Valve | 22619 | POC | EUR |  | 26095.46 | 2018-02-19 | 2018-09-26 |  | 21010.8374 |  | 14000 | [12 empty] | 0 | MIDEAST | OE
FCO | RU8031 | 22556 | BP Exploration Limited | 1821451 | P-BP Shah Deniz-1821451-POb 5 - 1 Kämmer Valve | 22620 | POC | EUR |  | 58799.21 | 2018-02-19 | 2018-09-26 |  | 47342.3591 |  | 19000 | [12 empty] | 0 | MIDEAST | OE
FCO | RU8031 | 22556 | BP Exploration Limited | 1821451 | P-BP Shah Deniz-1821451-POb 6 - 1 Mark One Valve | 22621 | POC | EUR |  | 36171.54 | 2018-02-19 | 2018-09-26 |  | 29123.6232 |  | 36000 | [12 empty] | 0 | MIDEAST | OE
FCO | RU8031 | 22556 | BP Exploration Limited | 1821451 | P-BP Shah Deniz-1821451-POb 7 - Spare Parts | 22622 | POC | EUR |  | 9445.82 | 2018-02-19 | 2018-09-26 |  | 7605.3301 |  | 2157.53 | [12 empty] | 0 | MIDEAST | OE
FCO | RU8031 | 24057 | Air Liquide Global E&C Solutions Hangzhou Co., Ltd | 1822309 | P-Air Liquide Shandong Lianmeng-1822309-POb 1 - 1 Mark One CL 600 Valve | 25953 | POC | EUR | 305905.6932 | 105703.81 | 2018-03-20 | 2018-07-30 |  | 86713.5439 | [14 empty] | 0 | ASIA | OE
FCO | RU8031 | 24057 | Air Liquide Global E&C Solutions Hangzhou Co., Ltd | 1822309 | P-Air Liquide Shandong Lianmeng-1822309-POb 2 - 1 Mark One CL 600 Valve | 25960 | POC | EUR |  | 14003.96 | 2018-03-20 | 2018-07-30 |  | 11488.0722 | [14 empty] | 0 | ASIA | OE
FCO | RU8031 | 24057 | Air Liquide Global E&C Solutions Hangzhou Co., Ltd | 1822309 | P-Air Liquide Shandong Lianmeng-1822309-POb 3 - 1 Mark One CL 900 Valve | 25961 | POC | EUR |  | 74558.65 | 2018-03-20 | 2018-07-30 |  | 61163.7818 | [14 empty] | 0 | ASIA | OE
FCO | RU8031 | 24057 | Air Liquide Global E&C Solutions Hangzhou Co., Ltd | 1822309 | P-Air Liquide Shandong Lianmeng-1822309-POb 4 - 1 Mark One CL 600 Valve | 25962 | POC | EUR |  | 79262.67 | 2018-03-20 | 2018-07-30 |  | 65022.6989 | [14 empty] | 0 | ASIA | OE
FCO | RU8031 | 24057 | Air Liquide Global E&C Solutions Hangzhou Co., Ltd | 1822309 | P-Air Liquide Shandong Lianmeng-1822309-POb 5 - 1 Mark One CL 600 Valve | 25964 | POC | EUR |  | 26935.19 | 2018-03-20 | 2018-07-30 |  | 22096.1362 | [14 empty] | 0 | ASIA | OE
FCO | RU8031 | 24057 | Air Liquide Global E&C Solutions Hangzhou Co., Ltd | 1822309 | P-Air Liquide Shandong Lianmeng-1822309-POb 6 - 2 Mark One CL 600 Valves | 25969 | POC | EUR |  | 23527.17 | 2018-03-20 | 2018-07-30 |  | 19300.3856 | [14 empty] | 0 | ASIA | OE
FCO | RU8031 | 24057 | Air Liquide Global E&C Solutions Hangzhou Co., Ltd | 1822309 | P-Air Liquide Shandong Lianmeng-1822309-POb 7 - 2 Mark One CL 600 Valves | 25980 | POC | EUR |  | 15885.47 | 2018-03-20 | 2018-07-30 |  | 13031.5587 | [14 empty] | 0 | ASIA | OE
FCO | RU8031 | 24057 | Air Liquide Global E&C Solutions Hangzhou Co., Ltd | 1822309 | P-Air Liquide Shandong Lianmeng-1822309-POb 8 - 2 Mark One CL 900 Valves | 25983 | POC | EUR |  | 12219.6 | 2018-03-20 | 2018-07-30 |  | 10024.2822 | [14 empty] | 0 | ASIA | OE
FCO | RU8031 | 24057 | Air Liquide Global E&C Solutions Hangzhou Co., Ltd | 1822309 | P-Air Liquide Shandong Lianmeng-1822309-POb 9 - 1 Mark One CL 600 Valve | 25984 | POC | EUR |  | 13207.83 | 2018-03-20 | 2018-07-30 |  | 10834.9713 | [14 empty] | 0 | ASIA | OE
FCO | RU8031 | 24057 | Air Liquide Global E&C Solutions Hangzhou Co., Ltd | 1822309 | P-Air Liquide Shandong Lianmeng-1822309-POb 10 - 1 Mark One CL 600 Valve | 25985 | POC | EUR |  | 7594.69 | 2018-03-20 | 2018-07-30 |  | 6230.2625 | [14 empty] | 0 | ASIA | OE
FCO | RU8031 | 24066 | Air Liquide Global E&C Solutions Hangzhou Co., Ltd | 1822305 | P-Air Liquide Yankuang RX-1822305-POb 1 - 2 Mark One CL 900 Valves | 25897 | POC | EUR | 497224.2986 | 286961.8 | 2018-03-20 | 2018-08-30 |  | 235407.5472 | [14 empty] | 0 | CHINA | OE
FCO | RU8031 | 24066 | Air Liquide Global E&C Solutions Hangzhou Co., Ltd | 1822305 | P-Air Liquide Yankuang RX-1822305-POb 2 - 2 Mark One CL 900 Valves | 25908 | POC | EUR |  | 212109.7 | 2018-03-20 | 2018-08-30 |  | 174003.0353 | [14 empty] | 0 | CHINA | OE
FCO | RU8031 | 24066 | Air Liquide Global E&C Solutions Hangzhou Co., Ltd | 1822305 | P-Air Liquide Yankuang RX-1822305-POb 3 - 2 Mark One CL 900 Valves | 25931 | POC | EUR |  | 30481.18 | 2018-03-20 | 2018-08-30 |  | 25005.0697 | [14 empty] | 0 | CHINA | OE
FCO | RU8031 | 24066 | Air Liquide Global E&C Solutions Hangzhou Co., Ltd | 1822305 | P-Air Liquide Yankuang RX-1822305-POb 4 - 2 Mark One CL 150 Valves | 25932 | POC | EUR |  | 32514.06 | 2018-03-20 | 2018-08-30 |  | 26672.7317 | [14 empty] | 0 | CHINA | OE
FCO | RU8031 | 24066 | Air Liquide Global E&C Solutions Hangzhou Co., Ltd | 1822305 | P-Air Liquide Yankuang RX-1822305-POb 5 - 2 Mark One CL 150 Valves | 25939 | POC | EUR |  | 23313.37 | 2018-03-20 | 2018-08-30 |  | 19124.9959 | [14 empty] | 0 | CHINA | OE
FCO | RU8031 | 24066 | Air Liquide Global E&C Solutions Hangzhou Co., Ltd | 1822305 | P-Air Liquide Yankuang RX-1822305-POb 6 - Spare Parts | 25940 | POC | EUR |  | 20736.31 | 2018-03-20 | 2018-08-30 |  | 17010.9188 | [14 empty] | 0 | CHINA | OE
FCO | RU8031 | 24067 | Air Liquide Global E&C Solutions Hangzhou Co., Ltd | 1822307 | P-Air Liquide Yankuang YL-1822307-POb 1 - 1 Mark One CL 900 Valve | 24149 | POC | EUR | 271362.7564 | 144968.77 | 2018-03-20 | 2018-08-30 |  | 118924.3396 | [14 empty] | 0 | CHINA | OE
FCO | RU8031 | 24067 | Air Liquide Global E&C Solutions Hangzhou Co., Ltd | 1822307 | P-Air Liquide Yankuang YL-1822307-POb 2 - 1 Mark One CL 900 Valve | 24165 | POC | EUR |  | 107154.62 | 2018-03-20 | 2018-08-30 |  | 87903.708 | [14 empty] | 0 | CHINA | OE
FCO | RU8031 | 24067 | Air Liquide Global E&C Solutions Hangzhou Co., Ltd | 1822307 | P-Air Liquide Yankuang YL-1822307-POb 3 - 1 Mark One CL 900 Valve | 24167 | POC | EUR |  | 15398.63 | 2018-03-20 | 2018-08-30 |  | 12632.1821 | [14 empty] | 0 | CHINA | OE
FCO | RU8031 | 24067 | Air Liquide Global E&C Solutions Hangzhou Co., Ltd | 1822307 | P-Air Liquide Yankuang YL-1822307-POb 4 - 1 Mark One CL 150 Valve | 24168 | POC | EUR |  | 8376.9 | 2018-03-20 | 2018-08-30 |  | 6871.9442 | [14 empty] | 0 | CHINA | OE
FCO | RU8031 | 24067 | Air Liquide Global E&C Solutions Hangzhou Co., Ltd | 1822307 | P-Air Liquide Yankuang YL-1822307-POb 5 - 1 Mark One CL 150 Valve | 24447 | POC | EUR |  | 5696.83 | 2018-03-20 | 2018-08-30 |  | 4673.3634 | [14 empty] | 0 | CHINA | OE
FCO | RU8031 | 24067 | Air Liquide Global E&C Solutions Hangzhou Co., Ltd | 1822307 | P-Air Liquide Yankuang YL-1822307-POb 6 - 1 Mark One CL 900 Valve | 24448 | POC | EUR |  | 32361.71 | 2018-03-20 | 2018-08-30 |  | 26547.7523 | [14 empty] | 0 | CHINA | OE
FCO | RU8031 | 24067 | Air Liquide Global E&C Solutions Hangzhou Co., Ltd | 1822307 | P-Air Liquide Yankuang YL-1822307-POb 7 - Spare Parts | 24452 | POC | EUR |  | 16833.74 | 2018-03-20 | 2018-08-30 |  | 13809.4668 | [14 empty] | 0 | CHINA | OE
FCO | RU8033 | 10115 | Jacobs Nederland BV | 9000090227 | P - Jacobs Nederland BV - SO 9000090227 - all PO line items | 11987 | POC | EUR | 335000 | 398918 | 2017-10-05 | 2018-03-28 |  | 335000 | 0 | 216854.1 |  | 216854 |  |  |  |  | 198809 | [5 empty] | 0 | EUROPE | OE
FCO | RU8033 | 12009 | BP Raffinaderij Rotterdam BV | 9000091192 | P - BP Raffinaderij Rotterdam BV - SO 9000091192 | 13914 | POC | EUR | 272250 | 321581.7 | 2017-11-17 | 2018-03-16 |  | 272250 | 0 | 179732 |  | 178179 |  |  |  |  | 119336 |  | 164708.75 |  | 2018-05-31 | 8014998 | 0 | EUROPE | OE
FCO | RU8033 | 22586 | Shell Nederland Raffinaderij BV | 9000093832 | P - Shell Nederland Chemie BV - 9000093832 | 22623 | POC | EUR | 390575 | 485094.15 | 2018-02-07 | 2018-06-25 |  | 390575 | 0 | 252167 |  | 66758 | [10 empty] | 0 | EUROPE | OE
FCO | RU8034 | 17282 | EDF SA | 9000092611 | P - EDF SA - SO 9000092611 - spare | 19519 | POC | EUR | 5963744.001 | 7098048.11 | 2017-12-18 | 2019-03-30 |  | 5963744.001 | 0 | 5390672 | [12 empty] | 0 | EUROPE | OE
FCO | RU8034 | 19541 | EDF SA | 9000092631 | P - EDF SA - SO 9000092631 | 19542 | POC | EUR | 2828660.2 | 3366671.37 | 2017-12-18 | 2018-10-24 |  | 2828660.2 | 0 | 2551713 |  | 53550 |  |  |  |  | 46267 |  | 49908 |  | 2018-05-23 | 3400013593 | 0 | EUROPE | OE
AMSS | RU8035 | 16022 | Electrabel NV/SA | ATW-64003639 | P-ENGIE ELECTRABEL-64003639 | 16027 | POC | EUR | 307725.917 | 369148.01 | 2017-12-13 | 2018-07-24 |  | 307725.917 | 0 | 246783 |  | 16092 | 0 | 0 | [8 empty] | 0 | EUROPE | AM
AMSS | RU8035 | 28122 | Electrabel NV/SA | ATW-64004591 | P-ENGIE ELECTRABEL-64004591 | 28251 | POC | EUR | 220000 | 265694 | 2018-05-09 | 2019-05-13 |  | 220000 | 0 | 177867 |  | 0 | 0 | 0 |  |  |  |  | 66000 | 0 | 2018-05-31 | ATW-1001155 | 0 | EUROPE | AM
AMSS | RU8035 | 28131 | Electrabel NV/SA | ATW-64004595 | P-ENGIE ELECTRABEL-64004595 | 28144 | POC | EUR | 373000 | 450472.1 | 2018-05-09 | 2019-05-13 |  | 373000 | 0 | 300927 |  | 0 | 0 | 0 |  |  |  |  | 111900 |  | 2018-05-31 | ATW-1001154 | 0 | EUROPE | AM
AMSS | RU8090 | 14044 | Syncrude Canada Ltd | 49857R | P - Syncrude Canada, LTD - 49857-HDO Pump Repair | 17260 | POC | CAD | 630185.6672 | 488743.33 | 2017-12-14 | 2018-07-13 |  | 630185.6672 |  | 409855.09 |  | 94789.71 | 0 | 0 | [8 empty] | 0 | CANADA | AM
AMSS | RU8090 | 27962 | CANADIAN NATURAL RESOURCES LIMITED | 49991R | P - Canadian Natural - 49991R - WO806279-20 CO#07 | 27969 | POC | CAD | 608740.2134 | 474170.58 | 2018-05-04 | 2018-10-22 |  | 608740.2134 |  | 412909.01 |  | 39002.5 | [10 empty] | 0 | CANADA | AM
AMSS | RU8090 | 28296 | CANADIAN NATURAL RESOURCES LIMITED | 20020R | P - Canadian Natural - 20020R - WO806279-20 CO#08 | 28628 | POC | CAD | 564761.1265 | 439913.62 | 2018-05-22 | 2018-11-13 |  | 564761.1265 |  | 383848.02 |  | 19120.23 | [10 empty] | 0 | CANADA | AM
AMSS | RU8095 | 16115 | City of Windsor | 20966 | P - City of Windsor - 20966 PO0000014150 | 16120 | POC | CAD | 522569.1056 | 388384.49 | 2017-05-31 | 2018-04-16 |  | 522569.1056 |  | 453462.02 |  | 453462.02 |  |  |  |  | 377636.97 | [5 empty] | 0 | CANADA | AM
AMSS | RU8115 | 4049 | Bruce Pwer | 101455/07968140 | P-Bruce Power-101455-Pump 1 | 4087 | POC | CAD | 2974857.2949 | 730209.33 | 2017-04-28 | 2018-06-28 |  | 984203 | 0 | 698077.39 |  | 0 | 391936.05 | 0 | [8 empty] | 0 | CANADA | AM
AMSS | RU8115 | 4049 | Bruce Pwer | 101455/07968140 | P-Bruce Power-101455-Pump2 | 4088 | POC | CAD |  | 730209.33 | 2017-04-28 | 2018-06-28 |  | 984203 | 0 | 698077.39 |  | 0 | 391936.05 | 0 | [8 empty] | 0 | CANADA | AM
AMSS | RU8115 | 4049 | Bruce Pwer | 101455/07968140 | P-Bruce Power-101455-Pump 3 | 4089 | POC | CAD |  | 730209.33 | 2017-04-28 | 2018-06-28 |  | 984203 | 0 | 698077.39 |  | 0 | 391936.05 | 0 | [8 empty] | 0 | CANADA | AM
AMSS | RU8115 | 4049 | Bruce Pwer | 101455/07968140 | P-Bruce Power-101455-Testing for first pump only | 4090 | POC | CAD |  | 16506.01 | 2017-04-28 | 2018-06-28 |  | 22248.2949 | 0 | 16455.6 |  | 0 | 9237.54 | 0 | [8 empty] | 0 | CANADA | AM
AMSS | RU8115 | 15720 | Bruce Power | 101434/07967997 | P - Bruce Power 07967997-PUMP MAIL BOILER FEED 10" x 12" x18" 2 STAGE | 17503 | POC | CAD | 1962356.0016 | 1474236.43 | 2017-03-31 | 2018-09-10 |  | 1962356.0016 | 0 | 1016500.5 |  | 413466.15 | 0 | 0 | [8 empty] | 0 | CANADA | AM
AMSS | RU8115 | 15723 | Bruce Power | 101225/07966851 | P - Bruce Power - 07966851-Bruce Power a VOA 85-75 REPLACEMENT PUMP | 17297 | POC | CAD | 975494.6494 | 751130.88 | 2016-06-28 | 2018-02-21 |  | 975494.6494 | 0 | 754626.3 |  | 754626.3 | 0 | 0 | [8 empty] | 0 | CANADA | AM
AMSS | RU8115 | 15735 | Bruce Power | 101468/07968164 | P - Bruce Power 07968164-Pump Centrifugal Vertical Mount | 17555 | POC | CAD | 2012224 | 1505053.52 | 2017-05-09 | 2018-07-02 |  | 2012224 | 0 | 1652044.86 |  | 0 | 1652044.86 | 0 | [8 empty] | 0 | CANADA | AM
AMSS | RU8115 | 15739 | Bruce Power | 101505/07968372 | P - Bruce Power 07968372-PUMP VERTICAL DOUBLE CASE DOUBLE SUCTION | 17547 | POC | CAD | 2644107.0018 | 2039891.27 | 2017-06-30 | 2018-08-10 |  | 2644107.0018 | 0 | 1673719.73 |  | 406878.4 | 0 | 0 | [8 empty] | 0 | CANADA | AM
AMSS | RU8115 | 15747 | Bruce Power | 101470/07968150 | P-Bruce Power-7968150-Suction Pump Assembly | 17433 | POC | CAD | 425372.0959 | 301896.36 | 2017-05-04 | 2018-05-10 |  | 425372.0959 | [7 empty] | 2018-02-21 | [6 empty] | 0 | CANADA | AM
AMSS | RU8120 | 7788 | COMPAÑIA MINERA LOMAS BAYAS | 2P0421700141 | P- COMPAÑIA MINERA LOMAS BAYAS I16813 | 9820 | POC | CLP | 410517557 | 463621.16 | 2017-06-30 | 2018-03-29 |  | 311155141 |  | 186139072 |  | 186139072 |  |  |  | 2018-03-07 | [6 empty] | 0 | LA | AM
AMSS | RU8120 | 7788 | COMPAÑIA MINERA LOMAS BAYAS | 2P0421700141 | P- COMPAÑIA MINERA LOMAS BAYAS I16813 | 9881 | POC | CLP |  | 148050 | 2017-06-30 | 2018-03-29 |  | 99362416 |  | 88690649 |  | 88690649 |  |  |  | 2017-06-12 | [6 empty] | 0 | LA | AM
AMSS | RU8120 | 17011 | SERVICIOS DE INGENIERIA BLACK Y VEATCH (CHILE) LTDA | 2P0421700137 | P- SERVICIOS DE INGENIERIA BLACK Y VEATCH (CHILE) LTDA EWS-COM-FPA-5-0128 | 17469 | POC | USD | 284133 | 94711 | 2017-10-03 | 2018-01-10 |  | 94711 |  | 41757821 |  | 41757821 |  |  |  | 2017-12-30 |  |  |  | 0 |  |  | 0 | LA | AM
AMSS | RU8120 | 17011 | SERVICIOS DE INGENIERIA BLACK Y VEATCH (CHILE) LTDA | 2P0421700137 | P- SERVICIOS DE INGENIERIA BLACK Y VEATCH (CHILE) LTDA EWS-COM-FPA-5-0128 | 17483 | POC | USD |  | 94711 | 2017-10-03 | 2018-01-10 |  | 94711 |  | 41904189 |  | 41904189 |  |  |  | 2018-01-30 | [6 empty] | 0 | LA | AM
AMSS | RU8120 | 17011 | SERVICIOS DE INGENIERIA BLACK Y VEATCH (CHILE) LTDA | 2P0421700137 | P- SERVICIOS DE INGENIERIA BLACK Y VEATCH (CHILE) LTDA EWS-COM-FPA-5-0128 | 17488 | POC | USD |  | 94711 | 2017-10-03 | 2018-01-10 |  | 94711 |  | 41904189 |  | 41904189 |  |  |  | 2018-01-30 | [6 empty] | 0 | LA | AM
IPO | RU8135 | 13535 | TECNICAS REUNIDAS UK Ltd. | 17200964 | P-Tecnicas Reunidas UK-17200964-CLOSED COOLING WATER PUMPS | 19002 | POC | EUR | 213700 | 253020.8 | 2017-07-31 | 2018-03-31 |  | 213700 |  | 168118 |  | 141191.5 | [10 empty] | 0 | EUROPE | OE
IPO | RU8135 | 13540 | EGA EMIRATES GLOBAL ALUMINIUM UAE AL TAWEELAH ABU DHABI | 51200992 | P - EGA EMIRATES GLOBAL ALUMINIUM UAE - 51200992 - Delivered items | 19903 | POC | USD | 1997941.1 | 7361475.16 | 2015-11-30 | 2018-07-31 | [13 empty] | 0 |  |  | 0 | MIDEAST | OE
IPO | RU8135 | 13540 | EGA EMIRATES GLOBAL ALUMINIUM UAE AL TAWEELAH ABU DHABI | 51200992 | P - EGA EMIRATES GLOBAL ALUMINIUM UAE - 51200992 - items to deliver 2nd 2018 Quarter | 19915 | POC | USD |  | 212240.64 | 2015-11-30 | 2018-07-31 |  | 212240.64 |  | 183215 |  | 129766.2 | [10 empty] | 0 | MIDEAST | OE
IPO | RU8135 | 13540 | EGA EMIRATES GLOBAL ALUMINIUM UAE AL TAWEELAH ABU DHABI | 51200992 | P - EGA EMIRATES GLOBAL ALUMINIUM UAE - 51200992 - items to deliver 2018 1st Quarter | 19916 | POC | USD |  | 1790334.75 | 2015-11-30 | 2018-07-31 |  | 1785700.46 |  | 1541495 |  | 1296518 | [10 empty] | 0 | MIDEAST | OE
IPO | RU8135 | 13540 | EGA EMIRATES GLOBAL ALUMINIUM UAE AL TAWEELAH ABU DHABI | 51200992 | P - EGA EMIRATES GLOBAL ALUMINIUM UAE - 51200992 - other pumps delivered | 19920 | POC | USD |  | 1893357 | 2015-11-30 | 2018-07-31 | [16 empty] | 0 | MIDEAST | OE
IPO | RU8135 | 13573 | SEPCO CHINA QINGDAO SMANDONG | 56200336 | P - SEPCO CHINA QINGDAO SMANDONG - 56200336 - Purge Water Pump and Electric Motor | 16975 | POC | USD | 663651 | 294890.36 | 2017-08-22 | 2018-03-15 |  | 294890 |  | 246780 |  | 215733.4 | [7 empty] | 0 |  |  | 0 | CHINA | OE
IPO | RU8135 | 13573 | SEPCO CHINA QINGDAO SMANDONG | 56200336 | P - SEPCO CHINA QINGDAO SMANDONG - 56200336 - Make-up Water Pump and Electric Motor | 16976 | POC | USD |  | 368760.54 | 2017-08-22 | 2018-03-15 |  | 368761 |  | 293761 |  | 266606.9 | [10 empty] | 0 | CHINA | OE
IPO | RU8135 | 13588 | VOPAK TERMINAL NETHERLANDS AMSTERDAM | 57200641 | P - VOPAK TERMINALS NETHERLANDS-57200641-1 Electric Pump Set 500-LNNV-1000 | 18872 | POC | EUR | 325180.0018 | 365534.84 | 2017-05-31 | 2018-01-31 |  | 325180.0018 |  | 276403 |  | 223318.8 | [10 empty] | 0 | EUROPE | OE
IPO | RU8135 | 13600 | Electricité de France | 66200010 | P - ELECTRICITE DE FRANCE (EDF) ERPC INGENIERIE FR CLAMART 92 - 66200010-X4567086 - POMPE COMPLET BK 300G - not delivered | 17152 | POC | EUR | 482942 | 253226.38 | 2010-09-22 | 2018-01-01 |  | 198360 |  | 110625 | [12 empty] | 0 | EUROPE | OE
IPO | RU8135 | 13600 | Electricité de France | 66200010 | P - ELECTRICITE DE FRANCE (EDF) ERPC INGENIERIE FR CLAMART 92 - 66200010 - Delivered items | 17156 | POC | EUR |  | 583417.38 | 2010-09-22 | 2018-01-01 |  | 284582 |  | 164148 |  | 243510.3 | [10 empty] | 0 | EUROPE | OE
IPO | RU8135 | 13606 | ELECTRABEL NV/SA BRUSSELS BELGIUM | 66200051 | P - ELECTRABEL NV/SA BRUSSELS BELGIUM - 66200051 - EAS horizontal multistage centrifugal pump | 18938 | POC | EUR | 1154000 | 1284286.6 | 2016-05-27 | 2018-06-15 |  | 1154000 |  | 1119380 |  | 5402.5 | [10 empty] | 0 | EUROPE | OE
IPO | RU8135 | 13611 | NNB GENERATION COMPANY LTD UK | 66200052 | P - NNB GENERATION COMPANY LDT - 66200052 - 2 sets of 4+1 pumps | 20288 | POC | EUR | 4983000 | 5634176.28 | 2016-07-01 | 2022-05-28 |  | 4733000 |  | 3536153 |  | 0 | [10 empty] | 0 | EUROPE | OE
IPO | RU8135 | 13611 | NNB GENERATION COMPANY LTD UK | 66200052 | P - NNB GENERATION COMPANY LDT - 66200052 - Engineering / design phase | 20295 | PIT | EUR |  | 297550 | 2016-07-01 | 2022-05-28 |  | 250000 |  | 186750 | [12 empty] | 0 | EUROPE | OE
IPO | RU8135 | 13616 | NNB GENERATION COMPANY LTD UK LONDON | 66200062 | P - NNB GENERATION COMPANY LDT UK LONDON - 66200062 unit 1 | 19308 | POC | EUR | 1223099.5861 | 781498.98 | 2017-07-06 | 2020-12-31 |  | 660049.8142 |  | 495037 | [12 empty] | 0 | EUROPE | OE
IPO | RU8135 | 13616 | NNB GENERATION COMPANY LTD UK LONDON | 66200062 | P - NNB GENERATION COMPANY LDT UK LONDON - 66200062 unit 2 | 19351 | POC | EUR |  | 666650.93 | 2017-07-06 | 2020-12-31 |  | 563049.772 |  | 422287 |  | 2127 | [10 empty] | 0 | EUROPE | OE
IPO | RU8135 | 13616 | NNB GENERATION COMPANY LTD UK LONDON | 66200062 | P - NNB GENERATION COMPANY LDT UK LONDON - 66200062 extended warranty | 22538 | SL | EUR |  | 196426.09 | 2017-07-06 | 2020-12-31 | [16 empty] | 0 | EUROPE | OE
IPO | RU8135 | 13637 | ELECTRABEL NV/SA BRUSSELS BELGIUM | 66200055 | P - ELECTRABEL NV/SA BRUSSELS BELGIUM - 66200055 - GLOBAL EQUIPMENT | 19649 | POC | EUR | 590000 | 647761 | 2016-10-26 | 2018-04-30 |  | 590000 |  | 572300 |  | 430103.1 | [10 empty] | 0 | EUROPE | OE
IPO | RU8135 | 13642 | ELECTRABEL NV/SA BRUSSELS BELGIUM | 66200057 | P - ELECTRABEL NV/SA BRUSSELS BELGIUM -66200057-5 SUBMERSIBLE MOTOR PUMP GROUPS WITH CAN | 4640 | POC | EUR | 764853.1881 | 797070.19 | 2017-07-28 | 2018-01-15 |  | 748492.9946 |  | 726038 |  | 9040.9 | [10 empty] | 0 | EUROPE | OE
IPO | RU8135 | 13642 | ELECTRABEL NV/SA BRUSSELS BELGIUM | 66200057 | P - ELECTRABEL NV/SA BRUSSELS BELGIUM -66200057-LIST OF SPARES PARTS | 4643 | POC | EUR |  | 17421.97 | 2017-07-28 | 2018-01-15 |  | 16360.1934 |  | 15869 | [12 empty] | 0 | EUROPE | OE
IPO | RU8135 | 13665 | ELECTRABEL NV/SA BRUSSELS BELGIUM | 66200058 | P - ELECTRABEL NV/SA BRUSSELS BELGIUM - 66200058 4 vertical motor pump groups | 19577 | POC | EUR | 859779.9981 | 788356.12 | 2017-03-23 | 2019-01-30 |  | 740310.0009 |  | 718101 | [12 empty] | 0 | EUROPE | OE
IPO | RU8135 | 13665 | ELECTRABEL NV/SA BRUSSELS BELGIUM | 66200058 | P - ELECTRABEL NV/SA BRUSSELS BELGIUM - 66200058 spare parts tied to units | 19594 | POC | EUR |  | 127223.6 | 2017-03-23 | 2019-01-30 |  | 119469.9972 |  | 115886 | [12 empty] | 0 | EUROPE | OE
IPO | RU8135 | 15778 | BUTACHIMIE FR CHALAMPE 93 | 52202282 | P - BUTACHIMIE FR CHALAMPE 93 - 52202282 batch A : 25 centrifugal pumps | 19624 | POC | EUR | 1530364.0025 | 875892.8 | 2017-06-29 | 2018-06-13 |  | 766780.0053 |  | 690102 |  | 657162 |  |  |  |  | 332433 |  | 457906 |  | 2018-05-30 | 1 | 0 | EUROPE | OE
IPO | RU8135 | 15778 | BUTACHIMIE FR CHALAMPE 93 | 52202282 | P - BUTACHIMIE FR CHALAMPE 93 - 52202282 Batch A : 4 capital spare part | 19626 | POC | EUR |  | 167164.18 | 2017-06-29 | 2018-06-13 |  | 146339.9982 |  | 131706 |  | 32587 | [10 empty] | 0 | EUROPE | OE
IPO | RU8135 | 15778 | BUTACHIMIE FR CHALAMPE 93 | 52202282 | P - BUTACHIMIE FR CHALAMPE 93 - 52202282 batch B : 12 centrifugal pumps | 19633 | POC | EUR |  | 373769.7 | 2017-06-29 | 2018-06-13 |  | 327208.0014 |  | 294487 |  | 40569 | [10 empty] | 0 | EUROPE | OE
IPO | RU8135 | 15778 | BUTACHIMIE FR CHALAMPE 93 | 52202282 | P - BUTACHIMIE FR CHALAMPE 93 - 52202282 batch C : 7 centrifugal pumps | 19640 | POC | EUR |  | 241459.37 | 2017-06-29 | 2018-06-13 |  | 211379.9965 |  | 190242 |  | 56357 | [10 empty] | 0 | EUROPE | OE
IPO | RU8135 | 15778 | BUTACHIMIE FR CHALAMPE 93 | 52202282 | P - BUTACHIMIE FR CHALAMPE 93 - 52202282 batch D : 1 centrifugal pumps | 19644 | POC | EUR |  | 43178.94 | 2017-06-29 | 2018-06-13 |  | 37800 |  | 34020 |  | 19629 | [10 empty] | 0 | EUROPE | OE
IPO | RU8135 | 15778 | BUTACHIMIE FR CHALAMPE 93 | 52202282 | P - BUTACHIMIE FR CHALAMPE 93 - 52202282 Batch C : capital spare part | 19648 | POC | EUR |  | 46669.81 | 2017-06-29 | 2018-06-13 |  | 40856.0011 |  | 36770 |  | 20768 | [10 empty] | 0 | EUROPE | OE
IPO | RU8135 | 15788 | CACG FR TARBES 65 | 17200952 | P - CACG FR TARBES 65 - 17200952 7 Vertical Multi-cell pumps | 19438 | POC | EUR | 592677 | 621853.33 | 2017-04-11 | 2018-02-28 |  | 592677 |  | 495969 |  | 495969 | [10 empty] | 0 | EUROPE | OE
IPO | RU8135 | 15793 | GE ENERGY BELFORT 90 | 56200328 | P - GE ENERGY BELFORT 90 - 56200328 Liquid fuel pump modul | 19136 | POC | EUR | 511414.3937 | 255053.79 | 2017-05-15 | 2018-02-28 |  | 226895.9968 |  | 232272 |  | 231742.2 |  |  |  |  | 231742 | [5 empty] | 0 | EUROPE | OE
IPO | RU8135 | 15793 | GE ENERGY BELFORT 90 | 56200328 | P - GE ENERGY BELFORT 90 - 56200328 water injection pump modul | 19169 | POC | EUR |  | 319827.13 | 2017-05-15 | 2018-02-28 |  | 284518.3969 |  | 231742 |  | 232272.4 |  |  |  | 2018-03-30 | 232272 | [5 empty] | 0 | EUROPE | OE
IPO | RU8135 | 15798 | TOTAL RAFFINAGE FR LAMEDE 13 TECHNIP | 57200600 | P- TOTAL RAFFINAGE FR LAMEDE -57200600-API 610 & ISO 5199 NEW CENTRIFUGAL PUMPS | 18528 | POC | EUR | 465575 | 474348.84 | 2016-12-28 | 2018-01-31 |  | 465575 | 32590 | 442600 |  | 443575.8 | [10 empty] | 0 | EUROPE | OE
IPO | RU8135 | 15820 | AZMET SOUTH AFRICA KEMPTON PARK | 51201359 | P - AZMET SOUTH AFRICA KEMPTON PARK - 51201359 3 batch of motor driven pump + spare | 19213 | POC | USD | 351817.01 | 339227.01 | 2017-05-31 | 2018-01-31 |  | 339227.01 |  | 240757 |  | 240757.3 |  |  |  |  | 240757 |  |  | 0 |  |  | 0 | SAFRICA | OE
IPO | RU8135 | 15820 | AZMET SOUTH AFRICA KEMPTON PARK | 51201359 | P - AZMET SOUTH AFRICA KEMPTON PARK - 51201359 spare parts for 2 years operation | 19218 | POC | USD |  | 12590 | 2017-05-31 | 2018-01-31 |  | 12590 |  | 7943 |  | 7943 |  |  |  |  | 5626 | [5 empty] | 0 | SAFRICA | OE
IPO | RU8135 | 15826 | SAFARI COMPANY SAUDI ARABIA RI | 51201274 | P - SAFARI COMPANY SAUDI ARABIA-51201274-4 Vertical pumps+ Motor + Spares | 18859 | POC | USD | 334077 | 334077 | 2017-03-05 | 2018-01-31 |  | 334077 |  | 275856 |  | 178908.8 | [7 empty] | 0 |  |  | 0 | MIDEAST | OE
IPO | RU8135 | 18801 | ESSO RAFFINAGE NOTREDAMEGRAVENCHON 76 | 771000184 | P - ESSO RAFFINAGE NOTREDAMEGRAVENCHON 76 - 771000184 5 Multi types pumps | 20149 | POC | EUR | 310056.002 | 371943.18 | 2018-01-30 | 2018-05-30 |  | 310056.002 |  | 186034 |  | 78135.9 | [10 empty] | 0 | EUROPE | AM
IPO | RU8135 | 20776 | OTV MARSEILLE | 17200937 | P - OTV MARSEILLE 13 - 17200937 - 5 group of pumps + testing + spare parts + installation | 20840 | POC | EUR | 770000 | 814275 | 2017-03-07 | 2018-03-31 |  | 770000 |  | 619352 |  | 599192 |  |  |  | 2018-04-01 | [6 empty] | 0 | EUROPE | OE
IPO | RU8135 | 20781 | STEREAU | 771000016 | P - STEREAU FR MAUREPAS 78 - 771000016 - work done | 20842 | POC | EUR | 1601564.207 | 1132893.2 | 2017-05-31 | 2018-10-31 |  | 1039828.5452 |  | 727880 |  | 603654.1 |  |  |  |  | 62027.17 |  | 35745 |  | 2018-05-30 | 1 | 0 | EUROPE | AM
IPO | RU8135 | 20781 | STEREAU | 771000016 | P - STEREAU FR MAUREPAS 78 - 771000016 - Remaining services to provide Jan 2018 | 20843 | POC | EUR |  | 318839.39 | 2017-05-31 | 2018-10-31 |  | 98233 |  | 68763 |  | 62027.2 | [10 empty] | 0 | EUROPE | AM
IPO | RU8135 | 20781 | STEREAU | 771000016 | P - STEREAU FR MAUREPAS 78 - 771000016 - Remaining services to provide Oct 2018 | 20882 | POC | EUR |  | 1431514.85 | 2017-05-31 | 2018-10-31 |  | 463502.6618 |  | 324452 |  | 0 | [10 empty] | 0 | EUROPE | AM
IPO | RU8135 | 20787 | EAU DU GRAND LYON FR | 771000120 | P - EAU DU GRAND LYON FR TSA10462 - 771000120 hydraullic pump + testing + installation | 20852 | POC | EUR | 341940.3396 | 372544 | 2017-05-19 | 2018-02-15 |  | 341940.3396 |  | 219725 |  | 219725 |  |  |  | 2018-04-01 | 220282.63 | [5 empty] | 0 | EUROPE | AM
IPO | RU8135 | 20797 | LYONDELL CHIMIE | 771000103 | P - LYONDELL CHIMIE FR FOS 13 - 771000103 1 pump | 20878 | POC | EUR | 240162.7235 | 259255.66 | 2017-02-23 | 2018-01-31 |  | 240162.7235 |  | 181757 |  | 181756.5 |  |  |  | 2018-04-01 | [6 empty] | 0 | EUROPE | AM
IPO | RU8135 | 22081 | SENER INGENIERIA Y SISTEMAS SA | 56200357 | P - SENER INGENIERIA Y SISTEMAS SA SPAIN GETXO -56200357-Condensate pumps | 22398 | POC | EUR | 383975 | 228200.48 | 2018-02-12 | 2018-09-27 |  | 186926.9987 |  | 135019 |  | 3763.5 | [10 empty] | 0 | EUROPE | OE
IPO | RU8135 | 22081 | SENER INGENIERIA Y SISTEMAS SA | 56200357 | P - SENER INGENIERIA Y SISTEMAS SA SPAIN GETXO -56200357-Circulating pumps | 22399 | POC | EUR |  | 240556.2 | 2018-02-12 | 2018-09-27 |  | 197048.0013 |  | 142330 |  | 8456.8 | [10 empty] | 0 | EUROPE | OE
IPO | RU8135 | 22085 | VEOLIA | 17200989 | P - VEOLIA TSA61043 FR LILLE 59 - 17200989 | 22341 | POC | EUR | 295595.9987 | 354596.96 | 2018-01-18 | 2018-10-01 |  | 295595.9987 |  | 251257 |  | 24866.8 | [10 empty] | 0 | EUROPE | OE
IPO | RU8135 | 22088 | ASSAREL MEDET JSC | 51201559 | P-ASSAREL MEDET JSC -51201559-Pumps | 22350 | POC | EUR | 203799.5169 | 224682 | 2018-02-02 | 2018-11-23 |  | 180903.3816 |  | 148341 |  | 4219.1 | [10 empty] | 0 | EUROPE | OE
IPO | RU8135 | 22088 | ASSAREL MEDET JSC | 51201559 | P-ASSAREL MEDET JSC -51201559-Spares | 22351 | POC | EUR |  | 28437 | 2018-02-02 | 2018-11-23 |  | 22896.1353 |  | 18775 | [12 empty] | 0 | EUROPE | OE
IPO | RU8135 | 23451 | GE ENERGY PRODUCTS FRANCE SNC | 56200361 | P - GE ENERGY BELFORT - 56200361-SKID BATCH 1 : 01 LIQUID FUEL PUMP MODULE + 01 WATER INJECTION PUMP MODULE + 01 PUMP GROUP | 23453 | POC | EUR | 903300 | 556717.3 | 2018-02-28 | 2019-03-04 |  | 450150 |  | 364622 |  | 44544.9 | [10 empty] | 0 | EUROPE | OE
IPO | RU8135 | 23451 | GE ENERGY PRODUCTS FRANCE SNC | 56200361 | P - GE ENERGY BELFORT - 56200361-SKID BATCH 2 : 01 LIQUID FUEL PUMP MODULE + 01 WATER INJECTION PUMP MODULE + 01 PUMP GROUP | 23693 | POC | EUR |  | 560443.3 | 2018-02-28 | 2019-03-04 |  | 453150 |  | 367051.5 |  | 34791.6 | [10 empty] | 0 | EUROPE | OE
IPO | RU8135 | 23712 | TOTAL E&P CONGO | 771000201 | P - TOTAL E&P CONGO - 771000201- 01 PUMP MRK3 | 23715 | POC | EUR | 224756.9485 | 58116.84 | 2018-02-23 | 2018-10-16 |  | 46792.9469 |  | 29947.486 |  | 2153.6 | [10 empty] | 0 | OTHERAFRICA | OE
IPO | RU8135 | 23712 | TOTAL E&P CONGO | 771000201 | P - TOTAL E&P CONGO - 771000201- 01 PUMP 3HE2S | 23740 | POC | EUR |  | 141068.64 | 2018-02-23 | 2018-10-16 |  | 113581.8357 |  | 72692.3749 |  | 1796.7 | [10 empty] | 0 | OTHERAFRICA | OE
IPO | RU8135 | 23712 | TOTAL E&P CONGO | 771000201 | P - TOTAL E&P CONGO - 771000201- SPARE PARTS FOR UYD PUMP & SMK PUMP | 23741 | POC | EUR |  | 79962.65 | 2018-02-23 | 2018-10-16 |  | 64382.1659 |  | 45068 |  | 21.8 | [10 empty] | 0 | OTHERAFRICA | OE
IPO | RU8135 | 24431 | MIDNIGHT SUN S.A TOGO | 17200999 | P - MIDNIGHT SUN S.A TOGO - 17200999 - ONE PUMPING SYTEM ( 4 VERTICAL PUMPS VTP 22ENM/1 + 4 MOTORS + ASSOCIATED SPARE PARTS) | 24438 | POC | EUR | 225903.0025 | 275375.76 | 2018-03-27 | 2018-07-27 |  | 225903.0025 |  | 180722.402 |  | 3783 | [10 empty] | 0 | OTHERAFRICA | OE
IPO | RU8135 | 26102 | ASHLAND INDUSTRIES NEDERLAND B.V | 52202327 | P - ASHLAND INDUSTRIES NEDERLAND - 52202327 | 26105 | POC | EUR | 225069.0402 | 274359.16 | 2018-03-30 | 2018-10-19 |  | 225069.0402 |  | 153047 |  | 31831 | [10 empty] | 0 | EUROPE | OE
IPO | RU8135 | 26475 | TECNIMONT SPA ABU DHABI | 217000007 | P - TECNIMONT SPA ABU DHABI - 217000007- 01 Closed Drain Pump | 26478 | POC | EUR | 225000 | 277200 | 2018-04-23 | 2018-09-28 |  | 225000 |  | 180000 |  | 0 | [10 empty] | 0 | EUROPE | OE
IPO | RU8135 | 27136 | FLOW TECHNOLOGIES UAB | 51201613 | P - FLOW TECHNOLOGIES LITHUANIA - 51201613 - 3 BARESHAT PUMPS TYPE LNN | 27139 | POC | EUR | 238000 | 293216 | 2018-04-26 | 2018-12-21 |  | 238000 |  | 197540 |  | 1904.9 | [10 empty] | 0 | EUROPE | OE
IPO | RU8135 | 27181 | JGC GULF INTERNATIONAL CO. LTD | 55200696 | P - JGC GULF INTERNATIONAL - 55200696 - 12 pumps and commissioning spares | 27226 | POC | EUR | 1149580 | 1416282.56 | 2018-04-23 | 2019-01-01 |  | 1149580 |  | 919664 |  | 0 | [10 empty] | 0 | MIDEAST | OE
IPO | RU8135 | 27249 | TOTAL RAFFINAGE FRANCE | 771000214 | P - TOTAL RAFFINAGE GRANDPUITS - 771000214 - Upgrade of 2 RPKN 100-32 PUMPS + spares + installation | 27250 | POC | EUR | 238922.0617 | 124859.4 | 2018-04-27 | 2018-08-08 |  | 101346.9156 |  | 52700 | [12 empty] | 0 | EUROPE | AM
IPO | RU8135 | 27249 | TOTAL RAFFINAGE FRANCE | 771000214 | P - TOTAL RAFFINAGE GRANDPUITS - 771000214 - Upgrade of 2 HNN132 PUMPS + spares + installation | 27318 | POC | EUR |  | 169492.58 | 2018-04-27 | 2018-08-08 |  | 137575.1461 |  | 71539 | [12 empty] | 0 | EUROPE | AM
IPO | RU8135 | 27674 | ANGOLA LNG LTD | 771000216 | P - ANGOLA LNG LTD - 771000216 | 27676 | POC | EUR | 389672.7922 | 480076.88 | 2018-04-27 | 2018-12-14 |  | 389672.7922 | [14 empty] | 0 | OTHERAFRICA | AM
IPO | RU8165 | 23747 | REGIE DES EAUX MONTPELLIER | 721000127 | P - REGIE DES EAUX MONTPELLIER - 721000127 - ONE PUMPING SYSTEM (2 groups of pumps ) + INSTALLATION + RENOVATION ( immaterial in the context of the contract) | 23750 | POC | EUR | 673040.9984 | 835916.92 | 2017-08-14 | 2019-02-28 |  | 673040.9984 | [14 empty] | 0 | EUROPE | AM
FCO | RU8179 | 5107 | ThyssenKrupp Marine | 5100094811 | P - ThyssenKrupp Marine - 5100094811 | 5109 | POC | EUR | 241756.6215 | 5740.8 | 2015-06-16 | 2019-04-30 |  | 5225.0842 |  | 1498 |  | 1498 |  |  |  | 2018-05-09 |  |  | 147977 |  | 2018-05-09 | 3100371949 | 0 | EUROPE | OE
FCO | RU8179 | 5107 | ThyssenKrupp Marine | 5100094811 | P - ThyssenKrupp Marine - 5100094811 | 5360 | POC | EUR |  | 156841.2 | 2015-06-16 | 2019-04-30 |  | 142751.6155 |  | 52753 |  | 52753 |  |  |  | 2018-05-09 | [6 empty] | 0 | EUROPE | OE
FCO | RU8179 | 5107 | ThyssenKrupp Marine | 5100094811 | P - ThyssenKrupp Marine - 5100094811 | 5361 | POC | EUR |  | 22889.27 | 2015-06-16 | 2019-04-30 |  | 20833.0481 |  | 14390 |  | 12136 | [10 empty] | 0 | EUROPE | OE
FCO | RU8179 | 5107 | ThyssenKrupp Marine | 5100094811 | P - ThyssenKrupp Marine - 5100094811 | 5362 | POC | EUR |  | 5690.72 | 2015-06-16 | 2019-04-30 |  | 5179.503 |  | 2242 |  | 2106 | [10 empty] | 0 | EUROPE | OE
FCO | RU8179 | 5107 | ThyssenKrupp Marine | 5100094811 | P - ThyssenKrupp Marine - 5100094811 | 5363 | POC | EUR |  | 60474.96 | 2015-06-16 | 2019-04-30 |  | 55042.2863 |  | 28512 |  | 4714 | [10 empty] | 0 | EUROPE | OE
FCO | RU8179 | 5107 | ThyssenKrupp Marine | 5100094811 | P - ThyssenKrupp Marine - 5100094811 | 5364 | POC | EUR |  | 13981.05 | 2015-06-16 | 2019-04-30 |  | 12725.0842 |  | 6490 | [12 empty] | 0 | EUROPE | OE
FCO | RU8179 | 5186 | ThyssenKrupp Marine | 5100094930 | P - ThyssenKrupp Marine - 5100094930 | 5188 | POC | EUR | 245375.4437 | 5826.91 | 2015-06-16 | 2020-04-30 |  | 5303.4586 |  | 2639 |  | 100 | [10 empty] | 0 | EUROPE | OE
FCO | RU8179 | 5186 | ThyssenKrupp Marine | 5100094930 | P - ThyssenKrupp Marine - 5100094930 | 5285 | POC | EUR |  | 159193.78 | 2015-06-16 | 2020-04-30 |  | 144892.8552 |  | 62941 | [12 empty] | 0 | EUROPE | OE
FCO | RU8179 | 5186 | ThyssenKrupp Marine | 5100094930 | P - ThyssenKrupp Marine - 5100094930 | 5287 | POC | EUR |  | 23232.6 | 2015-06-16 | 2020-04-30 |  | 21145.5356 |  | 14506 |  | 6654 | [10 empty] | 0 | EUROPE | OE
FCO | RU8179 | 5186 | ThyssenKrupp Marine | 5100094930 | P - ThyssenKrupp Marine - 5100094930 | 5288 | POC | EUR |  | 5776.02 | 2015-06-16 | 2020-04-30 |  | 5257.1403 |  | 2347 | [12 empty] | 0 | EUROPE | OE
FCO | RU8179 | 5186 | ThyssenKrupp Marine | 5100094930 | P - ThyssenKrupp Marine - 5100094930 | 5289 | POC | EUR |  | 61373.92 | 2015-06-16 | 2020-04-30 |  | 55860.4897 |  | 29767 |  | 944 | [10 empty] | 0 | EUROPE | OE
FCO | RU8179 | 5186 | ThyssenKrupp Marine | 5100094930 | P - ThyssenKrupp Marine - 5100094930 | 5291 | POC | EUR |  | 14190.77 | 2015-06-16 | 2020-04-30 |  | 12915.9643 |  | 6128 | [12 empty] | 0 | EUROPE | OE
FCO | RU8179 | 5371 | Jurong Shipyared Pte. Ltd | 5300017194 | P - Jurong Shipyared - 5300017194 | 5372 | POC | EUR | 2200832.0007 | 2455248.18 | 2016-09-28 | 2018-12-20 |  | 2200832.0007 |  | 1 | [12 empty] | 0 | LA | OE
FCO | RU8179 | 5387 | Hengli Petrochemical | 5300018032 | P - Hengli - 5300018032 | 5389 | POC | EUR | 720000 | 822456 | 2017-06-06 | 2018-01-23 |  | 720000 |  | 540869 |  | 540869 |  |  |  | 2018-02-28 | [6 empty] | 0 | CHINA | OE
FCO | RU8179 | 5419 | BASF SE | 5100105093 | P - BASF SE - 5100105093 | 5420 | POC | EUR | 474392.0054 | 564906 | 2017-09-20 | 2018-03-19 |  | 474392.0054 |  | 475234 |  | 475234 |  |  |  | 2018-05-07 |  |  | 474392 |  | 2018-05-07 | 3100371754 | 0 | EUROPE | OE
FCO | RU8179 | 5741 | Linde AG | 5100104690 | P - Linde 5100104690 | 5742 | POC | EUR | 552013 | 642763.94 | 2017-11-06 | 2018-04-30 |  | 552013 |  | 323124 |  | 323124 | [10 empty] | 0 | EUROPE | OE
FCO | RU8179 | 10384 | China Machinery & Equipment | 5300018180 | P - China Machinery - 5300018180 | 10385 | POC | EUR | 2712736.9932 | 3211880.6 | 2017-08-29 | 2018-03-16 |  | 2712736.9932 |  | 2462687 |  | 2462687 | [10 empty] | 0 | ASIA | OE
FCO | RU8179 | 13021 | Petronas Chemicals Isononanol | 5300018333 | P - Petronas 5300018333 | 13022 | POC | USD | 2524791 | 2524791 | 2017-10-25 | 2018-06-08 |  | 2524791 |  | 1360276 |  | 460558 | [7 empty] | 0 |  |  | 46111 | ASIA | OE
FCO | RU8179 | 13027 | Hyundai Engineering & Construction Co. LTD | 5300018280 | P - Hyundai 5300018280 | 13028 | POC | EUR | 2440478.8131 | 2841693.53 | 2017-11-09 | 2018-06-15 |  | 2440478.8131 |  | 1964518 |  | 1765938 | [10 empty] | 0 | ASIA | OE
FCO | RU8179 | 13181 | Evonik Antwerpen NV | 5100105656 | P - Evonik 5100105656 | 13182 | POC | EUR | 428748.0003 | 510295.87 | 2017-12-06 | 2018-04-27 |  | 428748.0003 |  | 358655 |  | 358655 |  |  |  | 2018-05-25 |  |  | 428748 |  | 2018-05-25 | 3100372716 | 0 | EUROPE | OE
FCO | RU8179 | 13359 | BASF SE | 5100105659 | P - BASF SE - 5100105659 | 13360 | POC | EUR | 696992 | 811577.14 | 2017-11-21 | 2018-05-31 |  | 696992 |  | 773816 |  | 640043 |  |  |  |  | 640043 |  | 147062 |  | 2018-05-30 | 3100372956 | 0 | EUROPE | OE
FCO | RU8179 | 13627 | KT Kinetics 5200048749 | 5200048749 | P - KT Kinetics 5200048749 | 13628 | POC | EUR | 718239 | 855279 | 2017-09-12 | 2018-04-12 |  | 718239 |  | 612907 |  | 192986 | [10 empty] | 28730 | EUROPE | OE
FCO | RU8179 | 17120 | Sinopec Europa GmbH | 5300018022 | P - Sinopec Europa GmbH 5300018022 | 17121 | POC | EUR | 810152 | 925436.06 | 2017-07-11 | 2018-01-31 |  | 810152 |  | 628244 |  | 628244 |  |  |  | 2018-01-09 | [6 empty] | 0 | CHINA | OE
FCO | RU8179 | 22962 | BASF SE | 5100106909 | P - BASF SE - 5100106909 | 22963 | POC | EUR | 281722 | 349898.71 | 2018-02-21 | 2018-06-15 |  | 281722 |  | 284755 |  | 249529 | [6 empty] | 4875 |  | 2018-05-17 | 3100372294 | 0 | EUROPE | OE
IPO | RU8195 | 8955 | NIS j.s.C. Novi Sad | 510600058/540600031/570100509 | P - NIS j.s.C. Novi Sad - PRE3000000/510600058 and 570100509 OEM Equipment and Documents | 15238 | POC | EUR | 3407791 | 3146284.95 | 2017-09-22 | 2018-02-28 |  | 2822726.65 |  | 2709373 |  | 2483886.79 | [10 empty] | 0 | RUSCIS | OE
IPO | RU8195 | 8955 | NIS j.s.C. Novi Sad | 510600058/540600031/570100509 | P - NIS j.s.C. Novi Sad - PRE3000000/540600031 Spare Parts | 15497 | POC | EUR |  | 515134.05 | 2017-09-22 | 2018-02-28 |  | 460064.35 |  | 385777 |  | 342420.09 | [10 empty] | 0 | RUSCIS | AM
IPO | RU8195 | 8955 | NIS j.s.C. Novi Sad | 510600058/540600031/570100509 | P - NIS j.s.C. Novi Sad - PRE300000/570100509 Site Supervision during Installation | 15498 | PIT | EUR |  | 139962.5 | 2017-09-22 | 2018-02-28 |  | 125000 |  | 82210 |  | 0 | [10 empty] | 0 | RUSCIS | AM
IPO | RU8195 | 15756 | AGI Industries Inc. | 110601012 | P - AGI Industries Inc. - 110601012/4112441 (8) Pump/Motor Units | 15900 | POC | USD | 0 | 1307116 | 2017-08-22 | 2018-08-22 |  | 1056112.66 |  | 504023 |  | 170831.23 | [7 empty] | 0 |  |  | 0 | US | OE
IPO | RU8195 | 15946 | L&T Hydrocarton Engineering Ltd. | HYDR/8300-00097/RR | P - L&T Hydrocarbon Engineering Ltd - 83000-0097-RR/150600270,273 Riser Piping Systems | 16061 | POC | EUR | 620952 | 547367.8 | 2017-02-10 | 2018-01-06 |  | 475972 |  | 350012 |  | 290086.21 | [10 empty] | 0 | ASIA | OE
IPO | RU8195 | 15946 | L&T Hydrocarton Engineering Ltd. | HYDR/8300-00097/RR | P - L&T Hydrocarbon Engineering Ltd - 83000-0097-RR/110600974,975 (2) Spare Pumps | 17552 | POC | EUR |  | 166727 | 2017-02-10 | 2018-01-06 |  | 144980 |  | 82476 |  | 42489.75 | [10 empty] | 0 | ASIA | OE
IPO | RU8195 | 21021 | Tedagua | 110601035 | P - Tedagua 110601035/ TE-CE-ALH-17-025 (6) Beach Well Pumps with motors (includes one spare) | 21023 | POC | EUR | 340494 | 353902.6 | 2018-01-26 | 2018-08-22 |  | 340494 |  | 227217 |  | 77169.29 |  | 34049.4 | [8 empty] | 0 |  | OE
EPO | RU8225 | 4464 | CHINA HUANQIU CONTRACTING & ENGINEERING CORPORATION (HQCEC) | 22213111 | P - China Huanqiu Contracting & Engineering corporation-ETL130063-POB 1 - Feed pump (0203-P-102A & 0203-P-103) | 4604 | POC | USD | 340020 | 2358680 | 2013-12-01 | 2018-02-02 | [9 empty] | 2018-03-14 |  |  |  | 0 |  |  | 84404 | ASIA | OE
EPO | RU8225 | 4464 | CHINA HUANQIU CONTRACTING & ENGINEERING CORPORATION (HQCEC) | 22213111 | P - China Huanqiu Contracting & Engineering corporation-ETL130063-POB 2- Feed pump (0203-P-102B) | 4605 | POC | USD |  | 1341460 | 2013-12-01 | 2018-02-02 | [9 empty] | 2018-03-14 | [6 empty] | 0 | ASIA | OE
EPO | RU8225 | 4464 | CHINA HUANQIU CONTRACTING & ENGINEERING CORPORATION (HQCEC) | 22213111 | P - China Huanqiu Contracting & Engineering corporation-ETL130063-POB 3 - Spareparts | 4606 | POC | USD |  | 312120 | 2013-12-01 | 2018-02-02 |  | 312120 |  | 173082 |  | 171794 |  | 0 | [8 empty] | 0 | ASIA | AM
EPO | RU8225 | 4464 | CHINA HUANQIU CONTRACTING & ENGINEERING CORPORATION (HQCEC) | 22213111 | P - China Huanqiu Contracting & Engineering corporation-ETL130063-POB 4 - training installation supervision | 4607 | POC | USD |  | 27900 | 2013-12-01 | 2018-02-02 |  | 27900 |  | 7782 |  | 213 |  | 0 | [8 empty] | 0 | ASIA | OE
EPO | RU8225 | 4756 | Sinopec Europa GmbH | 22217029 | P-SINOPEC EUROPA GMBH-ETL170062-POB 1 HP Amine pump and HPRT | 5053 | POC | USD | 1731558 | 1418690.4 | 2017-05-05 | 2018-03-28 |  | 1418690 |  | 1550233 |  | 1240869 |  | 9480 | [5 empty] | 0 |  |  | 0 | ASIA | OE
EPO | RU8225 | 4756 | Sinopec Europa GmbH | 22217029 | P-SINOPEC EUROPA GMBH-ETL170062-POB 2 Startup spare parts | 5054 | POC | USD |  | 301079.85 | 2017-05-05 | 2018-03-28 |  | 301080 |  | 156364 |  | 96963 |  | 0 | [8 empty] | 0 | ASIA | AM
EPO | RU8225 | 4756 | Sinopec Europa GmbH | 22217029 | P-SINOPEC EUROPA GMBH-ETL170062-POB 3 Jobsite service installation and training | 5055 | POC | USD |  | 11787.75 | 2017-05-05 | 2018-03-28 |  | 11788 |  | 12014 |  | 0 |  | 0 | [8 empty] | 0 | ASIA | OE
EPO | RU8225 | 5829 | CHINA HUANQIU CONTRACTING & ENGINEERING CORP (HQC) | ETL170007 | P-CHINA HUANQIU CONTRACTING & ENGINEERING CORP (HQC)-ETL170007-P-CHINA HUANQIU-ETL170007-PUMP SKID 1 | 5836 | POC | USD | 0 | 1176386.94 | 2017-03-31 | 2018-02-05 |  |  | 63745 | 1140067 |  | 959331 |  | 7065 | [5 empty] | 0 |  |  | 0 | ASIA | OE
EPO | RU8225 | 5829 | CHINA HUANQIU CONTRACTING & ENGINEERING CORP (HQC) | ETL170007 | P-CHINA HUANQIU CONTRACTING & ENGINEERING CORP (HQC)-ETL170007-P-CHINA HUANQIU-ETL170007-PUMP SKID 2 | 5837 | POC | USD |  | 1176386.94 | 2017-03-31 | 2018-02-05 |  |  | 63745 | 1140067 |  | 959331 |  | 7065 | [8 empty] | 0 | ASIA | OE
EPO | RU8225 | 5829 | CHINA HUANQIU CONTRACTING & ENGINEERING CORP (HQC) | ETL170007 | P-CHINA HUANQIU CONTRACTING & ENGINEERING CORP (HQC)-ETL170007-P-CHINA HUANQIU-ETL170007-SPARE PARTS | 5838 | POC | USD |  | 158764.42 | 2017-03-31 | 2018-02-05 |  |  | 5005 | 68118 |  | 55831 |  | 0 | [8 empty] | 0 | ASIA | AM
EPO | RU8225 | 5829 | CHINA HUANQIU CONTRACTING & ENGINEERING CORP (HQC) | ETL170007 | P-CHINA HUANQIU CONTRACTING & ENGINEERING CORP (HQC)-ETL170007-P-CHINA HUANQIU-ETL170007-SERVICE | 5839 | POC | USD |  | 24866.7 | 2017-03-31 | 2018-02-05 |  |  | 1000 | 18718 |  | 0 |  | 0 | [8 empty] | 0 | ASIA | OE
EPO | RU8225 | 6096 | ESSO NEDERLAND BV | ETL177176 | P-ESSO NEDERLAND BV-ETL177176 | 6102 | POC | EUR | 273485 | 309913.2 | 2017-09-15 | 2018-06-01 |  | 273485 |  | 288000 |  | 92951 |  | 0 | [8 empty] | 0 | EUROPE | AM
EPO | RU8225 | 8993 | DANGOTE OIL REFINING COMPANY LIMITED | 28970298 | P-DANGOTE OIL REFINING- POb1: ETL170064/65 | 16941 | POC | USD | 12331775 | 1213956 | 2017-09-30 | 2018-11-15 |  | 1213956 |  | 866000 |  | 415961 |  | 30849 | [5 empty] | 0 |  |  | 100213 | OTHERAFRICA | OE
EPO | RU8225 | 8993 | DANGOTE OIL REFINING COMPANY LIMITED | 28970298 | P-DANGOTE OIL REFINING- POb2: ETL170066/67 | 16942 | POC | USD |  | 1196618 | 2017-09-30 | 2018-11-15 |  | 1196618 |  | 765184 |  | 242146 |  | 33212 | [8 empty] | 0 | OTHERAFRICA | OE
EPO | RU8225 | 8993 | DANGOTE OIL REFINING COMPANY LIMITED | 28970298 | P-DANGOTE OIL REFINING- POb3: ETL170068/73 | 16943 | POC | USD |  | 7031492 | 2017-09-30 | 2018-11-15 |  | 7031492 |  | 6126818 |  | 261368 |  | 656276 | [8 empty] | 0 | OTHERAFRICA | OE
EPO | RU8225 | 8993 | DANGOTE OIL REFINING COMPANY LIMITED | 28970298 | P-DANGOTE OIL REFINING- POb4: ETL170074/79 | 16944 | POC | USD |  | 2889709 | 2017-09-30 | 2018-11-15 |  | 2889709 |  | 3232180 |  | 123858 |  | 187117 | [8 empty] | 0 | OTHERAFRICA | OE
EPO | RU8225 | 10060 | JSC MOZYR OIL REFINERY | 24310716 | P-JSC MOZYR OIL REFINERY-ETL170001 POB 1 | 10911 | POC | EUR | 3430000 | 3618307 | 2016-12-28 | 2018-01-31 |  | 3430000 |  | 3917447 |  | 2939126 |  | 135236 | [8 empty] | 102799 | RUSCIS | OE
EPO | RU8225 | 10065 | ZHONGHAI PETROCHEMICAL (YINGKOU) CO | 22216035 | P-ZHONGHAI PETROCHEMICAL (YINGKOU) CO-ETL160005 | 16362 | POC | EUR | 1920000 | 2135904 | 2016-03-31 | 2018-03-31 |  | 1920000 |  | 1550863 |  | 428303 |  | 0 | [8 empty] | 48000 | CHINA | OE
EPO | RU8225 | 11455 | SABIC PETROCHEMICALS B.V. | 64230539 | P-SABIC PETROCHEMICALS B.V.-HCC177824 | 16666 | POC | EUR | 300000 | 355800 | 2017-10-02 | 2018-06-30 |  | 300000 |  | 240000 |  | 44302 |  | 0 | [8 empty] | 0 | EUROPE | AM
EPO | RU8225 | 11475 | MAVEG INDUSTRIEAUSRUSTUNGEN GMBH | 26615010 | P-MAVEG INDUSTRIEAUSRUSTUNGEN GMBH-26615010-P-MAVEG -ETL150044 -PB1: Feed Pump (P3101AB) | 15541 | POC | EUR | 0 | 2593094.29 | 2015-06-19 | 2018-03-31 |  |  | 124188 | 3098251 |  | 2945755 | [10 empty] | 0 | RUSCIS | OE
EPO | RU8225 | 11475 | MAVEG INDUSTRIEAUSRUSTUNGEN GMBH | 26615010 | P-MAVEG INDUSTRIEAUSRUSTUNGEN GMBH-26615010-P-MAVEG -ETL150044 -PB2: Feed Pump (P3111AB) | 15542 | POC | EUR |  | 2650071.58 | 2015-06-19 | 2018-03-31 |  |  | 122984 | 2371255 |  | 2293765 | [10 empty] | 0 | RUSCIS | OE
EPO | RU8225 | 11475 | MAVEG INDUSTRIEAUSRUSTUNGEN GMBH | 26615010 | P-MAVEG INDUSTRIEAUSRUSTUNGEN GMBH-26615010-P-MAVEG -ETL150044 -PB3: HP Amine pump (P3112AB) | 15543 | POC | EUR |  | 1849855.23 | 2015-06-19 | 2018-03-31 |  |  | 90335 | 1720846 |  | 1648374 | [10 empty] | 0 | RUSCIS | OE
EPO | RU8225 | 12036 | SEPCO ELECTRIC POWER CONSTRUCTION CORPORATION | 22215035 | P - SEPCO ELECTRIC POWER CONSTRUCTION CORPORATION-ETL150019 POb 2 | 16701 | POC | EUR | 9810000 | 10277262 | 2015-04-30 | 2018-04-30 |  | 9810000 | 1134334 | 13763310 |  | 13223958 |  |  |  |  | 3417355 |  | 1273357.8 |  | 2018-05-15 | 8225529088 | 102180 | OTHERAFRICA | OE
EPO | RU8225 | 12036 | SEPCO ELECTRIC POWER CONSTRUCTION CORPORATION | 22215035 | P - SEPCO ELECTRIC POWER CONSTRUCTION CORPORATION-ETL150019 POb 1 | 16702 | POC | EUR |  | 2569315 | 2015-04-30 | 2018-04-30 | [7 empty] | 0 |  | 2017-03-04 | [6 empty] | 0
EPO | RU8225 | 13754 | HONG KONG JIANXIN INDUSTRIAL EQUIPMENT CO., LIMITED | 22213095 | P-HONG KONG JIAXIN INDUSTRIAL EQUIPMENT-ETL130067 -POb 1 | 15550 | POC | EUR | 831494 | 613898.72 | 2013-11-18 | 2018-05-31 |  | 452895 |  | 370314 |  | 351921 |  | 0 | [8 empty] | 20787 | CHINA | OE
EPO | RU8225 | 13754 | HONG KONG JIANXIN INDUSTRIAL EQUIPMENT CO., LIMITED | 22213095 | P-HONG KONG JIAXIN INDUSTRIAL EQUIPMENT-ETL130067 -POb 2 | 15551 | POC | EUR |  | 513190.57 | 2013-11-18 | 2018-05-31 |  | 378599 |  | 247038 |  | 229669 |  | 0 | [8 empty] | 0 | CHINA | OE
EPO | RU8225 | 15395 | EMDAD AVIATION FUEL STORAGE FZCO | 64231218 | P-EMDAD AVIATION FUEL STORAGE FZCO-ETL177303 - PB1 | 15417 | POC | EUR | 688700 | 819690.74 | 2017-12-28 | 2018-10-25 |  | 688700 |  | 565000 |  | 158885 |  | 24000 | [8 empty] | 0 | MIDEAST | AM
EPO | RU8225 | 15403 | Jacobs Nederland BV - ExxonMobil Chemical Nederland BV | ETL177291 to ETL177297 - 64231079, ETL177291B - 64232153 | P-Jacobs Nederland BV/ExxonMobil Chemical Nederland BV-ETL177291-ETL177297 POb 1 | 15869 | POC | EUR | 328164 | 81703.69 | 2017-11-14 | 2019-02-28 |  | 68077 |  | 53096 |  | 53096 |  | 0 |  | 2018-04-30 | [6 empty] | 0 | EUROPE | AM
EPO | RU8225 | 15403 | Jacobs Nederland BV - ExxonMobil Chemical Nederland BV | ETL177291 to ETL177297 - 64231079, ETL177291B - 64232153 | P-Jacobs Nederland BV/ExxonMobil Chemical Nederland BV-ETL177291-ETL177297 POb 2 | 15870 | POC | EUR |  | 48403.06 | 2017-11-14 | 2019-02-28 |  | 40668 |  | 48750 |  | 31552 |  | 0 | [8 empty] | 0 | EUROPE | AM
EPO | RU8225 | 15403 | Jacobs Nederland BV - ExxonMobil Chemical Nederland BV | ETL177291 to ETL177297 - 64231079, ETL177291B - 64232153 | P-Jacobs Nederland BV/ExxonMobil Chemical Nederland BV-ETL177291-ETL177297 POb 3 | 15871 | POC | EUR |  | 41692.71 | 2017-11-14 | 2019-02-28 |  | 35030 |  | 28500 |  | 16043 |  | 0 | [8 empty] | 0 | EUROPE | AM
EPO | RU8225 | 15403 | Jacobs Nederland BV - ExxonMobil Chemical Nederland BV | ETL177291 to ETL177297 - 64231079, ETL177291B - 64232153 | P-Jacobs Nederland BV/ExxonMobil Chemical Nederland BV-ETL177291-ETL177297 POb 4 | 15872 | POC | EUR |  | 54342.15 | 2017-11-14 | 2019-02-28 |  | 45658 |  | 37500 |  | 16821 |  | 0 | [8 empty] | 0 | EUROPE | AM
EPO | RU8225 | 15403 | Jacobs Nederland BV - ExxonMobil Chemical Nederland BV | ETL177291 to ETL177297 - 64231079, ETL177291B - 64232153 | P-Jacobs Nederland BV/ExxonMobil Chemical Nederland BV-ETL177291-ETL177297 POb 5 | 15873 | POC | EUR |  | 64005.37 | 2017-11-14 | 2019-02-28 |  | 53777 |  | 48500 |  | 28912 |  | 0 | [8 empty] | 0 | EUROPE | AM
EPO | RU8225 | 15403 | Jacobs Nederland BV - ExxonMobil Chemical Nederland BV | ETL177291 to ETL177297 - 64231079, ETL177291B - 64232153 | P-Jacobs Nederland BV/ExxonMobil Chemical Nederland BV-ETL177291-ETL177297 POb 6 | 15874 | POC | EUR |  | 50556.13 | 2017-11-14 | 2019-02-28 |  | 42477 |  | 35000 |  | 20735 |  | 0 | [8 empty] | 0 | EUROPE | AM
EPO | RU8225 | 15403 | Jacobs Nederland BV - ExxonMobil Chemical Nederland BV | ETL177291 to ETL177297 - 64231079, ETL177291B - 64232153 | P-Jacobs Nederland BV/ExxonMobil Chemical Nederland BV-ETL177291-ETL177297 POb 7 | 15875 | POC | EUR |  | 50556.13 | 2017-11-14 | 2019-02-28 |  | 42477 |  | 35000 |  | 27008 |  | 0 | [8 empty] | 0 | EUROPE | AM
EPO | RU8225 | 15424 | LUKOIL Neftohim Burgas AD | 64231166 | P - LUKOIL NEFTOHIM BURGAS AD - ETL177300 | 15548 | POC | EUR | 462937 | 545015.53 | 2017-11-16 | 2018-06-18 |  | 462937 |  | 343656 |  | 958 |  | 0 |  | 2018-04-30 | [6 empty] | 0 | EUROPE | AM
EPO | RU8225 | 15535 | Fortum Power and Heat Oy | ETL177330 | P-Fortum Power and Heat Oy-ETL177330 | 15557 | POC | EUR | 767093 | 914275.1 | 2017-11-21 | 2018-06-29 |  | 767093 |  | 640000 |  | 124147 |  | 0 |  |  |  |  | 36000 |  | 2018-05-25 | 8225529120 | 0 | EUROPE | AM
EPO | RU8225 | 15844 | BASF SE | 30317410 | P- BASF SE- ETL 64231305 | 15922 | POC | EUR | 299448 | 348677.25 | 2017-11-02 | 2018-04-06 |  | 299448 | [7 empty] | 2018-03-31 | [6 empty] | 0 | EUROPE | AM
EPO | RU8225 | 15880 | SHELL NEDERLAND | 64231095 | P - SHELL NEDERLAND CHEMIE B.V. - HCC177841 POb 1 | 16304 | POC | EUR | 593775 | 699051 | 2017-11-16 | 2018-11-15 |  | 593775 |  | 500000 |  | 77827 |  | 0 |  |  |  |  | 89066.25 |  | 2018-05-17 | 8225529099 | 0 | EUROPE | AM
EPO | RU8225 | 16029 | WATERSCHAP DRENTS OVERIJSSELSE DELTA | 64230701 | P - WS DRENTS OVERIJSSELSE DELTA - HCC177828 POb 1 Pump P4 | 16634 | POC | EUR | 1145648 | 368326 | 2017-10-25 | 2018-12-31 |  | 314057 |  | 366873 |  | 112159 |  | 44163 | [8 empty] | 0 | EUROPE | AM
EPO | RU8225 | 16029 | WATERSCHAP DRENTS OVERIJSSELSE DELTA | 64230701 | P - WS DRENTS OVERIJSSELSE DELTA - HCC177828 POb 2 temp pump | 16937 | POC | EUR |  | 338288 | 2017-10-25 | 2018-12-31 |  | 288445 |  | 260855 |  | 25082 |  | 0 | [8 empty] | 0 | EUROPE | AM
EPO | RU8225 | 16029 | WATERSCHAP DRENTS OVERIJSSELSE DELTA | 64230701 | P - WS DRENTS OVERIJSSELSE DELTA - HCC177828 POb 3 Pump P-1/2 | 16945 | POC | EUR |  | 637002 | 2017-10-25 | 2018-12-31 |  | 543146 |  | 448928 |  | 69320 |  | 0 | [8 empty] | 0 | EUROPE | AM
EPO | RU8225 | 16030 | Waterschap Rivierenland | 64228351 | P- WATERSCHAP RIVIERENLAND- HCC167052- POb 1 | 16629 | POC | EUR | 449805 | 488150.07 | 2017-03-22 | 2018-02-28 |  | 449805 |  | 507643 |  | 507643 |  | 0 |  | 2018-05-23 |  |  | 101206.05 |  | 2018-05-29 | 8225529126 | 0 | EUROPE | AM
EPO | RU8225 | 16030 | Waterschap Rivierenland | 64228351 | P- WATERSCHAP RIVIERENLAND- HCC167052- POb 2 | 16633 | POC | EUR |  | 244075.03 | 2017-03-22 | 2018-02-28 | [7 empty] | 0 |  | 2016-12-28 | [6 empty] | 0
EPO | RU8225 | 18279 | Aramco Overseas Company B.V. | 26217420 | P- Aramco Overseas Company B.V. - 26217420 | 20120 | POC | EUR | 209716 | 251575.7 | 2017-12-15 | 2018-03-30 |  | 209716 |  | 17197 |  | 17197 |  | 0 |  | 2018-04-10 | [6 empty] | 0 | EUROPE | AM
EPO | RU8225 | 18280 | Central Power Generation Company Ltd (Wapda) | 64230442 | P- Wapda- 64230442 | 19866 | POC | EUR | 560794 | 672728.47 | 2017-09-19 | 2018-06-22 |  | 560794 |  | 272145 |  | 0 |  | 37377 | [8 empty] | 0 | EUROPE | AM
EPO | RU8225 | 18281 | Sirte Oil Company | 33870184 | P- Sirte- 33870184 | 19260 | POC | EUR | 905579 | 1086333.06 | 2017-09-13 | 2018-05-13 |  | 905579 |  | 137377 |  | 0 |  | 38364 | [8 empty] | 0 | EUROPE | AM
EPO | RU8225 | 21029 | BP Raffinaderij Rotterdam B.V. | 64230393 - ETL177194 | P - BP Raffinaderij Rotterdam B.V. - ETL177194/64230393 | 21428 | POC | EUR | 214000 | 256714.4 | 2018-01-22 | 2018-05-18 |  | 214000 |  | 150000 |  | 109632 |  | 0 | [8 empty] | 0 | EUROPE | AM
EPO | RU8225 | 21384 | Lukoil Neftohim Burgas AD | 64231578 | P - LUKOIL NEFTOHIM BURGAS AD - 64231578 - POB1 No17635 | 21391 | POC | EUR | 324287 | 63063.85 | 2018-01-26 | 2018-06-04 |  | 52571 |  | 34869 |  | 0 |  | 0 |  | 2018-05-21 | [6 empty] | 0 | EUROPE | AM
EPO | RU8225 | 21384 | Lukoil Neftohim Burgas AD | 64231578 | P - LUKOIL NEFTOHIM BURGAS AD - 64231578 - POB2 No117203 | 21392 | POC | EUR |  | 325950.06 | 2018-01-26 | 2018-06-04 |  | 271716 |  | 188355 |  | 0 |  | 0 |  | 2018-05-21 | [6 empty] | 0 | RUSCIS | AM
EPO | RU8225 | 22345 | RWE GENERATION NL BV | 64231614 - ETL187012 t/m ETL187019B + 64232043 - ETL187055 + 64232240 - ETL187055B | P - RWE GENERATION NL BV - 64231614 - ETL187012-187019B | 22553 | POC | EUR | 306246 | 379597.13 | 2018-02-07 | 2018-05-25 |  | 306246 |  | 249500 |  | 158425 |  | 0 | [8 empty] | 0 | RUSCIS | AM
EPO | RU8225 | 22918 | LUKOIL PERMNEFTEORGINTEZ | 64228560 | P - LUKOIL PERMNEFTEORGINTEZ - ETL167654 + CPO ETL177268 | 22923 | POC | EUR | 350682 | 585386.37 | 2018-05-16 | 2018-09-10 |  | 350682 |  | 358922 |  | 49478 |  | 0 | [8 empty] | 0 | MIDEAST | AM
EPO | RU8225 | 22941 | Aramco Overseas Company BV | 26218113 | P - ARAMCO OVERSEAS COMPANY B.V. - 26218113 | 22946 | POC | EUR | 215772 | 267989.44 | 2018-02-13 | 2018-05-25 |  | 215772 |  | 76455 |  | 0 |  |  |  | 2018-05-25 | [6 empty] | 0 | EUROPE | AM
EPO | RU8225 | 24454 | Technip India Limited | 64231983 - ETL187477-ETL187480 + ETL187491 | P - TECHNIP INDIA LIMITED - ETL187477 to ETL187479 POB1 | 25899 | POC | EUR | 3200000 | 2954150.54 | 2018-03-30 | 2019-04-04 |  | 2422825 |  | 1616957 |  | 69361 |  | 0 |  |  |  |  | 324900 |  | 2018-05-30 | 8225529128 | 0 | INDIA | AM
EPO | RU8225 | 24454 | Technip India Limited | 64231983 - ETL187477-ETL187480 + ETL187491 | P - TECHNIP INDIA LIMITED - ETL187480 + ETL187491 POB2 | 25900 | POC | EUR |  | 1006786.78 | 2018-03-30 | 2019-04-04 |  | 777175 |  | 525043 |  | 2846 |  | 0 | [8 empty] | 0 | INDIA | AM
EPO | RU8225 | 28574 | Evides Waterbedrijf N.V. | HCC187865 - 64232248 | P - EVIDES WATERBEDRIJF N.V. - HCC187865 | 28579 | POC | EUR | 242024.9979 | 292293.59 |  | 2018-07-31 |  | 242024.9979 |  | 222000 |  | 0 |  | 0 | [8 empty] | 0 | EUROPE | AM
AMSS | RU8255 | 4466 | Weir Gabbioneta SRL | RSD-1183161; SYS-1182886; RSD-1183162; SYS-1182897; RSD-1183163; SYS-1182905 | P-Weir Gabbioneta SRL-4500006260-SYSTEM PLAN 53B 1 | 4597 | POC | EUR | 527777.7513 | 134875.95 | 2017-02-21 | 2018-01-31 |  | 123796.1909 | 0 | 128908 |  | 118263 | 0 | 0 | [8 empty] | 0 | EUROPE | OE
AMSS | RU8255 | 4466 | Weir Gabbioneta SRL | RSD-1183161; SYS-1182886; RSD-1183162; SYS-1182897; RSD-1183163; SYS-1182905 | P-Weir Gabbioneta SRL-4500006260-SYSTEM PLAN 53B 2 | 4598 | POC | EUR |  | 308288.21 | 2017-02-21 | 2018-01-31 |  | 282963.0197 | 0 | 294660 |  | 270327 | 0 | 0 | [8 empty] | 0 |  | OE
AMSS | RU8255 | 4466 | Weir Gabbioneta SRL | RSD-1183161; SYS-1182886; RSD-1183162; SYS-1182897; RSD-1183163; SYS-1182905 | P-Weir Gabbioneta SRL-4500006260-SYSTEM PLAN 53B 3 | 4599 | POC | EUR |  | 131849.7 | 2017-02-21 | 2018-01-31 |  | 121018.5406 | 0 | 119697 |  | 109813 | 0 | 0 | [8 empty] | 0 |  | OE
AMSS | RU8255 | 4466 | Weir Gabbioneta SRL | RSD-1183161; SYS-1182886; RSD-1183162; SYS-1182897; RSD-1183163; SYS-1182905 | P-Weir Gabbioneta SRL-4500006260-COMPL SEAL 1 | 4600 | PIT | EUR |  | 18158.34 | 2017-02-21 | 2018-01-31 | [9 empty] | 2017-10-31 | [6 empty] | 0 |  | OE
AMSS | RU8255 | 4466 | Weir Gabbioneta SRL | RSD-1183161; SYS-1182886; RSD-1183162; SYS-1182897; RSD-1183163; SYS-1182905 | P-Weir Gabbioneta SRL-4500006260-COMPL SEAL 2 | 4601 | PIT | EUR |  | 42369.45 | 2017-02-21 | 2018-01-31 | [9 empty] | 2017-10-31 | [6 empty] | 0 |  | OE
AMSS | RU8255 | 4466 | Weir Gabbioneta SRL | RSD-1183161; SYS-1182886; RSD-1183162; SYS-1182897; RSD-1183163; SYS-1182905 | P-Weir Gabbioneta SRL-4500006260-COMPL SEAL 3 | 4602 | PIT | EUR |  | 18158.34 | 2017-02-21 | 2018-01-31 | [9 empty] | 2017-10-31 | [6 empty] | 0 |  | OE
EPO | RU8265 | 3788 | RAMAGUNDAM FERTILIZERS & CHEMICALS LIMITED (RFCL) | 10004372 | P-RAMAGUNDAM FERTILIZERS & CHEMICALS LIMITED (RFCL)-10004372-200-P-1006A/B UREA SOULTION PUMPS | 3797 | POC | INR | 21377560 | 32363.34 | 2017-02-27 | 2018-02-02 |  | 2087936 | 0 | 1761746.752 |  | 1761746.752 | 0 | 0 |  | 2017-12-30 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 3788 | RAMAGUNDAM FERTILIZERS & CHEMICALS LIMITED (RFCL) | 10004372 | P-RAMAGUNDAM FERTILIZERS & CHEMICALS LIMITED (RFCL)-10004372-200-P-1008A/B UREA MELT PUMPS | 3798 | POC | INR |  | 68400.23 | 2017-02-27 | 2018-02-02 |  | 4387351 | 0 | 3701934.0508 |  | 3701934.0508 | 0 | 0 |  | 2017-12-30 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 3788 | RAMAGUNDAM FERTILIZERS & CHEMICALS LIMITED (RFCL) | 10004372 | P-RAMAGUNDAM FERTILIZERS & CHEMICALS LIMITED (RFCL)-10004372-200-P-1013A/B STEAM CONDENSATE PUMPS | 3799 | POC | INR |  | 29675.17 | 2017-02-27 | 2018-02-02 |  | 1945061 | 0 | 1641192.4979 |  | 1641192.4979 | 0 | 0 |  | 2017-12-30 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 3788 | RAMAGUNDAM FERTILIZERS & CHEMICALS LIMITED (RFCL) | 10004372 | P-RAMAGUNDAM FERTILIZERS & CHEMICALS LIMITED (RFCL)-10004372-200-P-1025 A/B OFF SPEC CONDENSTATE RECOVERY PUMPS | 3800 | POC | INR |  | 11278.4 | 2017-02-27 | 2018-02-02 |  | 719644 | 0 | 607217.1176 |  | 607217.1176 | 0 | 0 |  | 2017-11-30 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 3788 | RAMAGUNDAM FERTILIZERS & CHEMICALS LIMITED (RFCL) | 10004372 | P-RAMAGUNDAM FERTILIZERS & CHEMICALS LIMITED (RFCL)-10004372-200-P-1030 A/B CO2 COMPRESSOR CONDENSATE PUMPS | 3801 | POC | INR |  | 11304.99 | 2017-02-27 | 2018-02-02 |  | 721341 | 0 | 608649.0026 |  | 608649.0026 | 0 | 0 |  | 2017-11-30 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 3788 | RAMAGUNDAM FERTILIZERS & CHEMICALS LIMITED (RFCL) | 10004372 | P-RAMAGUNDAM FERTILIZERS & CHEMICALS LIMITED (RFCL)-10004372-200-P-1010A/B STEAM CONDENSATE FLUSHING PUMPS | 3802 | POC | INR |  | 180065.52 | 2017-02-27 | 2018-02-02 |  | 11516227 | 0 | 9717096.4592 |  | 9717096.4592 | 0 | 0 |  | 2017-11-30 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 4820 | CINDA ENGINEERING & CONSTRUCTION PVT LTD., | 10004211 | P-CINDA ENGINEERING & CONSTRUCTION PVT LTD.-10004372-4-P-342 A/B - Glycol Water Pump | 4968 | POC | INR | 27300001 | 244322.94 | 2017-01-23 | 2018-01-29 |  | 16288196 | 0 | 8947595.626 |  | 8947595.626 | 0 | 0 |  | 2018-03-31 |  |  | 724409.8 |  | 2018-05-17 | 22373 | 0 | INDIA | OE
EPO | RU8265 | 4820 | CINDA ENGINEERING & CONSTRUCTION PVT LTD., | 10004211 | P-CINDA ENGINEERING & CONSTRUCTION PVT LTD.-10004372-Spare Pump without baseplate | 4969 | POC | INR |  | 110160.29 | 2017-01-23 | 2018-01-29 |  | 7344019 | 0 | 4034290.554 |  | 4034290.554 | 0 | 0 |  | 2018-03-31 |  |  | 535590.2 |  | 2018-05-17 | 22374 | 0 | INDIA | OE
EPO | RU8265 | 4820 | CINDA ENGINEERING & CONSTRUCTION PVT LTD., | 10004211 | P-CINDA ENGINEERING & CONSTRUCTION PVT LTD.-10004372-Mandatory Spares | 4970 | POC | INR |  | 50516.79 | 2017-01-23 | 2018-01-29 |  | 3367786 | 0 | 1850026.0731 |  | 1850026.0731 | 0 | 0 |  | 2018-03-31 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 4820 | CINDA ENGINEERING & CONSTRUCTION PVT LTD., | 10004211 | P-CINDA ENGINEERING & CONSTRUCTION PVT LTD.-10004372-Supervission Charges for 12 days | 4971 | POC | INR |  | 4500 | 2017-01-23 | 2018-01-29 |  | 300000 | 0 | 164799.0169 |  | 164799.0169 | 0 | 0 |  | 2018-03-31 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 5994 | DANGOTE OIL REFINING COMPANY LIMITED | 10004877 | P-Dangote Oil Refining Company Limited-10004877-Pumps - EX1755003 | 20444 | POC | USD | 5237804 | 1322268.58 | 2017-06-22 | 2018-09-15 |  | 2118418.57 |  | 122570590.8984 |  | 170813.2981 | 4554277.7019 | 0 | [5 empty] | 0 |  |  | 1352187.8199 | OTHERAFRICA | OE
EPO | RU8265 | 5994 | DANGOTE OIL REFINING COMPANY LIMITED | 10004877 | P-Dangote Oil Refining Company Limited-10004877-Pumps - EX1755005 | 20445 | POC | USD |  | 75114 | 2017-06-22 | 2018-09-15 |  | 83337.86 |  | 3575614.6468 |  | 18856.6732 | 575623.5568 | 0 | [8 empty] | 53194.6051 | OTHERAFRICA | OE
EPO | RU8265 | 5994 | DANGOTE OIL REFINING COMPANY LIMITED | 10004877 | P-Dangote Oil Refining Company Limited-10004877-Pumps - EX1765007 | 20447 | POC | USD |  | 287386.4 | 2017-06-22 | 2018-09-15 |  | 287386.4 |  | 14333992.0531 |  | 3796692.5 | [10 empty] | 183438.9083 | OTHERAFRICA | OE
EPO | RU8265 | 5994 | DANGOTE OIL REFINING COMPANY LIMITED | 10004877 | P-Dangote Oil Refining Company Limited-10004877-Pumps - EX1765008 | 20448 | POC | USD |  | 724353.61 | 2017-06-22 | 2018-09-15 |  | 684118.29 |  | 37315913.3008 |  | 8181271.54 |  | 159812 | [8 empty] | 436673.1071 | OTHERAFRICA | OE
EPO | RU8265 | 5994 | DANGOTE OIL REFINING COMPANY LIMITED | 10004877 | P-Dangote Oil Refining Company Limited-10004877-Pumps - EX1785004 | 20449 | POC | USD |  | 2823963.7 | 2017-06-22 | 2018-09-15 |  | 1907623.88 |  | 99692546.9273 |  | 3429308.56 |  | 223008 | [8 empty] | 1217637.4453 | OTHERAFRICA | OE
EPO | RU8265 | 5994 | DANGOTE OIL REFINING COMPANY LIMITED | 10004877 | P-Dangote Oil Refining Company Limited-10004877-Spares - EX1750003 | 20450 | POC | USD |  | 41914 | 2017-06-22 | 2018-09-15 |  | 48257 |  | 2213539.5205 |  | 0 | [10 empty] | 30802.4715 | OTHERAFRICA | OE
EPO | RU8265 | 5994 | DANGOTE OIL REFINING COMPANY LIMITED | 10004877 | P-Dangote Oil Refining Company Limited-10004877-Spares - EX1750005 | 20451 | POC | USD |  | 1557.4 | 2017-06-22 | 2018-09-15 |  | 1299 |  | 98685.3935 |  | 0 | [10 empty] | 829.1525 | OTHERAFRICA | OE
EPO | RU8265 | 5994 | DANGOTE OIL REFINING COMPANY LIMITED | 10004877 | P-Dangote Oil Refining Company Limited-10004877-Spares - EX1760004 | 20452 | POC | USD |  | 14574 | 2017-06-22 | 2018-09-15 |  | 14574 |  | 930327.2489 |  | 163957.5 | [10 empty] | 9302.5928 | OTHERAFRICA | OE
EPO | RU8265 | 5994 | DANGOTE OIL REFINING COMPANY LIMITED | 10004877 | P-Dangote Oil Refining Company Limited-10004877-Spares - EX1760005 | 20453 | POC | USD |  | 32730 | 2017-06-22 | 2018-09-15 |  | 27398 |  | 1950601.8574 |  | 632465 | [10 empty] | 17488.1595 | OTHERAFRICA | OE
EPO | RU8265 | 5994 | DANGOTE OIL REFINING COMPANY LIMITED | 10004877 | P-Dangote Oil Refining Company Limited-10004877-Spares - EX1780004 | 20454 | POC | USD |  | 145899.31 | 2017-06-22 | 2018-09-15 |  | 65391 |  | 5334389.5027 |  | 1972.16 | [10 empty] | 41739.1138 | OTHERAFRICA | OE
EPO | RU8265 | 6773 | BHARAT PETROLEUM CORPORATION LIMITED | 10004581 | P-BHARAT PETROLEUM CORPORATION LIMITED-10004581-SOLVENT SEPARATOR DECANTER PUMP - PDA-P-016A/B | 6905 | POC | INR | 60908165 | 15078.57 | 2017-04-18 | 2018-02-12 |  | 1007678 |  | 849494 |  | 849494 |  |  |  | 2017-11-30 |  |  | 5352592.8 |  | 2018-05-31 | 22563 | 0 | INDIA | OE
EPO | RU8265 | 6773 | BHARAT PETROLEUM CORPORATION LIMITED | 10004581 | P-BHARAT PETROLEUM CORPORATION LIMITED-10004581-RAFFINATE STRIPPER BOTTOM PUMPS -PDA-P-024A/B | 6906 | POC | INR |  | 24411.91 | 2017-04-18 | 2018-02-12 |  | 1619002 |  | 1583441.5531 |  | 1583441.5531 |  |  |  | 2018-03-31 |  |  | 2904699.9 |  | 2018-05-31 | 22564 | 0 | INDIA | OE
EPO | RU8265 | 6773 | BHARAT PETROLEUM CORPORATION LIMITED | 10004581 | P-BHARAT PETROLEUM CORPORATION LIMITED-10004581-CAA RECOVERY VACUUM CONDENSATE PUMP - PDA-P-028A/B | 6907 | POC | INR |  | 15055.44 | 2017-04-18 | 2018-02-12 |  | 1006124 |  | 848191 |  | 848191 |  |  |  | 2017-11-30 |  |  | 1347311.2 |  | 2018-05-31 | 22565 | 0 | INDIA | OE
EPO | RU8265 | 6773 | BHARAT PETROLEUM CORPORATION LIMITED | 10004581 | P-BHARAT PETROLEUM CORPORATION LIMITED-10004581-HQ WATER PUMP PDA-P-030A/B | 6908 | POC | INR |  | 16991.3 | 2017-04-18 | 2018-02-12 |  | 1132464 |  | 957253 |  | 957253 |  |  |  | 2017-11-30 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 6773 | BHARAT PETROLEUM CORPORATION LIMITED | 10004581 | P-BHARAT PETROLEUM CORPORATION LIMITED-10004581-EAA PRODUCT COLUMN REBOILER PUMP PDA-P-032A/B | 6909 | POC | INR |  | 66478.85 | 2017-04-18 | 2018-02-12 |  | 4381820 |  | 3220210.9552 |  | 3220210.9552 |  |  |  | 2018-03-31 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 6773 | BHARAT PETROLEUM CORPORATION LIMITED | 10004581 | P-BHARAT PETROLEUM CORPORATION LIMITED-10004581-EAA PRODUCT COLUMN BOTTOM PUMP PDA-P-033A/B | 6910 | POC | INR |  | 25029.38 | 2017-04-18 | 2018-02-12 |  | 1662128 |  | 1221502.2056 |  | 1221502.2056 |  |  |  | 2018-03-31 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 6773 | BHARAT PETROLEUM CORPORATION LIMITED | 10004581 | P-BHARAT PETROLEUM CORPORATION LIMITED-10004581-DEDIMERIZER RECYLE PUMP PDA-P-037A/B | 6911 | POC | INR |  | 28912.15 | 2017-04-18 | 2018-02-12 |  | 1915348 |  | 1407594.2445 |  | 1407594.2445 |  |  |  | 2018-03-31 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 6773 | BHARAT PETROLEUM CORPORATION LIMITED | 10004581 | P-BHARAT PETROLEUM CORPORATION LIMITED-10004581-CAUSTIC RECIRCULATION PUMP PDA-P-042A/B | 6912 | POC | INR |  | 19086.04 | 2017-04-18 | 2018-02-12 |  | 1268342 |  | 1075266 |  | 1075266 |  |  |  | 2017-11-30 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 6773 | BHARAT PETROLEUM CORPORATION LIMITED | 10004581 | P-BHARAT PETROLEUM CORPORATION LIMITED-10004581-COOLING WATER BOOSTER PUMP PDA-P-043A/B | 6913 | POC | INR |  | 602096.87 | 2017-04-18 | 2018-02-12 |  | 39637875 |  | 27786483.54 |  | 27786483.54 |  |  |  | 2018-03-31 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 6773 | BHARAT PETROLEUM CORPORATION LIMITED | 10004581 | P-BHARAT PETROLEUM CORPORATION LIMITED-10004581-DEMIN WATER BOOSTER PUMP PDA-P-048A/B | 6914 | POC | INR |  | 14220.76 | 2017-04-18 | 2018-02-12 |  | 951122 |  | 801167 |  | 801167 |  |  |  | 2017-11-30 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 6773 | BHARAT PETROLEUM CORPORATION LIMITED | 10004581 | P-BHARAT PETROLEUM CORPORATION LIMITED-10004581-CYCLOEXANE UNLOADING PUMP - PDA-P-072A/B | 6915 | POC | INR |  | 23846.74 | 2017-04-18 | 2018-02-12 |  | 1585072 |  | 1254325.17 |  | 1254325.17 |  |  |  | 2018-03-31 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 6773 | BHARAT PETROLEUM CORPORATION LIMITED | 10004581 | P-BHARAT PETROLEUM CORPORATION LIMITED-10004581-IPAC UNLOADING PUMP PDA-P-073A/B | 6916 | POC | INR |  | 26450.35 | 2017-04-18 | 2018-02-12 |  | 1755166 |  | 1289876.0746 |  | 1289876.0746 |  |  |  | 2018-03-31 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 6773 | BHARAT PETROLEUM CORPORATION LIMITED | 10004581 | P-BHARAT PETROLEUM CORPORATION LIMITED-10004581-ATM CONDENSTATE PUMP (PURE) - PDA-P-070A/B | 6917 | POC | INR |  | 25498.01 | 2017-04-18 | 2018-02-12 |  | 1688204 |  | 1653889.7839 |  | 1653889.7839 |  |  |  | 2018-03-31 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 6773 | BHARAT PETROLEUM CORPORATION LIMITED | 10004581 | P-BHARAT PETROLEUM CORPORATION LIMITED-10004581-ATM CONDENSTATE PUMP (SUSPECT) - PDA-P-070A/B | 6918 | POC | INR |  | 19500.37 | 2017-04-18 | 2018-02-12 |  | 1297820 |  | 1264861.953 |  | 1264861.953 |  |  |  | 2018-03-31 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 6925 | INDIAN OIL CORPORATION LIMITED | 10004691 | P-INDIAN OIL CORPORATION LIMITED-10004691-REVAMPED SPLITTER BOTTOM PUMP - HPX Pumps / 1HPX11A - 803-P-10 A/B | 6932 | POC | INR | 35927969.52 | 32003.05 | 2017-05-16 | 2018-03-10 |  | 2108762 |  | 1587573.7024 |  | 1587573.7024 |  |  |  | 2017-12-31 |  |  | 536233 |  | 2018-05-07 | 22291 | 0 | INDIA | OE
EPO | RU8265 | 6925 | INDIAN OIL CORPORATION LIMITED | 10004691 | P-INDIAN OIL CORPORATION LIMITED-10004691-SPLITTER REFLUX PUMP - HPX Pumps / 3HPX11A - 904-P-02 A/B | 6933 | POC | INR |  | 33484.86 | 2017-05-16 | 2018-03-10 |  | 2206403 |  | 1661081.777 |  | 1661081.777 |  |  |  | 2017-12-31 |  |  | 4826091.76 |  | 2018-05-07 | 22292 | 0 | INDIA | OE
EPO | RU8265 | 6925 | INDIAN OIL CORPORATION LIMITED | 10004691 | P-INDIAN OIL CORPORATION LIMITED-10004691-FIRST STAGE HDS HOT SEPARATOR PUMPS - HPX Pumps / 3HPX11A - 904-P-04 A/B | 6934 | POC | INR |  | 30681.32 | 2017-05-16 | 2018-03-10 |  | 2021670 |  | 1522006.7083 |  | 1522006.7083 |  |  |  | 2017-12-31 |  |  | 4826091.76 |  | 2018-05-07 | 22293 | 0 | INDIA | OE
EPO | RU8265 | 6925 | INDIAN OIL CORPORATION LIMITED | 10004691 | P-INDIAN OIL CORPORATION LIMITED-10004691-FIRST STAGE HDS COLD SEPARATOR PUMPS - HPX Pumps / 3HPX12A - 904-P-06 A/B | 6935 | POC | INR |  | 31698.27 | 2017-05-16 | 2018-03-10 |  | 2088680 |  | 1572454.4961 |  | 1572454.4961 |  |  |  | 2017-12-31 |  |  | 1260165.9 |  | 2018-05-07 | 22290 | 0 | INDIA | OE
EPO | RU8265 | 6925 | INDIAN OIL CORPORATION LIMITED | 10004691 | P-INDIAN OIL CORPORATION LIMITED-10004691-SECOND STAGE HDS FEED PUMPS - HPX Pumps / 3HPX15A - 904-P-07 A/B | 6936 | POC | INR |  | 47988.07 | 2017-05-16 | 2018-03-10 |  | 3162056 |  | 2380541.7908 |  | 2380541.7908 |  |  |  | 2017-12-31 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 6925 | INDIAN OIL CORPORATION LIMITED | 10004691 | P-INDIAN OIL CORPORATION LIMITED-10004691-STABILIZER REFLUX PUMPS - HPX Pumps / 2HPX10A - 904-P-10 A/B | 6937 | POC | INR |  | 29655.3 | 2017-05-16 | 2018-03-10 |  | 1954063 |  | 1471108.9854 |  | 1471108.9854 |  |  |  | 2017-12-31 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 6925 | INDIAN OIL CORPORATION LIMITED | 10004691 | P-INDIAN OIL CORPORATION LIMITED-10004691-STABILIZER HEATER PUMPS - HPX Pumps / 6HPX21B - 904-P-11 A/B | 6938 | POC | INR |  | 53254.62 | 2017-05-16 | 2018-03-10 |  | 3509083 |  | 2641799.2736 |  | 2641799.2736 |  |  |  | 2017-12-31 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 6925 | INDIAN OIL CORPORATION LIMITED | 10004691 | P-INDIAN OIL CORPORATION LIMITED-10004691-RICH AMINE PUMPS - HPX Pumps / 1HPX9A - 904-P-12 A/B | 6939 | POC | INR |  | 26693.46 | 2017-05-16 | 2018-03-10 |  | 1758900 |  | 1324181.1365 |  | 1324181.1365 |  |  |  | 2017-12-31 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 6925 | INDIAN OIL CORPORATION LIMITED | 10004691 | P-INDIAN OIL CORPORATION LIMITED-10004691-CONDENSATE PUMPS - HPX Pumps / 1.5HPX10A - 904-P-20 A/B | 6940 | POC | INR |  | 17603.29 | 2017-05-16 | 2018-03-10 |  | 1159925 |  | 873245.5275 |  | 873245.5275 |  |  |  | 2017-12-31 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 6925 | INDIAN OIL CORPORATION LIMITED | 10004691 | P-INDIAN OIL CORPORATION LIMITED-10004691-RICH AMINE FEED PUMP - HPX Pumps / 2HPX10A - 908-P-01 A/B | 6941 | POC | INR |  | 31346.23 | 2017-05-16 | 2018-03-10 |  | 2065483 |  | 1554990.8654 |  | 1554990.8654 |  |  |  | 2017-12-31 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 6925 | INDIAN OIL CORPORATION LIMITED | 10004691 | P-INDIAN OIL CORPORATION LIMITED-10004691-AMINE REGENERATOR REFLUX PUMP - HPX Pumps / 1HPX9A - 908-P-02 A/B | 6942 | POC | INR |  | 27230.82 | 2017-05-16 | 2018-03-10 |  | 1794308 |  | 1350837.9272 |  | 1350837.9272 |  |  |  | 2017-12-31 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 6925 | INDIAN OIL CORPORATION LIMITED | 10004691 | P-INDIAN OIL CORPORATION LIMITED-10004691-NSU FEED PUMP - HPX Pumps - HPX Pumps / 3HPX13A - 041-PA-001C | 6943 | POC | INR |  | 20851.93 | 2017-05-16 | 2018-03-10 |  | 1373987 |  | 1034400.6497 |  | 1034400.6497 |  |  |  | 2017-12-31 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 6925 | INDIAN OIL CORPORATION LIMITED | 10004691 | P-INDIAN OIL CORPORATION LIMITED-10004691-SHU REACTOR FEED PUMP - WXB Pumps / 4WXB-11A - 904-P-01 A/B | 6944 | POC | INR |  | 162759.69 | 2017-05-16 | 2018-03-10 |  | 10724649.52 |  | 8699493.69 |  | 8699493.69 |  |  |  | 2018-05-04 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 6960 | INDIAN OIL CORPORATION LIMITED | 10004771 | P-INDIAN OIL CORPORATION LIMITED-10004771-CRUDE CHAREG PUMP-Packaging Pumps-1000WUC-4H-6-201-P-01 F | 6965 | POC | INR | 52859018.3567 | 567128.56 | 2017-05-31 | 2018-04-22 |  | 36515672.425 |  | 25872786.7935 |  | 0 | [6 empty] | 1634194.46 |  | 2018-05-09 | 22309 | 0 | INDIA | OE
EPO | RU8265 | 6960 | INDIAN OIL CORPORATION LIMITED | 10004771 | P-INDIAN OIL CORPORATION LIMITED-10004771-Spares for all above tags | 6966 | POC | INR |  | 253830.14 | 2017-05-31 | 2018-04-22 |  | 16343345.9317 |  | 11589901.979 |  | 0 | [6 empty] | 3651254.13 |  | 2018-05-09 | 22308 | 0 | INDIA | OE
EPO | RU8265 | 7002 | BHARAT PETROLEUM CORPORATION LIMITED | 10004896 | P-BHARAT PETROLEUM CORPORATION LIMITED-10004896-Decanted MS Tranfer Pump - VTP Pumps / 10 ELM/7 Stages | 7020 | POC | INR | 33098792.26 | 26311 | 2017-06-29 | 2018-04-08 |  | 1691610.2 |  | 1760193.8344 |  | 1760193.8344 |  |  |  | 2018-05-05 |  |  | 1132420.56 |  | 2018-05-29 | 22502 | 0 | INDIA | OE
EPO | RU8265 | 7002 | BHARAT PETROLEUM CORPORATION LIMITED | 10004896 | P-BHARAT PETROLEUM CORPORATION LIMITED-10004896-Decanted HSD Tranfer Pump - VTP Pumps / 10 ELM/7 Stages | 7021 | POC | INR |  | 24153.39 | 2017-06-29 | 2018-04-08 |  | 1553006.2 |  | 1615824.624 |  | 1615824.624 |  |  |  | 2018-05-05 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 7002 | BHARAT PETROLEUM CORPORATION LIMITED | 10004896 | P-BHARAT PETROLEUM CORPORATION LIMITED-10004896-Slop Transfer Pumps - VTP Pumps / 10 ELM/7 Stages | 7022 | POC | INR |  | 52709.65 | 2017-06-29 | 2018-04-08 |  | 3388977.75 |  | 3526274.8285 |  | 3526274.8285 |  |  |  | 2018-05-05 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 7002 | BHARAT PETROLEUM CORPORATION LIMITED | 10004896 | P-BHARAT PETROLEUM CORPORATION LIMITED-10004896-HSD Day Transfer Pumps - VTP Pumps / 06EJY/06EJH/7 Stages | 7023 | POC | INR |  | 17612.84 | 2017-06-29 | 2018-04-08 |  | 1132420.56 |  | 1178301.6231 |  | 1178301.6231 |  |  |  | 2018-05-05 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 7002 | BHARAT PETROLEUM CORPORATION LIMITED | 10004896 | P-BHARAT PETROLEUM CORPORATION LIMITED-10004896-MS BS3 Cent Pump - HPX Pumps / 8HPX19A - PC-101 A | 7024 | POC | INR |  | 33205.16 | 2017-06-29 | 2018-04-08 |  | 2134932 |  | 1473532.7094 |  | 1473532.7094 |  |  |  | 2018-03-03 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 7002 | BHARAT PETROLEUM CORPORATION LIMITED | 10004896 | P-BHARAT PETROLEUM CORPORATION LIMITED-10004896-MS BS4 Cent Pump - HPX Pumps / 8HPX19A - PC-101 B/C | 7025 | POC | INR |  | 66410.33 | 2017-06-29 | 2018-04-08 |  | 4269864 |  | 2947065.4189 |  | 2947065.4189 |  |  |  | 2018-03-03 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 7002 | BHARAT PETROLEUM CORPORATION LIMITED | 10004896 | P-BHARAT PETROLEUM CORPORATION LIMITED-10004896-HSD BS3 Cent Pump - HPX Pumps / 8HPX19A - PC-102 A/B/C | 7026 | POC | INR |  | 112011.34 | 2017-06-29 | 2018-04-08 |  | 7201791.49 |  | 4970693.3389 |  | 4970693.3389 |  |  |  | 2018-03-03 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 7002 | BHARAT PETROLEUM CORPORATION LIMITED | 10004896 | P-BHARAT PETROLEUM CORPORATION LIMITED-10004896-HSD BS4 Cent Pump - HPX Pumps / 8HPX19A - PC-102 D/E/F | 7027 | POC | INR |  | 112011.34 | 2017-06-29 | 2018-04-08 |  | 7201791 |  | 4970693.3389 |  | 4970693.3389 |  |  |  | 2018-03-03 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 7002 | BHARAT PETROLEUM CORPORATION LIMITED | 10004896 | P-BHARAT PETROLEUM CORPORATION LIMITED-10004896-Ethanol Cent Pump - HPX Pumps / 2HPX10A - PC-103 A/B | 7028 | POC | INR |  | 44733.64 | 2017-06-29 | 2018-04-08 |  | 2873152.32 |  | 1985153.2066 |  | 1985153.2066 |  |  |  | 2018-03-03 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 7002 | BHARAT PETROLEUM CORPORATION LIMITED | 10004896 | P-BHARAT PETROLEUM CORPORATION LIMITED-10004896-Ethanol Unloading Cent Pump - HPX Pumps / 2HPX10A - PC-104 A/B | 7029 | POC | INR |  | 25635.55 | 2017-06-29 | 2018-04-08 |  | 1651246.74 |  | 1137644.4674 |  | 1137644.4674 |  |  |  | 2018-03-03 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 7007 | Mangalore Refinery And Petrochemicals Limited | 10004785 | P-Mangalore Refinery And Petrochemicals Limited-10004785-New Charge Pump - Packaging Pumps - GA-41790 - 3x12 DMX-B | 7018 | POC | INR | 21500000 | 216799.44 | 2017-06-06 | 2018-05-01 |  | 14020960 |  | 9967910.39 |  | 9967910.39 |  |  |  | 2018-04-03 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 7007 | Mangalore Refinery And Petrochemicals Limited | 10004785 | P-Mangalore Refinery And Petrochemicals Limited-10004785-Spares for all above tags | 7019 | POC | INR |  | 116244.62 | 2017-06-06 | 2018-05-01 |  | 7479040 |  | 4987286.6 |  | 4987286.6 |  |  |  | 2018-04-03 | [6 empty] | 0 | INDIA | OE
EPO | RU8265 | 7037 | Grand Alpha International Corporation | 10004742 | P-Grand Alpha International Corporation-10004742-3HPX22A - P-10206HPX Pumps | 7050 | POC | USD | 468101 | 28612 | 2017-05-25 | 2018-01-31 |  | 28612 |  | 1505959.5238 |  | 1505959.5238 |  |  |  | 2018-03-27 |  |  |  | 0 |  |  | 0 | ASIA | OE
EPO | RU8265 | 7037 | Grand Alpha International Corporation | 10004742 | P-Grand Alpha International Corporation-10004742-8HPX19A - P-10209/210HPX Pumps | 7051 | POC | USD |  | 66674 | 2017-05-25 | 2018-01-31 |  | 66674 |  | 3303362.5646 |  | 3303362.5646 |  |  |  | 2018-05-06 | [6 empty] | 0 | ASIA | OE
EPO | RU8265 | 7037 | Grand Alpha International Corporation | 10004742 | P-Grand Alpha International Corporation-10004742-3HPX22A - P-10233HPX Pumps | 7052 | POC | USD |  | 28722 | 2017-05-25 | 2018-01-31 |  | 28722 |  | 1511749.2465 |  | 1511749.2465 |  |  |  | 2018-03-27 | [6 empty] | 0 | ASIA | OE
EPO | RU8265 | 7037 | Grand Alpha International Corporation | 10004742 | P-Grand Alpha International Corporation-10004742-3HPX22A - P-10235HPX Pumps | 7053 | POC | USD |  | 28722 | 2017-05-25 | 2018-01-31 |  | 28722 |  | 1511749.2465 |  | 1511749.2465 |  |  |  | 2018-03-27 | [6 empty] | 0 | ASIA | OE
EPO | RU8265 | 7037 | Grand Alpha International Corporation | 10004742 | P-Grand Alpha International Corporation-10004742-3HPX15A - P-10300/01HPX Pumps | 7054 | POC | USD |  | 37532 | 2017-05-25 | 2018-01-31 |  | 37532 |  | 1859522.5091 |  | 1859522.5091 |  |  |  | 2018-05-06 | [6 empty] | 0 | ASIA | OE
EPO | RU8265 | 7037 | Grand Alpha International Corporation | 10004742 | P-Grand Alpha International Corporation-10004742-4HPX15A - P-10403HPX Pumps | 7055 | POC | USD |  | 21870 | 2017-05-25 | 2018-01-31 |  | 21870 |  | 1151102.1524 |  | 1151102.1524 |  |  |  | 2018-03-27 | [6 empty] | 0 | ASIA | OE
EPO | RU8265 | 7037 | Grand Alpha International Corporation | 10004742 | P-Grand Alpha International Corporation-10004742-6HPX18B - P-10405/406HPX Pumps | 7056 | POC | USD |  | 58492 | 2017-05-25 | 2018-01-31 |  | 58492 |  | 3078658.7608 |  | 3078658.7608 |  |  |  | 2018-03-27 | [6 empty] | 0 | ASIA | OE
EPO | RU8265 | 7037 | Grand Alpha International Corporation | 10004742 | P-Grand Alpha International Corporation-10004742-6HPX21A - P-10409/410HPX Pumps | 7057 | POC | USD |  | 66750 | 2017-05-25 | 2018-01-31 |  | 66750 |  | 3307127.9837 |  | 3307127.9837 |  |  |  | 2018-05-06 | [6 empty] | 0 | ASIA | OE
EPO | RU8265 | 7037 | Grand Alpha International Corporation | 10004742 | P-Grand Alpha International Corporation-10004742-1.5HPXM12A - P3-702 A/BHPX Pumps | 7058 | POC | USD |  | 59000 | 2017-05-25 | 2018-01-31 |  | 59000 |  | 2923154.3227 |  | 2923154.3227 |  |  |  | 2018-05-06 | [6 empty] | 0 | ASIA | OE
EPO | RU8265 | 7037 | Grand Alpha International Corporation | 10004742 | P-Grand Alpha International Corporation-10004742-Spare for all above tags | 7059 | POC | USD |  | 71727 | 2017-05-25 | 2018-01-31 |  | 71727 |  | 3229276.79 |  | 3229276.79 |  |  |  | 2018-03-27 | [6 empty] | 0 | ASIA | OE
EPO | RU8265 | 7040 | CAIRN INDIA LIMITED | 10004526 | P-CAIRN INDIA LIMITED-10004526-Bare Pump - DMXD Pumps - AWP08-P-201D - 4X11 DMXD-A/5-STAGES | 7060 | POC | INR | 30000011.9194 | 453042.18 | 2017-04-04 | 2018-03-02 |  | 30000011.9194 |  | 24412005.7891 |  | 21500686.3419 | 0 | 1455 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 7062 | DANGOTE OIL REFINING COMPANY LIMITED | 10004870 | P-Dangote Oil Refining Company Limited-10004870-HDX Pump | 20658 | POC | USD | 4186920 | 673400 | 2017-06-22 | 2018-09-15 |  | 673400 |  | 32814980.28 |  | 9876054.12 |  | 9359389.3448 | [5 empty] | 0 |  |  | 429831.6163 | OTHERAFRICA | OE
EPO | RU8265 | 7062 | DANGOTE OIL REFINING COMPANY LIMITED | 10004870 | P-Dangote Oil Refining Company Limited-10004870-HPX Pump | 20659 | POC | USD |  | 350590 | 2017-06-22 | 2018-09-15 |  | 350590 |  | 13565936.911 |  | 11347498.18 |  | 0 | [8 empty] | 223781.8033 | OTHERAFRICA | OE
EPO | RU8265 | 7062 | DANGOTE OIL REFINING COMPANY LIMITED | 10004870 | P-Dangote Oil Refining Company Limited-10004870-Package Pump | 20660 | POC | USD |  | 2832604 | 2017-06-22 | 2018-09-15 |  | 2796877 |  | 161228306.3255 |  | 6936937.6068 | 22686791.7732 | 1279339.2608 | [8 empty] | 1785248.2351 | OTHERAFRICA | OE
EPO | RU8265 | 7062 | DANGOTE OIL REFINING COMPANY LIMITED | 10004870 | P-Dangote Oil Refining Company Limited-10004870-WXB Pump | 20661 | POC | USD |  | 160695 | 2017-06-22 | 2018-09-15 |  | 146634 |  | 5751423.421 |  | 2136934.65 |  | 434077.5394 | [8 empty] | 93596.5685 | OTHERAFRICA | OE
EPO | RU8265 | 7062 | DANGOTE OIL REFINING COMPANY LIMITED | 10004870 | P-Dangote Oil Refining Company Limited-10004870-HDX Pump Spares | 20662 | POC | USD |  | 19243 | 2017-06-22 | 2018-09-15 |  | 19243 |  | 1024111.5915 |  | 462329.3 | [10 empty] | 12282.8182 | OTHERAFRICA | OE
EPO | RU8265 | 7062 | DANGOTE OIL REFINING COMPANY LIMITED | 10004870 | P-Dangote Oil Refining Company Limited-10004870-HPX Pump Spares | 20663 | POC | USD |  | 31130 | 2017-06-22 | 2018-09-15 |  | 31130 |  | 1568986.0747 |  | 87850 | [10 empty] | 19870.2973 | OTHERAFRICA | OE
EPO | RU8265 | 7062 | DANGOTE OIL REFINING COMPANY LIMITED | 10004870 | P-Dangote Oil Refining Company Limited-10004870-Package Pump Spares | 20664 | POC | USD |  | 137063 | 2017-06-22 | 2018-09-15 |  | 149279 |  | 6060010.1705 |  | 0 | [10 empty] | 95284.8736 | OTHERAFRICA | OE
EPO | RU8265 | 7062 | DANGOTE OIL REFINING COMPANY LIMITED | 10004870 | P-Dangote Oil Refining Company Limited-10004870-WXB Pump Spares | 20665 | POC | USD |  | 27047 | 2017-06-22 | 2018-09-15 |  | 19767 |  | 525956.8655 |  | 392233.56 |  | 2500 | [8 empty] | 12617.2877 | OTHERAFRICA | OE
EPO | RU8265 | 7825 | DANGOTE OIL REFINING COMPANY LIMITED | 10004876 | P-DANGOTE OIL REFINING COMPANY LIMITED-10004876-HDX Pump | 20731 | POC | USD | 2732104 | 1475912.86 | 2017-06-22 | 2018-09-15 |  | 1528863 |  | 82283065.5695 |  | 9849736.15 |  | 19821480 | [5 empty] | 0 |  |  | 975874.1527 | OTHERAFRICA | OE
EPO | RU8265 | 7825 | DANGOTE OIL REFINING COMPANY LIMITED | 10004876 | P-DANGOTE OIL REFINING COMPANY LIMITED-10004876-HPX Pump | 20732 | POC | USD |  | 499035.7 | 2017-06-22 | 2018-09-15 |  | 381142 |  | 22132814.441 |  | 11097235.19 |  | 681111.8291 | [8 empty] | 243283.1629 | OTHERAFRICA | OE
EPO | RU8265 | 7825 | DANGOTE OIL REFINING COMPANY LIMITED | 10004876 | P-DANGOTE OIL REFINING COMPANY LIMITED-10004876-Package Pump | 20733 | POC | USD |  | 614988 | 2017-06-22 | 2018-09-15 |  | 614988 |  | 36693807.222 |  | 6305766.6385 | 4209273.9415 | 0 | [8 empty] | 392547.2023 | OTHERAFRICA | OE
EPO | RU8265 | 7825 | DANGOTE OIL REFINING COMPANY LIMITED | 10004876 | P-DANGOTE OIL REFINING COMPANY LIMITED-10004876-WXB Pump | 20734 | POC | USD |  | 131686 | 2017-06-22 | 2018-09-15 |  | 131686 |  | 6091161.789 |  | 1643556.85 |  | 0 | [8 empty] | 84055.2513 | OTHERAFRICA | OE
EPO | RU8265 | 7825 | DANGOTE OIL REFINING COMPANY LIMITED | 10004876 | P-DANGOTE OIL REFINING COMPANY LIMITED-10004876-HDX Pump Parts | 20735 | POC | USD |  | 24078 | 2017-06-22 | 2018-09-15 |  | 26349 |  | 1664863.3685 |  | 370.65 |  | 1094488 | [8 empty] | 16818.5822 | OTHERAFRICA | OE
EPO | RU8265 | 7825 | DANGOTE OIL REFINING COMPANY LIMITED | 10004876 | P-DANGOTE OIL REFINING COMPANY LIMITED-10004876-HPX Pump Parts | 20736 | POC | USD |  | 23386 | 2017-06-22 | 2018-09-15 |  | 21276 |  | 760514.094 |  | 587260 | [10 empty] | 13580.4833 | OTHERAFRICA | OE
EPO | RU8265 | 7825 | DANGOTE OIL REFINING COMPANY LIMITED | 10004876 | P-DANGOTE OIL REFINING COMPANY LIMITED-10004876-Package Pump Parts | 20737 | POC | USD |  | 9488 | 2017-06-22 | 2018-09-15 |  | 9488 |  | 629890.072 |  | 0 | [10 empty] | 6056.196 | OTHERAFRICA | OE
EPO | RU8265 | 7825 | DANGOTE OIL REFINING COMPANY LIMITED | 10004876 | P-DANGOTE OIL REFINING COMPANY LIMITED-10004876-WXB Pump Parts | 20738 | POC | USD |  | 18312 | 2017-06-22 | 2018-09-15 |  | 18312 |  | 565698.298 |  | 424759.02 | [10 empty] | 11688.5604 | OTHERAFRICA | OE
EPO | RU8265 | 9188 | DANGOTE OIL REFINING COMPANY LIMITED | 10005085 | P-DANGOTE OIL REFINING COMPANY LIMITED-10005085-HPX Pumps EX1765024 | 20789 | POC | USD | 3237872 | 24766 | 2017-09-20 | 2018-11-16 |  | 24766 |  | 1248073.999 |  | 389137.11 | [6 empty] | 465054.9 | 30902916.4922 | 2018-05-28 | 22485 | 15808.1524 | OTHERAFRICA | OE
EPO | RU8265 | 9188 | DANGOTE OIL REFINING COMPANY LIMITED | 10005085 | P-DANGOTE OIL REFINING COMPANY LIMITED-10005085-HPX Pumps Parts EX1760012 | 20790 | POC | USD |  | 1724 | 2017-09-20 | 2018-11-16 |  | 1724 |  | 61295.406 |  | 40530 | [6 empty] | 258.6 |  | 2018-05-30 | 22483 | 1100.4302 | OTHERAFRICA | OE
EPO | RU8265 | 9188 | DANGOTE OIL REFINING COMPANY LIMITED | 10005085 | P-DANGOTE OIL REFINING COMPANY LIMITED-10005085-Package Pumps EX1755008 | 20791 | POC | USD |  | 3100366 | 2017-09-20 | 2018-11-16 |  | 3100366 |  | 177782400.329 |  | 798619.2985 | 21484500.3815 | [5 empty] | 3714.9 |  | 2018-05-28 | 22484 | 1978965.4424 | OTHERAFRICA | OE
EPO | RU8265 | 9188 | DANGOTE OIL REFINING COMPANY LIMITED | 10005085 | P-DANGOTE OIL REFINING COMPANY LIMITED-10005085-Package Pumps Parts EX1750008 | 20794 | POC | USD |  | 111016 | 2017-09-20 | 2018-11-16 |  | 111016 |  | 7384038.904 |  | 0 | [10 empty] | 70861.5781 | OTHERAFRICA | OE
EPO | RU8265 | 9194 | DANGOTE OIL REFINING COMPANY LIMITED | 10005054 | P-Dangote Oil Refining Company Limited-10005054-HPX Pump | 20759 | POC | USD | 1962119 | 394563 | 2017-09-20 | 2018-11-16 |  | 394563 |  | 22917165.1975 |  | 4540102.77 |  | 514620 | [5 empty] | 0 |  |  | 251849.7951 | OTHERAFRICA | OE
EPO | RU8265 | 9194 | DANGOTE OIL REFINING COMPANY LIMITED | 10005054 | P-Dangote Oil Refining Company Limited-10005054-Package Pump | 20760 | POC | USD |  | 1479322 | 2017-09-20 | 2018-11-16 |  | 1479322 |  | 91516433.2582 |  | 166760.5611 | 4826827.2389 | 162120 | [8 empty] | 944252.1032 | OTHERAFRICA | OE
EPO | RU8265 | 9194 | DANGOTE OIL REFINING COMPANY LIMITED | 10005054 | P-Dangote Oil Refining Company Limited-10005054-HPX Pump Spares | 20761 | POC | USD |  | 14763 | 2017-09-20 | 2018-11-16 |  | 14763 |  | 747361.1095 |  | 0 | 0 | 0 | [8 empty] | 9423.2316 | OTHERAFRICA | OE
EPO | RU8265 | 9194 | DANGOTE OIL REFINING COMPANY LIMITED | 10005054 | P-Dangote Oil Refining Company Limited-10005054-Package Pump Spares | 20762 | POC | USD |  | 73471 | 2017-09-20 | 2018-11-16 |  | 73471 |  | 5042137.1115 |  | 0 | 0 | 0 | [8 empty] | 46896.5825 | OTHERAFRICA | OE
EPO | RU8265 | 9204 | L&T HYDROCARBON ENGINEERING LIMITED | 10005731, 10005082,10005158 | P-L&T HYDROCARBON ENGINEERING LIMITED-10005082-Motor Driven FRESH FEED Centrifugal Pump Package / 101-P-001 A/B | 9895 | POC | INR | 48450000.3202 | 43243.67 | 2017-08-23 | 2018-06-26 |  | 2423848.2281 |  | 1872673.3832 |  | 885737.2727 |  | 49999.5156 |  |  |  |  | 1347063 |  | 2018-05-12 | 22334 | 0 | INDIA | OE
EPO | RU8265 | 9204 | L&T HYDROCARBON ENGINEERING LIMITED | 10005731, 10005082,10005158 | P-L&T HYDROCARBON ENGINEERING LIMITED-10005082-Motor Driven LCO PRODUCT Centrifugal Pump Package / 101-P-006 A/B | 9896 | POC | INR |  | 32454.22 | 2017-08-23 | 2018-06-26 |  | 1732786.9902 |  | 1338776.1464 |  | 633214.4961 |  | 35744.7057 |  |  |  |  | 675000 |  | 2018-05-12 | 22336 | 0 | INDIA | OE
EPO | RU8265 | 9204 | L&T HYDROCARBON ENGINEERING LIMITED | 10005731, 10005082,10005158 | P-L&T HYDROCARBON ENGINEERING LIMITED-10005082-Motor Driven REFLUX DRUM SOUR WATER Centrifugal Pump Package / 101-P-010 A/B | 9897 | POC | INR |  | 27035.17 | 2017-08-23 | 2018-06-26 |  | 1731591.8247 |  | 1337835.9251 |  | 632769.7901 |  | 35719.6022 |  |  |  |  | 297394 |  | 2018-05-12 | 22335 | 0 | INDIA | OE
EPO | RU8265 | 9204 | L&T HYDROCARBON ENGINEERING LIMITED | 10005731, 10005082,10005158 | P-L&T HYDROCARBON ENGINEERING LIMITED-10005082-Motor Driven COMPRESSOR INTERSTAGE SOUR WATER Centrifugal Pump Package / 101-P-014 A/B | 9898 | POC | INR |  | 25647.47 | 2017-08-23 | 2018-06-26 |  | 1642710.1948 |  | 1269150.2856 |  | 600282.8484 |  | 33885.7273 |  |  |  |  | 211259 |  | 2018-05-12 | 22337 | 0 | INDIA | OE
EPO | RU8265 | 9204 | L&T HYDROCARBON ENGINEERING LIMITED | 10005731, 10005082,10005158 | P-L&T HYDROCARBON ENGINEERING LIMITED-10005082-Motor Driven STRIPPER CHARGE Centrifugal Pump Package / 101-P-015 A/B | 9899 | POC | INR |  | 59730.08 | 2017-08-23 | 2018-06-26 |  | 2353131.0647 |  | 1818041.5777 |  | 859897.5151 |  | 48540.8716 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 9204 | L&T HYDROCARBON ENGINEERING LIMITED | 10005731, 10005082,10005158 | P-L&T HYDROCARBON ENGINEERING LIMITED-10005082-Motor Driven PRIMARY ABSORBER UPPER COOLER Centrifugal Pump Package / 101-P-016 A/B | 9900 | POC | INR |  | 27059.69 | 2017-08-23 | 2018-06-26 |  | 1733162.3209 |  | 1339073.0584 |  | 633354.9296 |  | 35752.6331 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 9204 | L&T HYDROCARBON ENGINEERING LIMITED | 10005731, 10005082,10005158 | P-L&T HYDROCARBON ENGINEERING LIMITED-10005082-Motor Driven PRIMARY ABSORBER LOWER COOLER Centrifugal Pump Package / 101-P-017 A/B | 9901 | POC | INR |  | 27194.84 | 2017-08-23 | 2018-06-26 |  | 1741818.6243 |  | 1345753.5781 |  | 636514.6826 |  | 35930.9999 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 9204 | L&T HYDROCARBON ENGINEERING LIMITED | 10005731, 10005082,10005158 | P-L&T HYDROCARBON ENGINEERING LIMITED-10005082-Motor Driven PRIMARY ABSORBER REFLUX Centrifugal Pump Package / 101-P-020 A/B | 9902 | POC | INR |  | 30556.43 | 2017-08-23 | 2018-06-26 |  | 1957127.1192 |  | 1512073.7758 |  | 715180.8288 |  | 40371.6724 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 9204 | L&T HYDROCARBON ENGINEERING LIMITED | 10005731, 10005082,10005158 | P-L&T HYDROCARBON ENGINEERING LIMITED-10005082-Motor Driven DEBUTANIZER REFLUX Centrifugal Pump Package / 101-P-021 A/B | 9903 | POC | INR |  | 30060.89 | 2017-08-23 | 2018-06-26 |  | 1925387.9805 |  | 1487578.5369 |  | 703595.0679 |  | 39717.6609 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 9204 | L&T HYDROCARBON ENGINEERING LIMITED | 10005731, 10005082,10005158 | P-L&T HYDROCARBON ENGINEERING LIMITED-10005082-Motor Driven LEAN OIL Centrifugal Pump Package / 101-P-023 A/B | 9904 | POC | INR |  | 36865.87 | 2017-08-23 | 2018-06-26 |  | 2361244.2275 |  | 1824326.2148 |  | 862870.0234 |  | 48708.6685 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 9204 | L&T HYDROCARBON ENGINEERING LIMITED | 10005731, 10005082,10005158 | P-L&T HYDROCARBON ENGINEERING LIMITED-10005082-Motor Driven Caustic / 1st Stage Caustic Recycle Centrifugal Pump Package / 101-X-002-P01 A/B | 9905 | POC | INR |  | 14517.05 | 2017-08-23 | 2018-06-26 |  | 929811.2458 |  | 718378.551 |  | 339778.7699 |  | 19180.376 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 9204 | L&T HYDROCARBON ENGINEERING LIMITED | 10005731, 10005082,10005158 | P-L&T HYDROCARBON ENGINEERING LIMITED-10005082-Motor Driven 2nd Stage Caustic Recycle Centrifugal Pump Package / 101-X-002-P02 A/B | 9906 | POC | INR |  | 14517.03 | 2017-08-23 | 2018-06-26 |  | 929809.9648 |  | 718378.551 |  | 339778.7699 |  | 19180.376 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 9204 | L&T HYDROCARBON ENGINEERING LIMITED | 10005731, 10005082,10005158 | P-L&T HYDROCARBON ENGINEERING LIMITED-10005082-Spares of all above tags-HPX Pumps / Spares of all above tags | 9907 | POC | INR |  | 51748.9 | 2017-08-23 | 2018-06-26 |  | 3314496.346 |  | 2560816.3969 |  | 1211215.2347 |  | 68372.6167 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 9204 | L&T HYDROCARBON ENGINEERING LIMITED | 10005731, 10005082,10005158 | P-L&T HYDROCARBON ENGINEERING LIMITED-10005082-Motor Driven INTERSTAGE LIQUID Centrifugal Pump Package / 101-P-009 A/B | 9908 | POC | INR |  | 92863.74 | 2017-08-23 | 2018-06-26 |  | 5947885.4025 |  | 4595405.7833 |  | 2173535.5573 |  | 122695.215 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 9204 | L&T HYDROCARBON ENGINEERING LIMITED | 10005731, 10005082,10005158 | P-L&T HYDROCARBON ENGINEERING LIMITED-10005082-Spares of all above tags-WXB Pumps / Spares of all above tags | 9909 | POC | INR |  | 65967.44 | 2017-08-23 | 2018-06-26 |  | 4225188.1457 |  | 3264398.8339 |  | 1543995.7369 |  | 87157.9433 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 9204 | L&T HYDROCARBON ENGINEERING LIMITED | 10005731, 10005082,10005158 | P-L&T HYDROCARBON ENGINEERING LIMITED-10005082 10005213 & 10005158-Motor Driven Closed Blowdown Drum Liquid Vertical Centrifugal Pump / Tag No 101-P-030 A/B | 19600 | POC | INR |  | 73467.66 | 2017-08-23 | 2018-06-26 |  | 4705574.2367 |  | 3635588.3021 |  | 1719560.9744 |  | 97068.5309 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 9204 | L&T HYDROCARBON ENGINEERING LIMITED | 10005731, 10005082,10005158 | P-L&T HYDROCARBON ENGINEERING LIMITED-10005082 10005213 & 10005158-Motor Driven Closed Blowdown Drum Liquid Vertical Centrifugal Pump / Tag No 101-P-031 A/B | 19601 | POC | INR |  | 52452.51 | 2017-08-23 | 2018-06-26 |  | 3359562.285 |  | 2595654.07 |  | 1227692.7613 |  | 69302.7665 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 9204 | L&T HYDROCARBON ENGINEERING LIMITED | 10005731, 10005082,10005158 | P-L&T HYDROCARBON ENGINEERING LIMITED-10005082 10005213 & 10005158-Motor Driven Closed Blowdown Drum Liquid Vertical Centrifugal Pump / Tag No 101-P-042 A/B | 19602 | POC | INR |  | 41363.88 | 2017-08-23 | 2018-06-26 |  | 2649339.9689 |  | 2046911.2339 |  | 968148.3114 |  | 54651.5859 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 9204 | L&T HYDROCARBON ENGINEERING LIMITED | 10005731, 10005082,10005158 | P-L&T HYDROCARBON ENGINEERING LIMITED-10005082 10005213 & 10005158-Mendatory Spares for Erection -Commissioning / Spares of all above tags | 19603 | POC | INR |  | 43490.11 | 2017-08-23 | 2018-06-26 |  | 2785524.1499 |  | 2152117.0477 |  | 1017908.5694 |  | 57460.5326 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 10480 | BHARAT OMAN REFINERIES LIMITED | 10005156 | P-BHARAT OMAN REFINERIES LTD-10005156-Mainline Pump - DMX / 6x13DMX - AA/5 - 10-PA-CF-102D(N) | 13202 | POC | INR | 134574000.9691 | 694289.7 | 2017-09-13 | 2018-08-08 |  | 44858000.323 |  | 32587305.8105 |  | 2955995.5733 |  | 1928524.3107 |  |  |  |  | 20096100 |  | 2018-05-25 | 22473 | 0 | INDIA | OE
EPO | RU8265 | 10480 | BHARAT OMAN REFINERIES LIMITED | 10005156 | P-BHARAT OMAN REFINERIES LTD-10005156-Mainline Pump - DMX / 6x13DMX - AA/5 - 30-PA-CF-201D(N) | 13203 | POC | INR |  | 694289.7 | 2017-09-13 | 2018-08-08 |  | 44858000.323 |  | 32587305.8105 |  | 2955995.5733 |  | 1928524.3107 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 10480 | BHARAT OMAN REFINERIES LIMITED | 10005156 | P-BHARAT OMAN REFINERIES LTD-10005156-Mainline Pump - DMX / 6x13DMX - AA/5 - 40-PA-CF-301D(N) | 13204 | POC | INR |  | 694289.7 | 2017-09-13 | 2018-08-08 |  | 44858000.323 |  | 32587305.8105 |  | 2955995.5733 |  | 1928524.3107 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 10488 | CSTS JOINT VENTURE (CHIYODA-SAIPEM-TRIPATRA-SAE JOINT VENTURE) | 10005199 | P-CSTS JOINT VENTURE (CHIYODA-SAIPEM-TRIPATRA-SAE JOINT VENTURE)-10005199-Condensate Return Pump / 017-P-31101 A/B - 1.5HPXM12A | 13228 | POC | USD | 616946 | 69278 | 2017-10-11 | 2018-08-13 |  | 69278 |  | 2690386.4237 |  | 409560.5278 |  | 138.6804 | [5 empty] | 0 |  |  | 45106.9058 | MIDEAST | OE
EPO | RU8265 | 10488 | CSTS JOINT VENTURE (CHIYODA-SAIPEM-TRIPATRA-SAE JOINT VENTURE) | 10005199 | P-CSTS JOINT VENTURE (CHIYODA-SAIPEM-TRIPATRA-SAE JOINT VENTURE)-10005199-Condensate Return Pump / 053-P-31101 A/B - 6HPX23A | 13229 | POC | USD |  | 245682 | 2017-10-11 | 2018-08-13 |  | 245682 |  | 9540972.8534 |  | 1452432.9454 |  | 491.8052 | [8 empty] | 159963.5502 | MIDEAST | OE
EPO | RU8265 | 10488 | CSTS JOINT VENTURE (CHIYODA-SAIPEM-TRIPATRA-SAE JOINT VENTURE) | 10005199 | P-CSTS JOINT VENTURE (CHIYODA-SAIPEM-TRIPATRA-SAE JOINT VENTURE)-10005199-STG Condensate Recovery Pumps / 161-P-31001 A/B - 4HPX25A | 13231 | POC | USD |  | 100662 | 2017-10-11 | 2018-08-13 |  | 100662 |  | 3909172.8713 |  | 595097.7489 |  | 201.5048 | [8 empty] | 65541.0282 | MIDEAST | OE
EPO | RU8265 | 10488 | CSTS JOINT VENTURE (CHIYODA-SAIPEM-TRIPATRA-SAE JOINT VENTURE) | 10005199 | P-CSTS JOINT VENTURE (CHIYODA-SAIPEM-TRIPATRA-SAE JOINT VENTURE)-10005199-STG Condensate Recovery Pumps / 161-P-31002 A/B - 4HPX25A | 13232 | POC | USD |  | 100662 | 2017-10-11 | 2018-08-13 |  | 100662 |  | 3909172.8713 |  | 595097.7489 |  | 201.5048 | [8 empty] | 65541.0282 | MIDEAST | OE
EPO | RU8265 | 10488 | CSTS JOINT VENTURE (CHIYODA-SAIPEM-TRIPATRA-SAE JOINT VENTURE) | 10005199 | P-CSTS JOINT VENTURE (CHIYODA-SAIPEM-TRIPATRA-SAE JOINT VENTURE)-10005199-STG Condensate Recovery Pumps / 161-P-31003 A/B - 4HPX25A | 13233 | POC | USD |  | 100662 | 2017-10-11 | 2018-08-13 |  | 100662 |  | 3909172.8713 |  | 595097.7489 |  | 201.5048 | [8 empty] | 65541.0282 | MIDEAST | OE
EPO | RU8265 | 10513 | HINDUSTAN PETROLEUM CORPORATION LIMITED | 10005163 | P-HINDUSTAN PETROLEUM CORPORATION LIMITED-10005163-Mainline Pump - DMX / 6x13DMX - G/8 - P-10-12-D | 13221 | POC | INR | 68802462.3647 | 911417.33 | 2017-09-13 | 2018-09-11 |  | 58886598.6109 |  | 47444066.4889 |  | 4263334.06 |  | 9674066.7056 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 10513 | HINDUSTAN PETROLEUM CORPORATION LIMITED | 10005163 | P-HINDUSTAN PETROLEUM CORPORATION LIMITED-10005163-Spares for above tag | 13222 | POC | INR |  | 147784.8 | 2017-09-13 | 2018-09-11 |  | 9548363.7538 |  | 7918342.8925 |  | 920885.3 |  | 14500 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 10513 | HINDUSTAN PETROLEUM CORPORATION LIMITED | 10005163 | P-HINDUSTAN PETROLEUM CORPORATION LIMITED-10005163-Service for Supervision | 13223 | PIT | INR |  | 5687.98 | 2017-09-13 | 2018-09-11 |  | 367500 |  |  |  | 0 |  | 0 | [8 empty] | 0 | INDIA | OE | 2019-01-01 | 2020-12-31
EPO | RU8265 | 10523 | MEGHA ENGG & INFRASTRUCTURE LIMITED | 10003438 | P-MEGHA ENGG & INFRASTRUCTURE LIMITED-10003438-Condenser cooling water pump supply package - BCV Pumps / BCV 170 | 13790 | POC | INR | 72331000.4846 | 313925.97 | 2016-07-19 | 2017-11-15 |  | 20282731.0612 |  | 17910402.4497 |  | 16243763.7604 |  | 287801.7913 |  |  | 6042757.4277 | [5 empty] | 0 | INDIA | OE
EPO | RU8265 | 10523 | MEGHA ENGG & INFRASTRUCTURE LIMITED | 10003438 | P-MEGHA ENGG & INFRASTRUCTURE LIMITED-10003438-Condenser cooling water pump supply package - BCV Pumps / BCV 170 | 13791 | POC | INR |  | 307850.42 | 2016-07-19 | 2017-11-15 |  | 19890190.2762 |  | 17563774.4036 |  | 15929390.9198 |  | 282231.8342 |  |  | 5925809.2348 | [5 empty] | 0 | INDIA | OE
EPO | RU8265 | 10523 | MEGHA ENGG & INFRASTRUCTURE LIMITED | 10003438 | P-MEGHA ENGG & INFRASTRUCTURE LIMITED-10003438-Condenser cooling water pump supply package - BCV Pumps / BCV 170 | 13792 | POC | INR |  | 373659.66 | 2016-07-19 | 2017-11-15 |  | 24142119.8514 |  | 21318385.6367 |  | 19334619.6998 |  | 342564.5845 |  |  | 7192570.5475 | [5 empty] | 0 | INDIA | OE
EPO | RU8265 | 10523 | MEGHA ENGG & INFRASTRUCTURE LIMITED | 10003438 | P-MEGHA ENGG & INFRASTRUCTURE LIMITED-10003438-Spares for above tag | 13793 | POC | INR |  | 124067.01 | 2016-07-19 | 2017-11-15 |  | 8015959.2958 |  | 5387658.81 |  | 4590664.3 |  | 0 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 13105 | PETRONAS CARIIGALI SDN BHD | 10005300 | P-PETRONAS CARIIGALI SDN BHD-10005300-CRUDE OIL TRANSFER PUMP - DMX Package Pumps / P802 - 3X8DMX-B/9 STG | 13345 | POC | USD | 870682 | 435341 | 2017-11-03 | 2017-09-25 |  | 435341 |  | 21165887.2975 |  | 0 | [7 empty] | 0 |  |  | 283450.5251 | MIDEAST | OE
EPO | RU8265 | 13105 | PETRONAS CARIIGALI SDN BHD | 10005300 | P-PETRONAS CARIIGALI SDN BHD-10005300-CRUDE OIL TRANSFER PUMP - DMX Package Pumps / P803 - 3X8DMX-B/9 STG | 13346 | POC | USD |  | 435341 | 2017-11-03 | 2017-09-25 |  | 435341 |  | 21165887.2975 |  | 0 | [10 empty] | 283450.5251 | MIDEAST | OE
EPO | RU8265 | 13110 | Hindustan Petroleum Corporation Limited | 10005278 | P-Hindustan Petroleum Corporation Limited-10005278-Pipe line project Main Line pump at Vizag location-10-PA-CF-104 | 13821 | POC | INR | 173313010.6839 | 948854.89 | 2017-11-03 | 2018-09-28 |  | 61964819.628 |  | 51025497.8392 |  | 746553.5403 |  | 122387.2417 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 13110 | Hindustan Petroleum Corporation Limited | 10005278 | P-Hindustan Petroleum Corporation Limited-10005278-Pipe line project Main Line pump at Rajamundry location-20-PA-CF-103 | 13822 | POC | INR |  | 868128.27 | 2017-11-03 | 2018-09-28 |  | 56692980.3824 |  | 46684353.5633 |  | 683038.3025 |  | 111974.7873 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 13110 | Hindustan Petroleum Corporation Limited | 10005278 | P-Hindustan Petroleum Corporation Limited-10005278-Pipe line project Main Line pump at Vijaywada location-30-PA-CF-101D | 13823 | POC | INR |  | 719941.91 | 2017-11-03 | 2018-09-28 |  | 47015693.4068 |  | 38715503.0345 |  | 566446.1314 |  | 92861.0955 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 13110 | Hindustan Petroleum Corporation Limited | 10005278 | P-Hindustan Petroleum Corporation Limited-10005278-VFD for an existing motor at site-30-PA-CF-101C | 13824 | POC | INR |  | 116982.4 | 2017-11-03 | 2018-09-28 |  | 7639517.2666 |  | 6290830.4118 |  | 92041.0758 |  | 15088.8755 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 13115 | Hindustan Petroleum Corporation Limited | 10005239 | P-Hindustan Petroleum Corporation Limited-10005239-Pipe line project Main Line pump at MB patnam location-15-PA-CF-101 A/B/C | 13788 | POC | INR | 290699624.4972 | 2228058.16 | 2017-11-03 | 2018-09-27 |  | 145502988.3496 |  | 112629609.434 |  | 5156511.7709 |  | 1251867.0093 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 13115 | Hindustan Petroleum Corporation Limited | 10005239 | P-Hindustan Petroleum Corporation Limited-10005239-Pipe line project Main Line pump at JK Gudem location-25-PA-CF-101 A/B/C | 13789 | POC | INR |  | 2223367.05 | 2017-11-03 | 2018-09-27 |  | 145196636.1475 |  | 112392471.1507 |  | 5145654.8891 |  | 1249231.2407 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 13400 | JV OF TECNICAS REUNIDAS S.A(JV LEADER),SINOPEC ENGG.(GROUP)CO LTD AND HANWHA ENGG.&CONTRUCTION CORP | 10003381 | P-JV OF TECNICAS REUNIDAS S.A(JV LEADER),SINOPEC ENGG.(GROUP)CO LTD AND HANWHA ENGG.&CONTRUCTION CORP-10003381-Charge Pumps - WXB / 04-P-0001A - 4WXB-11A | 13886 | POC | USD | 1392993 | 163615.52 | 2016-07-06 | 2018-01-15 |  | 163616 |  | 5616049.1996 |  | 5616049.1996 |  | 0 |  | 2017-11-30 |  |  |  | 0 |  |  | 0 | MIDEAST | OE
EPO | RU8265 | 13400 | JV OF TECNICAS REUNIDAS S.A(JV LEADER),SINOPEC ENGG.(GROUP)CO LTD AND HANWHA ENGG.&CONTRUCTION CORP | 10003381 | P-JV OF TECNICAS REUNIDAS S.A(JV LEADER),SINOPEC ENGG.(GROUP)CO LTD AND HANWHA ENGG.&CONTRUCTION CORP-10003381-Charge Pumps - WXB / 04-P-0001B - 4WXB-11A | 13887 | POC | USD |  | 528191.21 | 2016-07-06 | 2018-01-15 |  | 528191 |  | 18129991.5604 |  | 18129991.5604 |  | 0 |  | 2017-11-30 | [6 empty] | 0 | MIDEAST | OE
EPO | RU8265 | 13400 | JV OF TECNICAS REUNIDAS S.A(JV LEADER),SINOPEC ENGG.(GROUP)CO LTD AND HANWHA ENGG.&CONTRUCTION CORP | 10003381 | P-JV OF TECNICAS REUNIDAS S.A(JV LEADER),SINOPEC ENGG.(GROUP)CO LTD AND HANWHA ENGG.&CONTRUCTION CORP-10003381-Charge Pumps - WXB / 14-P-0001A - 4WXB-11A | 13888 | POC | USD |  | 163615.52 | 2016-07-06 | 2018-01-15 |  | 163616 |  | 5734966 |  | 5734966 |  | 0 |  | 2018-02-28 | [6 empty] | 0 | MIDEAST | OE
EPO | RU8265 | 13400 | JV OF TECNICAS REUNIDAS S.A(JV LEADER),SINOPEC ENGG.(GROUP)CO LTD AND HANWHA ENGG.&CONTRUCTION CORP | 10003381 | P-JV OF TECNICAS REUNIDAS S.A(JV LEADER),SINOPEC ENGG.(GROUP)CO LTD AND HANWHA ENGG.&CONTRUCTION CORP-10003381-Charge Pumps - WXB / 14-P-0001B - 4WXB-11A | 13889 | POC | USD |  | 537569.84 | 2016-07-06 | 2018-01-15 |  | 537570 |  | 26494662 |  | 26494662 |  | 0 |  | 2018-03-30 | [6 empty] | 0 | MIDEAST | OE
EPO | RU8265 | 13400 | JV OF TECNICAS REUNIDAS S.A(JV LEADER),SINOPEC ENGG.(GROUP)CO LTD AND HANWHA ENGG.&CONTRUCTION CORP | 10003381 | P-JV OF TECNICAS REUNIDAS S.A(JV LEADER),SINOPEC ENGG.(GROUP)CO LTD AND HANWHA ENGG.&CONTRUCTION CORP-10003381-Warranty 23 Month | 21719 | SL | USD |  | 13929.92 | 2016-07-06 | 2018-01-15 | [5 empty] | 0 |  | 0 | [8 empty] | 0 | MIDEAST | OE | 2019-01-01 | 2020-12-31
EPO | RU8265 | 13405 | ROTARY ENGINEERING FUJAIRAH FZE | 10005336 | P-ROTARY ENGINEERING FUJAIRAH-10005336-Jet Fuel Sampling Return Pumps 24G-10924G-110 24G-111 | 13515 | POC | USD | 853082.97 | 102129.09 | 2017-11-26 | 2018-10-01 |  | 102129.09 |  | 3173676.4131 |  | 1679978.05 |  | 890771.3648 | [5 empty] | 0 |  |  | 0 | MIDEAST | OE
EPO | RU8265 | 13405 | ROTARY ENGINEERING FUJAIRAH FZE | 10005336 | P-ROTARY ENGINEERING FUJAIRAH-10005336-Heavy NAPHTHA Shipping Pump 24G-103A/B | 13516 | POC | USD |  | 375476.94 | 2017-11-26 | 2018-10-01 |  | 375476.94 |  | 18929500.4515 |  | 1258254.545 |  | 292650 | [8 empty] | 0 | MIDEAST | OE
EPO | RU8265 | 13405 | ROTARY ENGINEERING FUJAIRAH FZE | 10005336 | P-ROTARY ENGINEERING FUJAIRAH-10005336-Jet Fuel Shipping Pump 24G-102 A/B | 13519 | POC | USD |  | 375476.94 | 2017-11-26 | 2018-10-01 |  | 375476.94 |  | 18929500.4515 |  | 1258254.545 |  | 292650 | [8 empty] | 0 | MIDEAST | OE
EPO | RU8265 | 13410 | HINDUSTAN PETROLEUM CORPORATION LIMITED | 10005211 | P-HINDUSTAN PETROLEUM CORPORATION LIMITED-10005211-IFO ROAD LOADING PUMPS - HPX / 1717248/1717249 - 161?PA?005 A/B - 8HPX19A | 13828 | POC | INR | 44606503.4201 | 71255.25 | 2017-09-26 | 2018-05-22 |  | 4633101.6411 |  | 3786358.321 |  | 1776484.2809 |  | 80076.9674 |  |  |  |  | 6364024 |  | 2018-05-25 | 22471 | 0 | INDIA | OE
EPO | RU8265 | 13410 | HINDUSTAN PETROLEUM CORPORATION LIMITED | 10005211 | P-HINDUSTAN PETROLEUM CORPORATION LIMITED-10005211-RAW HSD DHT FEED PUMPS - HPX / 1717250/1717252 - 161?PA?006 A/B/C - 4HPX15A | 13829 | POC | INR |  | 45297.09 | 2017-09-26 | 2018-05-22 |  | 2945271.0083 |  | 2406994.7637 |  | 1129314.2379 |  | 50905.0716 |  |  |  |  | 2028112 |  | 2018-05-29 | 22487 | 0 | INDIA | OE
EPO | RU8265 | 13410 | HINDUSTAN PETROLEUM CORPORATION LIMITED | 10005211 | P-HINDUSTAN PETROLEUM CORPORATION LIMITED-10005211-RAW HSD DHDS FEED PUMPS - HPX / 1717253/1717255 - 161?PA?007 A/B/C - 4HPX15A | 13830 | POC | INR |  | 38749.44 | 2017-09-26 | 2018-05-22 |  | 2519534.9684 |  | 2059066.0278 |  | 966072.9708 |  | 43546.7933 |  |  |  |  | 1591006.1 |  | 2018-05-29 | 22488 | 0 | INDIA | OE
EPO | RU8265 | 13410 | HINDUSTAN PETROLEUM CORPORATION LIMITED | 10005211 | P-HINDUSTAN PETROLEUM CORPORATION LIMITED-10005211-SLOP - HPX / 1717256/1717257 - 161?PA?012 A/B - 4HPX13A | 13831 | POC | INR |  | 41531.76 | 2017-09-26 | 2018-05-22 |  | 2700444.745 |  | 2206912.8248 |  | 1035439.7577 |  | 46673.5769 |  |  |  |  | 1748423 |  | 2018-05-25 | 22472 | 0 | INDIA | OE
EPO | RU8265 | 13410 | HINDUSTAN PETROLEUM CORPORATION LIMITED | 10005211 | P-HINDUSTAN PETROLEUM CORPORATION LIMITED-10005211-SOLVENT ROAD LOADING PUMPS - HPX / 1717258/1717259 - 161?PA?013 A/B - 4HPX10A | 13832 | POC | INR |  | 64873.92 | 2017-09-26 | 2018-05-22 |  | 4218179.9267 |  | 3447267.4899 |  | 1617389.5835 |  | 72905.6003 |  |  |  |  | 437105.9 |  | 2018-05-29 | 22489 | 0 | INDIA | OE
EPO | RU8265 | 13410 | HINDUSTAN PETROLEUM CORPORATION LIMITED | 10005211 | P-HINDUSTAN PETROLEUM CORPORATION LIMITED-10005211-LDO ROAD LOADING PUMPS - HPX / 1717260/1717261 - 161?PA?014 A/B - 4HPX10A | 13833 | POC | INR |  | 46665.64 | 2017-09-26 | 2018-05-22 |  | 3034255.7674 |  | 2479716.7131 |  | 1163433.9353 |  | 52443.0541 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 13410 | HINDUSTAN PETROLEUM CORPORATION LIMITED | 10005211 | P-HINDUSTAN PETROLEUM CORPORATION LIMITED-10005211-MTO ROAD LOADING PUMPS - HPX / 1717262/1717263 - 161?PA?015 A/B - 4HPX10A | 13834 | POC | INR |  | 50860.75 | 2017-09-26 | 2018-05-22 |  | 3307026.8408 |  | 2702636.2826 |  | 1268023.3792 |  | 57157.5375 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 13410 | HINDUSTAN PETROLEUM CORPORATION LIMITED | 10005211 | P-HINDUSTAN PETROLEUM CORPORATION LIMITED-10005211-RPO ROAD LOADING PUMPS - HPX / 1717264/1717265 - 161?PA?017 A/B - 8HPX19A | 13835 | POC | INR |  | 71235.42 | 2017-09-26 | 2018-05-22 |  | 4631812.2708 |  | 3785304.5953 |  | 1775989.8937 |  | 80054.6824 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 13410 | HINDUSTAN PETROLEUM CORPORATION LIMITED | 10005211 | P-HINDUSTAN PETROLEUM CORPORATION LIMITED-10005211-ELASTO SUPREME ROAD LOADIND PUMPS - HPX / 1717266/1717267 - 161?PA?018 A/B - 3HPX11A | 13836 | POC | INR |  | 50788.35 | 2017-09-26 | 2018-05-22 |  | 3302319.3061 |  | 2698789.0946 |  | 1266218.3548 |  | 57076.174 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 13410 | HINDUSTAN PETROLEUM CORPORATION LIMITED | 10005211 | P-HINDUSTAN PETROLEUM CORPORATION LIMITED-10005211-WO SICK TANKER UNLOADING PUMPS - HPX / 1717268 - 161?PA?020 - 1.5HPX10A | 13837 | POC | INR |  | 13139.29 | 2017-09-26 | 2018-05-22 |  | 854332.3624 |  | 698195.0105 |  | 327579.2611 |  | 14765.9926 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 13410 | HINDUSTAN PETROLEUM CORPORATION LIMITED | 10005211 | P-HINDUSTAN PETROLEUM CORPORATION LIMITED-10005211-HSD MPSPL BOOSTER PUMPS - HDX / 2017008/2017009 - 161?PA?010 A/B - 10HDX27B | 13838 | POC | INR |  | 135828.39 | 2017-09-26 | 2018-05-22 |  | 8831724.4922 |  | 7217642.9766 |  | 3386375.0352 |  | 152644.5498 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 13410 | HINDUSTAN PETROLEUM CORPORATION LIMITED | 10005211 | P-HINDUSTAN PETROLEUM CORPORATION LIMITED-10005211-Service for Eraction and commissioning | 13839 | PIT | INR |  | 55804.88 | 2017-09-26 | 2018-05-22 |  | 3628500.091 |  | 431640 |  | 0 |  | 0 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 14739 | NTPC Limited | 10005414 | P-NTPC Limited-10005414-Complete cartridge for BFP | 15559 | POC | INR | 47500000 | 735186 | 2017-12-08 | 2018-06-18 |  | 47500000 |  | 31426001.8 |  | 29769931.5517 | 0 | 0 |  | 2018-05-30 |  |  | 48450020.4 |  | 2018-05-30 | 22531 | 0 | INDIA | AM
EPO | RU8265 | 14741 | Indian Oil Corporation Limited | 10005373 | P-Indian Oil Corp Limited-10005373-PUMPS CENTRIFUGAL and Assoc parts | 15571 | POC | INR | 27888414.2244 | 431645.72 | 2017-12-08 | 2018-07-24 |  | 27888414.2244 |  | 14786134.15 |  | 93705.6195 | 2860480.9705 | 0 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 14748 | Hindustan Petroleum Corporation Limited | 10005430 | P-HINDUSTAN PETROLEUM CORP-10005430-PUSHBACK PUMPSBUNKERING PUMPSHFHSD PUMPS | 15615 | POC | INR | 18046531.762 | 279317 | 2017-12-01 | 2018-05-06 |  | 18046531.762 |  | 14461710.47 |  | 3522615 |  | 2350254.65 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 15846 | CSTS JOINT VENTURE | 10005432 | P-CSTS JOINT VENTURE-10005432-CENTRIFUGAL PUMPS | 16728 | POC | USD | 584506 | 584506 | 2017-12-08 | 2018-10-20 |  | 584506 |  | 28561018.3431 |  | 367912.15 | [7 empty] | 0 |  |  | 380571.8566 | ASIA | OE
EPO | RU8265 | 15987 | JV OF TECNICAS REUNIDAS S.A(JV LEADER),SINOPEC ENGG.(GROUP)CO LTD AND HANWHA ENGG.&CONTRUCTION CORP | 10003589 | P-JV of Tecnica Reunidas S.A.-10003589 CC&I Kuwait Refinery Project | 20693 | POC | USD | 5373103 | 5373103 | 2016-08-16 | 2018-02-07 |  | 5373103 |  | 225441002.81 |  | 225441002.81 |  |  |  | 2018-03-31 |  |  |  | 0 |  |  | 6859309.6141 | ASIA | OE
EPO | RU8265 | 15990 | BHARAT PETROLEUM CORPORATION LIMITED | 10004633 | P-BHARAT PETROLEUM CORPORATION LIMITED-10004633-HPX PUMP | 16759 | POC | INR | 16917257.8825 | 330172.7 | 2017-04-27 | 2018-03-31 |  | 16917257.8825 |  | 16362610.2031 |  | 15845421.87 |  |  |  |  | 14488846.14 | [5 empty] | 0 | INDIA | OE
EPO | RU8265 | 15991 | L&T HYDROCARBON ENGINEERING LIMITED | 10005443 | P-L&T Hydrocarbon Engineering Limited-10005443 | 16777 | POC | INR | 70164136 | 1077624.57 | 2017-11-21 | 2018-08-15 |  | 70164136 |  | 50559620.6387 |  | 9260277.368 | 504409.472 | 678424 |  |  |  |  | 6844710.98 |  | 2018-05-31 | 22592 | 1052462.0363 | OTHER | OE
EPO | RU8265 | 19407 | BHARAT PETROLEUM CORPORATION LIMITED | 10005557 | P-BHARAT PETROLEUM CORPORATION LIMITED-10005557-HPX Pumps (18 Nos) | 20261 | POC | INR | 21719839.3605 | 338562.34 | 2017-12-19 | 2018-08-19 |  | 21719839.3605 |  | 16043879.15 |  | 1544529.98 |  | 144846 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 19412 | INDIAN OIL CORPORATION LIMITED | 10005567 | P-Indian Oil Corporation Limited-10005567-HPX Pumps | 20539 | POC | INR | 17455002.3416 | 190138.99 | 2017-12-20 | 2018-10-15 |  | 12198014.4601 |  | 9047348.119 |  | 852629.13 |  | 23348 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 19412 | INDIAN OIL CORPORATION LIMITED | 10005567 | P-Indian Oil Corporation Limited-10005567-HDX Pumps | 20540 | POC | INR |  | 81944.35 | 2017-12-20 | 2018-10-15 |  | 5256987.8815 |  | 3999438.49 |  | 270872.8 |  | 546308 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 19414 | INDIAN OIL CORPORATION LIMITED | 10005475 | P-Indian Oil Corporation Limited-10005475-HPX Pumps | 20468 | POC | INR | 40097359.4565 | 625025.61 | 2017-11-28 | 2018-09-27 |  | 40097359.4565 |  | 31589418.845 |  | 2288351.72 |  | 146399.2 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 21898 | HINDUSTAN PETROLEUM CORPORATION LIMITED | 10005533 | P-Hindustan Petroleum Corporation Limited-10005533-Mainline Pumps for SBS | 22101 | POC | INR | 215291398.8996 | 1399655.74 | 2018-02-05 | 2018-12-14 |  | 89340108.2558 |  | 65947975.5344 |  | 338121.5694 |  | 47163.7633 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 21898 | HINDUSTAN PETROLEUM CORPORATION LIMITED | 10005533 | P-Hindustan Petroleum Corporation Limited-10005533-Mainline Pumps for IPS3 | 22102 | POC | INR |  | 1973228.49 | 2018-02-05 | 2018-12-14 |  | 125951290.6438 |  | 92973124.7306 |  | 476682.0906 |  | 66491.2367 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 21907 | Indian Oil Corporation Limited | 10005668 | P-Indian Oil Corporation Limited-10005668-HPX Pumps | 22331 | POC | INR | 17472360.913 | 274358 | 2018-02-05 | 2018-11-12 |  | 17472360.913 |  | 14046576.3344 |  | 840898.57 |  | 22514.3 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 22947 | MANGALORE REFINERY & PETROCHEMICALS LTD | 10005821 | P-MANGALORE REFINERY & PETROCHEMICALS LTD-10005821-Bareshaft pump | 23342 | POC | INR | 23825280.0529 | 374964.64 | 2018-02-28 | 2019-01-10 |  | 23825280.0529 |  | 13917737.7164 |  | 0 |  | 0 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 22950 | FARABI DOWNSTREAM COMPANY | 10005576 | P - Farabi Downstream Company - 10005576 - EX1765039-HPX Pumps | 23512 | POC | USD | 1175633.34 | 1150653.26 | 2018-02-01 | 2018-10-13 |  | 1150653.6 |  | 60522436.0426 |  | 2630875.52 |  | 402804 | [5 empty] | 0 |  |  | 1123785.5064 | MIDEAST | OE
EPO | RU8265 | 22950 | FARABI DOWNSTREAM COMPANY | 10005576 | P - Farabi Downstream Company - 10005576 - EX1773009-CPX Pumps | 23513 | POC | USD |  | 24979.74 | 2018-02-01 | 2018-10-13 |  | 24979.74 |  | 1313892.296 |  | 0 |  | 0 | [8 empty] | 24396.4631 | MIDEAST | OE
EPO | RU8265 | 22958 | HADAF INTERNATIONAL ENERGY COMPANY | 10005577 | P-HADAF INTERNATIONAL ENERGY COMPANY-10005577-API Pumps | 23510 | POC | USD | 426366.81 | 426366.81 | 2018-02-21 | 2018-10-13 |  | 426366.81 |  | 22426178.9556 |  | 825725.22 |  | 106122 | [5 empty] | 0 |  |  | 416411.145 | MIDEAST | OE
EPO | RU8265 | 23863 | RAMAGUNDAM FERTILIZERS & CHEMICALS LIMITED (RFCL) | 10004538 | P-RAMAGUNDAM FERTILIZERS AND CHEMICALS LTD (RFCL) -10004538-Mandatory Spares | 24076 | POC | INR | 92186066.8294 | 182751.86 | 2017-04-05 | 2018-05-31 |  | 11809425.2794 |  | 10629303.2811 |  | 2745276.05 |  | 3000 |  |  |  |  | 13782911 |  | 2018-05-24 | 22453 | 0 | INDIA | OE
EPO | RU8265 | 23863 | RAMAGUNDAM FERTILIZERS & CHEMICALS LIMITED (RFCL) | 10004538 | P-RAMAGUNDAM FERTILIZERS AND CHEMICALS LTD (RFCL) -10004538-(2) Centrifugal Motor Pumps BB3-8X15DMX | 24078 | POC | INR |  | 1243835.36 | 2017-04-05 | 2018-05-31 |  | 80376641.5499 |  | 64141722.978 |  | 22548945.45 | [10 empty] | 0 | INDIA | OE
EPO | RU8265 | 23880 | CTCI CORPORATION | 10005764 | P - CTCI Corporation - 10005764 - HPX Pumps | 24044 | POC | USD | 1262568.62 | 1237317.62 | 2018-03-21 | 2018-12-14 |  | 1237317.62 |  | 70565849.4262 |  | 891916.01 |  | 493638 |  |  |  |  | 126256.9 | 8389775.9969 | 2018-05-14 | 22343 | 0 | ASIA | OE
EPO | RU8265 | 23880 | CTCI CORPORATION | 10005764 | P - CTCI Corporation - 10005764 - Extended warranty | 24045 | SL | USD |  | 25251.38 | 2018-03-21 | 2018-12-14 |  | 25251 |  |  |  | 0 | 0 | 0 |  |  |  |  | 189385.35 |  | 2018-05-23 | 22423 | 0 | ASIA | OE | 2019-01-01 | 2020-12-31
EPO | RU8265 | 23881 | CTCI CORPORATION | 10005765 | P - CTCI Corporation - 10005765 - HPX Pumps | 24063 | POC | USD | 472727 | 472727 | 2018-03-21 | 2019-01-10 |  | 472727 |  | 26421037.0298 |  | 83827.2 | 0 | 43736 |  |  |  |  | 118181.25 | 7853148.7351 | 2018-05-16 | 22372 / 22452 | 0 | ASIA | OE
EPO | RU8265 | 23882 | NLC INDIA LIMITED | 10005897 | P-NLC INDIA LIMITED-10005897-Spares | 24441 | POC | INR | 30090283.8812 | 461506.72 | 2018-03-15 | 2018-10-12 |  | 30090283.8812 |  | 11881974.4688 |  | 0 |  | 0 | [8 empty] | 0 | INDIA | AM
EPO | RU8265 | 24186 | INDIAN OIL CORPORATION LIMITED | 10005933 | P - Indian Oil Corporation Limited - 10005933 (WPX Pumps) | 25892 | POC | INR | 17647743.5202 | 216737 | 2018-03-23 | 2019-01-22 |  | 13999137.5885 |  | 12379381.6551 |  | 0 |  | 0 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 24186 | INDIAN OIL CORPORATION LIMITED | 10005933 | P - Indian Oil Corporation Limited - 10005933 (HPX Pumps) | 25929 | POC | INR |  | 56488.33 | 2018-03-23 | 2019-01-22 |  | 3648605.9317 |  | 3083010.4775 |  | 19075.8 |  | 25256.7 | [8 empty] | 0 | INDIA | OE
EPO | RU8265 | 25926 | INDIAN OIL CORPORATION LIMITED | 10005804 | P - Indian Oil Corporation Limited - 10005804 (HPX Pumps) | 25959 | POC | INR | 16534795.0441 | 253951.7 | 2018-02-26 | 2018-05-31 |  | 16534795.0441 |  | 11039881.5264 |  | 3808041.42 |  | 1227000 |  |  | 3111502.14 | [5 empty] | 0 | INDIA | OE
EPO | RU8265 | 27147 | HYUNDAI ENGINEERING CO LTD | 10006057 | P-HYUNDAI ENGINEERING CO LTD-10006057- HED Pumps | 27243 | POC | USD | 1463083 | 1463083 | 2018-04-17 | 2019-05-31 |  | 1463083 |  | 71539429.5897 |  | 30229.86 | [6 empty] | 146308.3 | 9722192.3197 | 2018-05-30 | 22509 | 0 | ASIA | OE
EPO | RU8265 | 27148 | HYUNDAI ENGINEERING CO LTD | 10006029 | P - Hyundai Engineering Co. Ltd. - 10006029 - HPX Pumps | 27221 | POC | USD | 900000 | 900000 | 2018-04-17 | 2019-03-06 |  | 900000 |  | 46462183.0986 |  | 5842.4 |  | 910 |  |  |  |  | 90000 | 5980503.5584 | 2018-05-30 | 22511 | 0 | ASIA | OE
EPO | RU8265 | 27152 | HYUNDAI ENGINEERING CO LTD | 10006041 | P-HYUNDAI ENGINEERING CO LTD-10006041 | 27307 | POC | USD | 805000 | 805000 | 2018-04-16 | 2019-04-13 |  | 805000 |  | 28933787.037 |  | 0 | 0 | 0 |  |  |  |  | 80500 | 5349228.1828 | 2018-05-30 | 22512 | 0 | ASIA | OE
EPO | RU8265 | 27158 | HYUNDAI ENGINEERING CO LTD | 10005716 | P - Hyundai Engineering Co. Ltd. - 10005716 | 27245 | POC | USD | 830000 | 830000 | 2018-04-09 | 2019-03-15 |  | 830000 |  | 41556180.2721 |  | 366167.15 | 0 | 0 |  |  |  |  | 83000 | 5515353.2816 | 2018-05-30 | 22510 | 0 | ASIA | OE
EPO | RU8265 | 28155 | NTPC Limited | 10006101 | P-NATIONAL THERMAL POWER CORPORATION LIMITED-10006101 | 28325 | POC | INR | 27730731.8424 | 417317.26 | 2018-05-04 | 2018-09-10 |  | 27730731.8424 |  | 13161432.1288 |  | 0 | 0 | 0 | [8 empty] | 0 | ASIA | AM
EPO | RU8265 | 28221 | DANGOTE OIL REFINING COMPANY LIMITED | 10006130 | P - Dangote Oil Refining Company Limited - 10006130 - VTP Pump | 28315 | POC | USD | 1013473 | 97502 | 2018-05-02 | 2019-08-02 |  | 97502 |  | 6112895.5451 |  | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | OTHERAFRICA | OE
EPO | RU8265 | 28221 | DANGOTE OIL REFINING COMPANY LIMITED | 10006130 | P - Dangote Oil Refining Company Limited - 10006130 - HPX Pump | 28324 | POC | USD |  | 159123 | 2018-05-02 | 2019-08-02 |  | 159123 |  | 11128202.3148 |  | 0 | 0 | 0 | [8 empty] | 0 | OTHERAFRICA | OE
EPO | RU8265 | 28221 | DANGOTE OIL REFINING COMPANY LIMITED | 10006130 | P - Dangote Oil Refining Company Limited - 10006130 - HED Pump | 28327 | POC | USD |  | 715982 | 2018-05-02 | 2019-08-02 |  | 715982 |  | 43930103.3906 |  | 0 | 0 | 0 | [8 empty] | 0 | OTHERAFRICA | OE
EPO | RU8265 | 28221 | DANGOTE OIL REFINING COMPANY LIMITED | 10006130 | P - Dangote Oil Refining Company Limited - 10006130 - VTP Spares | 28329 | POC | USD |  | 1997 | 2018-05-02 | 2019-08-02 |  | 1997 |  | 125202.0718 |  | 0 | 0 | 0 | [8 empty] | 0 | OTHERAFRICA | OE
EPO | RU8265 | 28221 | DANGOTE OIL REFINING COMPANY LIMITED | 10006130 | P - Dangote Oil Refining Company Limited - 10006130 - HPX Spares | 28333 | POC | USD |  | 14225 | 2018-05-02 | 2019-08-02 |  | 14225 |  | 994819.5919 |  | 0 | 0 | 0 | [8 empty] | 0 | OTHERAFRICA | OE
EPO | RU8265 | 28221 | DANGOTE OIL REFINING COMPANY LIMITED | 10006130 | P - Dangote Oil Refining Company Limited - 10006130 - HED Spares | 28334 | POC | USD |  | 24644 | 2018-05-02 | 2019-08-02 |  | 24644 |  | 1512067.9961 |  | 0 | 0 | 0 | [8 empty] | 0 | OTHERAFRICA | OE
IPO | RU8279 | 6089 | AECOM Energy & Construction Inc | 10004636 | P-AECOM Energy & Construction Inc-10004636 | 6119 | POC | USD | 403302 | 403302 | 2017-04-28 | 2018-02-23 |  | 403302 | 0 | 16488500.58 |  | 16488500.58 |  |  |  | 2017-12-31 |  |  |  | 0 |  |  | 257427.9039 | US | OE
IPO | RU8279 | 6103 | JGC CORPORATION | 10004694 | P-JGC CORPORATION-10004694-SIA OILY WATER PUMP / 210-GA-623A/B | 6193 | POC | USD | 462978 | 61350 | 2017-05-16 | 2018-05-30 |  | 61350 | 0 | 2689939.6786 |  | 2689939.6786 |  |  |  | 2018-04-11 |  |  | 46295.2 | 3076317.8704 | 2018-05-29 | 22508 | 0 | ASIA | OE
IPO | RU8279 | 6103 | JGC CORPORATION | 10004694 | P-JGC CORPORATION-10004694-SIA OILY WATER PUMP / 220-GA-1423A/B | 6194 | POC | USD |  | 48118 | 2017-05-16 | 2018-05-30 |  | 48118 | 0 | 2109772.0857 |  | 2109772.0857 |  |  |  | 2018-04-11 | [6 empty] | 0 |  | OE
IPO | RU8279 | 6103 | JGC CORPORATION | 10004694 | P-JGC CORPORATION-10004694-WIC OILY WATER PUMP / 230-GA-2423A/B | 6195 | POC | USD |  | 64812 | 2017-05-16 | 2018-05-30 |  | 64812 | 0 | 2841733.8297 |  | 2841733.8297 |  |  |  | 2018-04-11 | [6 empty] | 0 |  | OE
IPO | RU8279 | 6103 | JGC CORPORATION | 10004694 | P-JGC CORPORATION-10004694-W2A OILY WATER PUMP / 240-GA-1523A/B | 6196 | POC | USD |  | 53318 | 2017-05-16 | 2018-05-30 |  | 53318 | 0 | 2337770.2328 |  | 2337770.2328 |  |  |  | 2018-04-11 | [6 empty] | 0 |  | OE
IPO | RU8279 | 6103 | JGC CORPORATION | 10004694 | P-JGC CORPORATION-10004694-EIC OILY WATER PUMP / 250-GA-2123A/B | 6197 | POC | USD |  | 78460 | 2017-05-16 | 2018-05-30 |  | 78460 | 0 | 3440141.2744 |  | 3440141.2744 |  |  |  | 2018-04-11 | [6 empty] | 0 |  | OE
IPO | RU8279 | 6103 | JGC CORPORATION | 10004694 | P-JGC CORPORATION-10004694-E2A OILY WATER PUMP / 260-GA-1923A/B | 6198 | POC | USD |  | 78460 | 2017-05-16 | 2018-05-30 |  | 78460 | 0 | 3440141.2744 |  | 3440141.2744 |  |  |  | 2018-04-11 | [6 empty] | 0 |  | OE
IPO | RU8279 | 6103 | JGC CORPORATION | 10004694 | P-JGC CORPORATION-10004694-E2A F OILY WATER PUMP / 280-GA-1623A/B | 6199 | POC | USD |  | 78460 | 2017-05-16 | 2018-05-30 |  | 78460 | 0 | 3440141.2744 |  | 3440141.2744 |  |  |  | 2018-04-11 | [6 empty] | 0 |  | OE
IPO | RU8279 | 6111 | HSS JV (HYUNDAI E&C CO. LTD. / SAIPEM S.P.A / SK E&C CO.LTD | 10005394 | P-HSS JV (HYUNDAI E&C CO. LTD. / SAIPEM S.P.A / SK E&C CO.LTD)-10005394-SERVICE WATER PUMP UNIT 85 / 85-P-2002 A/B | 6233 | POC | USD | 688000 | 269197 | 2017-04-28 | 2018-01-28 |  | 269197 | 0 | 15975696.9826 |  | 940812.09 | [7 empty] | 0 |  |  | 0 | ASIA | OE
IPO | RU8279 | 6111 | HSS JV (HYUNDAI E&C CO. LTD. / SAIPEM S.P.A / SK E&C CO.LTD | 10005394 | P-HSS JV (HYUNDAI E&C CO. LTD. / SAIPEM S.P.A / SK E&C CO.LTD)-10005394-SERVICE WATER PUMP UNIT 93 / 93-P-1006 A/B | 6234 | POC | USD |  | 348126 | 2017-04-28 | 2018-01-28 |  | 348126 | 0 | 20659797.4263 |  | 940812.09 | [10 empty] | 0 |  | OE
IPO | RU8279 | 6111 | HSS JV (HYUNDAI E&C CO. LTD. / SAIPEM S.P.A / SK E&C CO.LTD | 10005394 | P-HSS JV (HYUNDAI E&C CO. LTD. / SAIPEM S.P.A / SK E&C CO.LTD)-10005394-POTABLE WATER PUMP UNIT 85 / 85-P-2003 A/B | 6235 | POC | USD |  | 16107 | 2017-04-28 | 2018-01-28 |  | 16107 | 0 | 955881.9426 |  | 871361.13 | [10 empty] | 0 |  | OE
IPO | RU8279 | 6111 | HSS JV (HYUNDAI E&C CO. LTD. / SAIPEM S.P.A / SK E&C CO.LTD | 10005394 | P-HSS JV (HYUNDAI E&C CO. LTD. / SAIPEM S.P.A / SK E&C CO.LTD)-10005394-POTABLE WATER PUMP UNIT 93 / 93-P-1008 A/B/C | 6237 | POC | USD |  | 28626 | 2017-04-28 | 2018-01-28 |  | 28626 | 0 | 1698831.3459 |  | 871361.13 | [10 empty] | 0 |  | OE
IPO | RU8279 | 6111 | HSS JV (HYUNDAI E&C CO. LTD. / SAIPEM S.P.A / SK E&C CO.LTD | 10005394 | P-HSS JV (HYUNDAI E&C CO. LTD. / SAIPEM S.P.A / SK E&C CO.LTD)-10005394-DIESEL TRANSFER PUMP UNIT 93 / 93-P-1009 A/B | 6238 | POC | USD |  | 25944 | 2017-04-28 | 2018-01-28 |  | 25944 | 0 | 1539666.0532 |  | 1173550.56 | [10 empty] | 0 |  | OE
IPO | RU8279 | 9212 | DANGOTE OIL REFINING COMPANY LIMITED | 10005093 | P-DANGOTE OIL REFINING COMPANY LIMITED-10005093-Package Pump EX1755009A | 20767 | POC | USD | 1627254 | 1395108 | 2017-09-20 | 2018-11-16 |  | 1395108 | 0 | 68534922.0286 |  | 157063.38 | 6431696.02 | [6 empty] | 0 |  |  | 1059505.0794 | OTHERAFRICA | OE
IPO | RU8279 | 9212 | DANGOTE OIL REFINING COMPANY LIMITED | 10005093 | P-DANGOTE OIL REFINING COMPANY LIMITED-10005093-Package Pump Parts EX1750009A | 20768 | POC | USD |  | 232146 | 2017-09-20 | 2018-11-16 |  | 232146 | 0 | 11809009.6886 |  | 0 | [10 empty] | 0 | OTHERAFRICA | OE
IPO | RU8279 | 16001 | PUNJ LLOYD LIMITED | 10005423 | P-Punj Lloyd Limited-10005423-BULLET PUMPS | 17017 | POC | INR | 21050203.2468 | 324173.13 | 2017-11-15 | 2018-07-10 |  | 21050203.2468 | 0 | 14672377.4053 |  | 1617356.92 | 770234.08 | [9 empty] | 0 | OTHER | OE
IPO | RU8279 | 19404 | SAFBON WATER TECHNOLOGY, INC | 10005575 | P-SAFBON WATER TECHNOLOGY, INC-10005575 spare parts brine discharge pump | 19839 | PIT | USD | 283518 | 1546 | 2017-11-07 | 2018-05-29 |  | 1546 | 0 | 79890.5 |  | 79890.5 |  |  |  | 2018-01-30 |  |  |  | 0 |  |  | 0 | EUROPE | OE
IPO | RU8279 | 19404 | SAFBON WATER TECHNOLOGY, INC | 10005575 | P-SAFBON WATER TECHNOLOGY, INC-10005575 ERD Booster Pump | 20525 | POC | USD |  | 57412 | 2017-11-07 | 2018-05-29 |  | 57412 | 0 | 2815595.86 |  | 2815595.86 |  |  |  | 2018-05-15 |  |  | 62512 |  | 2018-05-14 | 22341 | 0 | EUROPE | OE
IPO | RU8279 | 19404 | SAFBON WATER TECHNOLOGY, INC | 10005575 | P-SAFBON WATER TECHNOLOGY, INC-10005575 Spare parts for ERD Booster Pump | 20526 | POC | USD |  | 5782 | 2017-11-07 | 2018-05-29 |  | 5782 | 0 | 275651.88 |  | 275651.88 |  |  |  | 2018-05-15 |  |  | 5782 |  | 2018-05-14 | 22342 | 0 | EUROPE | OE
IPO | RU8279 | 19404 | SAFBON WATER TECHNOLOGY, INC | 10005575 | P-SAFBON WATER TECHNOLOGY, INC-10005575 Brine Discharge Pump | 20527 | PIT | USD |  | 180274 | 2017-11-07 | 2018-05-29 |  | 180274 | 0 | 4946686.3506 |  | 4768276.29 |  | 178410.0606 |  | 2018-01-30 | [6 empty] | 0 | EUROPE | OE
IPO | RU8279 | 19404 | SAFBON WATER TECHNOLOGY, INC | 10005575 | P-SAFBON WATER TECHNOLOGY, INC-10005575 Treated water | 20528 | PIT | USD |  | 37365 | 2017-11-07 | 2018-05-29 |  | 37365 | 0 | 1170906.28 |  | 1170906.28 |  |  |  | 2018-01-30 | [6 empty] | 0 | EUROPE | OE
IPO | RU8279 | 19404 | SAFBON WATER TECHNOLOGY, INC | 10005575 | P-SAFBON WATER TECHNOLOGY, INC-10005575 Spare parts Treated water | 20529 | PIT | USD |  | 1139 | 2017-11-07 | 2018-05-29 |  | 1139 | 0 | 9041.64 |  | 9041.64 |  |  |  | 2018-01-30 | [6 empty] | 0 | EUROPE | OE
IPO | RU8279 | 21906 | L&T Hydrocarbon Engineering | 10005584 | P-L&T Hydrocarbon Engineering-10005584-VTP Pump | 22337 | POC | INR | 22999987.4426 | 201774 | 2017-12-25 | 2018-09-21 |  | 12849883 | 0 | 11431870.274 |  | 771844.57 |  | 1380 |  |  |  |  | 3450000 |  | 2018-05-12 | 22330 /22331 / 22332 / 22333 | 344999.8089 | OTHER | OE
IPO | RU8279 | 21906 | L&T Hydrocarbon Engineering | 10005584 | P-L&T Hydrocarbon Engineering-10005584-CPX Pump | 22338 | POC | INR |  | 159381 | 2017-12-25 | 2018-09-21 |  | 10150104.4426 | 0 | 8100766.5785 |  | 657221.67 |  | 542993 | [8 empty] | 0 | OTHER | OE
IPO | RU8279 | 22934 | Yinson Lavender Limited | 10005778 | P - Yinson Lavender Limited - 10005778 - Seawater lift pumps (2 Nos) | 23341 | POC | USD | 396192 | 396192 | 2018-02-01 | 2018-09-21 |  | 396192 | 0 | 21222990.112 |  | 127799.4 | [6 empty] | 79238.4 | 5265394.8129 | 2018-05-09 | 22314 | 386940.9168 | CHINA | OE
IPO | RU8279 | 23877 | CTCI CORPORATION | 10005766 | P-CTCI CORPORATION-10005766-VTP Pumps | 24049 | POC | USD | 1035637.24 | 1014924.24 | 2018-03-21 | 2019-01-05 |  | 1014924.24 | 0 | 58535513.2692 |  | 2630875.52 |  | 402804 |  |  |  |  | 103563.8 | 6881818.6047 | 2018-05-09 | 22310 | 337151.6253 | ASIA | OE
IPO | RU8279 | 23877 | CTCI CORPORATION | 10005766 | P-CTCI CORPORATION-10005766-Extended warranty | 24050 | SL | USD |  | 20712.76 | 2018-03-21 | 2019-01-05 |  | 20713 | 0 |  |  | 0 | [6 empty] | 155345.7 |  | 2018-05-23 | 22424 | 0 | ASIA | OE | 2019-10-01 | 2020-09-30
IPO | RU8279 | 23878 | SK ENGINEERING & CONSTRACTION | 10005882 | P - SK Engineering & Construction - 10005882 - Steam condensate transfer pumps | 23917 | POC | USD | 438371 | 42401 | 2018-03-21 | 2019-02-10 |  | 42401 | 0 | 6468471.591 |  | 0 | [7 empty] | 0 |  |  | 0 | ASIA | OE
IPO | RU8279 | 23878 | SK ENGINEERING & CONSTRACTION | 10005882 | P - SK Engineering & Construction - 10005882 - Water pumps | 23918 | POC | USD |  | 286764 | 2018-03-21 | 2019-02-10 |  | 286764 | 0 | 16985557.454 |  | 2383.8 | [10 empty] | 0 | ASIA | OE
IPO | RU8279 | 23878 | SK ENGINEERING & CONSTRACTION | 10005882 | P - SK Engineering & Construction - 10005882 - Cooling water supply pumps | 23919 | POC | USD |  | 109206 | 2018-03-21 | 2019-02-10 |  | 109206 | 0 | 2511488.9652 |  | 0 | [10 empty] | 0 | ASIA | OE
IPO | RU8279 | 28138 | FARABI DOWNSTREAM COMPANY | 10006018 | P - Farabi Downstream Company - 10006018 - EX1825003 LNN Pumps | 28217 | POC | USD | 783892.76 | 161230.68 | 2018-05-02 | 2018-10-30 |  | 161230.68 | 0 | 10333128.9802 |  | 3640 | [7 empty] | 0 |  |  | 0 | MIDEAST | OE
IPO | RU8279 | 28138 | FARABI DOWNSTREAM COMPANY | 10006018 | P - Farabi Downstream Company - 10006018 - EX1865006 HPX Pumps | 28218 | POC | USD |  | 46911 | 2018-05-02 | 2018-10-30 |  | 46911 | 0 | 2990154.8598 |  | 0 | [10 empty] | 0 | MIDEAST | OE
IPO | RU8279 | 28138 | FARABI DOWNSTREAM COMPANY | 10006018 | P - Farabi Downstream Company - 10006018 - EX1873001 CPX Pumps | 28219 | POC | USD |  | 54851.42 | 2018-05-02 | 2018-10-30 |  | 54851.42 | 0 | 4318153.8339 |  | 0 | [10 empty] | 0 | MIDEAST | OE
IPO | RU8279 | 28138 | FARABI DOWNSTREAM COMPANY | 10006018 | P - Farabi Downstream Company - 10006018 - EX1874003 CPX Pumps | 28220 | POC | USD |  | 520899.66 | 2018-05-02 | 2018-10-30 |  | 520899.66 | 0 | 28999168.2453 |  | 42942.57 | [10 empty] | 0 | MIDEAST | OE
FCO | RU8293 | 3857 | JGC Corporation | 62777 | P - JGC Corporation - 62777 | 3861 | POC | EUR | 1139271.9954 | 1280655.65 | 2017-10-26 | 2019-01-01 |  | 1139271.9954 |  | 860836 |  | 846900.36 |  |  |  |  | 292858 |  | 75942.9 |  | 2018-05-21 | 1802000227/229 | 5411 | JAPAN | OE
FCO | RU8293 | 7839 | CONSUMERS ENERGY COMPANY | 62876 | P - Consumers Energy Company - 62876 | 9349 | POC | USD | 1069055 | 1054055 | 2017-09-26 | 2018-04-20 |  | 1054055 |  | 799400.38 |  | 588900.57 |  |  |  |  | 605769 |  | 71288 | 59027.9043 | 2018-05-04 | 1802000154 | 17066.0393 | US | OE
FCO | RU8293 | 7839 | CONSUMERS ENERGY COMPANY | 62876 | P - Consumers Energy Company - 62876 | 9416 | SL | USD |  | 15000 | 2017-09-26 | 2018-04-20 |  | 15000 |  |  |  | 0 | [10 empty] | 0 | US | OE | 2019-10-01 | 2020-09-30
FCO | RU8293 | 9924 | Monobuoy SARL | 62896 | P - Monobuoy Sarl - 62896 | 9926 | POC | EUR | 213763.999 | 254550.17 | 2017-09-25 | 2018-04-03 |  | 213763.999 |  | 130740 |  | 117301.67 | [10 empty] | 0 | EUROPE | OE
FCO | RU8293 | 9939 | Eaching International Limited | 62904 | P - Eaching International Limited - 62904 | 9941 | POC | EUR | 399269.995 | 459695.24 | 2017-09-27 | 2018-04-06 |  | 386038.999 |  | 307621.42 |  | 307621.42 |  |  |  | 2018-04-05 | [6 empty] | 0 | CHINA | OE
FCO | RU8293 | 9939 | Eaching International Limited | 62904 | P - Eaching International Limited - 62904 | 12432 | POC | EUR |  | 10003.91 | 2017-09-27 | 2018-04-06 |  | 8400.9993 |  | 6067 |  | 6066.78 |  |  |  | 2018-04-05 | [6 empty] | 0 | CHINA | OE
FCO | RU8293 | 9939 | Eaching International Limited | 62904 | P - Eaching International Limited - 62904 | 12435 | POC | EUR |  | 5751.56 | 2017-09-27 | 2018-04-06 |  | 4829.9966 |  | 4439.74 |  | 4439.74 |  |  |  | 2018-04-05 | [6 empty] | 0 | CHINA | OE
FCO | RU8293 | 12760 | SAMSUNG ENGINEERING CO LTD | 62941 | P - Samsung Engineering Co Ltd - 62941/5000030008 (18) Trunnion Ball Top Entry Valves (Spare Parts) | 12762 | POC | USD | 795000 | 795000 | 2017-11-15 | 2018-06-11 |  | 795000 |  | 514330 |  | 319217.86 | [7 empty] | 0 |  |  | 0 | ASIA | OE
FCO | RU8293 | 12766 | WELLIGHT CHINA LIMITED | 62947 | P - WELLIGHT CHINA LIMITED - 62947 | 12768 | POC | EUR | 315361.9997 | 363565.27 | 2017-12-28 | 2018-07-26 |  | 312234.0003 |  | 270642 |  | 189064.2 | [6 empty] | 220753 |  | 2018-05-17 | 1802000218 | 0 | CHINA | OE
FCO | RU8293 | 12766 | WELLIGHT CHINA LIMITED | 62947 | P - WELLIGHT CHINA LIMITED - 62947 | 17129 | POC | EUR |  | 2278.73 | 2017-12-28 | 2018-07-26 |  | 1956.9993 |  | 1290 |  | 1290 | [10 empty] | 0 | CHINA | OE
FCO | RU8293 | 12766 | WELLIGHT CHINA LIMITED | 62947 | P - WELLIGHT CHINA LIMITED - 62947 | 17142 | SL | EUR |  | 1363.51 | 2017-12-28 | 2018-07-26 |  | 1171 |  |  |  | 0 | [10 empty] | 0 | CHINA | OE | 2020-01-26 | 2021-01-25
FCO | RU8293 | 14769 | WELLIGHT CHINA LIMITED | 62966 | P - Wellight China Limited - 62966 | 16946 | POC | EUR | 536948 | 639075.51 | 2017-11-20 | 2018-07-06 |  | 536948 |  | 507386 |  | 236617.33 | [6 empty] | 1167 |  | 2018-05-10 | 1802000210 | 0 | CHINA | OE
FCO | RU8293 | 14786 | SAMSUNG ENGINEERING CO., LTD | 62969/2017 | P - Samsung Engineering Co, Ltd - 62969 | 14788 | POC | USD | 514737 | 514737 | 2017-12-13 | 2018-08-13 |  | 514737 |  | 370979 |  | 360982.37 |  |  |  |  | 153074 |  | 112845 | 93437.9399 | 2018-05-14 | 1802000212 | 0 | ASIA | OE
FCO | RU8293 | 14956 | CHEVRON AUSTRALIA | 62971 and 62978 | P - Chevron Australia Pty Ltd - 62971 62978 | 14958 | POC | AUD | 6140327.346 | 1773099.82 | 2017-12-15 | 2019-10-31 |  | 2343510.2035 |  | 1264718 |  | 1084666.45 | [7 empty] | 0 |  |  | 0 | OTHER | OE
FCO | RU8293 | 14956 | CHEVRON AUSTRALIA | 62971 and 62978 | P - Chevron Australia Pty Ltd - 62971 62978 | 18700 | POC | AUD |  | 1257462.81 | 2017-12-15 | 2019-10-31 |  | 1661991.5543 |  | 897068 |  | 0 | [10 empty] | 0 | OTHER | OE
FCO | RU8293 | 14956 | CHEVRON AUSTRALIA | 62971 and 62978 | P - Chevron Australia Pty Ltd - 62971 62978 | 18713 | POC | AUD |  | 1615209.04 | 2017-12-15 | 2019-10-31 |  | 2134825.5882 |  | 1152279 |  | 6329.35 | [10 empty] | 0 | OTHER | OE
FCO | RU8293 | 18193 | JGC Corporation | 62996 | P - JGC Corporation - 62996 | 18197 | POC | EUR | 893268.6812 | 1075343.85 | 2018-02-05 | 2019-01-31 |  | 893268.6812 |  | 728637.06 |  | 0 | [6 empty] | 315 |  | 2018-05-22 | 1802000233 | 4243 | JAPAN | OE
FCO | RU8293 | 18259 | Petrofac E&C Oman LLC | 62995 | P - PETROFAC E&C OMAN LLC - 62995 | 18261 | POC | USD | 900000 | 900000 | 2017-12-29 | 2018-08-29 |  | 900000 |  | 628520 |  | 29006.05 | [7 empty] | 0 |  |  | 0 | OTHER | OE
FCO | RU8293 | 18402 | Hyundai Engineering Co., Ltd. | 62796 | P - Hyundai Engineering Co., Ltd. - 62796 - Supply of 48 valves | 18826 | POC | EUR | 4300000 | 5158280 | 2017-04-28 | 2018-02-28 |  | 4300000 |  | 4616969 |  | 4616969 |  |  |  |  | 3497073 | [5 empty] | 4044 | ASIA | OE
FCO | RU8293 | 18619 | Intecsa Industrial | 62794 - 62795 | P - Intecsa Industrial - 62794 - 62795 | 18694 | POC | EUR | 887267 | 955764.01 | 2017-10-13 | 2018-07-16 |  | 887267 |  | 858726.47 |  | 779400.82 |  |  |  |  | 752593 |  | 112627 |  | 2018-05-16 | 1801000045/46/54/55 | 0 | EUROPE | OE
FCO | RU8293 | 19004 | Tengizchevroil LLP | 62579 | P - Tengizchevroil LLP - 62579 | 19535 | POC | EUR | 6392930.0087 | 5733013.44 | 2017-02-06 | 2018-12-10 |  | 4779104 |  | 1980487 |  | 1980487 |  |  |  | 2017-12-15 | [6 empty] | 92715 | ASIA | OE
FCO | RU8293 | 19004 | Tengizchevroil LLP | 62579 | P - Tengizchevroil LLP - 62579 - 2 | 19560 | POC | EUR |  | 1768054.45 | 2017-02-06 | 2018-12-10 |  | 1473869.9983 |  | 519090 |  | 244546.66 | [10 empty] | 28593 | ASIA | OE
FCO | RU8293 | 19004 | Tengizchevroil LLP | 62579 | P - Tengizchevroil LLP - 62579 - 5^ change order | 22056 | POC | EUR |  | 167891.23 | 2017-02-06 | 2018-12-10 |  | 139956.0103 |  | 66878 |  | 3897.32 | [10 empty] | 4413 | ASIA | OE
FCO | RU8293 | 22475 | SAMSUNG ENGINEERING CO., LTD | 63034 | P - Samsung Engineering Co Ltd - 63034 | 22477 | POC | USD | 1069275 | 1069275 | 2018-02-16 | 2018-07-15 |  | 1069275 |  | 378057 |  | 77350.77 | [7 empty] | 0 |  |  | 0 | ASIA | OE
FCO | RU8293 | 23222 | Dubai Supply Authority | 63050 | P - DUSUP - 63050 | 23226 | POC | USD | 609595 | 609595 | 2018-03-07 | 2018-10-05 |  | 609595 |  | 412426 |  | 49441.68 | [7 empty] | 0 |  |  | 0 | MIDEAST | OE
FCO | RU8293 | 23797 | Petrofac International (UAE) LLC | 63055 | P - PETROFAC UAE - 63055 - Margins > 15% | 23799 | POC | EUR | 3558174.81 | 3386127.53 | 2018-03-23 | 2018-11-30 |  | 2422366.06 |  | 2244935.8 |  | 0 | [6 empty] | 43659 |  | 2018-05-22 | 1802000234 | 0 | ASIA | OE
FCO | RU8293 | 23797 | Petrofac International (UAE) LLC | 63055 | P - PETROFAC UAE - 63055 - Margins < 15% | 26180 | POC | EUR |  | 1833773.3 | 2018-03-23 | 2018-11-30 |  | 1135808.75 |  | 1328934 |  | 193940.24 | [10 empty] | 0 | ASIA | OE
FCO | RU8293 | 26354 | Basrah Gas Company | 63087 | P - Basrah Gas Company - 63087 | 26356 | POC | USD | 1778496 | 1778496 | 2018-04-19 | 2018-11-19 |  | 1778496 |  | 1153970.44 |  | 0 | [6 empty] | 533549 | 441789.3517 | 2018-05-22 | 1802000232 | 0 | IRAQ | OE
FCO | RU8293 | 27618 | Chevron Australia Pty Ltd | 63076 | P - Chevron Australia Pty Ltd - 63076 | 27623 | POC | AUD | 2196661.9971 | 1654306.15 | 2018-04-30 | 2020-07-31 |  | 2196661.9971 |  | 1093671.53 |  | 0 | [7 empty] | 0 |  |  | 0 | OTHER | OE
FCO | RU8295 | 4474 | TECNIMONT SPA | 7MI-7171336 | P - TECNIMONT - 7500063385 | 4500 | POC | EUR | 793999.8249 | 41671.09 | 2017-06-21 | 2018-03-31 |  | 36479.9877 |  | 29352 |  | 29352 |  |  |  |  | 29352 | [5 empty] | 0 | RUSCIS | OE
FCO | RU8295 | 4474 | TECNIMONT SPA | 7MI-7171336 | P - TECNIMONT - 7500063385 | 9110 | POC | EUR |  | 131958.47 | 2017-06-21 | 2018-03-31 |  | 115519.9772 |  | 92947 |  | 92947 |  |  |  |  | 92947 | [5 empty] | 0 | RUSCIS | OE
FCO | RU8295 | 4474 | TECNIMONT SPA | 7MI-7171336 | P - TECNIMONT - 7500063385 | 9111 | POC | EUR |  | 138903.65 | 2017-06-21 | 2018-03-31 |  | 121599.9737 |  | 97839 |  | 97839 |  |  |  |  | 97839 | [5 empty] | 0 | RUSCIS | OE
FCO | RU8295 | 4474 | TECNIMONT SPA | 7MI-7171336 | P - TECNIMONT - 7500063385 | 9112 | POC | EUR |  | 138903.65 | 2017-06-21 | 2018-03-31 |  | 121599.9737 |  | 97839 |  | 97839 |  |  |  |  | 97839 | [5 empty] | 0 | RUSCIS | OE
FCO | RU8295 | 4474 | TECNIMONT SPA | 7MI-7171336 | P - TECNIMONT - 7500063385 | 9113 | POC | EUR |  | 138903.65 | 2017-06-21 | 2018-03-31 |  | 121599.9737 |  | 97839 |  | 97839 |  |  |  |  | 97839 | [5 empty] | 0 | RUSCIS | OE
FCO | RU8295 | 4474 | TECNIMONT SPA | 7MI-7171336 | P - TECNIMONT - 7500063385 | 9114 | POC | EUR |  | 138903.65 | 2017-06-21 | 2018-03-31 |  | 121599.9737 |  | 97839 |  | 97839 |  |  |  |  | 97839 | [5 empty] | 0 | RUSCIS | OE
FCO | RU8295 | 4474 | TECNIMONT SPA | 7MI-7171336 | P - TECNIMONT - 7500063385 | 9115 | POC | EUR |  | 177741.84 | 2017-06-21 | 2018-03-31 |  | 155599.965 |  | 125196 |  | 125196 |  |  |  |  | 125196 | [5 empty] | 0 | RUSCIS | OE
FCO | RU8295 | 8849 | TECNIMONT SPA | 7MI 7171318 and 7MI 7171332 | P - TECNIMONT - 7500062926 - Delivery by the end of April 2018 | 8852 | POC | EUR | 1513916.0028 | 1662011.09 | 2017-06-29 | 2018-09-10 |  | 1454969.0011 |  | 1565577 |  | 1298576 |  |  |  |  | 71615 |  | 406998.6 |  | 2018-05-28 | 6180317/6180318/6180370 | 0 | MIDEAST | OE
FCO | RU8295 | 8849 | TECNIMONT SPA | 7MI 7171318 and 7MI 7171332 | P - TECNIMONT - 7500062926 - Second delivery date | 23284 | POC | EUR |  | 33836.64 | 2017-06-29 | 2018-09-10 |  | 29621.5005 |  | 31873 |  | 26438 |  |  |  |  | 1458 | [5 empty] | 0 | MIDEAST | OE
FCO | RU8295 | 8849 | TECNIMONT SPA | 7MI 7171318 and 7MI 7171332 | P - TECNIMONT - 7500062926 - Third delivery date | 23285 | POC | EUR |  | 33498.52 | 2017-06-29 | 2018-09-10 |  | 29325.5012 |  | 31555 |  | 26173 |  |  |  |  | 1443 | [5 empty] | 0 | MIDEAST | OE
FCO | RU8295 | 10043 | TECHNIP ITALY SPA | 7MI 7171445 | P - TECHNIP - O5090 - Lot 1 | 10044 | POC | EUR | 431383.003 | 6690.59 | 2017-08-02 | 2018-10-05 |  | 5618.5673 |  | 4405 |  | 1502 | [6 empty] | 011668.80 |  | 2018-03-14 | 6180163 | 0 | ASIA | OE
FCO | RU8295 | 10043 | TECHNIP ITALY SPA | 7MI 7171445 | P - TECHNIP - O5090 - Lot 2 | 10045 | POC | EUR |  | 34327.06 | 2017-08-02 | 2018-10-05 |  | 28826.8895 |  | 22599 |  | 7706 | [10 empty] | 0 | ASIA | OE
FCO | RU8295 | 10043 | TECHNIP ITALY SPA | 7MI 7171445 | P - TECHNIP - O5090 - Lot 3 | 10046 | POC | EUR |  | 100616.11 | 2017-08-02 | 2018-10-05 |  | 84494.5499 |  | 66241 |  | 22586 | [10 empty] | 0 | ASIA | OE
FCO | RU8295 | 10043 | TECHNIP ITALY SPA | 7MI 7171445 | P - TECHNIP - O5090 - Lot 4 | 23293 | POC | EUR |  | 79895.39 | 2017-08-02 | 2018-10-05 |  | 67093.8781 |  | 52599 |  | 17935 | [10 empty] | 0 | ASIA | OE
FCO | RU8295 | 10043 | TECHNIP ITALY SPA | 7MI 7171445 | P - TECHNIP - O5090 - Lot 5 | 23294 | POC | EUR |  | 142388.37 | 2017-08-02 | 2018-10-05 |  | 119573.7068 |  | 93742 |  | 31964 | [10 empty] | 0 | ASIA | OE
FCO | RU8295 | 10043 | TECHNIP ITALY SPA | 7MI 7171445 | P - TECHNIP - O5090 - Lot 6 | 23295 | POC | EUR |  | 115840 | 2017-08-02 | 2018-10-05 |  | 97279.1401 |  | 76263 |  | 26004 | [10 empty] | 0 | ASIA | OE
FCO | RU8295 | 10043 | TECHNIP ITALY SPA | 7MI 7171445 | P - TECHNIP - O5090 - Lot 7 | 23296 | POC | EUR |  | 33933.36 | 2017-08-02 | 2018-10-05 |  | 28496.2714 |  | 22340 |  | 7617 | [10 empty] | 0 | ASIA | OE
FCO | RU8295 | 10913 | SNAMPROGETTI ENG | 7MI/7171461 | P - SNAMPROGETTI - 1188553 | 10914 | POC | EUR | 1452146.8422 | 290471.8 | 2017-09-25 | 2018-06-20 |  | 245912.4619 |  | 214807 |  | 161491 |  |  |  |  | 96406 |  | 253555.06 |  | 2018-04-24 | 6180287 | 0 | MIDEAST | OE
FCO | RU8295 | 10913 | SNAMPROGETTI ENG | 7MI/7171461 | P - SNAMPROGETTI - 1188553 | 10916 | POC | EUR |  | 299499.23 | 2017-09-25 | 2018-06-20 |  | 253555.0542 |  | 221483 |  | 166510 |  |  |  |  | 99402 | [5 empty] | 0 | MIDEAST | OE
FCO | RU8295 | 10913 | SNAMPROGETTI ENG | 7MI/7171461 | P - SNAMPROGETTI - 1188553 | 12789 | POC | EUR |  | 322295.69 | 2017-09-25 | 2018-06-20 |  | 272854.4616 |  | 238341 |  | 179184 |  |  |  |  | 106968 | [5 empty] | 0 | MIDEAST | OE
FCO | RU8295 | 10913 | SNAMPROGETTI ENG | 7MI/7171461 | P - SNAMPROGETTI - 1188553 | 12790 | POC | EUR |  | 423578.75 | 2017-09-25 | 2018-06-20 |  | 358600.364 |  | 313241 |  | 235493 |  |  |  |  | 140583 | [5 empty] | 0 | MIDEAST | OE
FCO | RU8295 | 10913 | SNAMPROGETTI ENG | 7MI/7171461 | P - SNAMPROGETTI - 1188553 | 19657 | POC | EUR |  | 379430.38 | 2017-09-25 | 2018-06-20 |  | 321224.5005 |  | 280592 |  | 210948 |  |  |  |  | 125931 | [5 empty] | 0 | MIDEAST | OE
FCO | RU8295 | 19113 | Amec Foster Wheeler Italiana S.r.l. | 7MI7170801 | P - Amec Foster Wheeler Italiana S.r.l. - 7MI7170801 - 1621A/01 | 19293 | POC | EUR | 537061.1204 | 312366.58 | 2017-03-02 | 2018-02-15 |  | 260392.2808 | 0 | 190544 |  | 189178 |  |  |  |  | 174982 | [5 empty] | 0 | EUROPE | OE
FCO | RU8295 | 19113 | Amec Foster Wheeler Italiana S.r.l. | 7MI7170801 | P - Amec Foster Wheeler Italiana S.r.l. - 7MI7170801 - 1621B/01 | 19294 | POC | EUR |  | 130312.88 | 2017-03-02 | 2018-02-15 |  | 108630.2768 | 0 | 79491 |  | 78921 |  |  |  |  | 72961 | [5 empty] | 0 | EUROPE | OE
FCO | RU8295 | 19113 | Amec Foster Wheeler Italiana S.r.l. | 7MI7170801 | P - Amec Foster Wheeler Italiana S.r.l. - 7MI7170801 - 1621C/01 | 19295 | POC | EUR |  | 195740.27 | 2017-03-02 | 2018-02-15 |  | 163171.2821 | 0 | 119402 |  | 118546 |  |  |  |  | 109594 | [5 empty] | 0 | EUROPE | OE
FCO | RU8295 | 19113 | Amec Foster Wheeler Italiana S.r.l. | 7MI7170801 | P - Amec Foster Wheeler Italiana S.r.l. - 7MI7170801 - 1624A/01 | 19296 | POC | EUR |  | 5838.79 | 2017-03-02 | 2018-02-15 |  | 4867.2808 | 0 | 3562 |  | 3536 |  |  |  |  | 3269 | [5 empty] | 0 | EUROPE | OE
FCO | RU8295 | 19508 | Tecnimont Spa | 7MI 7170314 | P-TECNIMONT SPA-7MI 7170314 -Supply of PEUMATIC DRIVEN BALLS | 19890 | POC | EUR | 2280388.9963 | 2710962.84 | 2016-06-27 | 2018-03-31 |  | 2259888.9963 |  | 1680109 |  | 1679109 |  |  |  |  | 1494308 | [5 empty] | 0 | RUSCIS | OE
FCO | RU8295 | 19508 | Tecnimont Spa | 7MI 7170314 | P-TECNIMONT SPA-7MI 7170314 -Warranty | 19891 | SL | EUR |  | 24591.8 | 2016-06-27 | 2018-03-31 |  | 20500 |  |  |  | 0 | [10 empty] | 0 | RUSCIS | OE | 2020-07-31 | 2022-01-31
FCO | RU8295 | 19566 | SAIPEM S.p.A. | 7MI7171646 | P - SAIPEM - 7MI 7171646 - Delivery Date 07/01/2018 | 19871 | POC | EUR | 707142 | 156848.07 | 2017-12-27 | 2018-09-10 |  | 130750 |  | 103568 |  | 53356 | [10 empty] | 0 | MIDEAST | OE
FCO | RU8295 | 19566 | SAIPEM S.p.A. | 7MI7171646 | P - SAIPEM - 7MI 7171646 - Delivery Date 07/15/2018 | 20107 | POC | EUR |  | 231918.92 | 2017-12-27 | 2018-09-10 |  | 193330 |  | 153139 |  | 78893 | [10 empty] | 0 | MIDEAST | OE
FCO | RU8295 | 19566 | SAIPEM S.p.A. | 7MI7171646 | P - SAIPEM - 7MI 7171646 - Delivery Date 08/15/2018 | 20108 | POC | EUR |  | 198309.22 | 2017-12-27 | 2018-09-10 |  | 165313 |  | 130946 |  | 67460 | [10 empty] | 0 | MIDEAST | OE
FCO | RU8295 | 19566 | SAIPEM S.p.A. | 7MI7171646 | P - SAIPEM - 7MI 7171646 - Delivery Date 09/10/2018 | 20109 | POC | EUR |  | 261212.29 | 2017-12-27 | 2018-09-10 |  | 217749 |  | 172481 |  | 88858 | [10 empty] | 0 | MIDEAST | OE
FCO | RU8295 | 19581 | Anagold Madencilik San. Ve Ticaret A.S. | 7MI7171157 | P - Anagold Madencilik - 7MI7171157 - 1621A/01 | 19591 | POC | EUR | 2201642.3891 | 398130.43 | 2016-10-01 | 2018-03-30 |  | 331885.987 |  | 248407 |  | 248407 |  |  |  |  | 204794 |  | 7644 |  | 2018-05-14 | 6180322 | 0 | OTHER | OE
FCO | RU8295 | 19581 | Anagold Madencilik San. Ve Ticaret A.S. | 7MI7171157 | P - Anagold Madencilik - 7MI7171157 - 1621B/01 | 19927 | POC | EUR |  | 760594.65 | 2016-10-01 | 2018-03-30 |  | 634040.2217 |  | 474561 |  | 474561 |  |  |  |  | 391242 | [5 empty] | 0 | OTHER | OE
FCO | RU8295 | 19581 | Anagold Madencilik San. Ve Ticaret A.S. | 7MI7171157 | P - Anagold Madencilik - 7MI7171157 - 1621B/02 | 19928 | POC | EUR |  | 481662.77 | 2016-10-01 | 2018-03-30 |  | 401519.4815 |  | 300526 |  | 300526 |  |  |  |  | 247763 | [5 empty] | 0 | OTHER | OE
FCO | RU8295 | 19581 | Anagold Madencilik San. Ve Ticaret A.S. | 7MI7171157 | P - Anagold Madencilik - 7MI7171157 - 1621C/02 | 19930 | POC | EUR |  | 902111.96 | 2016-10-01 | 2018-03-30 |  | 752010.6369 |  | 562858 |  | 562858 |  |  |  |  | 464037 | [5 empty] | 0 | OTHER | OE
FCO | RU8295 | 19581 | Anagold Madencilik San. Ve Ticaret A.S. | 7MI7171157 | P - Anagold Madencilik - 7MI7171157 - 1626A/01 | 19931 | POC | EUR |  | 50512.83 | 2016-10-01 | 2018-03-30 |  | 42108.061 |  | 31517 |  | 31517 |  |  |  |  | 25983 | [5 empty] | 0 | OTHER | OE
FCO | RU8295 | 19581 | Anagold Madencilik San. Ve Ticaret A.S. | 7MI7171157 | P - Anagold Madencilik - 7MI7171157 - 1621A/01 Commissioning Spares | 19933 | POC | EUR |  | 3572.41 | 2016-10-01 | 2018-03-30 |  | 2978.001 |  | 2229 |  | 2229 |  |  |  |  | 1838 | [5 empty] | 0 | OTHER | OE
FCO | RU8295 | 19581 | Anagold Madencilik San. Ve Ticaret A.S. | 7MI7171157 | P - Anagold Madencilik - 7MI7171157 - 1621B/01 Commissioning Spares | 19935 | POC | EUR |  | 20393.2 | 2016-10-01 | 2018-03-30 |  | 17000 |  | 12724 |  | 12724 |  |  |  |  | 10490 | [5 empty] | 0 | OTHER | OE
FCO | RU8295 | 19581 | Anagold Madencilik San. Ve Ticaret A.S. | 7MI7171157 | P - Anagold Madencilik - 7MI7171157 - 1621B/02 Commissioning Spares | 19936 | POC | EUR |  | 3958.68 | 2016-10-01 | 2018-03-30 |  | 3300 |  | 2470 |  | 2470 |  |  |  |  | 2036 | [5 empty] | 0 | OTHER | OE
FCO | RU8295 | 19581 | Anagold Madencilik San. Ve Ticaret A.S. | 7MI7171157 | P - Anagold Madencilik - 7MI7171157 - 1621C/02 Commissioning Spares | 19937 | POC | EUR |  | 17994 | 2016-10-01 | 2018-03-30 |  | 15000 |  | 11227 |  | 11227 |  |  |  |  | 9256 | [5 empty] | 0 | OTHER | OE
FCO | RU8295 | 19581 | Anagold Madencilik San. Ve Ticaret A.S. | 7MI7171157 | P - Anagold Madencilik - 7MI7171157 - 1626A/01 Commissioning Spares | 19938 | POC | EUR |  | 2159.28 | 2016-10-01 | 2018-03-30 |  | 1800 |  | 1347 |  | 1347 |  |  |  |  | 1111 | [5 empty] | 0 | OTHER | OE
FCO | RU8295 | 19653 | Tecnimont Spa | 7MI 7163276 | P-TECNIMONT SPA-7MI 7163276 -Supply of ON/OFF VALVE BALLS | 19892 | POC | EUR | 1995375 | 2361382.61 | 2016-12-14 | 2018-03-31 |  | 1968475 |  | 1656600 |  | 1656600 |  |  |  |  | 1259111 | [5 empty] | 0 | RUSCIS | OE
FCO | RU8295 | 19653 | Tecnimont Spa | 7MI 7163276 | P-TECNIMONT SPA-7MI 7163276 -Warranty | 19893 | SL | EUR |  | 32269.24 | 2016-12-14 | 2018-03-31 |  | 26900 |  |  |  | 0 | [10 empty] | 0 | RUSCIS | OE | 2019-10-01 | 2022-03-31
FCO | RU8295 | 19654 | Amec Foster Wheeler Italiana S.r.l. - 7MI7170950 | 7MI7170950 | P - Amec Foster Wheeler Italiana S.r.l. - 7MI7170950 - valves | 19669 | POC | EUR | 854399.0113 | 998197.97 | 2017-10-27 | 2018-02-15 |  | 832109.0113 |  | 701574 |  | 701574 |  |  |  |  | 618935 |  | 62902.88 |  | 2018-05-21 | 6180338 | 0 | EUROPE | OE
FCO | RU8295 | 19654 | Amec Foster Wheeler Italiana S.r.l. - 7MI7170950 | 7MI7170950 | P - Amec Foster Wheeler Italiana S.r.l. - 7MI7170950 - warranty | 19895 | SL | EUR |  | 26739.08 | 2017-10-27 | 2018-02-15 |  | 22290 |  |  |  | 0 | [10 empty] | 0 | EUROPE | OE | 2019-08-18 | 2021-02-15
FCO | RU8295 | 22864 | TECHNIP BENELUX B.V. | 7180049 | P-TECHNIP-7180049-072793C001Azerikimya | 22877 | POC | EUR | 243115.306 | 301949.21 | 2018-02-12 | 2018-07-05 |  | 243115.306 |  | 180458 |  | 67508 | [10 empty] | 0 | RUSCIS | OE
FCO | RU8295 | 22878 | KT KINETICS TECHNOLOGY SPA | 7180090 | P - KT KINETICS TECHNOLOGY SPA (pob 1^ delivery)- 7180090 | 22880 | POC | EUR | 779625.004 | 542758.5 | 2018-02-22 | 2018-08-28 |  | 436933.2636 |  | 293028 |  | 76094 | [10 empty] | 0 | NAFRICA | OE
FCO | RU8295 | 22878 | KT KINETICS TECHNOLOGY SPA | 7180090 | P - KT KINETICS TECHNOLOGY SPA (pob 2^ delivery) - 7180090 | 22926 | POC | EUR |  | 168171.22 | 2018-02-22 | 2018-08-28 |  | 135381.7582 |  | 90794 |  | 23577 | [10 empty] | 0 | NAFRICA | OE
FCO | RU8295 | 22878 | KT KINETICS TECHNOLOGY SPA | 7180090 | P - KT KINETICS TECHNOLOGY SPA (pob 3^ delivery) - 7180090 | 22927 | POC | EUR |  | 257520.46 | 2018-02-22 | 2018-08-28 |  | 207309.9823 |  | 139032 |  | 36104 | [10 empty] | 0 | NAFRICA | OE
FCO | RU8295 | 22968 | TECHNIP ITALY S.p.A. | 7180098 | P - Technip Italy S.p.A. - 7180098 | 23209 | POC | EUR | 859390.0016 | 1067534.26 | 2018-02-23 | 2018-08-31 |  | 859390.0016 |  | 701495 |  | 311026 | [10 empty] | 0 | RUSCIS | OE
EPO | RU8310 | 4034 | Shell Chemical Appalachia LLC | 2015SHE5315511 | P - Sheel Chemical Appalachia LLC - 2015SHE5315511 - Pumping System P-24004/34004 | 4048 | POC | USD | 1712797 | 1202530.1 | 2015-09-11 | 2018-10-31 |  | 1202530 | 0 | 1023360 |  | 393608 | 0 | 347266.63 |  |  |  |  | 476946.14 | 394921.04 | 2018-05-03 | 320 | 0 | US | OE
EPO | RU8310 | 4034 | Shell Chemical Appalachia LLC | 2015SHE5315511 | P - Sheel Chemical Appalachia LLC - 2015SHE5315511 - Pump P-34004S | 4114 | POC | USD |  | 510267.36 | 2015-09-11 | 2018-10-31 |  | 510267 | 0 | 424815 |  | 151274 | 0 | 173633.32 | [8 empty] | 0 | US | OE
EPO | RU8310 | 4523 | MARATHON PETROLEUM COMPANY, LP C/O AMBITECH ENGINEERING | 2016MAP2810151 | P - Ambitech Engineering Corporation - 2016MAP2810151 - Pumping System 11P150 A/B | 4639 | POC | USD | 0 | 261993 | 2016-09-30 | 2018-02-16 | [9 empty] | 2018-02-28 |  |  |  | 0
EPO | RU8310 | 4533 | Tecnimont Spa | 2017TEC0747521 | P - Tecnimont Spa - 2017TEC0747521 - Pumping System P-5603 A/B | 4668 | POC | EUR | 1130496 | 46114.97 | 2017-04-28 | 2018-02-15 |  | 43188 | 0 | 42876 |  | 769 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 4533 | Tecnimont Spa | 2017TEC0747521 | P - Tecnimont Spa - 2017TEC0747521 - Pumping System P-7821 A/B/C/D | 7562 | POC | EUR |  | 1020197.16 | 2017-04-28 | 2018-02-15 | [9 empty] | 2018-04-30
EPO | RU8310 | 4533 | Tecnimont Spa | 2017TEC0747521 | P - Tecnimont Spa - 2017TEC0747521 - Pumping System P-3018 A/B | 7569 | POC | EUR |  | 44074.46 | 2017-04-28 | 2018-02-15 |  | 41277 | 0 | 40979 |  | 769 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 4533 | Tecnimont Spa | 2017TEC0747521 | P - Tecnimont Spa - 2017TEC0747521 - Pumping System P-3042 | 7573 | POC | EUR |  | 34558.47 | 2017-04-28 | 2018-02-15 |  | 32365 | 0 | 32252 |  | 1507 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 4533 | Tecnimont Spa | 2017TEC0747521 | P - Tecnimont Spa - 2017TEC0747521 - Pumping System P-3404 A/B | 7574 | POC | EUR |  | 525833.28 | 2017-04-28 | 2018-02-15 |  | 492458 | 0 | 543668 |  | 537854 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 4533 | Tecnimont Spa | 2017TEC0747521 | P - Tecnimont Spa - 2017TEC0747521 - Pumping System P-4404 A/B | 7575 | POC | EUR |  | 525833.28 | 2017-04-28 | 2018-02-15 |  | 492458 | 0 | 630762 |  | 594878 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 4533 | Tecnimont Spa | 2017TEC0747521 | P - Tecnimont Spa - 2017TEC0747521 - Training | 7578 | PIT | EUR |  | 30698.47 | 2017-04-28 | 2018-02-15 |  | 28750 | 0 | 28542 |  | 705 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 5308 | Technip France (agent of Shell Chemical Appalachia LLC) | 2015SHE2314501 | P - Technip France (Shell) - 2015SHE2314501 - Pumping system P-43004A/B | 7704 | POC | USD | 791504 | 791504 | 2016-01-22 | 2018-09-01 |  | 791504 | 0 | 643699 |  | 238018 | 0 | 193398.42 |  |  |  |  | 296814 | 245767.9887 | 2018-05-17 | 362-363 | 0 | US | OE
EPO | RU8310 | 7718 | Motiva Enterprises LLC | 2017MOT0541401 | P - Motiva Enterprises LLC - 2017MOT0541401 - Pumping System P-8142/8143 | 7840 | POC | USD | 0 | 666571 | 2017-04-05 | 2018-02-01 | [9 empty] | 2018-03-31 |  |  |  | 0
EPO | RU8310 | 7761 | Fluor Enterprises Inc. (agent of Blanchard Reﬁning Company LLC) | 2016MAP1348401 | P - Fluor Enterprises (Marathon) - 2016MAP1348401 - Pumping system J201 A/B | 7768 | POC | USD | 2284260 | 904588 | 2016-09-06 | 2018-03-31 |  | 904588 | 0 | 671072 |  | 621814 | 0 | [6 empty] | 0 |  |  | 0 | US | OE
EPO | RU8310 | 7761 | Fluor Enterprises Inc. (agent of Blanchard Reﬁning Company LLC) | 2016MAP1348401 | P - Fluor Enterprises (Marathon) - 2016MAP1348401 - Pumping system J204 A/B | 8003 | POC | USD |  | 456299 | 2016-09-06 | 2018-03-31 |  | 456299 | 0 |  |  | 335466 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 7761 | Fluor Enterprises Inc. (agent of Blanchard Reﬁning Company LLC) | 2016MAP1348401 | P - Fluor Enterprises (Marathon) - 2016MAP1348401 - Pumping system J301 A/B | 8004 | POC | USD |  | 473368 | 2016-09-06 | 2018-03-31 |  | 473368 | 0 | 364121 |  | 328845 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 7761 | Fluor Enterprises Inc. (agent of Blanchard Reﬁning Company LLC) | 2016MAP1348401 | P - Fluor Enterprises (Marathon) - 2016MAP1348401 - Pumping system J303 A/B | 8006 | POC | USD |  | 450005 | 2016-09-06 | 2018-03-31 |  | 450005 | 0 |  |  | 320818 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8079 | Technip France (agent of Shell Chemical Appalachia LLC) | 2016SHE3417011 | P - Technip France (Shell) - 2016SHE3417011 - Pumping system P-45006 A/B | 8107 | POC | USD | 526209 | 158787.33 | 2016-03-07 | 2018-08-18 |  | 158787 | 0 | 124975 |  | 96453 | 0 | [5 empty] | 52621 | 43571.2511 | 2018-05-17 | 365 | 0 | US | OE
EPO | RU8310 | 8079 | Technip France (agent of Shell Chemical Appalachia LLC) | 2016SHE3417011 | P - Technip France (Shell) - 2016SHE3417011 - Pumping system P-46001 A/B | 8111 | POC | USD |  | 88380.33 | 2016-03-07 | 2018-08-18 |  | 88380 | 0 | 69325 |  | 53226 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8079 | Technip France (agent of Shell Chemical Appalachia LLC) | 2016SHE3417011 | P - Technip France (Shell) - 2016SHE3417011 - Pumping system P-45014 | 8113 | POC | USD |  | 279042.34 | 2016-03-07 | 2018-08-18 |  | 279042 | 0 | 244666 |  | 193402 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-12871A/B | 8592 | POC | USD | 7179661 | 488172.7 | 2015-09-01 | 2018-05-31 |  | 488179 | 0 | 399170 |  | 325843 | 0 | [6 empty] | 0 |  |  | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-12872A/B | 9013 | POC | USD |  | 880725.72 | 2015-09-01 | 2018-05-31 |  | 880737 | 0 | 733049 |  | 599588 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-12873A/B | 9014 | POC | USD |  | 516678.93 | 2015-09-01 | 2018-05-31 |  | 516686 | 0 | 422454 |  | 300899 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-13871A/B | 9015 | POC | USD |  | 812112.83 | 2015-09-01 | 2018-05-31 |  | 812124 | 0 | 647269 |  | 372720 | 114534 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-13872A/B | 9016 | POC | USD |  | 412934.26 | 2015-09-01 | 2018-05-31 |  | 412940 | 0 | 331246 |  | 150983 | 114534 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-13873A/B | 9017 | POC | USD |  | 77649.35 | 2015-09-01 | 2018-05-31 |  | 77650 | 0 | 67164 |  | 60587 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-12875A/B | 9018 | POC | USD |  | 78485.78 | 2015-09-01 | 2018-05-31 |  | 78391 | 0 | 67942 |  | 62196 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-12876A/B | 9019 | POC | USD |  | 121374.87 | 2015-09-01 | 2018-05-31 |  | 121376 | 0 | 109572 |  | 89653 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-12877A/B | 9020 | POC | USD |  | 130491.99 | 2015-09-01 | 2018-05-31 |  | 130494 | 0 | 107982 |  | 92252 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-13071A/B | 9021 | POC | USD |  | 94568.7 | 2015-09-01 | 2018-05-31 |  | 94570 | 0 | 88061 |  | 78407 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-13171A/B | 9022 | POC | USD |  | 67272.3 | 2015-09-01 | 2018-05-31 |  | 67273 | 0 | 63108 |  | 53996 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-13172A/B | 9023 | POC | USD |  | 130280.01 | 2015-09-01 | 2018-05-31 |  | 130282 | 0 | 108391 |  | 93303 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-13472A/B | 9024 | POC | USD |  | 55896.39 | 2015-09-01 | 2018-05-31 |  | 55897 | 0 | 53871 |  | 46653 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-13971A/B | 9025 | POC | USD |  | 86096.55 | 2015-09-01 | 2018-05-31 |  | 86098 | 0 | 74085 |  | 65155 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-14471A/B | 9027 | POC | USD |  | 125542.26 | 2015-09-01 | 2018-05-31 |  | 125544 | 0 | 118075 |  | 104663 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-15871A/B | 9028 | POC | USD |  | 181331.96 | 2015-09-01 | 2018-05-31 |  | 181334 | 0 | 150043 |  | 108050 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-15872A/B | 9029 | POC | USD |  | 145332.73 | 2015-09-01 | 2018-05-31 |  | 145335 | 0 | 120272 |  | 103358 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-18271A/B | 9030 | POC | USD |  | 115300.69 | 2015-09-01 | 2018-05-31 |  | 115302 | 0 | 110535 |  | 896 | 63436 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-18371A/B | 9031 | POC | USD |  | 622800.51 | 2015-09-01 | 2018-05-31 |  | 622809 | 0 | 597060 |  | 1857 | 445033 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-18873 | 9032 | POC | USD |  | 64173.69 | 2015-09-01 | 2018-05-31 |  | 64175 | 0 | 54169 |  | 49271 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-19071A/B | 9034 | POC | USD |  | 136175.91 | 2015-09-01 | 2018-05-31 |  | 136178 | 0 | 112689 |  | 104233 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-19771 | 9037 | POC | USD |  | 86856.12 | 2015-09-01 | 2018-05-31 |  | 86857 | 0 | 83266 |  | 832 | 29623 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-19772 | 9038 | POC | USD |  | 75782.99 | 2015-09-01 | 2018-05-31 |  | 75784 | 0 | 72651 |  | 768 | 22062 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-19773 | 9039 | POC | USD |  | 78885.83 | 2015-09-01 | 2018-05-31 |  | 78887 | 0 | 75625 |  | 832 | 22885 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-12874A/B | 9040 | POC | USD |  | 129631.01 | 2015-09-01 | 2018-05-31 |  | 129633 | 0 | 107269 |  | 91337 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-13471A/B | 9041 | POC | USD |  | 221257.06 | 2015-09-01 | 2018-05-31 |  | 221260 | 0 | 183106 |  | 154446 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-13474A/B | 9048 | POC | USD |  | 132267.08 | 2015-09-01 | 2018-05-31 |  | 132269 | 0 | 109452 |  | 97209 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-13475A/B | 9049 | POC | USD |  | 146798.69 | 2015-09-01 | 2018-05-31 |  | 146801 | 0 | 121486 |  | 107188 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-13571A/B | 9052 | POC | USD |  | 142813.79 | 2015-09-01 | 2018-05-31 |  | 142816 | 0 | 118186 |  | 94907 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-12878 | 9053 | POC | USD |  | 228079.79 | 2015-09-01 | 2018-05-31 |  | 228083 | 0 | 188779 |  | 89579 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System P-12879 | 9054 | POC | USD |  | 225971.76 | 2015-09-01 | 2018-05-31 |  | 225975 | 0 | 187133 |  | 70233 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Pumping System A-18864 | 9055 | POC | USD |  | 195615.7 | 2015-09-01 | 2018-05-31 |  | 195618 | 0 | 160345 |  | 2970 | 120050 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8581 | Shell Chemical Appalachia LLC | 2015SHE3829351 | P - Shell Chemical Appalachia LLC - 2015SHE3829351 - Spare pump for P-12878/9 | 9056 | POC | USD |  | 172302.05 | 2015-09-01 | 2018-05-31 |  | 172304 | 0 | 142327 |  | 21834 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 8970 | LIMA REFINING COMPANY | 2017LIM1352101 | P - Lima Refining Company - 2017LIM1352101 - Pumping System PR-210956/57 | 9318 | POC | USD | 467089 | 110618.4 | 2017-07-10 | 2018-03-28 |  | 110618 | 0 | 74972 |  | 74972 | 0 |  |  | 2018-05-31 |  |  | 513798.86 | 425435.8367 | 2018-05-25 | 275-55501190 | 0 | US | OE
EPO | RU8310 | 8970 | LIMA REFINING COMPANY | 2017LIM1352101 | P - Lima Refining Company - 2017LIM1352101 - Pumping System PR-211937/38 | 9360 | POC | USD |  | 100528 | 2017-07-10 | 2018-03-28 |  | 100528 | 0 | 67992 |  | 67992 | 0 |  |  | 2018-05-31 | [6 empty] | 0 | US | OE
EPO | RU8310 | 8970 | LIMA REFINING COMPANY | 2017LIM1352101 | P - Lima Refining Company - 2017LIM1352101 - Pumping System PR-212021 | 9361 | POC | USD |  | 42330.68 | 2017-07-10 | 2018-03-28 |  | 42331 | 0 | 33287 |  | 33287 | 0 |  |  | 2018-05-31 | [6 empty] | 0 | US | OE
EPO | RU8310 | 8970 | LIMA REFINING COMPANY | 2017LIM1352101 | P - Lima Refining Company - 2017LIM1352101 - Pumping System PR-212023/24 | 9363 | POC | USD |  | 161318.4 | 2017-07-10 | 2018-03-28 |  | 161318 | 0 | 114182 |  | 114182 | 0 |  |  | 2018-05-31 | [6 empty] | 0 | US | OE
EPO | RU8310 | 8970 | LIMA REFINING COMPANY | 2017LIM1352101 | P - Lima Refining Company - 2017LIM1352101 - Pumping System PR-211945 | 9364 | POC | USD |  | 52294.4 | 2017-07-10 | 2018-03-28 |  | 52294 | 0 | 41800 |  | 41800 | 0 |  |  | 2018-05-31 | [6 empty] | 0 | US | OE
EPO | RU8310 | 8971 | TECNIMONT HQC S.C.A.R.L | 2017TEC0446351 | P - TecnimontHQC S.c.a.r.l. - 2017TEC0446351 - Pumping System 3215-P-411 A/B | 9861 | POC | EUR | 0 | 105315.72 | 2017-07-06 | 2018-04-20 | [9 empty] | 2018-01-31
EPO | RU8310 | 8971 | TECNIMONT HQC S.C.A.R.L | 2017TEC0446351 | P - TecnimontHQC S.c.a.r.l. - 2017TEC0446351 - Pumping System 3215-P-115 | 9865 | POC | EUR |  | 108616.51 | 2017-07-06 | 2018-04-20 | [9 empty] | 2018-02-28
EPO | RU8310 | 8971 | TECNIMONT HQC S.C.A.R.L | 2017TEC0446351 | P - TecnimontHQC S.c.a.r.l. - 2017TEC0446351 - Pumping System 3215-P-114 A/B | 9866 | POC | EUR |  | 211766.1 | 2017-07-06 | 2018-04-20 | [9 empty] | 2018-02-28
EPO | RU8310 | 8971 | TECNIMONT HQC S.C.A.R.L | 2017TEC0446351 | P - TecnimontHQC S.c.a.r.l. - 2017TEC0446351 - Pumping System 3215-P-612 A/B | 9867 | POC | EUR |  | 125636.2 | 2017-07-06 | 2018-04-20 | [9 empty] | 2018-02-28
EPO | RU8310 | 8971 | TECNIMONT HQC S.C.A.R.L | 2017TEC0446351 | P - TecnimontHQC S.c.a.r.l. - 2017TEC0446351 - Pumping System 3215-P-211 A/B | 9868 | POC | EUR |  | 415383.38 | 2017-07-06 | 2018-04-20 | [9 empty] | 2018-02-28
EPO | RU8310 | 8971 | TECNIMONT HQC S.C.A.R.L | 2017TEC0446351 | P - TecnimontHQC S.c.a.r.l. - 2017TEC0446351 - Pumping System 3215-P-412 A/B | 9869 | POC | EUR |  | 155446.43 | 2017-07-06 | 2018-04-20 | [9 empty] | 2018-02-28
EPO | RU8310 | 8971 | TECNIMONT HQC S.C.A.R.L | 2017TEC0446351 | P - TecnimontHQC S.c.a.r.l. - 2017TEC0446351 - Pumping System 3215-P-415 | 9870 | POC | EUR |  | 56835.42 | 2017-07-06 | 2018-04-20 | [9 empty] | 2018-04-30
EPO | RU8310 | 8971 | TECNIMONT HQC S.C.A.R.L | 2017TEC0446351 | P - TecnimontHQC S.c.a.r.l. - 2017TEC0446351 - Pumping System 3215-P-311 A/B | 9871 | POC | EUR |  | 121200.77 | 2017-07-06 | 2018-04-20 | [9 empty] | 2018-02-28
EPO | RU8310 | 8971 | TECNIMONT HQC S.C.A.R.L | 2017TEC0446351 | P - TecnimontHQC S.c.a.r.l. - 2017TEC0446351 - Pumping System 3215-P-312 A/B | 9872 | POC | EUR |  | 110679.51 | 2017-07-06 | 2018-04-20 | [9 empty] | 2018-01-31
EPO | RU8310 | 8971 | TECNIMONT HQC S.C.A.R.L | 2017TEC0446351 | P - TecnimontHQC S.c.a.r.l. - 2017TEC0446351 - Pumping System 3215-P-313 A/B | 9873 | POC | EUR |  | 88192.9 | 2017-07-06 | 2018-04-20 | [9 empty] | 2018-01-31
EPO | RU8310 | 8971 | TECNIMONT HQC S.C.A.R.L | 2017TEC0446351 | P - TecnimontHQC S.c.a.r.l. - 2017TEC0446351 - Pumping System 3215-P-314 | 9874 | POC | EUR |  | 46004.71 | 2017-07-06 | 2018-04-20 | [9 empty] | 2018-01-31
EPO | RU8310 | 8971 | TECNIMONT HQC S.C.A.R.L | 2017TEC0446351 | P - TecnimontHQC S.c.a.r.l. - 2017TEC0446351 - Pumping System 3215-P-351 BS | 9875 | POC | EUR |  | 18876.38 | 2017-07-06 | 2018-04-20 | [9 empty] | 2018-01-31
EPO | RU8310 | 8971 | TECNIMONT HQC S.C.A.R.L | 2017TEC0446351 | P - TecnimontHQC S.c.a.r.l. - 2017TEC0446351 - Pumping System 3215-P-341 A/B | 9876 | POC | EUR |  | 90359.04 | 2017-07-06 | 2018-04-20 | [9 empty] | 2018-01-31
EPO | RU8310 | 8971 | TECNIMONT HQC S.C.A.R.L | 2017TEC0446351 | P - TecnimontHQC S.c.a.r.l. - 2017TEC0446351 - Pumping System 3215-P-351 | 9877 | POC | EUR |  | 48996.05 | 2017-07-06 | 2018-04-20 | [9 empty] | 2018-01-31
EPO | RU8310 | 8971 | TECNIMONT HQC S.C.A.R.L | 2017TEC0446351 | P - TecnimontHQC S.c.a.r.l. - 2017TEC0446351 - Pumping System 3215-P-611 A/B | 9879 | POC | EUR |  | 129555.88 | 2017-07-06 | 2018-04-20 | [9 empty] | 2018-02-28
EPO | RU8310 | 8972 | Enimed Spa - Eni Mediterranea Idrocarburi Spa | 2017ENI5042101 | P - Enimed Spa - Eni Mediterranea Idrocarburi Spa - 2017ENI5042101 - Pumping System - 005600PH101 A/B/C | 15654 | POC | EUR | 580034 | 196600.88 | 2017-05-31 | 2018-01-31 |  | 177630 | 0 | 179981 |  | 2758 | 102562 | [9 empty] | 0 | EUROPE | OE
EPO | RU8310 | 8972 | Enimed Spa - Eni Mediterranea Idrocarburi Spa | 2017ENI5042101 | P - Enimed Spa - Eni Mediterranea Idrocarburi Spa - 2017ENI5042101 - Pumping System - 005600PA101 A/B/C | 15727 | POC | EUR |  | 98914.72 | 2017-05-31 | 2018-01-31 | [9 empty] | 2017-12-31
EPO | RU8310 | 8972 | Enimed Spa - Eni Mediterranea Idrocarburi Spa | 2017ENI5042101 | P - Enimed Spa - Eni Mediterranea Idrocarburi Spa - 2017ENI5042101 - Pumping System - 005100PA101 A/B/C | 15728 | POC | EUR |  | 445380.92 | 2017-05-31 | 2018-01-31 |  | 402404 | 0 | 353433 |  | 336955 | 0 |  |  |  | 324631 | [5 empty] | 0 | EUROPE | OE
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-Pumping System - 43G-102A/B | 17204 | POC | EUR | 3895637 | 76837.14 | 2017-07-28 | 2018-02-12 |  | 67098 | 0 | 71555 |  | 71555 | 0 |  |  | 2018-05-31 |  |  | 718800 |  | 2018-05-30 | 55501383-55501436-55501549-55501632-400 | 0 | ASIA | OE
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-Pumping System - 42G-202A/B | 17205 | POC | EUR |  | 88547.85 | 2017-07-28 | 2018-02-12 | [9 empty] | 2018-04-30
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-Pumping System - 48G-108A/B | 17206 | POC | EUR |  | 158056.59 | 2017-07-28 | 2018-02-12 |  | 138023 | 0 | 160199 |  | 160199 | 0 |  |  | 2018-05-31 | [6 empty] | 0 | ASIA | OE
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-Pumping System - 48G-111 A/B | 17207 | POC | EUR |  | 161716.11 | 2017-07-28 | 2018-02-12 |  | 141219 | 0 | 129947 |  | 129947 | 0 |  |  | 2018-05-31 | [6 empty] | 0 | ASIA | OE
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-Pumping System - 42G-110 A/B | 17208 | POC | EUR |  | 211208.9 | 2017-07-28 | 2018-02-12 |  | 184438 | 0 | 168649 |  | 166858 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-Pumping System - 44G-102 A/B | 17210 | POC | EUR |  | 87316.39 | 2017-07-28 | 2018-02-12 |  | 75815 | 434 | 87116 |  | 87116 | 0 |  |  | 2018-05-31 | [6 empty] | 0 | ASIA | OE
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-Pumping System - 44G-202 A/B | 17211 | POC | EUR |  | 87220.09 | 2017-07-28 | 2018-02-12 |  | 74547 | 1618 | 84140 |  | 84140 | 0 |  |  | 2018-05-31 | [6 empty] | 0 | ASIA | OE
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-Pumping System - 48G-104 A/B | 17212 | POC | EUR |  | 102691.89 | 2017-07-28 | 2018-02-12 | [9 empty] | 2018-04-30
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-Pumping System - 22G-125X A/B | 17213 | POC | EUR |  | 49850.26 | 2017-07-28 | 2018-02-12 | [9 empty] | 2018-05-31
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-Pumping System - 42G-101A/B | 17214 | POC | EUR |  | 198744.29 | 2017-07-28 | 2018-02-12 |  | 173553 | 0 | 160170 |  | 158677 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-Pumping System - 42G-104A/B | 17215 | POC | EUR |  | 180576.64 | 2017-07-28 | 2018-02-12 |  | 157688 | 0 | 149429 |  | 146409 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-Pumping System - 42G-106A/B | 17216 | POC | EUR |  | 187613.35 | 2017-07-28 | 2018-02-12 |  | 163833 | 0 | 158651 |  | 153658 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-Pumping System - 42G-108 A/B | 17217 | POC | EUR |  | 221403.17 | 2017-07-28 | 2018-02-12 |  | 193340 | 0 | 192001 |  | 192121 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-Pumping System - 43G-106 A/B | 17218 | POC | EUR |  | 178574.12 | 2017-07-28 | 2018-02-12 |  | 155940 | 0 | 174154 |  | 174154 | 0 |  |  | 2018-05-31 | [6 empty] | 0 | ASIA | OE
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-Pumping System - 44G-104 A/B | 17219 | POC | EUR |  | 123609.68 | 2017-07-28 | 2018-02-12 | [9 empty] | 2018-04-30
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-Pumping System - 44G-204 A/B | 17220 | POC | EUR |  | 330654.22 | 2017-07-28 | 2018-02-12 |  | 288744 | 0 | 300944 |  | 291126 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-Pumping System - 23G-117/118B | 17221 | POC | EUR |  | 203036.24 | 2017-07-28 | 2018-02-12 |  | 172722 | 4579 | 153787 |  | 153787 | 0 |  |  | 2018-05-31 | [6 empty] | 0 | ASIA | OE
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-Pumping System - 44G-205 A/B | 17223 | POC | EUR |  | 147698.57 | 2017-07-28 | 2018-02-12 |  | 128978 | 0 | 137436 |  | 134640 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-Pumping System - 48G-101 A/B | 17224 | POC | EUR |  | 208400.42 | 2017-07-28 | 2018-02-12 |  | 181986 | 0 | 170873 |  | 169711 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-Pumping System - 48G-103 A/B | 17225 | POC | EUR |  | 202788.47 | 2017-07-28 | 2018-02-12 |  | 177085 | 0 | 191717 |  | 190307 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-Pumping System - 48G-105 A/B | 17226 | POC | EUR |  | 234375.98 | 2017-07-28 | 2018-02-12 |  | 204669 | 0 | 198282 |  | 196782 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-Pumping System - 48G-107 A/B | 17227 | POC | EUR |  | 194517.43 | 2017-07-28 | 2018-02-12 |  | 169862 | 0 | 193813 |  | 192041 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-Pumping System - 20G-428 | 17228 | POC | EUR |  | 166506.02 | 2017-07-28 | 2018-02-12 |  | 145401 | 0 | 114811 |  | 112100 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-Pumping System - 42G-221 A/B | 17229 | POC | EUR |  | 95877.52 | 2017-07-28 | 2018-02-12 |  | 83725 | 0 | 85655 |  | 1958 | 44707 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-Pumping System - 43G-203 A/B | 17230 | POC | EUR |  | 70999.18 | 2017-07-28 | 2018-02-12 |  | 62000 | 0 | 63572 |  | 1823 | 31994 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-Pumping System - 43G-221 A/B | 17231 | POC | EUR |  | 89075.34 | 2017-07-28 | 2018-02-12 |  | 77785 | 0 | 79617 |  | 1958 | 38981 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351- Pumping System - 44G-321 A/B | 17232 | POC | EUR |  | 101156.65 | 2017-07-28 | 2018-02-12 |  | 88335 | 0 | 90341 |  | 1958 | 44131 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-Pumping System - 48G-201 A/B | 17233 | POC | EUR |  | 74085.35 | 2017-07-28 | 2018-02-12 |  | 64695 | 0 | 66311 |  | 1823 | 35113 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-Pumping System - 48G-221 A/B | 17234 | POC | EUR |  | 95574.05 | 2017-07-28 | 2018-02-12 |  | 83460 | 0 | 85386 |  | 1958 | 42643 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-Pumping System - 02G-705A/B | 17235 | POC | EUR |  | 80904.15 | 2017-07-28 | 2018-02-12 | [9 empty] | 2018-04-30
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351- Pumping System - 42G-107A/B | 17236 | POC | EUR |  | 100118.09 | 2017-07-28 | 2018-02-12 |  | 85590 | 1838 | 92752 |  | 92752 | 0 |  |  | 2018-05-31 | [6 empty] | 0 | ASIA | OE
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-Pumping System - 42G-109 A/B | 17237 | POC | EUR |  | 116478.98 | 2017-07-28 | 2018-02-12 | [9 empty] | 2018-04-30
EPO | RU8310 | 8975 | Technip Italy S.p.a. | 2017TCI0546351 | P-Technip Italy S.p.a.-2017TCI0546351-2 Years Spare Parts | 17238 | POC | EUR |  | 406649.34 | 2017-07-28 | 2018-02-12 |  | 355106 | 0 | 215000 |  | 172086 | 0 | [9 empty] | 0 | ASIA | AM
EPO | RU8310 | 8976 | ZHEJIANG PETROLEUM & CHEMICAL CO., Ltd. | 2017ZPC2208281 | P - Zhejiang Petroleum & Chemicals Co., Ltd - 2017ZPC2208281 - Pumping system 12141/2-P-2001A/B | 10262 | POC | EUR | 1268000 | 793335.68 | 2017-06-22 | 2018-05-30 |  | 705752 | 0 | 631053 |  | 552439 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 8976 | ZHEJIANG PETROLEUM & CHEMICAL CO., Ltd. | 2017ZPC2208281 | P - Zhejiang Petroleum & Chemicals Co., Ltd - 2017ZPC2208281 - Pumping system 12141/12142-P-2501 A/B | 10263 | POC | EUR |  | 344478.48 | 2017-06-22 | 2018-05-30 |  | 306448 | 0 | 277964 |  | 246124 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 8976 | ZHEJIANG PETROLEUM & CHEMICAL CO., Ltd. | 2017ZPC2208281 | P - Zhejiang Petroleum & Chemicals Co., Ltd - 2017ZPC2208281 - Spare parts pumping system 12141/12142-P-2001 A/B | 10264 | POC | EUR |  | 188245.89 | 2017-06-22 | 2018-05-30 |  | 167464 | 0 | 50343 |  | 26674 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 8976 | ZHEJIANG PETROLEUM & CHEMICAL CO., Ltd. | 2017ZPC2208281 | P - Zhejiang Petroleum & Chemicals Co., Ltd - 2017ZPC2208281 - Spare parts pumping system 12141/12142-P-2501 A/B | 10270 | POC | EUR |  | 99298.75 | 2017-06-22 | 2018-05-30 |  | 88336 | 0 | 31544 |  | 15062 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 8977 | ZHEJIANG PETROLEUM & CHEMICAL CO., Ltd. | 2017ZPC2611401 | P - Zhejiang Petroleum & Chemicals Co., Ltd. - 2017ZPC2611401 - Pumping system 1115-P-5201 A/B/C | 9912 | POC | EUR | 6300001 | 1640495.53 | 2017-06-21 | 2018-05-31 |  | 1459386 | 0 | 1229307 |  | 764222 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 8977 | ZHEJIANG PETROLEUM & CHEMICAL CO., Ltd. | 2017ZPC2611401 | P - Zhejiang Petroleum & Chemicals Co., Ltd. - 2017ZPC2611401 - Pumping system 1116-P-5201 A/B/C | 9949 | POC | EUR |  | 1519555.31 | 2017-06-21 | 2018-05-31 |  | 1351797 | 0 | 1215246 |  | 745499 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 8977 | ZHEJIANG PETROLEUM & CHEMICAL CO., Ltd. | 2017ZPC2611401 | P - Zhejiang Petroleum & Chemicals Co., Ltd. - 2017ZPC2611401 - Pumping system 1116-P-5206 A/B/C/D/S | 9953 | POC | EUR |  | 1396176.79 | 2017-06-21 | 2018-05-31 |  | 1242040 | 0 | 1163855 |  | 511786 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 8977 | ZHEJIANG PETROLEUM & CHEMICAL CO., Ltd. | 2017ZPC2611401 | P - Zhejiang Petroleum & Chemicals Co., Ltd. - 2017ZPC2611401 - Pumping system 1115-P-5206 A/B/C/D/S | 9955 | POC | EUR |  | 1399102.76 | 2017-06-21 | 2018-05-31 |  | 1244643 | 0 | 1102549 |  | 787831 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 8977 | ZHEJIANG PETROLEUM & CHEMICAL CO., Ltd. | 2017ZPC2611401 | P - Zhejiang Petroleum & Chemicals Co., Ltd. - 2017ZPC2611401 - Pumping system 1113-P-4101 A/S | 9956 | POC | EUR |  | 564712.79 | 2017-06-21 | 2018-05-31 |  | 502369 | 0 | 409866 |  | 244245 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 8977 | ZHEJIANG PETROLEUM & CHEMICAL CO., Ltd. | 2017ZPC2611401 | P - Zhejiang Petroleum & Chemicals Co., Ltd. - 2017ZPC2611401 - Pumping system 1114-P-4101 A/S | 9957 | POC | EUR |  | 561786.82 | 2017-06-21 | 2018-05-31 |  | 499766 | 0 | 417860 |  | 240775 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 8978 | ZHEJIANG PETROLEUM & CHEMICAL CO., Ltd. | 2017ZPC2613431 | P - Zhejiang Petroleum & Chemicals Co., Ltd - 2017ZPC2613431 - Pumping systems 1201-P-1210 A/B/S | 11546 | POC | EUR | 3000000 | 1631808 | 2017-06-22 | 2018-05-31 |  | 1440000 | 0 | 1288045 |  | 601053 | 0 | 138000 | [8 empty] | 0 | CHINA | OE
EPO | RU8310 | 8978 | ZHEJIANG PETROLEUM & CHEMICAL CO., Ltd. | 2017ZPC2613431 | P - Zhejiang Petroleum & Chemicals Co., Ltd - 2017ZPC2613431 - Pumping system 1201-P-1220A/B/C/S | 13932 | POC | EUR |  | 1767792 | 2017-06-22 | 2018-05-31 |  | 1560000 | 0 | 1537271 |  | 865104 | 0 | 138000 | [8 empty] | 0 | CHINA | OE
EPO | RU8310 | 8979 | BP Oil Espana S.A.U. | 2017BPH1202011 | P - BP Oil Espana S.A.U. - 2017BPH1202011 - Pumping System P-2320 A/B | 13878 | POC | EUR | 517232 | 429981.76 | 2017-06-28 | 2018-03-23 |  | 375762 | 0 | 354653 |  | 343065 | 0 | [5 empty] | 49514.5 |  | 2018-05-04 | 323-324 | 0 | EUROPE | OE
EPO | RU8310 | 8979 | BP Oil Espana S.A.U. | 2017BPH1202011 | P - BP Oil Espana S.A.U. - 2017BPH1202011 - 2 Years Spare Parts P-2320 | 23516 | POC | EUR |  | 164940.84 | 2017-06-28 | 2018-03-23 |  | 141470 | 0 | 68252 |  | 45825 | 0 | [9 empty] | 0 | EUROPE | OE
EPO | RU8310 | 8980 | Marathon Petroleum Company, LP C/O Ambitech Engineering | 2017MAP2105361 | P - Marathon Petroleum Company, LP C/O Ambitech Engineering - 2017MAP2105361 - Pumping system 4P49A/B | 14908 | POC | USD | 722440 | 722440 | 2017-09-05 | 2018-05-09 |  | 722440 | 0 | 534400 |  | 463272 | 0 | [6 empty] | 0 |  |  | 0 | US | OE
EPO | RU8310 | 9086 | Statoil Refining Denmark A/S | 2017STA0847011 | P - Statoil Refining Denmark A/S - 2017STA0847011 - Pumping system P-1010A/B | 9096 | POC | EUR | 0 | 359986.07 | 2017-03-17 | 2018-01-31 | [9 empty] | 2018-01-31
EPO | RU8310 | 9244 | China Tianchen Engineering Corporation | 2017TCC0947501 | P - China Tianchen Engineering Corp - 2017TCC0947501 - Pumping system 21-P-761 A/B | 9290 | POC | EUR | 664000 | 517512.5 | 2017-05-29 | 2018-02-28 |  | 475000 | 0 | 512497 |  | 521241 | 0 | [9 empty] | 15300 | ASIA | OE
EPO | RU8310 | 9244 | China Tianchen Engineering Corporation | 2017TCC0947501 | P - China Tianchen Engineering Corp - 2017TCC0947501 - Pumping system 23-P-512 A/B | 9319 | POC | EUR |  | 387862 | 2017-05-29 | 2018-02-28 | [9 empty] | 2018-04-30
EPO | RU8310 | 9244 | China Tianchen Engineering Corporation | 2017TCC0947501 | P - China Tianchen Engineering Corp - 2017TCC0947501 - Pumping system 23-P-601 D | 9320 | POC | EUR |  | 205915.5 | 2017-05-29 | 2018-02-28 |  | 189000 | 0 | 261963 |  | 231670 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 9978 | PA Italy Netherlands Operating Company Italy Branch | 2016CCJ0136651 | P - PA Italy Netherlands Operating Company Italy Branch - 2016CCJ0136651-V56 Pump Package | 15163 | POC | EUR | 4676495 | 5108329.87 | 2016-11-03 | 2018-04-28 |  | 4676495 | 11372 | 5553782 |  | 5384578 | 0 |  |  |  | 1737618 |  | 479818.3 |  | 2018-05-08 | 55501422 | 23439 | ASIA | OE
EPO | RU8310 | 10033 | PA Italy Netherlands Operating Company Italy Branch | 2016CCJ4929541 | P - PA Italy Netherlands Operating Company Italy Branch - 2016CCJ4929541- Pumping System - P-21004 A - P-21004 B/C | 15171 | POC | EUR | 4379749 | 1604566.31 | 2016-10-21 | 2018-05-10 |  | 1547474 | 0 | 1665529 |  | 1555306 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 10033 | PA Italy Netherlands Operating Company Italy Branch | 2016CCJ4929541 | P - PA Italy Netherlands Operating Company Italy Branch - 2016CCJ4929541- Pumping System - P-21001 A/B - P-21001 C/D | 15179 | POC | EUR |  | 3134577.09 | 2016-10-21 | 2018-05-10 |  | 2832275 | 0 | 2474267 |  | 1831340 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 10034 | PA Italy Netherlands Operating Company Italy Branch | 2016CCJ4930511 | P - PA Italy Netherlands Operating Company Italy Branch - 2016CCJ4930511- Pumping System - P-73101 A/B - P - 73101 C/D/E | 15192 | POC | EUR | 4258332 | 4750072.99 | 2016-10-24 | 2018-05-05 |  | 4258332 | 0 | 2406127 |  | 2214958 | 0 | [5 empty] | 216476.6 |  | 2018-05-30 | 394 | 0 | ASIA | OE
EPO | RU8310 | 10066 | Tecnicas Reunidas (Ute TR Fadhili Project) | 2017TRS1708391 | P - Tecnicas Reunidas (Ute TR Fadhili Project) - 2017TRS1708391-10HDX23A | 14325 | POC | EUR | 870926 | 648935.18 | 2017-09-22 | 2018-04-23 |  | 546350 | 0 | 442394 |  | 404752 | 0 | [9 empty] | 13331 | ASIA | OE
EPO | RU8310 | 10066 | Tecnicas Reunidas (Ute TR Fadhili Project) | 2017TRS1708391 | P-Tecnicas Reunidas (Ute TR Fadhili Project) - 2017TRS1708391-8LPN14 | 14326 | POC | EUR |  | 385519.87 | 2017-09-22 | 2018-04-23 |  | 324576 | 0 | 277161 |  | 256537 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 10068 | Petrotime HK Limited | 2017PHK3222601 | P - Petrotime HK Limited - 2017PHK3222601 - Pumping System P-1101 | 15050 | POC | EUR | 590000 | 698560 | 2017-09-12 | 2018-08-06 |  | 590000 | 0 | 422317 |  | 185369 | 0 | [5 empty] | 413000 |  | 2018-05-11 | 345 | 0 | ASIA | OE
EPO | RU8310 | 10079 | GS Engineering & Construction Corporation | 201716RS621551 | P - GS Engineering & Construction Corporation - 201716RS621551 - Pumping System - 1630-G-006 A/B | 15461 | POC | EUR | 0 | 628265 | 2017-07-26 | 2018-04-20 | [9 empty] | 2018-04-30
EPO | RU8310 | 10081 | CEPSA, Compania Espanola De Petroleos SAU | 2017CEP0547401 | P - CEPSA, Compania Espanola De Petroleos SAU - 2017CEP0547401 - Pumping system Y-P-31C | 18242 | POC | EUR | 0 | 395417.17 | 2017-05-19 | 2018-02-08 | [9 empty] | 2018-02-28
EPO | RU8310 | 10082 | Hamechadesh Industries (MNTS) LTD | 2017HCH0851401 | P - Hamechadesh Industries (MNTS) LTD - 2017HCH0851401 | 18328 | POC | EUR | 0 | 384523.54 | 2017-08-08 | 2018-02-22 | [9 empty] | 2018-04-30
EPO | RU8310 | 10083 | PA Italy Netherlands Operating Company Italy Branch | 2016CCJ0641651 | P - PA Italy Netherlands Operating Company Italy Branch - 2016CCJ0641651- Pumping System P- 22010 A/B | 15301 | POC | EUR | 0 | 148511.5 | 2016-11-03 | 2018-02-08 | [9 empty] | 2018-01-31
EPO | RU8310 | 10083 | PA Italy Netherlands Operating Company Italy Branch | 2016CCJ0641651 | P - PA Italy Netherlands Operating Company Italy Branch - 2016CCJ0641651- Pumping System P-22011 A/B | 15309 | POC | EUR |  | 205417.34 | 2016-11-03 | 2018-02-08 | [9 empty] | 2018-01-31
EPO | RU8310 | 10120 | Neste Singapore PTE LTD | 2017NES2104141 | P - Neste Singapore PTE LTD - 2017NES2104141- Pumping System | 16817 | POC | EUR | 0 | 273116.28 | 2017-04-12 | 2018-05-22 | [9 empty] | 2018-04-30
EPO | RU8310 | 10121 | CSTS (Chiyoda-Saipem-Tripatra-SAE Joint Operation) | 2017BPT3119601 | P - CSTS (Chiyoda-Saipem-Tripatra-SAE Joint Operation) - 2017BPT3119601 | 12976 | POC | EUR | 4149368 | 4926959.56 | 2017-09-29 | 2018-08-01 |  | 4149368 | 0 | 3670619 |  | 601021 | 0 | [9 empty] | 41494 | ASIA | OE
EPO | RU8310 | 10122 | Luoyang Petrochemical Engineering Corporation | 2017LUO2917361 | P - Luoyang Petrochemical Engineering Corporation - 2017LUO2917361 - Pumping system 10P2203 A/B | 13435 | POC | EUR | 2336500 | 134494.42 | 2017-08-31 | 2018-07-20 |  | 113268 | 0 | 90690 |  | 79001 | 0 | [9 empty] | 23365 | CHINA | OE
EPO | RU8310 | 10122 | Luoyang Petrochemical Engineering Corporation | 2017LUO2917361 | P - Luoyang Petrochemical Engineering Corporation - 2017LUO2917361 - Pumping system 10P2205 A/B | 13525 | POC | EUR |  | 110499.44 | 2017-08-31 | 2018-07-20 |  | 93060 | 0 | 75191 |  | 68554 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 10122 | Luoyang Petrochemical Engineering Corporation | 2017LUO2917361 | P - Luoyang Petrochemical Engineering Corporation - 2017LUO2917361 - Pumping system 10P2301 A/B | 13531 | POC | EUR |  | 134807.9 | 2017-08-31 | 2018-07-20 |  | 113532 | 0 | 93967 |  | 84094 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 10122 | Luoyang Petrochemical Engineering Corporation | 2017LUO2917361 | P - Luoyang Petrochemical Engineering Corporation - 2017LUO2917361 - Pumping system 10P2303 A/B | 13578 | POC | EUR |  | 164739.88 | 2017-08-31 | 2018-07-20 |  | 138740 | 0 | 115270 |  | 105195 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 10122 | Luoyang Petrochemical Engineering Corporation | 2017LUO2917361 | P - Luoyang Petrochemical Engineering Corporation - 2017LUO2917361 - Pumping system 10P2305 A/B | 13580 | POC | EUR |  | 108457.12 | 2017-08-31 | 2018-07-20 |  | 91340 | 0 | 74641 |  | 65487 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 10122 | Luoyang Petrochemical Engineering Corporation | 2017LUO2917361 | P - Luoyang Petrochemical Engineering Corporation - 2017LUO2917361 - Pumping System 10P1201 A/B | 13598 | POC | EUR |  | 409486.75 | 2017-08-31 | 2018-07-20 |  | 344860 | 0 | 283169 |  | 264700 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 10122 | Luoyang Petrochemical Engineering Corporation | 2017LUO2917361 | P - Luoyang Petrochemical Engineering Corporation - 2017LUO2917361 - Pumping system 10P1203 A/B/C | 13601 | POC | EUR |  | 842305.94 | 2017-08-31 | 2018-07-20 |  | 709370 | 0 | 585800 |  | 425751 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 10122 | Luoyang Petrochemical Engineering Corporation | 2017LUO2917361 | P - Luoyang Petrochemical Engineering Corporation - 2017LUO2917361 - Pumping system 10P2307 A/B | 13621 | POC | EUR |  | 519891.22 | 2017-08-31 | 2018-07-20 |  | 437840 | 0 | 355990 |  | 329094 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 10122 | Luoyang Petrochemical Engineering Corporation | 2017LUO2917361 | P - Luoyang Petrochemical Engineering Corporation - 2017LUO2917361 - Pumping system 10P2309 A/B | 13622 | POC | EUR |  | 349677.43 | 2017-08-31 | 2018-07-20 |  | 294490 | 0 | 235543 |  | 197821 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 10123 | Lima Refining Company | 2017LIM0744011 | P - Lima Refining Company - 2017LIM0744011 - Pumping System PR-210961/62 | 14026 | POC | USD | 1528697 | 396730.04 | 2017-08-08 | 2018-05-16 |  | 396730 | 0 | 263673 |  | 236138 | 0 | [6 empty] | 0 |  |  | 0 | US | OE
EPO | RU8310 | 10123 | Lima Refining Company | 2017LIM0744011 | P - Lima Refining Company - 2017LIM0744011 - Pumping System PR-210959/60 | 14262 | POC | USD |  | 142505.52 | 2017-08-08 | 2018-05-16 |  | 142506 | 0 | 91981 |  | 83253 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 10123 | Lima Refining Company | 2017LIM0744011 | P - Lima Refining Company - 2017LIM0744011 - Pumping System PR-211904/05 | 14265 | POC | USD |  | 130120.65 | 2017-08-08 | 2018-05-16 |  | 130121 | 0 | 83844 |  | 74236 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 10123 | Lima Refining Company | 2017LIM0744011 | P - Lima Refining Company - 2017LIM0744011 - Pumping System PR-212035/36 | 14266 | POC | USD |  | 129577.19 | 2017-08-08 | 2018-05-16 |  | 129577 | 0 | 82966 |  | 73676 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 10123 | Lima Refining Company | 2017LIM0744011 | P - Lima Refining Company - 2017LIM0744011 - Pumping System PR-212039/40 | 14267 | POC | USD |  | 149204.84 | 2017-08-08 | 2018-05-16 |  | 149205 | 0 | 94053 |  | 78608 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 10123 | Lima Refining Company | 2017LIM0744011 | P - Lima Refining Company - 2017LIM0744011 - Pumping System PR-210967/68 | 14268 | POC | USD |  | 580557.76 | 2017-08-08 | 2018-05-16 |  | 580558 | 0 | 440982 |  | 428685 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 10124 | JGC Gulf International Co. Ltd. | 2017JGC0751011 | P - JGC Gulf International Ltd. - 2017JGC0751011 - Pumping System P-9602 A/B | 17044 | POC | EUR | 0 | 59916.91 | 2017-11-06 | 2018-02-15 | [9 empty] | 2018-04-30
EPO | RU8310 | 10124 | JGC Gulf International Co. Ltd. | 2017JGC0751011 | P - JGC Gulf International Ltd. - 2017JGC0751011 - Pumping System P-9605 A/B | 17045 | POC | EUR |  | 51303.22 | 2017-11-06 | 2018-02-15 | [9 empty] | 2018-04-30
EPO | RU8310 | 10124 | JGC Gulf International Co. Ltd. | 2017JGC0751011 | P - JGC Gulf International Ltd. - 2017JGC0751011 - Pumping System P-9606 A/B | 17046 | POC | EUR |  | 84550.85 | 2017-11-06 | 2018-02-15 | [9 empty] | 2018-04-30
EPO | RU8310 | 10124 | JGC Gulf International Co. Ltd. | 2017JGC0751011 | P - JGC Gulf International Ltd. - 2017JGC0751011 - Pumping System P-9607 A/B | 17047 | POC | EUR |  | 87166.06 | 2017-11-06 | 2018-02-15 | [9 empty] | 2018-04-30
EPO | RU8310 | 10124 | JGC Gulf International Co. Ltd. | 2017JGC0751011 | P - JGC Gulf International Ltd. - 2017JGC0751011 - Pumping System P-9608 | 17048 | POC | EUR |  | 50103.78 | 2017-11-06 | 2018-02-15 | [9 empty] | 2018-04-30
EPO | RU8310 | 10124 | JGC Gulf International Co. Ltd. | 2017JGC0751011 | P - JGC Gulf International Ltd. - 2017JGC0751011 - Pumping System P-9603 A/B | 17049 | POC | EUR |  | 83665.02 | 2017-11-06 | 2018-02-15 | [9 empty] | 2018-04-30
EPO | RU8310 | 10125 | BP Oil Espana S.A.U. | 201706RS4D1741 | P - BP Oil Espana S.A.U. - 201706RS4D1741 - Pumping System - P 2125 A/B | 17028 | POC | EUR | 234312 | 280013.91 | 2017-12-12 | 2018-02-10 |  | 234312 | 0 | 159603 |  | 157814 | 0 | [9 empty] | 0 | EUROPE | AM
EPO | RU8310 | 10132 | Hengli Petrochemical (Dalian) Refinery Co. LTD | 2017HGL3212601 | P - Hengli Petrochemical (Dalian) Refinery Co. LTD - 2017HGL3212601 - Pumping System PX Unit | 13704 | POC | EUR | 18969656 | 4457904.07 | 2017-02-10 | 2018-08-10 |  | 4208848 | 0 | 4024520 |  | 1478351 | 1360593 | [9 empty] | 189697 | CHINA | OE
EPO | RU8310 | 10132 | Hengli Petrochemical (Dalian) Refinery Co. LTD | 2017HGL3212601 | P - Hengli Petrochemical (Dalian) Refinery Co. LTD - 2017HGL3212601 - Pumping System Diesel Hydrocracker Reaction Unit - Train A | 13713 | POC | EUR |  | 2073222.69 | 2017-02-10 | 2018-08-10 |  | 1957395 | 0 | 1928048 |  | 1381831 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 10132 | Hengli Petrochemical (Dalian) Refinery Co. LTD | 2017HGL3212601 | P - Hengli Petrochemical (Dalian) Refinery Co. LTD - 2017HGL3212601 - Pumping System Diesel Hydrocracker Reaction Unit - Train B | 13718 | POC | EUR |  | 2073222.69 | 2017-02-10 | 2018-08-10 |  | 1957395 | 0 | 1928048 |  | 1381831 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 10132 | Hengli Petrochemical (Dalian) Refinery Co. LTD | 2017HGL3212601 | P - Hengli Petrochemical (Dalian) Refinery Co. LTD - 2017HGL3212601 - Pumping System H-Oil-Train Fraction Section Unit - Train A | 13722 | POC | EUR |  | 2276120.25 | 2017-02-10 | 2018-08-10 |  | 2148957 | 0 | 2119279 |  | 1755431 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 10132 | Hengli Petrochemical (Dalian) Refinery Co. LTD | 2017HGL3212601 | P - Hengli Petrochemical (Dalian) Refinery Co. LTD - 2017HGL3212601 - Pumping System H-Oil-Train Fraction Section Unit - Train B | 13723 | POC | EUR |  | 2272133.52 | 2017-02-10 | 2018-08-10 |  | 2145193 | 0 | 2119279 |  | 1755431 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 10132 | Hengli Petrochemical (Dalian) Refinery Co. LTD | 2017HGL3212601 | P - Hengli Petrochemical (Dalian) Refinery Co. LTD - 2017HGL3212601 - Pumping System VGO Hydrocracker-Fractionator Section Unit - SR VGO Unit | 13724 | POC | EUR |  | 3094471.23 | 2017-02-10 | 2018-08-10 |  | 2921588 | 0 | 2928709 |  | 2415167 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 10132 | Hengli Petrochemical (Dalian) Refinery Co. LTD | 2017HGL3212601 | P - Hengli Petrochemical (Dalian) Refinery Co. LTD - 2017HGL3212601 - Pumping System VGO Hydrocracker-Fractionator Section Unit - Mixed VGO Unit | 13725 | POC | EUR |  | 3304312.74 | 2017-02-10 | 2018-08-10 |  | 3119706 | 0 | 3138668 |  | 2428447 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 10132 | Hengli Petrochemical (Dalian) Refinery Co. LTD | 2017HGL3212601 | P - Hengli Petrochemical (Dalian) Refinery Co. LTD - 2017HGL3212601 - Pumping System Base Oil Isodewaxing Unit - Dewaxing Unit | 13726 | POC | EUR |  | 540786.91 | 2017-02-10 | 2018-08-10 |  | 510574 | 0 | 509908 |  | 451556 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 10140 | Hengli Petrochemical (Dalian) Refinery Co. LTD | 2017ZIR2614201 | P - HENGLI PETROCHEMICAL (DALIAN) REFINERY CO.LTD - 2017ZIR2614201 - Pumping System 4181P001 A/B | 13772 | POC | EUR | 2398000 | 1007696.76 | 2017-06-27 | 2018-07-01 |  | 849660 | 0 | 683084 |  | 497547 | 0 | [5 empty] | 359700 |  | 2018-05-24 | 383 | 0 | CHINA | OE
EPO | RU8310 | 10140 | Hengli Petrochemical (Dalian) Refinery Co. LTD | 2017ZIR2614201 | P - HENGLI PETROCHEMICAL (DALIAN) REFINERY CO.LTD - 2017ZIR2614201 - Pumping System 4181P002 A/B | 13865 | POC | EUR |  | 1836331.24 | 2017-06-27 | 2018-07-01 |  | 1548340 | 0 | 1345961 |  | 815395 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 10158 | JV of Tecnicas Reunidas,Sinopec,Hanwaha | 2016TRS2411341 | P-JV of Tecnicas Reunidas,Sipopec,Hanwaha-2016TRS2411341 - Pumping System - 03-P-0002 A/B | 16100 | POC | USD | 1654532 | 552094.44 | 2017-01-24 | 2018-08-03 |  | 551958 | 0 | 356681 |  | 252551 | 0 | [6 empty] | 0 |  |  | 0 | ASIA | OE
EPO | RU8310 | 10158 | JV of Tecnicas Reunidas,Sinopec,Hanwaha | 2016TRS2411341 | P-JV of Tecnicas Reunidas,Sipopec,Hanwaha-2016TRS2411341 - Pumping System - 13-P-0002 A/B | 16101 | POC | USD |  | 551434.27 | 2017-01-24 | 2018-08-03 |  | 551287 | 0 | 349788 |  | 229417 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 10158 | JV of Tecnicas Reunidas,Sinopec,Hanwaha | 2016TRS2411341 | P-JV of Tecnicas Reunidas,Sipopec,Hanwaha-2016TRS2411341 - Pumping System - 23-P-0002 A/B | 16102 | POC | USD |  | 551434.27 | 2017-01-24 | 2018-08-03 |  | 551287 | 0 | 349789 |  | 222527 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 10158 | JV of Tecnicas Reunidas,Sinopec,Hanwaha | 2016TRS2411341 | P-JV of Tecnicas Reunidas,Sipopec,Hanwaha-2016TRS2411341 - Pumping System - 03 - P-0004 A/B | 16103 | POC | USD |  | 715679.88 | 2017-01-24 | 2018-08-03 | [9 empty] | 2017-12-31
EPO | RU8310 | 10158 | JV of Tecnicas Reunidas,Sinopec,Hanwaha | 2016TRS2411341 | P-JV of Tecnicas Reunidas,Sipopec,Hanwaha-2016TRS2411341 - Pumping System - 13 - P-0004 A/B | 16104 | POC | USD |  | 715679.88 | 2017-01-24 | 2018-08-03 | [9 empty] | 2017-12-31
EPO | RU8310 | 10158 | JV of Tecnicas Reunidas,Sinopec,Hanwaha | 2016TRS2411341 | P-JV of Tecnicas Reunidas,Sipopec,Hanwaha-2016TRS2411341 - Pumping System - 23 - P-0004 A/B | 16105 | POC | USD |  | 715679.88 | 2017-01-24 | 2018-08-03 | [9 empty] | 2017-12-31
EPO | RU8310 | 10158 | JV of Tecnicas Reunidas,Sinopec,Hanwaha | 2016TRS2411341 | P-JV of Tecnicas Reunidas,Sipopec,Hanwaha-2016TRS2411341 - Pumping System - 05 - P-0004 A/B | 16106 | POC | USD |  | 870430.19 | 2017-01-24 | 2018-08-03 | [9 empty] | 2017-12-31
EPO | RU8310 | 10158 | JV of Tecnicas Reunidas,Sinopec,Hanwaha | 2016TRS2411341 | P-JV of Tecnicas Reunidas,Sipopec,Hanwaha-2016TRS2411341 - Pumping System - 25 - P-0004 A/B | 16107 | POC | USD |  | 870430.19 | 2017-01-24 | 2018-08-03 | [9 empty] | 2017-12-31
EPO | RU8310 | 10160 | Zawawi Business Development Co. L.L.C. | 201713RS4D1861 | P - Zawawi Business Development Co. L.L.C. - 201713RS4D1861 - A0LCB10AP001 | 15956 | POC | EUR | 276887 | 327834.21 | 2017-10-02 | 2018-03-28 |  | 276887 | 0 | 97461 |  | 97461 | 0 |  |  | 2018-05-31 |  |  | 276887 |  | 2018-05-09 | 341 | 0 | ASIA | AM
EPO | RU8310 | 10172 | Mansrich Limited | 2017MAS2008011 | P - Mansrich Limited - 2017MAS2008011 - P-101/102 | 14863 | POC | EUR | 655000 | 155366 | 2017-09-28 | 2018-07-04 |  | 131000 | 0 | 118603 |  | 102784 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 10172 | Mansrich Limited | 2017MAS2008011 | P - Mansrich Limited - 2017MAS2008011 - P-103/104 | 16031 | POC | EUR |  | 155366 | 2017-09-28 | 2018-07-04 |  | 131000 | 0 | 107939 |  | 97075 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 10172 | Mansrich Limited | 2017MAS2008011 | P - Mansrich Limited - 2017MAS2008011 - P-105/106 | 16032 | POC | EUR |  | 155366 | 2017-09-28 | 2018-07-04 |  | 131000 | 0 | 108003 |  | 95008 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 10172 | Mansrich Limited | 2017MAS2008011 | P - Mansrich Limited - 2017MAS2008011 - P-107/108 | 16033 | POC | EUR |  | 155366 | 2017-09-28 | 2018-07-04 |  | 131000 | 0 | 108195 |  | 88761 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 10172 | Mansrich Limited | 2017MAS2008011 | P - Mansrich Limited - 2017MAS2008011 - P-109/110 | 16035 | POC | EUR |  | 155366 | 2017-09-28 | 2018-07-04 |  | 131000 | 0 | 113315 |  | 95021 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 10196 | Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone | 2017DOR4224551_2017DOR4223371_2017DOR1142301 | P-Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone-2017DOR4223371-2017DOR1142301 - 2017DOR1142311 | 17891 | POC | USD | 18043976 | 5270017.47 | 2017-09-29 | 2019-03-13 |  | 5270017 | 0 | 3656226 |  | 129321 | 0 | [5 empty] | 1372296.8 | 1136289.4759 | 2018-05-24 | 337-384 | 156675 | OTHER AFRICA | OE
EPO | RU8310 | 10196 | Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone | 2017DOR4224551_2017DOR4223371_2017DOR1142301 | P-Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone-2017DOR4223371-2017DOR1144291 | 17892 | POC | USD |  | 1026398.95 | 2017-09-29 | 2019-03-13 |  | 1026399 | 0 | 753685 |  | 36061 | 0 | [9 empty] | 0 | OTHER AFRICA | OE
EPO | RU8310 | 10196 | Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone | 2017DOR4224551_2017DOR4223371_2017DOR1142301 | P-Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone-2017DOR4223371-2017DOR4223371 | 17893 | POC | USD |  | 237290.78 | 2017-09-29 | 2019-03-13 |  | 237291 | 0 | 185622 |  | 36848 | 0 | [9 empty] | 0 | OTHER AFRICA | OE
EPO | RU8310 | 10196 | Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone | 2017DOR4224551_2017DOR4223371_2017DOR1142301 | P-Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone-2017DOR4223371-2017DOR4223381 | 17894 | POC | USD |  | 105942.93 | 2017-09-29 | 2019-03-13 |  | 105943 | 0 | 84451 |  | 19280 | 0 | [9 empty] | 0 | OTHER AFRICA | OE
EPO | RU8310 | 10196 | Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone | 2017DOR4224551_2017DOR4223371_2017DOR1142301 | P-Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone-2017DOR4223371-2017DOR4223441 | 17895 | POC | USD |  | 378525.93 | 2017-09-29 | 2019-03-13 |  | 378526 | 0 | 285378 |  | 63352 | 0 | [9 empty] | 0 | OTHER AFRICA | OE
EPO | RU8310 | 10196 | Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone | 2017DOR4224551_2017DOR4223371_2017DOR1142301 | P-Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone-2017DOR4223371-2017DOR4224451 | 17896 | POC | USD |  | 1375259.74 | 2017-09-29 | 2019-03-13 |  | 1375260 | 0 | 977371 |  | 81084 | 0 | 20219.84 | [8 empty] | 0 | OTHER AFRICA | OE
EPO | RU8310 | 10196 | Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone | 2017DOR4224551_2017DOR4223371_2017DOR1142301 | P-Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone-2017DOR4223371-2017DOR4224461 | 17897 | POC | USD |  | 333266.71 | 2017-09-29 | 2019-03-13 |  | 333267 | 0 | 249253 |  | 93149 | 0 | [9 empty] | 0 | OTHER AFRICA | OE
EPO | RU8310 | 10196 | Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone | 2017DOR4224551_2017DOR4223371_2017DOR1142301 | P-Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone-2017DOR4223371-2017DOR4224471 | 17898 | POC | USD |  | 551821.57 | 2017-09-29 | 2019-03-13 |  | 551822 | 0 | 426062 |  | 163420 | 0 | [9 empty] | 0 | OTHER AFRICA | OE
EPO | RU8310 | 10196 | Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone | 2017DOR4224551_2017DOR4223371_2017DOR1142301 | P-Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone-2017DOR4223371-2017DOR4225401 | 17899 | POC | USD |  | 541655.91 | 2017-09-29 | 2019-03-13 |  | 541656 | 0 | 433463 |  | 74790 | 0 | [9 empty] | 0 | OTHER AFRICA | OE
EPO | RU8310 | 10196 | Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone | 2017DOR4224551_2017DOR4223371_2017DOR1142301 | P-Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone-2017DOR4223371-2017DOR4225481 | 17900 | POC | USD |  | 223347.01 | 2017-09-29 | 2019-03-13 |  | 223347 | 0 | 166963 |  | 61473 | 0 | [9 empty] | 0 | OTHER AFRICA | OE
EPO | RU8310 | 10196 | Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone | 2017DOR4224551_2017DOR4223371_2017DOR1142301 | P-Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone-2017DOR4223371-2017DOR4225491 | 17901 | POC | USD |  | 1276344.27 | 2017-09-29 | 2019-03-13 |  | 1276344 | 0 | 908313 |  | 23529 | 0 | 19182.21 | [8 empty] | 0 | OTHER AFRICA | OE
EPO | RU8310 | 10196 | Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone | 2017DOR4224551_2017DOR4223371_2017DOR1142301 | P-Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone-2017DOR4223371-2017DOR4222341 | 17902 | POC | USD |  | 250456.2 | 2017-09-29 | 2019-03-13 |  | 250456 | 0 | 193512 |  | 61165 | 0 | [9 empty] | 0 | OTHER AFRICA | OE
EPO | RU8310 | 10196 | Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone | 2017DOR4224551_2017DOR4223371_2017DOR1142301 | P-Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone-2017DOR4223371-2017DOR4222351 | 17903 | POC | USD |  | 326956.16 | 2017-09-29 | 2019-03-13 |  | 326956 | 0 | 257637 |  | 50605 | 0 | [9 empty] | 0 | OTHER AFRICA | OE
EPO | RU8310 | 10196 | Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone | 2017DOR4224551_2017DOR4223371_2017DOR1142301 | P-Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone-2017DOR4223371-2017DOR4222361 | 17904 | POC | USD |  | 1105657.52 | 2017-09-29 | 2019-03-13 |  | 1105658 | 0 | 697397 |  | 27185 | 0 | 19588.91 | [8 empty] | 0 | OTHER AFRICA | OE
EPO | RU8310 | 10196 | Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone | 2017DOR4224551_2017DOR4223371_2017DOR1142301 | P-Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone-2017DOR4223371-2017DOR4224401 | 17905 | POC | USD |  | 2395649.55 | 2017-09-29 | 2019-03-13 |  | 2395650 | 0 | 1893931 |  | 8313 | 0 | 248400 | [8 empty] | 0 | OTHER AFRICA | OE
EPO | RU8310 | 10196 | Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone | 2017DOR4224551_2017DOR4223371_2017DOR1142301 | P-Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone-2017DOR4223371-2017DOR4224411 | 17906 | POC | USD |  | 1112588.28 | 2017-09-29 | 2019-03-13 |  | 1112588 | 0 | 855300 |  | 4948 | 0 | 81000 | [8 empty] | 0 | OTHER AFRICA | OE
EPO | RU8310 | 10196 | Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone | 2017DOR4224551_2017DOR4223371_2017DOR1142301 | P-Dangote Oil Ref Co.LTD & Dangote Petroleum Ref. & Petroch Free Zone-2017DOR4223371-2017DOR4224551 | 17907 | POC | USD |  | 1532796.02 | 2017-09-29 | 2019-03-13 |  | 1532796 | 0 | 1265608 |  | 317503 | 0 | 165600 | [8 empty] | 0 | OTHER AFRICA | OE
EPO | RU8310 | 11547 | Amec Foster Wheeler Asia Pacific Pte LTD | 2017FWE3923651 | P - Amec Foster Wheeler Asia Pacific Pte LTD - 2017FWE3923651 - Pumping System - P-5517 A/B | 16803 | POC | EUR | 2002230 | 681129.82 | 2017-10-30 | 2018-09-30 |  | 577125 | 0 | 464142 |  | 161677 | 0 | 126000 |  |  |  |  | 576807.5 |  | 2018-05-17 | 364 | 0 | ASIA | OE
EPO | RU8310 | 11547 | Amec Foster Wheeler Asia Pacific Pte LTD | 2017FWE3923651 | P - Amec Foster Wheeler Asia Pacific Pte LTD - 2017FWE3923651 - Pumping System - 832-P1 A/B/C | 16804 | POC | EUR |  | 1009869.55 | 2017-10-30 | 2018-09-30 |  | 855065 | 0 | 688014 |  | 217014 | 0 | 195000 | [8 empty] | 0 | ASIA | OE
EPO | RU8310 | 11547 | Amec Foster Wheeler Asia Pacific Pte LTD | 2017FWE3923651 | P - Amec Foster Wheeler Asia Pacific Pte LTD - 2017FWE3923651 - Pumping System - 832-P2 A/B | 16805 | POC | EUR |  | 674034.71 | 2017-10-30 | 2018-09-30 |  | 570040 | 0 | 469072 |  | 136859 | 0 | 130000 | [8 empty] | 0 | ASIA | OE
EPO | RU8310 | 12008 | Shell Nederland Chemie B.V. | 2017SHE2010011 | P - Shell Nederland Chemie B.V. - 2017SHE2010011 - Pumping System P-314 A/B | 17240 | POC | EUR | 780205 | 89771.37 | 2017-10-27 | 2018-05-17 |  | 79117 | 0 | 93570 |  | 61358 | 0 | [5 empty] | 230311.2 |  | 2018-05-10 | 343 | 0 | EUROPE | OE
EPO | RU8310 | 12008 | Shell Nederland Chemie B.V. | 2017SHE2010011 | P - Shell Nederland Chemie B.V. - 2017SHE2010011 - Pumping System P-315 A/B | 17241 | POC | EUR |  | 139485.04 | 2017-10-27 | 2018-05-17 |  | 121739 | 0 | 112546 |  | 55178 | 0 | [9 empty] | 0 | EUROPE | OE
EPO | RU8310 | 12008 | Shell Nederland Chemie B.V. | 2017SHE2010011 | P - Shell Nederland Chemie B.V. - 2017SHE2010011 - Pumping System P-316 | 17242 | POC | EUR |  | 74885.63 | 2017-10-27 | 2018-05-17 |  | 65279 | 0 | 65309 |  | 37422 | 0 | [9 empty] | 0 | EUROPE | OE
EPO | RU8310 | 12008 | Shell Nederland Chemie B.V. | 2017SHE2010011 | P - Shell Nederland Chemie B.V. - 2017SHE2010011 - Pumping System P-317 A/B | 17243 | POC | EUR |  | 165304.32 | 2017-10-27 | 2018-05-17 |  | 143876 | 0 | 137112 |  | 66606 | 0 | [9 empty] | 0 | EUROPE | OE
EPO | RU8310 | 12008 | Shell Nederland Chemie B.V. | 2017SHE2010011 | P - Shell Nederland Chemie B.V. - 2017SHE2010011 - Pumping System P-318 A/B | 17244 | POC | EUR |  | 163426.7 | 2017-10-27 | 2018-05-17 |  | 142410 | 0 | 135862 |  | 51317 | 0 | [9 empty] | 0 | EUROPE | OE
EPO | RU8310 | 12008 | Shell Nederland Chemie B.V. | 2017SHE2010011 | P - Shell Nederland Chemie B.V. - 2017SHE2010011 - Pumping System P-330 A/B | 17245 | POC | EUR |  | 53636.98 | 2017-10-27 | 2018-05-17 |  | 48283 | 0 | 46246 |  | 35044 | 0 | [9 empty] | 0 | EUROPE | OE
EPO | RU8310 | 12008 | Shell Nederland Chemie B.V. | 2017SHE2010011 | P - Shell Nederland Chemie B.V. - 2017SHE2010011 - Pumping System P-348 A/B | 17246 | POC | EUR |  | 138447.75 | 2017-10-27 | 2018-05-17 |  | 120850 | 0 | 119640 |  | 61427 | 0 | [9 empty] | 0 | EUROPE | OE
EPO | RU8310 | 12008 | Shell Nederland Chemie B.V. | 2017SHE2010011 | P - Shell Nederland Chemie B.V. - 2017SHE2010011 - Pumping System P-399 | 17247 | POC | EUR |  | 67069.21 | 2017-10-27 | 2018-05-17 |  | 58651 | 0 | 59161 |  | 31323 | 0 | [9 empty] | 0 | EUROPE | OE
EPO | RU8310 | 12543 | Valero Refining-Texas, Lp | 2017VAL2209401 | P - Valero Refining-Texas, Lp - 2017VAL2209401 - Pumping system P3853/P3854 | 14806 | POC | USD | 444396 | 444396 | 2017-10-27 | 2018-05-28 |  | 444396 | 0 | 306784 |  | 259242 | 0 | [5 empty] | 88879.2 | 73593.7733 | 2018-05-04 | 321 | 11200 | US | OE
EPO | RU8310 | 12544 | Aereon Europe Srl | 2017ARE0802301 | P - Aereon Europe Srl - 2017ARE0802301 - Pumping System 2 A TR2/ 2 B TR2/ 2 C TR2/ 2 D TR2 | 14910 | POC | EUR | 0 | 331667.84 | 2017-10-30 | 2018-04-20 | [9 empty] | 2018-04-30
EPO | RU8310 | 12545 | John Zink International Luxembourg Sarl | 2017JZI1711011 | P - John Zink International Luxembourg Sarl - 2017JZI1711011 - Pumping system 93-P-861 A/B | 14893 | POC | EUR | 235885 | 162180.65 | 2017-10-27 | 2018-04-27 |  | 138285 | 0 | 104057 |  | 43479 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 12545 | John Zink International Luxembourg Sarl | 2017JZI1711011 | P - John Zink International Luxembourg Sarl - 2017JZI1711011 - Pumping system 93-P-871 A/B | 14896 | POC | EUR |  | 114465.28 | 2017-10-27 | 2018-04-27 |  | 97600 | 0 | 73424 |  | 25089 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 12554 | Shell Nederland Raffinaderij B.V. | 2017SHE2212011 | P - Shell Nederland Raffinaderij B.V. - 2017SHE2212011 - Pumping System - P323 | 14929 | POC | EUR | 219366 | 128811.04 | 2017-10-30 | 2018-05-30 |  | 109051 | 0 | 96331 |  | 85248 | 0 | [9 empty] | 0 | EUROPE | OE
EPO | RU8310 | 12554 | Shell Nederland Raffinaderij B.V. | 2017SHE2212011 | P - Shell Nederland Raffinaderij B.V. - 2017SHE2212011 - Pumping System - P411 | 16512 | POC | EUR |  | 130304.08 | 2017-10-30 | 2018-05-30 |  | 110315 | 0 | 96352 |  | 85559 | 0 | [9 empty] | 0 | EUROPE | OE
EPO | RU8310 | 13445 | CSTS (Chiyoda-Saipem-Tripatra-Sae) Joint Operation | 2017BPT3422011 | P - CSTS(Chiyoda-Saipem-Tripatra-SAE) Joint Operation - 2017BPT3422011 - Pumping System 011-P-31001 A/B | 13677 | POC | EUR | 2653805 | 342729.54 | 2017-10-24 | 2018-09-30 |  | 291919 | 0 | 218055 |  | 23977 | 0 | [9 empty] | 26538 | ASIA | OE
EPO | RU8310 | 13445 | CSTS (Chiyoda-Saipem-Tripatra-Sae) Joint Operation | 2017BPT3422011 | P - CSTS (Chiyoda-Saipem-Tripatra-SAE) Joint Operation - 2017BPT3422011 - Pumping System 017-P-31002 A/B | 13815 | POC | EUR |  | 218100.61 | 2017-10-24 | 2018-09-30 |  | 185766 | 0 | 152567 |  | 31871 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 13445 | CSTS (Chiyoda-Saipem-Tripatra-Sae) Joint Operation | 2017BPT3422011 | P - CSTS (Chiyoda-Saipem-Tripatra-SAE) Joint Operation - 2017BPT3422011 - Pump 017-P-31006 | 13820 | POC | EUR |  | 124628.92 | 2017-10-24 | 2018-09-30 |  | 106152 | 0 | 85467 |  | 9625 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 13445 | CSTS (Chiyoda-Saipem-Tripatra-Sae) Joint Operation | 2017BPT3422011 | P - CSTS (Chiyoda-Saipem-Tripatra-SAE) Joint Operation - 2017BPT3422011 - Pumping System 017-P-31007 A/B | 13825 | POC | EUR |  | 218100.61 | 2017-10-24 | 2018-09-30 |  | 185766 | 0 | 146768 |  | 34156 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 13445 | CSTS (Chiyoda-Saipem-Tripatra-Sae) Joint Operation | 2017BPT3422011 | P - CSTS (Chiyoda-Saipem-Tripatra-SAE) Joint Operation - 2017BPT3422011 - Pump 187-P-31009 | 13826 | POC | EUR |  | 62314.46 | 2017-10-24 | 2018-09-30 |  | 53076 | 0 | 38518 |  | 11331 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 13445 | CSTS (Chiyoda-Saipem-Tripatra-Sae) Joint Operation | 2017BPT3422011 | P - CSTS (Chiyoda-Saipem-Tripatra-SAE) Joint Operation - 2017BPT3422011 - Pumping System 023-P-31006 A/B/C | 13827 | POC | EUR |  | 1028188.61 | 2017-10-24 | 2018-09-30 |  | 875756 | 0 | 734738 |  | 88339 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 13445 | CSTS (Chiyoda-Saipem-Tripatra-Sae) Joint Operation | 2017BPT3422011 | P - CSTS (Chiyoda-Saipem-Tripatra-SAE) Joint Operation - 2017BPT3422011 - Pumping System 023-P-31002 A/B/C | 17515 | POC | EUR |  | 1121660.3 | 2017-10-24 | 2018-09-30 |  | 955370 | 0 | 798576 |  | 100285 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 14724 | Mansrich Limited | 2017MAS3524501 | P - Mansrich Limited - 2017MAS3524501 - Pumping System - PS01-1761-PA-01/PS01-1762-PA-02/PS01-1763-PA-03 | 15554 | POC | EUR | 1317150 | 513825.87 | 2017-11-27 | 2017-08-31 |  | 436435 | 0 | 353056 |  | 68750 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 14724 | Mansrich Limited | 2017MAS3524501 | P - Mansrich Limited - 2017MAS3524501 - Pumping System - PS01-1741-PA-04 | 15555 | POC | EUR |  | 321250.81 | 2017-11-27 | 2017-08-31 |  | 272865 | 0 | 223498 |  | 45610 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 14724 | Mansrich Limited | 2017MAS3524501 | P - Mansrich Limited - 2017MAS3524501 - Pumping System - PS01-1742-PA-05/PS01-1743-PA-06 | 15556 | POC | EUR |  | 715637.05 | 2017-11-27 | 2017-08-31 |  | 607850 | 0 | 497727 |  | 56289 | 0 | 95000 | [8 empty] | 0 | CHINA | OE
EPO | RU8310 | 14780 | CB&I, LLC | 2017CBI5137511 | P - CB&I, LLC - 2017CBI5137511- LPN1 - P-1104 A | 15357 | POC | USD | 1585446 | 520512 | 2017-11-28 | 2017-12-21 |  | 520512 | 0 | 383638 |  | 11810 | 0 | 35479.7 | [5 empty] | 0 |  |  | 0 | US | OE
EPO | RU8310 | 14780 | CB&I, LLC | 2017CBI5137511 | P - CB&I, LLC - 2017CBI5137511- LPN2 - P-1104 R | 15358 | POC | USD |  | 223222 | 2017-11-28 | 2017-12-21 |  | 223222 | 0 | 157921 |  | 10987 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 14780 | CB&I, LLC | 2017CBI5137511 | P - CB&I, LLC - 2017CBI5137511- HED - P-1133 A/R | 15361 | POC | USD |  | 361708 | 2017-11-28 | 2017-12-21 |  | 361708 | 0 | 256325 |  | 30735 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 14780 | CB&I, LLC | 2017CBI5137511 | P - CB&I, LLC - 2017CBI5137511-HDX - P-1403 A/R | 15362 | POC | USD |  | 480003.5 | 2017-11-28 | 2017-12-21 |  | 480004 | 0 | 339941 |  | 45126 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 14801 | CSTS (Chiyoda-Saipem-Tripatra-Sae) Joint Operation | 2017BPT4431601 | P - CSTS (Chiyoda-Saipem-Tripatra-Sae) Joint Operation - 2017BPT4431601-Pumping System - 162-P-31001 A/B/C | 17306 | POC | EUR | 999300 | 1176475.89 | 2017-11-30 | 2018-10-30 |  | 999300 | 0 | 867788 |  | 14088 | 0 | [5 empty] | 149895 |  | 2018-05-28 | 387 | 9993 | ASIA | OE
EPO | RU8310 | 14814 | Rotary Engineering Fujairah Fze | 2017RGC4129651 | P - Rotary Engineering Fujairah Fze - 2017RGC4129651- Pumping System - 24G-104 A/B | 15416 | POC | EUR | 979234 | 576425.49 | 2017-11-22 | 2017-10-25 |  | 489617 | 0 | 415638 |  | 110461 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 14814 | Rotary Engineering Fujairah Fze | 2017RGC4129651 | P - Rotary Engineering Fujairah Fze - 2017RGC4129651- Pumping System - 24G-101 A/B | 15418 | POC | EUR |  | 576425.49 | 2017-11-22 | 2017-10-25 |  | 489617 | 0 | 415011 |  | 84772 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 14825 | CEPSA Compania Espanola De Petroleos, Sau | 2017CEP3524351 | P - CEPSA Compania Espanola De Petroleos, Sau - 2017CEP3524351-HED16DS | 15423 | POC | EUR | 447556 | 288941.27 | 2017-11-30 | 2018-08-31 |  | 245427 | 0 | 240161 |  | 187565 | 0 | [9 empty] | 0 | EUROPE | OE
EPO | RU8310 | 14825 | CEPSA Compania Espanola De Petroleos, Sau | 2017CEP3524351 | P - CEPSA Compania Espanola De Petroleos, Sau - 2017CEP3524351-HPX13A | 15425 | POC | EUR |  | 119682.4 | 2017-11-30 | 2018-08-31 |  | 101658 | 0 | 100833 |  | 77533 | 0 | [9 empty] | 0 | EUROPE | OE
EPO | RU8310 | 14825 | CEPSA Compania Espanola De Petroleos, Sau | 2017CEP3524351 | P - CEPSA Compania Espanola De Petroleos, Sau - 2017CEP3524351-HPX12A | 15426 | POC | EUR |  | 118283.99 | 2017-11-30 | 2018-08-31 |  | 100471 | 0 | 99172 |  | 77268 | 0 | [9 empty] | 0 | EUROPE | OE
EPO | RU8310 | 14826 | Hongkong Wisdom Universal Technology Co. Ltd | 2017HOW3423401 | P - Hongkong Wisdom Universal Technology Co. Ltd - 2017HOW3423401- Pumping System - 1100-P-201 A/B/C | 15436 | POC | EUR | 813820 | 958110.29 | 2017-11-27 | 2018-08-21 |  | 813820 | 0 | 703533 |  | 190352 | 0 | 46500 | [8 empty] | 0 | CHINA | OE
EPO | RU8310 | 14887 | CSTS (Chiyoda-Saipem-Tripatra-Sae) Joint Operation | 2017BPT3828011 | P - CSTS (Chiyoda-Saipem-Tripatra-Sae) Joint Operation - 2017BPT3828011-Pumping System - 017-P-31005 PKG 2 | 17315 | POC | EUR | 358600 | 78879.1 | 2017-11-28 | 2018-09-20 |  | 67000 | 0 | 57110 |  | 8976 | 0 | [9 empty] | 3586 | ASIA | OE
EPO | RU8310 | 14887 | CSTS (Chiyoda-Saipem-Tripatra-Sae) Joint Operation | 2017BPT3828011 | P - CSTS (Chiyoda-Saipem-Tripatra-Sae) Joint Operation - 2017BPT3828011-Pumping System - 076-P-31004 PKG 2 | 17316 | POC | EUR |  | 80998.24 | 2017-11-28 | 2018-09-20 |  | 68800 | 0 | 58913 |  | 10145 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 14887 | CSTS (Chiyoda-Saipem-Tripatra-Sae) Joint Operation | 2017BPT3828011 | P - CSTS (Chiyoda-Saipem-Tripatra-Sae) Joint Operation - 2017BPT3828011-Pumping System - 187-P-31006 A/B PKG 2 | 17317 | POC | EUR |  | 169531.2 | 2017-11-28 | 2018-09-20 |  | 144000 | 0 | 121763 |  | 9712 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 14887 | CSTS (Chiyoda-Saipem-Tripatra-Sae) Joint Operation | 2017BPT3828011 | P - CSTS (Chiyoda-Saipem-Tripatra-Sae) Joint Operation - 2017BPT3828011-Pumping System - 187-P-31042 PKG 2 | 17318 | POC | EUR |  | 92771.24 | 2017-11-28 | 2018-09-20 |  | 78800 | 0 | 64750 |  | 10592 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 14888 | Sarpom Srl | 2017SRP3132391 | P - Sarpom Srl - 2017SRP3132391 - 71PP-40 | 15787 | POC | EUR | 360185 | 227697.4 | 2017-11-30 | 2017-07-31 |  | 192190 | 0 | 131808 |  | 58607 | 0 | [9 empty] | 0 | EUROPE | OE
EPO | RU8310 | 14888 | Sarpom Srl | 2017SRP3132391 | P - Sarpom Srl - 2017SRP3132391 - 71PP-50 | 15896 | POC | EUR |  | 184294.03 | 2017-11-30 | 2017-07-31 |  | 155555 | 0 | 114433 |  | 50915 | 0 | [9 empty] | 0 | EUROPE | OE
EPO | RU8310 | 14888 | Sarpom Srl | 2017SRP3132391 | P - Sarpom Srl - 2017SRP3132391 - Spare parts | 22441 | POC | EUR |  | 14738.31 | 2017-11-30 | 2017-07-31 |  | 12440 | 0 | 6006 |  | 6006 | 0 | [9 empty] | 0 | EUROPE | OE
EPO | RU8310 | 14892 | Equilon Enterprises LLC | 2017MOT4224201 | P - Equilon Enterprises LLC - 2017MOT4224201 - Pumping System - P-7213-1/P-7214-1 | 16095 | POC | USD | 344194 | 183684 | 2017-11-27 | 2018-10-19 |  | 183684 | 0 | 127171 |  | 26206 | 0 | [6 empty] | 0 |  |  | 0 | US | OE
EPO | RU8310 | 14892 | Equilon Enterprises LLC | 2017MOT4224201 | P - Equilon Enterprises LLC - 2017MOT4224201 - Pumping System - P-7217-1/P-7218-1 | 17814 | POC | USD |  | 160510 | 2017-11-27 | 2018-10-19 |  | 160510 | 0 | 105952 |  | 22222 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 14895 | Madan Technologies | 2017MAD2619301 | P - Madan Technologies - 2017MAD2619301- Pumping System - P-2301 A/B | 15464 | POC | EUR | 310639 | 372420.3 | 2017-11-28 | 2018-06-29 |  | 310639 | 0 | 244221 |  | 168740 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 16058 | Amec Foster Wheeler Asia Pacific Pte LTD | 2017FWE3923651 | P - Amec Foster Wheeler Asia Pacific Pte LTD - 2017FWE3923651_01 - Pumping System P-1138 A/B | 16069 | POC | EUR | 305000 | 355142 | 2017-11-10 | 2018-09-15 |  | 305000 | 0 | 276599 |  | 109018 | 0 | 119000 | [8 empty] | 0 | ASIA | OE
EPO | RU8310 | 18170 | Casale SA | 2017CAS4229621 | P - CASALE S.A. -2017CAS4229621 - Pumping System - 10-P-1003 A/B - 2017CAS3121011 | 19311 | POC | EUR | 6309980 | 210677.5 | 2017-12-22 | 2018-10-18 |  | 176400 | 0 | 147702 |  | 41456 | 0 | [5 empty] | 0 |  | 2018-05-31 | 390-404 | 0 | RUSCIS | OE
EPO | RU8310 | 18170 | Casale SA | 2017CAS4229621 | P - CASALE S.A. -2017CAS4229621 - Pumping System - 10-P-1005 A/B - 2017CAS3121021 | 19469 | POC | EUR |  | 234802.7 | 2017-12-22 | 2018-10-18 |  | 196600 | 0 | 163982 |  | 65397 | 0 | [9 empty] | 0 | RUSCIS | OE
EPO | RU8310 | 18170 | Casale SA | 2017CAS4229621 | P - CASALE S.A. -2017CAS4229621 - Pumping System - 10-P-1007 A/B - 2017CAS3121031 | 19470 | POC | EUR |  | 118356.81 | 2017-12-22 | 2018-10-18 |  | 99100 | 0 | 83059 |  | 44975 | 0 | [9 empty] | 0 | RUSCIS | OE
EPO | RU8310 | 18170 | Casale SA | 2017CAS4229621 | P - CASALE S.A. -2017CAS4229621 - Pumping System - 40-P-5451 A/B - 2017CAS3121051 | 19471 | POC | EUR |  | 117879.08 | 2017-12-22 | 2018-10-18 |  | 98700 | 0 | 83782 |  | 47326 | 0 | [9 empty] | 0 | RUSCIS | OE
EPO | RU8310 | 18170 | Casale SA | 2017CAS4229621 | P - CASALE S.A. -2017CAS4229621 - Pumping System - 10-P-1008 A/B - 2017CAS3122041 | 19472 | POC | EUR |  | 89454.34 | 2017-12-22 | 2018-10-18 |  | 74900 | 0 | 62926 |  | 32412 | 0 | [9 empty] | 0 | RUSCIS | OE
EPO | RU8310 | 18170 | Casale SA | 2017CAS4229621 | P - CASALE S.A. -2017CAS4229621 - Pumping System - 40-P-5434 A/B - 2017CAS3726601 | 19473 | POC | EUR |  | 468423.03 | 2017-12-22 | 2018-10-18 |  | 392210 | 0 | 328899 |  | 15612 | 14910 | [9 empty] | 0 | RUSCIS | OE
EPO | RU8310 | 18170 | Casale SA | 2017CAS4229621 | P - CASALE S.A. -2017CAS4229621 - Pumping System - 30-P-2001 A/B - 2017CAS3727201 | 19474 | POC | EUR |  | 134241.22 | 2017-12-22 | 2018-10-18 |  | 112400 | 0 | 93781 |  | 26914 | 0 | [9 empty] | 0 | RUSCIS | OE
EPO | RU8310 | 18170 | Casale SA | 2017CAS4229621 | P - CASALE S.A. -2017CAS4229621 - Pumping System - 30-P-7002 A/B - 2017CAS3727351 | 19476 | POC | EUR |  | 287209.33 | 2017-12-22 | 2018-10-18 |  | 240480 | 0 | 200825 |  | 46056 | 0 | [9 empty] | 0 | RUSCIS | OE
EPO | RU8310 | 18170 | Casale SA | 2017CAS4229621 | P - CASALE S.A. -2017CAS4229621 - Pumping System 12 LPN 17 - 10-P-1001 A/B - 2017CAS3727501 | 19477 | POC | EUR |  | 457745.84 | 2017-12-22 | 2018-10-18 |  | 383270 | 0 | 320079 |  | 45333 | 0 | [9 empty] | 0 | RUSCIS | OE
EPO | RU8310 | 18170 | Casale SA | 2017CAS4229621 | P - CASALE S.A. -2017CAS4229621 - Pumping System 10 LPN 12 - 10-P-1002 A/B - 2017CAS3727511 | 19481 | POC | EUR |  | 251105.13 | 2017-12-22 | 2018-10-18 |  | 210250 | 0 | 175648 |  | 46141 | 0 | [9 empty] | 0 | RUSCIS | OE
EPO | RU8310 | 18170 | Casale SA | 2017CAS4229621 | P - CASALE S.A. -2017CAS4229621 - Pumping System 12 LPN 17 - 30-P-3004 A/B - 2017CAS3727521 | 19483 | POC | EUR |  | 263908.21 | 2017-12-22 | 2018-10-18 |  | 220970 | 0 | 182786 |  | 39714 | 0 | [9 empty] | 0 | RUSCIS | OE
EPO | RU8310 | 18170 | Casale SA | 2017CAS4229621 | P - CASALE S.A. -2017CAS4229621 - Pumping System ECPJ-50-125-R - 10-P-1006 A/B - 2017CAS3729011 | 19490 | POC | EUR |  | 109280 | 2017-12-22 | 2018-10-18 |  | 91500 | 0 | 77129 |  | 3699 | 0 | [9 empty] | 0 | RUSCIS | OE
EPO | RU8310 | 18170 | Casale SA | 2017CAS4229621 | P - CASALE S.A. -2017CAS4229621 - Pumping System ECPJ-40-160-R - 40-P-1551 A/B - 2017CAS3729021 | 19491 | POC | EUR |  | 116636.99 | 2017-12-22 | 2018-10-18 |  | 97660 | 0 | 82426 |  | 1022 | 0 | [9 empty] | 0 | RUSCIS | OE
EPO | RU8310 | 18170 | Casale SA | 2017CAS4229621 | P - CASALE S.A. -2017CAS4229621 - Pumping System ECPJ-32-160-R - 30-P-4504 A/B - 2017CAS3729031 | 19492 | POC | EUR |  | 118476.24 | 2017-12-22 | 2018-10-18 |  | 99200 | 0 | 83870 |  | 1087 | 0 | [9 empty] | 0 | RUSCIS | OE
EPO | RU8310 | 18170 | Casale SA | 2017CAS4229621 | P - CASALE S.A. -2017CAS4229621 - Pumping System ECPJ-32-160-R - 30-P-7006 A/B - 2017CAS3729041 | 19493 | POC | EUR |  | 131542.06 | 2017-12-22 | 2018-10-18 |  | 110140 | 0 | 92954 |  | 2226 | 0 | [9 empty] | 0 | RUSCIS | OE
EPO | RU8310 | 18170 | Casale SA | 2017CAS4229621 | P - CASALE S.A. - 2017CAS4229621 - Pumping System 1.5HPX10A - 30-P-4501 A/B - 2017CAS3828051 | 19501 | POC | EUR |  | 131016.56 | 2017-12-22 | 2018-10-18 |  | 109700 | 0 | 92270 |  | 19891 | 0 | [9 empty] | 0 | RUSCIS | OE
EPO | RU8310 | 18170 | Casale SA | 2017CAS4229621 | P - CASALE S.A. -2017CAS4229621 - Pumping System 2HPX15B - 30-P-4001 A/B - 2017CAS3828061 | 19502 | POC | EUR |  | 175564.58 | 2017-12-22 | 2018-10-18 |  | 147000 | 0 | 123700 |  | 23883 | 0 | [9 empty] | 0 | RUSCIS | OE
EPO | RU8310 | 18170 | Casale SA | 2017CAS4229621 | P - CASALE S.A. -2017CAS4229621 - Pumping System 3x6x13LL HDO - 30-P-3001 A/B - 2017CAS3928611 | 19503 | POC | EUR |  | 1797446.94 | 2017-12-22 | 2018-10-18 |  | 1505000 | 0 | 1478982 |  | 112198 | 0 | [9 empty] | 0 | RUSCIS | OE
EPO | RU8310 | 18170 | Casale SA | 2017CAS4229621 | P - CASALE S.A. -2017CAS4229621 - Pumping System 4X10x12 HSO - 30-P-1001 A/B - 2017CAS4229621 | 19505 | POC | EUR |  | 2143798.84 | 2017-12-22 | 2018-10-18 |  | 1795000 | 0 | 1748923 |  | 51680 | 0 | [9 empty] | 0 | RUSCIS | OE
EPO | RU8310 | 18170 | Casale SA | 2017CAS4229621 | P - CASALE S.A. -2017CAS4229621 - Pumping System - 40-P-1341 A/B - 2017CAS4235101 | 26007 | POC | EUR |  | 178550.38 | 2017-12-22 | 2018-10-18 |  | 149500 | 0 | 122405 |  | 7926 | 0 | [9 empty] | 0 | RUSCIS | OE
EPO | RU8310 | 18190 | Marathon Petroleum Co. LP C/O Jacobs Eng. Group (Acting as Agent) | 2017MAP4632401 | P - Marathon Petroleum Co. LP C/O Jacobs Eng. Group (Acting as Agent) - 2017MAP4632401 - Pumping System - 10-1595-01/02 | 18930 | POC | USD | 1975002 | 862046 | 2017-12-22 | 2018-11-16 |  | 862046 | 0 | 574496 |  | 10022 | 0 | [6 empty] | 0 |  |  | 0 | US | OE
EPO | RU8310 | 18190 | Marathon Petroleum Co. LP C/O Jacobs Eng. Group (Acting as Agent) | 2017MAP4632401 | P - Marathon Petroleum Co. LP C/O Jacobs Eng. Group (Acting as Agent) - 2017MAP4632401 - Pumping System - 10-1513-01/02 | 18967 | POC | USD |  | 1112956 | 2017-12-22 | 2018-11-16 |  | 1112956 | 0 | 768651 |  | 14318 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 18192 | Providence Doytch AG | 2017PRD4024501 | P - Providence Doytch AG - 2017PRD4024501 - Pumping System - 645G-002 A/B | 18939 | POC | EUR | 2400000 | 205894.92 | 2017-12-28 | 2018-10-05 |  | 172528 | 0 | 149270 |  | 14372 | 0 | [5 empty] | 240000 |  | 2018-05-07 | 329 | 0 | ASIA | OE
EPO | RU8310 | 18192 | Providence Doytch AG | 2017PRD4024501 | P - Providence Doytch AG - 2017PRD4024501 - Pumping System - 645G-004 A/B | 18955 | POC | EUR |  | 205894.92 | 2017-12-28 | 2018-10-05 |  | 172528 | 0 | 149270 |  | 13873 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 18192 | Providence Doytch AG | 2017PRD4024501 | P - Providence Doytch AG - 2017PRD4024501 - Pumping System - 645G-008 A/B LCS MV | 18962 | POC | EUR |  | 171276.77 | 2017-12-28 | 2018-10-05 |  | 143520 | 0 | 162404 |  | 10420 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 18192 | Providence Doytch AG | 2017PRD4024501 | P - Providence Doytch AG - 2017PRD4024501 - Pumping System - 645G-001 A/B | 18965 | POC | EUR |  | 507508.87 | 2017-12-28 | 2018-10-05 |  | 425263 | 0 | 362102 |  | 42753 | 0 | 7920 | [8 empty] | 0 | ASIA | OE
EPO | RU8310 | 18192 | Providence Doytch AG | 2017PRD4024501 | P - Providence Doytch AG - 2017PRD4024501 - Pumping System - 645G-005 A/B | 18968 | POC | EUR |  | 282430.05 | 2017-12-28 | 2018-10-05 |  | 236660 | 0 | 204164 |  | 23757 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 18192 | Providence Doytch AG | 2017PRD4024501 | P - Providence Doytch AG - 2017PRD4024501 - Pumping System - 645G-006 A/B | 18970 | POC | EUR |  | 533591.82 | 2017-12-28 | 2018-10-05 |  | 447119 | 0 | 380216 |  | 55696 | 0 | 7920 | [8 empty] | 0 | ASIA | OE
EPO | RU8310 | 18192 | Providence Doytch AG | 2017PRD4024501 | P - Providence Doytch AG - 2017PRD4024501 - Pumping System - 645G-003 A/B | 18971 | POC | EUR |  | 395754.12 | 2017-12-28 | 2018-10-05 |  | 331619 | 0 | 285035 |  | 29469 | 0 | 6640 | [8 empty] | 0 | ASIA | OE
EPO | RU8310 | 18192 | Providence Doytch AG | 2017PRD4024501 | P - Providence Doytch AG - 2017PRD4024501 - Pumping System - 645G-007 A/B | 18972 | POC | EUR |  | 561808.57 | 2017-12-28 | 2018-10-05 |  | 470763 | 0 | 400460 |  | 59803 | 0 | 9440 | [8 empty] | 0 | ASIA | OE
EPO | RU8310 | 18215 | C - GS Engineering & Construction | 201731RS6D2271 - 201731RS6D2331 | P - GS Engineering & Construction - 201731RS6D2271 - 201731RS6D2331 - Pumping System - 1220-G-010 A/B | 19257 | POC | EUR | 12125136 | 1312695.84 | 2017-12-05 | 2018-05-31 |  | 1099614 | 0 | 719634 |  | 719634 | 0 |  |  | 2018-05-31 |  |  | 4255886.2 |  | 2018-05-30 | 334-373-391-397 | 0 | ASIA | AM
EPO | RU8310 | 18215 | C - GS Engineering & Construction | 201731RS6D2271 - 201731RS6D2331 | P - GS Engineering & Construction - 201731RS6D2271 - 201731RS6D2331 - Pumping System - 1220-G-013 A/B | 19264 | POC | EUR |  | 1858816.19 | 2017-12-05 | 2018-05-31 |  | 1557086 | 0 | 1090797 |  | 775020 | 0 | [9 empty] | 0 | ASIA | AM
EPO | RU8310 | 18215 | C - GS Engineering & Construction | 201731RS6D2271 - 201731RS6D2331 | P - GS Engineering & Construction - 201731RS6D2271 - 201731RS6D2331 - Pumping System - 1620-G-005 A/B | 19267 | POC | EUR |  | 1588112.53 | 2017-12-05 | 2018-05-31 |  | 1330324 | 0 | 775315 |  | 775315 | 0 |  |  | 2018-05-31 | [6 empty] | 0 | ASIA | AM
EPO | RU8310 | 18215 | C - GS Engineering & Construction | 201731RS6D2271 - 201731RS6D2331 | P - GS Engineering & Construction - 201731RS6D2271 - 201731RS6D2331 - Pumping System - 1620-G-007 A/B | 19270 | POC | EUR |  | 4202552.49 | 2017-12-05 | 2018-05-31 |  | 3520378 | 0 | 2454458 |  | 1147705 | 0 | [9 empty] | 0 | ASIA | AM
EPO | RU8310 | 18215 | C - GS Engineering & Construction | 201731RS6D2271 - 201731RS6D2331 | P - GS Engineering & Construction - 201731RS6D2271 - 201731RS6D2331 - Pumping System - 1600-G-115 A/B | 19271 | POC | EUR |  | 1896491.85 | 2017-12-05 | 2018-05-31 |  | 1588646 | 0 | 1105733 |  | 839049 | 0 | [9 empty] | 0 | ASIA | AM
EPO | RU8310 | 18215 | C - GS Engineering & Construction | 201731RS6D2271 - 201731RS6D2331 | P - GS Engineering & Construction - 201731RS6D2271 - 201731RS6D2331 - Pumping System - 1600-G-116 A/B | 19273 | POC | EUR |  | 2145588.11 | 2017-12-05 | 2018-05-31 |  | 1797308 | 0 | 1266360 |  | 819031 | 0 | [9 empty] | 0 | ASIA | AM
EPO | RU8310 | 18215 | C - GS Engineering & Construction | 201731RS6D2271 - 201731RS6D2331 | P - GS Engineering & Construction - 201731RS6D2271 - 201731RS6D2331 - Pumping System - 1220-G-001 A/B | 19274 | POC | EUR |  | 1470472.8 | 2017-12-05 | 2018-05-31 |  | 1231780 | 0 | 844966 |  | 844966 | 0 |  |  | 2018-05-31 | [6 empty] | 0 | ASIA | AM
EPO | RU8310 | 18266 | Sinopec Europa GMBH | 2017SEU4532401 | P - Sinopec Europa GMBH - 2017SEU4532401 - Pumping System - A155-P-205 A/B | 19122 | POC | EUR | 1475630 | 945984.32 | 2017-12-21 | 2018-11-08 |  | 792680 | 0 | 671137 |  | 14882 | 0 | 60500 | [8 empty] | 0 | CHINA | OE
EPO | RU8310 | 18266 | Sinopec Europa GMBH | 2017SEU4532401 | P - Sinopec Europa GMBH - 2017SEU4532401 - Pumping System - A155-P-402 A/B | 19128 | POC | EUR |  | 815032.53 | 2017-12-21 | 2018-11-08 |  | 682950 | 0 | 571052 |  | 180198 | 0 | 40000 | [8 empty] | 0 | CHINA | OE
EPO | RU8310 | 18275 | APS S.p.a. | 2017APS3425351 | P - APS S.p.a. - 2017APS3425351 - Pumping system - VB-P-101 A/B | 18946 | POC | EUR | 765000 | 409694.22 | 2017-12-28 | 2018-08-20 |  | 343300 | 0 | 288680 |  | 69617 | 0 | [5 empty] | 229500 |  | 2018-05-23 | 376 | 0 | EUROPE | OE
EPO | RU8310 | 18275 | APS S.p.a. | 2017APS3425351 | P - APS S.p.a. - 2017APS3425351 - Pumping system - VB-P-103 A/B | 18975 | POC | EUR |  | 118504.62 | 2017-12-28 | 2018-08-20 |  | 99300 | 0 | 83633 |  | 65946 | 0 | [9 empty] | 0 | EUROPE | OE
EPO | RU8310 | 18275 | APS S.p.a. | 2017APS3425351 | P - APS S.p.a. - 2017APS3425351 - Pumping system - VB-P-104 A/B | 18988 | POC | EUR |  | 83657.34 | 2017-12-28 | 2018-08-20 |  | 70100 | 0 | 58862 |  | 43433 | 0 | [9 empty] | 0 | EUROPE | OE
EPO | RU8310 | 18275 | APS S.p.a. | 2017APS3425351 | P - APS S.p.a. - 2017APS3425351 - Pumping system - VB-P-105 A/B | 18992 | POC | EUR |  | 84970.08 | 2017-12-28 | 2018-08-20 |  | 71200 | 0 | 61113 |  | 48411 | 0 | [9 empty] | 0 | EUROPE | OE
EPO | RU8310 | 18275 | APS S.p.a. | 2017APS3425351 | P - APS S.p.a. - 2017APS3425351 - Pumping system - VB-P-102 A/B | 18996 | POC | EUR |  | 216124.74 | 2017-12-28 | 2018-08-20 |  | 181100 | 0 | 153388 |  | 25859 | 0 | [9 empty] | 0 | EUROPE | OE
EPO | RU8310 | 18285 | PCS Process Containment Solutions pty Ltd | 2017SAP4532431 | P - PCS Process Containment Solution pty Ltd - 2017SAP4532431 - Pumping System - P-7102 A/B | 19160 | POC | EUR | 597750 | 674390.34 | 2017-12-29 | 2018-11-09 |  | 565100 | 0 | 494766 |  | 10048 | 0 | [9 empty] | 0 | OTHER AFRICA | OE
EPO | RU8310 | 18285 | PCS Process Containment Solutions pty Ltd | 2017SAP4532431 | P - PCS Process Containment Solution pty Ltd - 2017SAP4532431 - Pumping System - P-1618 R1 | 19207 | POC | EUR |  | 38964.51 | 2017-12-29 | 2018-11-09 |  | 32650 | 0 | 26691 |  | 6584 | 0 | [9 empty] | 0 | OTHER AFRICA | OE
EPO | RU8310 | 18297 | Valero Mckee Refinery (Diamond Shamrock Refining Co. LP) | 2017VAL3520401 | P - Valero Mckee Refinery (Diamond Shamrock Refining Co. LP) - 2017VAL3520401 - pumping system 0460-P124 A/B | 18899 | POC | USD | 575256 | 575256 | 2017-12-29 | 2018-09-20 |  | 575256 | 0 | 398655 |  | 109701 | 0 | 81197.67 |  |  |  |  | 250090.2 | 207079.7383 | 2018-05-24 | 381 | 0 | US | OE
EPO | RU8310 | 18305 | CEPSA - Compania Espanola De Petroleos, SAU | 2017CEP2820401 | P - CEPSA - Compagnia Espanola De Petroleos, SAU - 2017CEP2820401 - Y-P-57 | 19033 | POC | EUR | 450000 | 96492.97 | 2017-12-28 | 2018-07-13 |  | 80856 | 0 | 63548 |  | 26319 | 0 | [9 empty] | 0 | EUROPE | OE
EPO | RU8310 | 18305 | CEPSA - Compania Espanola De Petroleos, SAU | 2017CEP2820401 | P - CEPSA - Compagnia Espanola De Petroleos, SAU - 2017CEP2820401 - Y-P-50 A/B | 19112 | POC | EUR |  | 440537.03 | 2017-12-28 | 2018-07-13 |  | 369144 | 0 | 288875 |  | 192766 | 0 | [9 empty] | 0 | EUROPE | OE
EPO | RU8310 | 18307 | Grupa Azoty Zaklady Azotowe 'Pulawy' Spolka Akcynjna | 2017ZAK3120361 | P - Grupa Azoty Zaklady Azotowe 'Pulawy' Spolka Akcynjna - 2017ZAK3120361 - Pumping System - 4T-312 / 4P-312 | 19111 | POC | EUR | 275054 | 328249.44 | 2017-12-27 | 2018-07-31 |  | 275054 | 0 | 233254 |  | 105367 | 0 | [5 empty] | 96268.9 |  | 2018-05-08 | 333 | 0 | EUROPE | OE
EPO | RU8310 | 18308 | Sarlux Refining Srl | 2017SRX2920201 | P - Sarlux Refining Srl - 2017SRX2920201 - Pumping System - MOV-MP 1601 A/B | 18761 | POC | EUR | 258000 | 307897.2 | 2017-12-21 | 2018-07-20 |  | 258000 | 0 | 192452 |  | 36894 | 0 | [5 empty] | 64500 |  | 2018-05-16 | 360 | 0 | EUROPE | OE
EPO | RU8310 | 18313 | China Petroleum Engineering & Constr. Corp. | 2016CPN5035501 | P - China Petroleum Engineering & Constr. Corp. - 2016CPN5035501 - Pumping System - P-1201 A/B - P-1201 C/D/E - P-2201 A/B - P-2201 C/D | 19176 | POC | EUR | 5781058 | 6026368.66 | 2017-01-26 | 2018-02-28 |  | 5719056 | 33973 | 5493092 |  | 5493092 | 0 |  |  | 2018-05-31 |  |  | 2886033.62 |  | 2018-05-31 |  | 0 | OTHER AFRICA | OE
EPO | RU8310 | 18313 | China Petroleum Engineering & Constr. Corp. | 2016CPN5035501 | P - China Petroleum Engineering & Constr. Corp. - 2016CPN5035501 - Training | 19194 | PIT | EUR |  | 64945.73 | 2017-01-26 | 2018-02-28 |  | 62002 | 0 | 42562 |  | 2562 | 0 | [9 empty] | 0 | OTHER AFRICA | OE
EPO | RU8310 | 18319 | PA Italy Netherland Operating Company Italy Branch | 2016CCJ2920831 | P - PA Italy Netherland Operating Company Italy Branch - 2016CCJ2920831 - Pumping System - P-10002 A | 18730 | POC | EUR | 0 | 50696.38 | 2017-11-29 | 2018-01-08 | [9 empty] | 2018-01-31
EPO | RU8310 | 18319 | PA Italy Netherland Operating Company Italy Branch | 2016CCJ2920831 | P - PA Italy Netherland Operating Company Italy Branch - 2016CCJ2920831 - Pumping System - P-10003 S | 18800 | POC | EUR |  | 26990.16 | 2017-11-29 | 2018-01-08 | [9 empty] | 2017-12-31
EPO | RU8310 | 18319 | PA Italy Netherland Operating Company Italy Branch | 2016CCJ2920831 | P - PA Italy Netherland Operating Company Italy Branch - 2016CCJ2920831 - Pumping System - P-21011 A/B | 18807 | POC | EUR |  | 100143.29 | 2017-11-29 | 2018-01-08 | [9 empty] | 2017-12-31
EPO | RU8310 | 18319 | PA Italy Netherland Operating Company Italy Branch | 2016CCJ2920831 | P - PA Italy Netherland Operating Company Italy Branch - 2016CCJ2920831 - Pumping System - P-11054 S | 18809 | POC | EUR |  | 30993.87 | 2017-11-29 | 2018-01-08 | [9 empty] | 2018-01-31
EPO | RU8310 | 18319 | PA Italy Netherland Operating Company Italy Branch | 2016CCJ2920831 | P - PA Italy Netherland Operating Company Italy Branch - 2016CCJ2920831 - Pumping System - P-10002 S | 18815 | POC | EUR |  | 32996.84 | 2017-11-29 | 2018-01-08 | [9 empty] | 2018-01-31
EPO | RU8310 | 18319 | PA Italy Netherland Operating Company Italy Branch | 2016CCJ2920831 | P - PA Italy Netherland Operating Company Italy Branch - 2016CCJ2920831 - Pumping System - P-10003 A | 18816 | POC | EUR |  | 40563.4 | 2017-11-29 | 2018-01-08 | [9 empty] | 2017-12-31
EPO | RU8310 | 18319 | PA Italy Netherland Operating Company Italy Branch | 2016CCJ2920831 | P - PA Italy Netherland Operating Company Italy Branch - 2016CCJ2920831 - Pumping System - P-11053 A | 18817 | POC | EUR |  | 62544.43 | 2017-11-29 | 2018-01-08 | [9 empty] | 2018-01-31
EPO | RU8310 | 18319 | PA Italy Netherland Operating Company Italy Branch | 2016CCJ2920831 | P - PA Italy Netherland Operating Company Italy Branch - 2016CCJ2920831 - Pumping System - P-11053 S | 18818 | POC | EUR |  | 48971.19 | 2017-11-29 | 2018-01-08 | [9 empty] | 2018-01-31
EPO | RU8310 | 18319 | PA Italy Netherland Operating Company Italy Branch | 2016CCJ2920831 | P - PA Italy Netherland Operating Company Italy Branch - 2016CCJ2920831 - Pumping System - P-11054 A | 18819 | POC | EUR |  | 49030.79 | 2017-11-29 | 2018-01-08 | [9 empty] | 2018-01-31
EPO | RU8310 | 18322 | Worley Parsons, INC Acting as Representative of Chevron Products Co. | 2016WPC5238401 | P - Worley Parsons, INC Acting as Representative of Chevron Products Co. - 2016WPC5238401 - Pumping System - P36120 A/B | 19022 | POC | USD | 0 | 1972298 | 2017-03-20 | 2018-02-28 | [9 empty] | 2018-04-30 |  |  |  | 0
EPO | RU8310 | 18331 | Technip Italia | 2016TCI2916031 | P - Technip Italia - 2016TCI2916031 - Pumping System - H-5-NEW 1/2 | 19530 | POC | EUR | 350372 | 119417.48 | 2018-01-03 | 2017-12-08 | [9 empty] | 2017-12-31 |  |  | 39600 |  | 2018-05-04 | 55501393
EPO | RU8310 | 18331 | Technip Italia | 2016TCI2916031 | P - Technip Italia - 2016TCI2916031 - Pumping System - P-1102 A/B | 19552 | POC | EUR |  | 79654.05 | 2018-01-03 | 2017-12-08 |  | 74300 | 0 | 83101 |  | 70863 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 18331 | Technip Italia | 2016TCI2916031 | P - Technip Italia - 2016TCI2916031 - Pumping System - H-403 | 19553 | POC | EUR |  | 83299.05 | 2018-01-03 | 2017-12-08 |  | 77700 | 0 | 92930 |  | 83430 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 18331 | Technip Italia | 2016TCI2916031 | P - Technip Italia - 2016TCI2916031 - Pumping System - H-66-NEW 1/2 | 19554 | POC | EUR |  | 101845.69 | 2018-01-03 | 2017-12-08 | [9 empty] | 2017-12-31
EPO | RU8310 | 18331 | Technip Italia | 2016TCI2916031 | P - Technip Italia - 2016TCI2916031 - Pumping System - H-40-NEW 1/2 | 19555 | POC | EUR |  | 83620.67 | 2018-01-03 | 2017-12-08 | [9 empty] | 2017-12-31
EPO | RU8310 | 18331 | Technip Italia | 2016TCI2916031 | P - Technip Italia - 2016TCI2916031 - Pumping System - P-2201 A/B | 19559 | POC | EUR |  | 212666.66 | 2018-01-03 | 2017-12-08 |  | 198372 | 0 | 196934 |  | 1089 | 176033 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 18331 | Technip Italia | 2016TCI2916031 | P - Technip Italia - 2016TCI2916031 - Pumping System - P-2101 A/B | 19561 | POC | EUR |  | 266548.38 | 2018-01-03 | 2017-12-08 | [9 empty] | 2017-12-31
EPO | RU8310 | 18331 | Technip Italia | 2016TCI2916031 | P - Technip Italia - 2016TCI2916031 - Pumping System - P-1202+Z | 19562 | POC | EUR |  | 102015.07 | 2018-01-03 | 2017-12-08 | [9 empty] | 2017-12-31
EPO | RU8310 | 18331 | Technip Italia | 2016TCI2916031 | P - Technip Italia - 2016TCI2916031 - Pumping System - H-502 1/2 | 19563 | POC | EUR |  | 100773.63 | 2018-01-03 | 2017-12-08 | [9 empty] | 2017-12-31
EPO | RU8310 | 18331 | Technip Italia | 2016TCI2916031 | P - Technip Italia - 2016TCI2916031 - Pumping System - P-2102 A/B | 19564 | POC | EUR |  | 70083.45 | 2018-01-03 | 2017-12-08 | [9 empty] | 2017-12-31
EPO | RU8310 | 18331 | Technip Italia | 2016TCI2916031 | P - Technip Italia - 2016TCI2916031 - Pumping System - H-25-NEW 1/2 | 19565 | POC | EUR |  | 112566.28 | 2018-01-03 | 2017-12-08 | [9 empty] | 2017-12-31
EPO | RU8310 | 18331 | Technip Italia | 2016TCI2916031 | P - Technip Italia - 2016TCI2916031 - Pumping System - H-901 1/2 | 19567 | POC | EUR |  | 76515.81 | 2018-01-03 | 2017-12-08 | [9 empty] | 2017-12-31
EPO | RU8310 | 18331 | Technip Italia | 2016TCI2916031 | P - Technip Italia - 2016TCI2916031 - Pumping System - P-1201 A/B/C | 19568 | POC | EUR |  | 114613.06 | 2018-01-03 | 2017-12-08 | [9 empty] | 2017-12-31
EPO | RU8310 | 18331 | Technip Italia | 2016TCI2916031 | P - Technip Italia - 2016TCI2916031 - Pumping System - P-1203 A/B | 19570 | POC | EUR |  | 96884.94 | 2018-01-03 | 2017-12-08 | [9 empty] | 2017-12-31
EPO | RU8310 | 18331 | Technip Italia | 2016TCI2916031 | P - Technip Italia - 2016TCI2916031 - Pumping System - H-34-NEW 1/2 | 19575 | POC | EUR |  | 388085.67 | 2018-01-03 | 2017-12-08 | [9 empty] | 2017-12-31
EPO | RU8310 | 18332 | Technip Italy Spa | 2017TCI5242351 | P - TECHNIP ITALY SPA - 2017TCI5242351 - Pumping System - 20G-320A/B | 19630 | POC | EUR | 250950 | 266458.1 | 2017-03-27 | 2018-02-28 |  | 250950 | 0 | 223171 |  | 223171 | 0 |  |  | 2018-05-31 | [6 empty] | 0 | ASIA | OE
EPO | RU8310 | 18332 | Technip Italy Spa | 2017TCI5242351 | P - TECHNIP ITALY SPA - 2017TCI5242351 - Pumping System - 20G-330 A/B/C | 19650 | POC | EUR |  | 247319.2 | 2017-03-27 | 2018-02-28 | [9 empty] | 2018-04-30
EPO | RU8310 | 18332 | Technip Italy Spa | 2017TCI5242351 | P - TECHNIP ITALY SPA - 2017TCI5242351 - Pumping System - 20G-426 A/B/C | 19652 | POC | EUR |  | 707077.53 | 2017-03-27 | 2018-02-28 | [9 empty] | 2018-01-31
EPO | RU8310 | 18337 | Indeni Petroleum Refinery Company Limited | 201745RS121001 | P - Indeni Petroleum Refinery Company Limited - 201745RS121001 - Pumping System P-402B | 19605 | POC | EUR | 258500 | 281273.85 | 2017-06-12 | 2018-03-05 |  | 258500 | 0 | 153759 |  | 134673 | 0 | [9 empty] | 10340 | OTHER AFRICA | AM
EPO | RU8310 | 18341 | Tecnimont | 20174711563738 | P - Tecnimont S.p.a. - 20174711563738 - Spare Parts | 18721 | POC | EUR | 1220626 | 1363805.27 | 2017-07-28 | 2018-04-01 |  | 1220626 | 0 | 553000 |  | 546652 | 0 |  |  |  | 539527 | [5 empty] | 0 | RUSCIS | AM
EPO | RU8310 | 18635 | EniPower S.p.a. | 201742RS121511 | P - EniPower S.p.a. - 201742RS121511 - Pumping System Upgrade | 19460 | POC | EUR | 440310 | 521326.56 | 2017-09-06 | 2018-02-15 |  | 440310 | 0 | 286599 |  | 275658 | 0 | [9 empty] | 0 | EUROPE | AM
EPO | RU8310 | 19335 | Marathon Petroleum Co. Lp C/O Jacobs Eng. Group ( Acting As Agent) | 2017MAP4031041 - 2017MAP4226381 - 2017MAP4222301 | P - Marathon Petroleum Co. Lp C/O Jacobs Eng. Group (Acting As Agent) - 2017MAP4031041 - 2017MAP4226381 - 2017MAP4222301 - Pumping system - 2-23-G-166/167 | 20102 | POC | USD | 2764680 | 398938 | 2017-12-31 | 2018-10-17 |  | 398938 | 0 | 280525 |  | 6707 | 0 |  |  |  | 539527 |  | 312713.4 | 258933.0132 | 2018-05-16 | 357-358 | 0 | US | OE
EPO | RU8310 | 19335 | Marathon Petroleum Co. Lp C/O Jacobs Eng. Group ( Acting As Agent) | 2017MAP4031041 - 2017MAP4226381 - 2017MAP4222301 | P - Marathon Petroleum Co. Lp C/O Jacobs Eng. Group (Acting As Agent) - 2017MAP4031041 - 2017MAP4226381 - 2017MAP4222301 - Pumping system - 2-23-G-168/169 | 20133 | POC | USD |  | 415094 | 2017-12-31 | 2018-10-17 |  | 415094 | 0 | 288703 |  | 6628 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 19335 | Marathon Petroleum Co. Lp C/O Jacobs Eng. Group ( Acting As Agent) | 2017MAP4031041 - 2017MAP4226381 - 2017MAP4222301 | P - Marathon Petroleum Co. Lp C/O Jacobs Eng. Group (Acting As Agent) - 2017MAP4031041 - 2017MAP4226381 - 2017MAP4222301 - Pumping system - 2-23-G-170/171 | 20135 | POC | USD |  | 646888 | 2017-12-31 | 2018-10-17 |  | 646888 | 0 | 462357 |  | 29436 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 19335 | Marathon Petroleum Co. Lp C/O Jacobs Eng. Group ( Acting As Agent) | 2017MAP4031041 - 2017MAP4226381 - 2017MAP4222301 | P - Marathon Petroleum Co. Lp C/O Jacobs Eng. Group (Acting As Agent) - 2017MAP4031041 - 2017MAP4226381 - 2017MAP4222301 - Pumping system - 2-23-G-114/116 | 20136 | POC | USD |  | 359698 | 2017-12-31 | 2018-10-17 |  | 359698 | 0 | 253196 |  | 6095 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 19335 | Marathon Petroleum Co. Lp C/O Jacobs Eng. Group ( Acting As Agent) | 2017MAP4031041 - 2017MAP4226381 - 2017MAP4222301 | P - Marathon Petroleum Co. Lp C/O Jacobs Eng. Group (Acting As Agent) - 2017MAP4031041 - 2017MAP4226381 - 2017MAP4222301 - Pumping system - 2-23-G-161/162 | 20137 | POC | USD |  | 679924 | 2017-12-31 | 2018-10-17 |  | 679924 | 0 | 452067 |  | 37819 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 19335 | Marathon Petroleum Co. Lp C/O Jacobs Eng. Group ( Acting As Agent) | 2017MAP4031041 - 2017MAP4226381 - 2017MAP4222301 | P - Marathon Petroleum Co. Lp C/O Jacobs Eng. Group (Acting As Agent) - 2017MAP4031041 - 2017MAP4226381 - 2017MAP4222301 - Pumping system - 2-30-G-16/17 | 20138 | POC | USD |  | 143690 | 2017-12-31 | 2018-10-17 |  | 143690 | 0 | 99580 |  | 3401 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 19335 | Marathon Petroleum Co. Lp C/O Jacobs Eng. Group ( Acting As Agent) | 2017MAP4031041 - 2017MAP4226381 - 2017MAP4222301 | P - Marathon Petroleum Co. Lp C/O Jacobs Eng. Group (Acting As Agent) - 2017MAP4031041 - 2017MAP4226381 - 2017MAP4222301 - Pumping system - 2-30-G-18/19 | 20139 | POC | USD |  | 120448 | 2017-12-31 | 2018-10-17 |  | 120448 | 0 | 86011 |  | 1882 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 20905 | Hong Kong Jianxin Industrial Equipment CO. LTD | 2014HKJ5142351 | P - Hong Kong Jianxin Industrial Equipment CO. LTD - 2014HKJ5142351 - 800-A-206 A (Turbine) | 20918 | POC | EUR | 1337300 | 666008.31 | 2014-02-05 | 2018-06-15 |  | 490650 | 0 | 442145 |  | 442145 | 0 |  |  | 2018-05-31 |  |  | 2408600 |  | 2018-05-10 | 55500703 | 20060 | CHINA | OE
EPO | RU8310 | 20905 | Hong Kong Jianxin Industrial Equipment CO. LTD | 2014HKJ5142351 | P - Hong Kong Jianxin Industrial Equipment CO. LTD - 2014HKJ5142351 - 800-P-206 B (Motor) | 20924 | POC | EUR |  | 438440.2 | 2014-02-05 | 2018-06-15 |  | 323000 | 0 | 285825 |  | 285825 | 0 |  |  | 2018-05-31 | [6 empty] | 0 | CHINA | OE
EPO | RU8310 | 20905 | Hong Kong Jianxin Industrial Equipment CO. LTD | 2014HKJ5142351 | P - Hong Kong Jianxin Industrial Equipment CO. LTD - 2014HKJ5142351 - 800-P-211 A (Turbine) | 20926 | POC | EUR |  | 436607.71 | 2014-02-05 | 2018-06-15 |  | 321650 | 0 | 273657 |  | 273657 | 0 |  |  | 2018-05-31 | [6 empty] | 0 | CHINA | OE
EPO | RU8310 | 20905 | Hong Kong Jianxin Industrial Equipment CO. LTD | 2014HKJ5142351 | P - Hong Kong Jianxin Industrial Equipment CO. LTD - 2014HKJ5142351 - 800-P-211 B (Motor) | 20929 | POC | EUR |  | 274194.8 | 2014-02-05 | 2018-06-15 |  | 202000 | 0 | 174092 |  | 174092 | 0 |  |  | 2018-05-31 | [6 empty] | 0 | CHINA | OE
EPO | RU8310 | 20908 | Hong Kong Jianxin Industrial Equipment | 2013HKJ4234371 | P - HONG KONG JIAXIN INDUSTRIAL EQUIPMENT - 2013HKJ4234371 - Pumping system P-501 A/B | 20914 | POC | EUR | 0 | 205117.23 | 2014-02-06 | 2018-06-30 | [9 empty] | 2018-05-31
EPO | RU8310 | 20908 | Hong Kong Jianxin Industrial Equipment | 2013HKJ4234371 | P - HONG KONG JIAXIN INDUSTRIAL EQUIPMENT - 2013HKJ4234371 - Pumping system P-602 A/B | 20919 | POC | EUR |  | 194341.68 | 2014-02-06 | 2018-06-30 | [9 empty] | 2018-05-31
EPO | RU8310 | 20908 | Hong Kong Jianxin Industrial Equipment | 2013HKJ4234371 | P - HONG KONG JIAXIN INDUSTRIAL EQUIPMENT - 2013HKJ4234371 - Pumping system P-612 A/B | 20920 | POC | EUR |  | 627914.89 | 2014-02-06 | 2018-06-30 | [9 empty] | 2018-05-31
EPO | RU8310 | 20908 | Hong Kong Jianxin Industrial Equipment | 2013HKJ4234371 | P - HONG KONG JIAXIN INDUSTRIAL EQUIPMENT - 2013HKJ4234371 - Pumping system P-613 A/B | 20922 | POC | EUR |  | 677456.5 | 2014-02-06 | 2018-06-30 | [9 empty] | 2018-05-31
EPO | RU8310 | 21141 | Profit Making International Limited | 2018PMI4030401 | P - Profit Making International Limited - 2018PMI4030401 - Pumping System - P-2001 A/B/C | 22190 | POC | EUR | 470460 | 243178.34 | 2018-01-31 | 2018-11-19 |  | 195780 | 0 | 155930 |  | 56516 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 21141 | Profit Making International Limited | 2018PMI4030401 | P - Profit Making International Limited - 2018PMI4030401 - Pumping System - P-4006 A/B | 22191 | POC | EUR |  | 135711.85 | 2018-01-31 | 2018-11-19 |  | 109260 | 0 | 85550 |  | 21581 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 21141 | Profit Making International Limited | 2018PMI4030401 | P - Profit Making International Limited - 2018PMI4030401 - Pumping System - P-1009 A/B | 22192 | POC | EUR |  | 205468.18 | 2018-01-31 | 2018-11-19 |  | 165420 | 0 | 129873 |  | 10282 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 21350 | Raffineria di Gela S.p.a. | 2018RDG2821011 | P - Raffineria di Gela S.p.a. - 2018RDG2821011 - Pumping System - 5525-P902 A/B | 22193 | POC | EUR | 264000 | 185693.95 | 2018-01-29 | 2018-05-31 |  | 149500 | 0 | 115089 |  | 55475 | 0 | [5 empty] | 52800 |  | 2018-05-23 | 378-379 | 0 | EUROPE | OE
EPO | RU8310 | 21350 | Raffineria di Gela S.p.a. | 2018RDG2821011 | P - Raffineria di Gela S.p.a. - 2018RDG2821011 - Pumping System - 344-P94 A/B | 22194 | POC | EUR |  | 142220.45 | 2018-01-29 | 2018-05-31 |  | 114500 | 0 | 85117 |  | 39115 | 0 | [9 empty] | 0 | EUROPE | OE
EPO | RU8310 | 21436 | Aereon Europe S.r.l. | 2017ARE2416111 | P - Aereon Europe S.r.l. - 2017ARE2416111-VRU-MP2 - 2017ARE3022011 | 22012 | POC | EUR | 241240 | 45103.94 | 2018-01-29 | 2018-07-23 |  | 37840 | 0 | 29482 |  | 14614 | 0 | [5 empty] | 48248 |  | 2018-05-14 | 346 | 0 | EUROPE | OE
EPO | RU8310 | 21436 | Aereon Europe S.r.l. | 2017ARE2416111 | P - Aereon Europe S.r.l. - 2017ARE2416111 - VRU-MP-570A-P (centrifugal pumps) - 2017ARE2416111 | 22013 | POC | EUR |  | 242445.6 | 2018-01-29 | 2018-07-23 |  | 203400 | 0 | 179827 |  | 113423 | 0 | [9 empty] | 0 | EUROPE | OE
EPO | RU8310 | 21753 | Shell Chemicals Seraya PTE Ltd | 2018SHE3526011 | P - Shell Chemical Seraya PTE Ltd - 2018SHE3526011 - Pumping System - P-1470 | 22271 | POC | EUR | 239367 | 98778.52 | 2018-01-31 | 2018-08-31 |  | 79347 | 0 | 70461 |  | 5312 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 21753 | Shell Chemicals Seraya PTE Ltd | 2018SHE3526011 | P - Shell Chemical Seraya PTE Ltd - 2018SHE3526011 - Pumping System - P-1403 | 22272 | POC | EUR |  | 98778.52 | 2018-01-31 | 2018-08-31 |  | 79347 | 0 | 67685 |  | 5575 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 21753 | Shell Chemicals Seraya PTE Ltd | 2018SHE3526011 | P - Shell Chemical Seraya PTE Ltd - 2018SHE3526011 - Pumping System - P-1403 Spare | 22273 | POC | EUR |  | 100429.26 | 2018-01-31 | 2018-08-31 |  | 80673 | 0 | 51959 |  | 3289 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 22933 | Air Products and Chemicals Inc | 2018AIR3930011 | P - Air Products and Chemicals Inc - 2018AIR3930011 - Pumping system 100-G353 A/B | 22957 | POC | USD | 400056 | 143352 | 2018-02-27 | 2018-09-25 |  | 143352 | 0 | 87102 |  | 14074 | 0 | [6 empty] | 0 |  |  | 0 | US | OE
EPO | RU8310 | 22933 | Air Products and Chemicals Inc | 2018AIR3930011 | P - Air Products and Chemicals Inc - 2018AIR3930011 - Pumping system - 100-G412 A/B | 22959 | POC | USD |  | 143496 | 2018-02-27 | 2018-09-25 |  | 143496 | 0 | 88736 |  | 12139 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 22933 | Air Products and Chemicals Inc | 2018AIR3930011 | P - Air Products and Chemicals Inc - 2018AIR3930011 - Pumping system - 100-G352 A/B | 22960 | POC | USD |  | 113208 | 2018-02-27 | 2018-09-25 |  | 113208 | 0 | 75870 |  | 9568 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 23536 | HITRANS TECHNOLOGIES LIMITED | 2018HIT3929011 | P - HITRANS TECHNOLOGIES LIMITED - 2018HIT3929011 - Pumping System P - 53152 A/B | 23547 | POC | EUR | 223500 | 274798.9 | 2018-02-28 | 2018-09-30 |  | 223500 | 0 | 172432 |  | 4615 | 0 | [9 empty] | 0 | CHINA | OE
EPO | RU8310 | 23578 | ENI SPA | 201845RS622861 | P - ENI SPA - 201845RS622861 - Pump J - 90121 C | 23584 | POC | EUR | 312900 | 384898.29 | 2018-02-27 | 2018-11-05 |  | 312900 | 0 | 249730 |  | 8155 | 0 | [9 empty] | 0 | EUROPE | AM
EPO | RU8310 | 24449 | Slovnaft s.a. | 201809RS423081 | P - Slovnaft a.s. - 201809RS423081 | 26101 | POC | EUR | 473000 | 582783.3 | 2018-03-29 | 2019-03-28 |  | 473000 | 0 | 344421 |  | 3928 | 0 | [9 empty] | 0 | EUROPE | AM
EPO | RU8310 | 24453 | HES Wilhelmshaven | 2018HES3123141 | P - HES Wilhelmshaven - 2018HES3123141 - Pumping System - G-4165 A/B | 26226 | POC | EUR | 270000 | 204976.98 | 2018-03-29 | 2018-07-30 |  | 166364 | 0 | 133870 |  | 4922 | 0 | [5 empty] | 81000 |  | 2018-05-04 | 327 | 0 | EUROPE | OE
EPO | RU8310 | 24453 | HES Wilhelmshaven | 2018HES3123141 | P - HES Wilhelmshaven - 2018HES3123141 - Pump G-4226 | 26236 | POC | EUR |  | 127690.02 | 2018-03-29 | 2018-07-30 |  | 103636 | 0 | 88838 |  | 4324 | 0 | [9 empty] | 0 | EUROPE | OE
EPO | RU8310 | 24468 | Valero Refining- New Orleans L.L.C. | 2018VAL0842011 | P - Valero Refining - New Orleans L.L.C - 2018VAL0842011 - Pumping System P-12-106 A/B | 26190 | POC | USD | 543399 | 158950 | 2018-03-30 | 2019-02-20 |  | 158950 | 0 | 92388 |  | 3659 | 0 | [5 empty] | 81510 | 67491.9268 | 2018-05-29 | 389 | 0 | US | OE
EPO | RU8310 | 24468 | Valero Refining- New Orleans L.L.C. | 2018VAL0842011 | P - Valero Refining - New Orleans L.L.C - 2018VAL0842011 - Pumping System P-12-004 A/B | 26191 | POC | USD |  | 208128 | 2018-03-30 | 2019-02-20 |  | 208128 | 0 | 135652 |  | 4431 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 24468 | Valero Refining- New Orleans L.L.C. | 2018VAL0842011 | P - Valero Refining - New Orleans L.L.C - 2018VAL0842011 - Pumping System P-12-003 A/B | 26192 | POC | USD |  | 80272 | 2018-03-30 | 2019-02-20 |  | 80272 | 0 | 48714 |  | 3374 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 24468 | Valero Refining- New Orleans L.L.C. | 2018VAL0842011 | P - Valero Refining - New Orleans L.L.C - 2018VAL0842011 - Pumping System P-12-117 A/B | 26193 | POC | USD |  | 61892 | 2018-03-30 | 2019-02-20 |  | 61892 | 0 | 37887 |  | 3090 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 24468 | Valero Refining- New Orleans L.L.C. | 2018VAL0842011 | P - Valero Refining - New Orleans L.L.C - 2018VAL0842011 - Pump P-12-209 | 26194 | POC | USD |  | 34157 | 2018-03-30 | 2019-02-20 |  | 34157 | 0 | 23241 |  | 2947 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 24471 | Cairo Oil Refining Company | 2018COR5038301 | P - Cairo Oil Refining Company - 2018COR5038301 - Pumping System - 3 P-1 A/B | 26179 | POC | EUR | 392433 | 439161.22 | 2018-03-29 | 2018-06-24 |  | 356433 | 0 | 303038 |  | 5159 | 0 | [9 empty] | 9811 | OTHER AFRICA | OE
EPO | RU8310 | 24471 | Cairo Oil Refining Company | 2018COR5038301 | P - Cairo Oil Refining Company - 2018COR5038301 - 2 years spare parts | 26182 | POC | EUR |  | 44355.6 | 2018-03-29 | 2018-06-24 |  | 36000 | 0 | 25527 |  | 354 | 0 | [9 empty] | 0 | OTHER AFRICA | OE
EPO | RU8310 | 24477 | Repsol Petròleo S.A. | 2018RES4234401 | P - Repsol Petròleo S.A. - 2018RES4234401 - Pump 650 G 183 A | 26177 | POC | EUR | 249160 | 222948.5 | 2018-03-29 | 2018-10-19 |  | 180950 | 0 | 133847 |  | 10987 | 0 | [9 empty] | 0 | EUROPE | OE
EPO | RU8310 | 24477 | Repsol Petròleo S.A. | 2018RES4234401 | P - Repsol Petròleo S.A. - 2018RES4234401 - 2 years spare parts | 26178 | POC | EUR |  | 84041.54 | 2018-03-29 | 2018-10-19 |  | 68210 | 0 | 22827 |  | 0 | 0 | [9 empty] | 0 | EUROPE | OE
EPO | RU8310 | 25923 | Enppi | 2018ENP1049601 | P - ENPPI - 2018ENP1049601 - Pumping System P-4304 A/B | 26211 | POC | EUR | 2999080 | 3138318.88 | 2018-03-29 | 2019-03-29 |  | 2547130 | 0 | 2146997 |  | 19126 | 0 | [9 empty] | 14995 | OTHER AFRICA | OE
EPO | RU8310 | 25923 | Enppi | 2018ENP1049601 | P - ENPPI - 2018ENP1049601 - Pumping System P-4303 A/B | 26218 | POC | EUR |  | 556847.6 | 2018-03-29 | 2019-03-29 |  | 451950 | 0 | 373551 |  | 8048 | 0 | [9 empty] | 0 | OTHER AFRICA | OE
EPO | RU8310 | 25952 | Jacobs engineering group inc. | 2018MAP0643401 | P - Jacobs engineering group inc. - 2018MAP0643401 - Pumping system 46-1513-01/02 | 26219 | POC | USD | 449854 | 449854 | 2018-03-30 | 2018-12-27 |  | 449854 | 0 | 300406 |  | 18535 | 0 | [6 empty] | 0 |  |  | 0 | US | OE
EPO | RU8310 | 25978 | Amreya Petroleum Refining co. | 20183401593778 | P - Amreya Petroleum Refining co. - 20183401593778 - Spare parts | 26126 | POC | EUR | 465884 | 574015.66 | 2018-03-14 | 2018-08-26 |  | 465884 | 0 | 141000 |  | 65125 | 0 | [9 empty] | 19618 | OTHER AFRICA | AM
EPO | RU8310 | 27843 | Eni S.p.A. | 2018ENI0444311 | P - ENI SANNAZARO - 2018ENI0444311 | 28077 | POC | EUR | 639000 | 771273 | 2018-04-27 | 2019-01-22 |  | 639000 | 0 | 504348 |  | 6371 | 0 | [9 empty] | 0 | EUROPE | OE
EPO | RU8310 | 27856 | ENPPI | 2018ENP0143301 | P - ENPPI - 2018ENP0143301 - Pumping system 35P-011 A/B | 28266 | POC | EUR | 407992 | 210298.02 | 2018-04-30 | 2019-01-27 |  | 174232 | 0 | 149428 |  | 6623 | 0 | [9 empty] | 0 | OTHER AFRICA | OE
EPO | RU8310 | 27856 | ENPPI | 2018ENP0143301 | P - ENPPI - 2018ENP0143301 - Pumping system 70-P-07 A/B | 28273 | POC | EUR |  | 282148.32 | 2018-04-30 | 2019-01-27 |  | 233760 | 0 | 187568 |  | 7910 | 0 | [9 empty] | 2040 | OTHER AFRICA | OE
EPO | RU8310 | 27858 | NINGBO TOPOO PETROTECH LIMITED | 2018NIN0848401 | P - NINGBO TOPOO PETROTECH LIMITED - 2018NIN0848401 | 28165 | POC | EUR | 700000 | 844900 | 2018-04-27 | 2019-02-18 |  | 700000 | 0 | 552818 |  | 6700 | 0 | [5 empty] | 140000 |  | 2018-05-31 | 314 | 0 | CHINA | OE
EPO | RU8310 | 27866 | PETROFAC E&C OMAN LLC | 2018PTR1614301 | P - PETROFAC E&C OMAN LLC - 2018PTR1614301 - Pumping System FAC1-P-244201 A/B/C | 28117 | POC | EUR | 2301214 | 813327.29 | 2018-04-30 | 2019-04-15 |  | 673842 | 0 | 494243 |  | 0 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 27866 | PETROFAC E&C OMAN LLC | 2018PTR1614301 | P - PETROFAC E&C OMAN LLC - 2018PTR1614301 - Pumping System FAC1-P-244001 A/B/C | 28123 | POC | EUR |  | 479628 | 2018-04-30 | 2019-04-15 |  | 397372 | 0 | 310714 |  | 0 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 27866 | PETROFAC E&C OMAN LLC | 2018PTR1614301 | P - PETROFAC E&C OMAN LLC - 2018PTR1614301 - Pumping System FAC1-P-223201A/B/C | 28124 | POC | EUR |  | 372963 | 2018-04-30 | 2019-04-15 |  | 309000 | 0 | 241172 |  | 0 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 27866 | PETROFAC E&C OMAN LLC | 2018PTR1614301 | P - PETROFAC E&C OMAN LLC - 2018PTR1614301 - Pumping System FAC1-P-223202A/B | 28125 | POC | EUR |  | 188292 | 2018-04-30 | 2019-04-15 |  | 156000 | 0 | 122625 |  | 0 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 27866 | PETROFAC E&C OMAN LLC | 2018PTR1614301 | P - PETROFAC E&C OMAN LLC - 2018PTR1614301 - Pumping System FAC1-P-223203 | 28126 | POC | EUR |  | 109837 | 2018-04-30 | 2019-04-15 |  | 91000 | 0 | 71528 |  | 0 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 27866 | PETROFAC E&C OMAN LLC | 2018PTR1614301 | P - PETROFAC E&C OMAN LLC - 2018PTR1614301 - Pumping System FAC1-P-232201A/B | 28127 | POC | EUR |  | 576946 | 2018-04-30 | 2019-04-15 |  | 478000 | 0 | 369256 |  | 0 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 27866 | PETROFAC E&C OMAN LLC | 2018PTR1614301 | P - PETROFAC E&C OMAN LLC - 2018PTR1614301 - Pumping System FAC1-P-223204A/B | 28158 | POC | EUR |  | 236572 | 2018-04-30 | 2019-04-15 |  | 196000 | 0 | 153821 |  | 0 | 0 | [9 empty] | 0 | ASIA | OE
EPO | RU8310 | 27894 | VALERO TERMINALING AND DISTRIBUTION CO. | 2018VAL4840501 | P - VALERO TERMINALING AND DISTRIBUTION CO. - 2018VAL4840501 | 28171 | POC | USD | 381276 | 381276 | 2018-04-30 | 2018-12-17 |  | 381276 | 0 | 245211 |  | 0 | 0 | [6 empty] | 0 |  |  | 0 | US | OE
EPO | RU8310 | 27898 | Equilon Enterprises LLC | 2018MOT0446301 | P - Equilon Enterprises LLC - 2018MOT0446301 Pumping System P-8700 | 28110 | POC | USD | 385723 | 169359 | 2018-04-30 | 2019-01-24 |  | 169359 | 0 |  |  | 237 | 0 | [6 empty] | 0 |  |  | 0 | US | OE
EPO | RU8310 | 27898 | Equilon Enterprises LLC | 2018MOT0446301 | P - Equilon Enterprises LLC - 2018MOT0446301 Pumping System P-8704 | 28116 | POC | USD |  | 169544.4 | 2018-04-30 | 2019-01-24 |  | 169544 | 0 |  |  | 0 | 0 | [9 empty] | 0 | US | OE
EPO | RU8310 | 27898 | Equilon Enterprises LLC | 2018MOT0446301 | P - Equilon Enterprises LLC - 2018MOT0446301 Pumping System P-8700/04 BARESHAFT PUMP | 28118 | POC | USD |  | 46820.4 | 2018-04-30 | 2019-01-24 |  | 46820 | 0 |  |  | 0 | 0 | [9 empty] | 0 | US | OE
EPO | RU8321 | 5345 | NIPPON STEEL & SUMIKIN Pipeline & Engineering Co. Ltd. | 10009607 | P - NIPPON STEEL & SUMIKIN Pipeline & Engineering-10009607-8LHS-142S | 5453 | POC | JPY | 68280000 | 490116.32 | 2016-12-22 | 2018-05-08 |  | 57280000 |  | 37337181 |  | 37337181 |  |  |  | 2018-05-09 | [6 empty] | 0 | JAPAN | OE
EPO | RU8321 | 5345 | NIPPON STEEL & SUMIKIN Pipeline & Engineering Co. Ltd. | 10009607 | P - NIPPON STEEL & SUMIKIN Pipeline & Engineering-10009607-3HNNS-122 | 5454 | POC | JPY |  | 87276.3 | 2016-12-22 | 2018-05-08 |  | 10200000 |  | 9160223 |  | 9160223 |  |  |  | 2018-05-09 | [6 empty] | 0 | JAPAN | OE
EPO | RU8321 | 5345 | NIPPON STEEL & SUMIKIN Pipeline & Engineering Co. Ltd. | 10009607 | P - NIPPON STEEL & SUMIKIN Pipeline & Engineering-10009607-Service | 5455 | SL | JPY |  | 6845.2 | 2016-12-22 | 2018-05-08 |  | 800000 |  | 800000 |  | 0 | [10 empty] | 0 | JAPAN | AM | 2019-05-10 | 2019-05-30
EPO | RU8321 | 8925 | TAKA INT'L CO., LTD. | 10011164 | P - TAKA INT'L CO., LTD.-10011164-6BP-1311L | 8930 | POC | JPY | 69500000 | 632205.25 | 2017-08-03 | 2018-06-30 |  | 69500000 |  | 49520807 |  | 48928050 | [10 empty] | 0 | JAPAN | OE
EPO | RU8321 | 19402 | PROFIT MAKING INTERNATIONAL | 10011998 | P - PROFIT MAKING - 10011998 | 20362 | POC | JPY | 46000000 | 406837.8 | 2017-12-28 | 2018-09-25 |  | 46000000 |  | 38131088 |  | 2682173 | [10 empty] | 0 | CHINA | OE
EPO | RU8321 | 26043 | GS E&C Corporation | 10012417 | P - GS E&C-10012417-1600-G-003A/B/C Supply Pump | 26061 | POC | USD | 2623397 | 2623397 | 2018-03-26 | 2018-09-30 |  | 2623397 |  | 92192000 |  | 21537758 | [6 empty] | 262339.7 | 28681663.1317 | 2018-04-04 | B1180274 | 0 | MIDEAST | AM
EPO | RU8321 | 27991 | EUAP FLOW CONTROL | 10012736 | P - EUAP FLOW CONTROL - 10012736 | 28005 | POC | USD | 436300 | 436300 | 2018-05-11 | 2019-03-20 |  | 436300 |  | 24364900 |  | 46200 | [6 empty] | 130890 | 14310235.4973 | 2018-05-11 | A1180007 | 0 | CHINA | AM
EPO | RU8321 | 28065 | NIPPON STEEL & SUMIKIN TEXENG, KANSAI BRANCH | 10012649 | P - NIPPON STEEL & SUMIKIN TEXENG - 10012649 - Plunger Pump/78x140 V3220L | 28073 | POC | JPY | 32000000 | 281440.88 | 2018-05-30 | 2018-11-30 |  | 30769999.7813 |  | 22615850 |  | 52800 | [10 empty] | 0 | JAPAN | OE
EPO | RU8321 | 28065 | NIPPON STEEL & SUMIKIN TEXENG, KANSAI BRANCH | 10012649 | P - NIPPON STEEL & SUMIKIN TEXENG - 10012649 - On-Site Supervisor Fee for Test Run | 28074 | PIT | JPY |  | 11250.32 | 2018-05-30 | 2018-11-30 |  | 1230000.2187 |  | 1230000 |  | 0 | [10 empty] | 0 | JAPAN | AM
AMSS | RU8328 | 23906 | BASF Petronas Chemicals Sdn Bhd | 719-I044-04 | P - BASF Petronas Chemicals Sdn Bhd - 719-I044-04_March 2018 | 23966 | POC | MYR | 1190000.0195 | 304563.25 | 2018-02-28 | 2018-11-20 |  | 1190000.0195 |  | 564777.31 |  | 0 | 0 | 0 | [8 empty] | 0 | ASIA | AM
EPO | RU8330 | 4233 | Oxy Vinyls, LP | 027-41712 | P-Oxy Vinyls LP -4502364830-Pump | 4344 | POC | USD | 394825 | 394825 | 2017-06-13 | 2018-03-07 |  | 394825 | [7 empty] | 2018-02-26 |  |  |  | 0 |  |  | 0 | US | OE
EPO | RU8330 | 4442 | APS-Four Corners Power Plant | 050-36243 | P-APS-Four Corners Power Plant-100586771-17PE0143 | 4444 | POC | USD | 725600 | 725600 | 2017-05-19 | 2018-03-30 |  | 725600 | [7 empty] | 2018-02-28 |  |  |  | 0 |  |  | 0 | US | OE
EPO | RU8330 | 4677 | Jacobs Engineering Group, Inc. | 052-41717 | P-Jacobs Engineering Group Inc-052-41717-Pump PP217 /A | 4679 | POC | USD | 590212.96 | 99355.86 | 2017-04-27 | 2018-04-06 |  | 99355.86 |  | 1514227 |  | 1514227.12 |  | 0 |  | 2018-05-17 | 1514227 |  |  | 0 |  |  | 0 | US | OE
EPO | RU8330 | 4677 | Jacobs Engineering Group, Inc. | 052-41717 | P-Jacobs Engineering Group Inc-052-41717-Pump J-PP 90/90A | 13490 | POC | USD |  | 160517.66 | 2017-04-27 | 2018-04-06 |  | 160517.66 |  | 2467936 |  | 2467936.2 |  | 0 |  | 2018-05-16 | 2467936 | [5 empty] | 0 | US | OE
EPO | RU8330 | 4677 | Jacobs Engineering Group, Inc. | 052-41717 | P-Jacobs Engineering Group Inc-052-41717-Pump J-PP91/A | 13491 | POC | USD |  | 60065.7 | 2017-04-27 | 2018-04-06 |  | 60065.7 |  | 1127217 |  | 1127217.02 |  | 0 |  | 2018-05-16 | 1127217 | [5 empty] | 0 | US | OE
EPO | RU8330 | 4677 | Jacobs Engineering Group, Inc. | 052-41717 | P-Jacobs Engineering Group Inc-052-41717-Pump J-PP 92/92A | 13492 | POC | USD |  | 270273.74 | 2017-04-27 | 2018-04-06 |  | 270273.74 |  | 3837509 |  | 3814228.24 |  | 23280.93 | [8 empty] | 0 | US | OE
EPO | RU8330 | 4725 | AECOM Energy & Construction Inc. | 050-36245 | P-AECOM Energy & Construction Inc_31845-002-15-008-PO_050-36245_17PE0198-199:Pump Vertical | 4727 | POC | USD | 795586 | 698113 | 2017-05-29 | 2018-04-30 |  | 698113 | 29000 | 13510486 |  | 13510485.88 |  | 0 |  | 2018-05-28 | 13510486 |  |  | 0 |  |  | 0 | US | OE
EPO | RU8330 | 4725 | AECOM Energy & Construction Inc. | 050-36245 | P-AECOM Energy & Construction Inc_31845-002-15-008-PO_050-36245_17PP0200:Pump Aux | 4742 | POC | USD |  | 97473 | 2017-05-29 | 2018-04-30 |  | 97473 |  | 1544605 |  | 0 |  | 0 |  | 2018-02-06 | [6 empty] | 0 | US | OE
EPO | RU8330 | 4750 | Jacobs Engineering Group, Inc | 052-41670 | P-Jacobs Engineering Group Inc_052-41670 Pump:HPXM12A,TAG J-K80/A | 4752 | POC | USD | 1281214 | 79470.98 | 2016-12-20 | 2018-03-01 |  | 87538 | [7 empty] | 2018-02-13 |  |  | 26674 | 499137.3535 | 2018-05-23 | SCF28557 | 0 | US | OE
EPO | RU8330 | 4750 | Jacobs Engineering Group, Inc | 052-41670 | P-Jacobs Engineering Group Inc-052-41670-Pump:HPXM12ATAG J-K061 | 13497 | POC | USD |  | 35920.33 | 2016-12-20 | 2018-03-01 |  | 39955 | [7 empty] | 2017-12-22 | [6 empty] | 0 | US | OE
EPO | RU8330 | 4750 | Jacobs Engineering Group, Inc | 052-41670 | P-Jacobs Engineering Group Inc-052-41670-Pump:HPX9ATAG J-K089/A | 13498 | POC | USD |  | 59006.29 | 2016-12-20 | 2018-03-01 |  | 67075 | [7 empty] | 2017-12-22 | [6 empty] | 0 | US | OE
EPO | RU8330 | 4750 | Jacobs Engineering Group, Inc | 052-41670 | P-Jacobs Engineering Group Inc-052-41670-Pump:HDX23ATAG J-PF39/A | 13499 | POC | USD |  | 408441.33 | 2016-12-20 | 2018-03-01 |  | 423071 | [7 empty] | 2018-01-04 | [6 empty] | 0 | US | OE
EPO | RU8330 | 4750 | Jacobs Engineering Group, Inc | 052-41670 | P-Jacobs Engineering Group Inc-052-41670-Pump:HPX7ATAG J-PP00009 | 13500 | POC | USD |  | 31836.21 | 2016-12-20 | 2018-03-01 |  | 32725 | [7 empty] | 2017-12-22 | [6 empty] | 0 | US | OE
EPO | RU8330 | 4750 | Jacobs Engineering Group, Inc | 052-41670 | P-Jacobs Engineering Group Inc-052-41670-Pump:HPX13ATAG J-PP11/A | 13501 | POC | USD |  | 59021.59 | 2016-12-20 | 2018-03-01 |  | 67090 | [7 empty] | 2017-12-07 | [6 empty] | 0 | US | OE
EPO | RU8330 | 4750 | Jacobs Engineering Group, Inc | 052-41670 | P-Jacobs Engineering Group Inc-052-41670-Pump:HPX9ATAG J-PP29/A | 13502 | POC | USD |  | 63927.07 | 2016-12-20 | 2018-03-01 |  | 65705 | [7 empty] | 2018-03-20 | [6 empty] | 0 | US | OE
EPO | RU8330 | 4750 | Jacobs Engineering Group, Inc | 052-41670 | P-Jacobs Engineering Group Inc-052-41670-Pump:HPX9ATAG J-PP30/A | 13503 | POC | USD |  | 63927.07 | 2016-12-20 | 2018-03-01 |  | 65705 | [7 empty] | 2018-03-20 | [6 empty] | 0 | US | OE
EPO | RU8330 | 4750 | Jacobs Engineering Group, Inc | 052-41670 | P-Jacobs Engineering Group Inc-052-41670-Pump:HPX10ATAG J-PP46/A | 13504 | POC | USD |  | 50830.5 | 2016-12-20 | 2018-03-01 |  | 58899 | [7 empty] | 2017-12-22 | [6 empty] | 0 | US | OE
EPO | RU8330 | 4750 | Jacobs Engineering Group, Inc | 052-41670 | P-Jacobs Engineering Group Inc-052-41670-Pump:HPX10ATAG J-PP49/A | 13505 | POC | USD |  | 63763.11 | 2016-12-20 | 2018-03-01 |  | 71832 | [7 empty] | 2017-12-08 | [6 empty] | 0 | US | OE
EPO | RU8330 | 4750 | Jacobs Engineering Group, Inc | 052-41670 | P-Jacobs Engineering Group Inc-052-41670-Pump:HPX9ATAG J-PP52/A | 13506 | POC | USD |  | 51146.42 | 2016-12-20 | 2018-03-01 |  | 59215 | [7 empty] | 2017-12-22 | [6 empty] | 0 | US | OE
EPO | RU8330 | 4750 | Jacobs Engineering Group, Inc | 052-41670 | P-Jacobs Engineering Group Inc-052-41670-Pump:HPX10ATAG J-PP53/A | 13507 | POC | USD |  | 59363.67 | 2016-12-20 | 2018-03-01 |  | 67432 | [7 empty] | 2017-12-22 | [6 empty] | 0 | US | OE
EPO | RU8330 | 4750 | Jacobs Engineering Group, Inc | 052-41670 | P-Jacobs Engineering Group Inc-052-41670-Pump:HPX9ATAG J-PP56/A | 13508 | POC | USD |  | 59006.29 | 2016-12-20 | 2018-03-01 |  | 67075 | [7 empty] | 2017-12-07 | [6 empty] | 0 | US | OE
EPO | RU8330 | 4750 | Jacobs Engineering Group, Inc | 052-41670 | P-Jacobs Engineering Group Inc-052-41670-Pump:HPX9ATAG J-PP64/A | 13509 | POC | USD |  | 64328.39 | 2016-12-20 | 2018-03-01 |  | 66106 | [7 empty] | 2017-12-08 | [6 empty] | 0 | US | OE
EPO | RU8330 | 4750 | Jacobs Engineering Group, Inc | 052-41670 | P-Jacobs Engineering Group Inc-052-41670-Pump:HPXM12A TAG J-PP65 | 13510 | POC | USD |  | 37756.33 | 2016-12-20 | 2018-03-01 |  | 41791 | [7 empty] | 2018-02-13 | [6 empty] | 0 | US | OE
EPO | RU8330 | 5089 | Jacobs Field Services North America Inc. As agent for Meglobal Americas Inc. | 052-41718 | P-Jacobs Field Services North America. As agent for Meglobal Americas Inc_58RH44XX-HQ133429:Pump BFW G-8114+BFW G-8115+BFW G-81146 | 5091 | POC | USD | 758151.28 | 758151.28 | 2017-05-11 | 2018-02-16 |  | 758151.28 |  | 13216521 |  | 6587393 |  | 276944 | [5 empty] | 0 |  |  | 0 | US | OE
EPO | RU8330 | 5244 | Jacobs Field Services North America Inc. As agent for Meglobal Americas Inc. | 052-41720 | P-Jacobs Field Services North America. As agent for Meglobal Americas_58RH44XX-HQ133808:Pump G-6131/6132/6133/6134 | 5246 | POC | USD | 1996362.22 | 178687.74 | 2017-07-11 | 2018-02-18 |  | 178687.74 |  | 3740291 |  | 3739258.29 |  | 1033.1 | [5 empty] | 0 |  |  | 0 | US | OE
EPO | RU8330 | 5244 | Jacobs Field Services North America Inc. As agent for Meglobal Americas Inc. | 052-41720 | P-Jacobs Field Services North America. As agent for Meglobal Americas_58RH44XX-HQ133808:Pump G-6204/6205 | 5269 | POC | USD |  | 107851.7 | 2017-07-11 | 2018-02-18 |  | 107851.7 |  | 2323434 |  | 2323434.2 |  | 0 |  | 2018-05-04 | 2323434 | [5 empty] | 0 | US | OE
EPO | RU8330 | 5244 | Jacobs Field Services North America Inc. As agent for Meglobal Americas Inc. | 052-41720 | P-Jacobs Field Services North America. As agent for Meglobal Americas_58RH44XX-HQ133808:Pump G-6206/6207 | 5270 | POC | USD |  | 131451.7 | 2017-07-11 | 2018-02-18 |  | 131451.7 |  | 2559609 |  | 2556921.32 |  | 2687.23 | [8 empty] | 0 | US | OE
EPO | RU8330 | 5244 | Jacobs Field Services North America Inc. As agent for Meglobal Americas Inc. | 052-41720 | P-Jacobs Field Services North America. As agent for Meglobal Americas_58RH44XX-HQ133808:Pump G-6237/6238 | 5271 | POC | USD |  | 116724.1 | 2017-07-11 | 2018-02-18 |  | 116724.1 |  | 2347540 |  | 2347540.25 |  | 0 |  | 2018-05-04 | 2347540 | [5 empty] | 0 | US | OE
EPO | RU8330 | 5244 | Jacobs Field Services North America Inc. As agent for Meglobal Americas Inc. | 052-41720 | P-Jacobs Field Services North America. As agent for Meglobal Americas_58RH44XX-HQ133808:Pump G-6497/6498 | 5272 | POC | USD |  | 130677.32 | 2017-07-11 | 2018-02-18 |  | 130677.32 |  | 2346241 |  | 2346240.58 |  | 0 |  | 2018-05-04 | 2346241 | [5 empty] | 0 | US | OE
EPO | RU8330 | 5244 | Jacobs Field Services North America Inc. As agent for Meglobal Americas Inc. | 052-41720 | P-Jacobs Field Services North America. As agent for Meglobal Americas_58RH44XX-HQ133808:Pump G-6702/6703 | 5273 | POC | USD |  | 463715.7 | 2017-07-11 | 2018-02-18 |  | 463715.7 |  | 8083754 |  | 5736481.47 |  | 11766 | [8 empty] | 0 | US | OE
EPO | RU8330 | 5244 | Jacobs Field Services North America Inc. As agent for Meglobal Americas Inc. | 052-41720 | P-Jacobs Field Services North America. As agent for Meglobal Americas_58RH44XX-HQ133808:Pump G-6726/6727 | 5274 | POC | USD |  | 154231.7 | 2017-07-11 | 2018-02-18 |  | 154231.7 |  | 3620354 |  | 3620353.68 |  | 0 |  | 2018-05-04 | 3620354 | [5 empty] | 0 | US | OE
EPO | RU8330 | 5244 | Jacobs Field Services North America Inc. As agent for Meglobal Americas Inc. | 052-41720 | P-Jacobs Field Services North America. As agent for Meglobal Americas_58RH44XX-HQ133808:Pump G-6826/G-6826(S) | 5275 | POC | USD |  | 266397.03 | 2017-07-11 | 2018-02-18 |  | 266397.03 |  | 4988254 |  | 4988253.55 |  | 0 |  | 2018-05-28 | 4988254 | [5 empty] | 0 | US | OE
EPO | RU8330 | 5244 | Jacobs Field Services North America Inc. As agent for Meglobal Americas Inc. | 052-41720 | P-Jacobs Field Services North America. As agent for Meglobal Americas_58RH44XX-HQ133808:Pump G-8125/8126 | 5276 | POC | USD |  | 87647.3 | 2017-07-11 | 2018-02-18 |  | 87647.3 |  | 1650113 |  | 1650113.01 |  | 0 |  | 2018-05-04 | 1650113 | [5 empty] | 0 | US | OE
EPO | RU8330 | 5244 | Jacobs Field Services North America Inc. As agent for Meglobal Americas Inc. | 052-41720 | P-Jacobs Field Services North America. As agent for Meglobal Americas_58RH44XX-HQ133808:Pump G-6110/6112 | 5277 | POC | USD |  | 161434.93 | 2017-07-11 | 2018-02-18 |  | 161434.93 |  | 3272110 |  | 3272110.05 |  | 0 |  |  | 3272110 | [5 empty] | 0 | US | OE
EPO | RU8330 | 5244 | Jacobs Field Services North America Inc. As agent for Meglobal Americas Inc. | 052-41720 | P-Jacobs Field Services North America. As agent for Meglobal Americas_58RH44XX-HQ133808:Pump G-6812/6817 | 5278 | POC | USD |  | 197543 | 2017-07-11 | 2018-02-18 |  | 197543 |  | 3434875 |  | 3434875.34 |  | 0 |  | 2018-05-28 | 3434875 | [5 empty] | 0 | US | OE
EPO | RU8330 | 5429 | Jacobs Field Services North America Inc. As agent for Meglobal Americas Inc. | 052-41719 | P-Jacobs Field Services North America. As agent for Meglobal Americas_58RH44XX-HQ133809:Pump:G-6310/G-6311 | 5434 | POC | USD | 3645859.57 | 646158.58 | 2017-05-11 | 2018-03-30 |  | 646158.58 |  | 11809547 |  | 11026031 |  | 783516 | [5 empty] | 0 |  |  | 0 | US | OE
EPO | RU8330 | 5429 | Jacobs Field Services North America Inc. As agent for Meglobal Americas Inc. | 052-41719 | P-Jacobs Field Services North America. As agent for Meglobal Americas_58RH44XX-HQ133809:Pump:G-6313/G-6314 | 5608 | POC | USD |  | 435747.3 | 2017-05-11 | 2018-03-30 |  | 435747.3 |  | 7596193 |  | 6419880 |  | 618846 | [8 empty] | 0 | US | OE
EPO | RU8330 | 5429 | Jacobs Field Services North America Inc. As agent for Meglobal Americas Inc. | 052-41719 | P-Jacobs Field Services North America. As agent for Meglobal Americas_58RH44XX-HQ133809:Pump:G-6352/G-6353 | 5631 | POC | USD |  | 333265.14 | 2017-05-11 | 2018-03-30 |  | 333265.14 |  | 5809666 |  | 4472581 |  | 103320 | [8 empty] | 0 | US | OE
EPO | RU8330 | 5429 | Jacobs Field Services North America Inc. As agent for Meglobal Americas Inc. | 052-41719 | P-Jacobs Field Services North America. As agent for Meglobal Americas_58RH44XX-HQ133809:Pump:G-6415/G-6416 | 5637 | POC | USD |  | 690956.87 | 2017-05-11 | 2018-03-30 |  | 690956.87 |  | 12045151 |  | 7273115 |  | 2051743 | [8 empty] | 0 | US | OE
EPO | RU8330 | 5429 | Jacobs Field Services North America Inc. As agent for Meglobal Americas Inc. | 052-41719 | P-Jacobs Field Services North America. As agent for Meglobal Americas_58RH44XX-HQ133809:Pump:G-6417/G-6418 | 5638 | POC | USD |  | 543746.8 | 2017-05-11 | 2018-03-30 |  | 543746.8 |  | 10653731 |  | 9883142 |  | 770589 | [8 empty] | 0 | US | OE
EPO | RU8330 | 5429 | Jacobs Field Services North America Inc. As agent for Meglobal Americas Inc. | 052-41719 | P-Jacobs Field Services North America. As agent for Meglobal Americas_58RH44XX-HQ133809:Pump:G-6772/G-6773 | 5658 | POC | USD |  | 588588.4 | 2017-05-11 | 2018-03-30 |  | 588588.4 |  | 10260606 |  | 8957036 |  | 591911 | [8 empty] | 0 | US | OE
EPO | RU8330 | 5429 | Jacobs Field Services North America Inc. As agent for Meglobal Americas Inc. | 052-41719 | P-Jacobs Field Services North America. As agent for Meglobal Americas_58RH44XX-HQ133809:Pump:G-6227 | 5661 | POC | USD |  | 407396.48 | 2017-05-11 | 2018-03-30 |  | 407396.48 |  | 7101966 |  | 1743051 |  | 2999009 | [8 empty] | 0 | US | OE
EPO | RU8330 | 5813 | Ningxia Baofeng Energy Ltd | 222-41722 | P-Ningxia Baofeng Energy Ltd_BFNY-GY-2017-1092: Pump 103-P-4101/103-P-4201 | 5815 | POC | USD | 4200000 | 4200000 | 2017-05-15 | 2018-08-13 |  | 4200000 |  | 56991426 |  | 15983454 |  | 21635776 | [5 empty] | 0 |  |  | 0 | CHINA | OE
EPO | RU8330 | 5954 | Yibin Tianyuan Haifeng Hetai Co. LTD | 222-41729 | P-Yibin Tianyuan Haifeng Hetai Co. LTD_Z2GF1706092522:Pump_Crude TiCl4 Storage | 5958 | POC | USD | 2275000 | 464100 | 2017-06-26 | 2018-06-28 |  | 464100 |  | 4510714 |  | 1485257 |  | 412685 | [5 empty] | 0 |  |  | 0 | CHINA | OE
EPO | RU8330 | 5954 | Yibin Tianyuan Haifeng Hetai Co. LTD | 222-41729 | P-Yibin Tianyuan Haifeng Hetai Co. LTD_Z2GF1706092522:Pump_Purge TiCl4 | 6171 | POC | USD |  | 236600 | 2017-06-26 | 2018-06-28 |  | 236600 |  | 2299580 |  | 826760 |  | 521282 | [8 empty] | 0 | CHINA | OE
EPO | RU8330 | 5954 | Yibin Tianyuan Haifeng Hetai Co. LTD | 222-41729 | P-Yibin Tianyuan Haifeng Hetai Co. LTD_Z2GF1706092522:Pump_No.2 Contact Condenser | 6172 | POC | USD |  | 247725 | 2017-06-26 | 2018-06-28 |  | 247725 |  | 2407707 |  | 1418334 |  | 222508 | [8 empty] | 0 | CHINA | OE
EPO | RU8330 | 5954 | Yibin Tianyuan Haifeng Hetai Co. LTD | 222-41729 | P-Yibin Tianyuan Haifeng Hetai Co. LTD_Z2GF1706092522:Pump_Solid Removal | 6173 | POC | USD |  | 248225 | 2017-06-26 | 2018-06-28 |  | 248225 |  | 2412566 |  | 751872 |  | 336724 | [8 empty] | 0 | CHINA | OE
EPO | RU8330 | 5954 | Yibin Tianyuan Haifeng Hetai Co. LTD | 222-41729 | P-Yibin Tianyuan Haifeng Hetai Co. LTD_Z2GF1706092522:Pump_Purge Pump | 6174 | POC | USD |  | 254800 | 2017-06-26 | 2018-06-28 |  | 254800 |  | 2476471 |  | 899150 |  | 402213 | [8 empty] | 0 | CHINA | OE
EPO | RU8330 | 5954 | Yibin Tianyuan Haifeng Hetai Co. LTD | 222-41729 | P-Yibin Tianyuan Haifeng Hetai Co. LTD_Z2GF1706092522:Pump_Solid Removal | 6175 | POC | USD |  | 261625 | 2017-06-26 | 2018-06-28 |  | 261625 |  | 2542805 |  | 751872 |  | 336724 | [8 empty] | 0 | CHINA | OE
EPO | RU8330 | 5954 | Yibin Tianyuan Haifeng Hetai Co. LTD | 222-41729 | P-Yibin Tianyuan Haifeng Hetai Co. LTD_Z2GF1706092522:Pump_Contact Condenser | 6176 | POC | USD |  | 266175 | 2017-06-26 | 2018-06-28 |  | 266175 |  | 2587027 |  | 959232 |  | 411731 | [8 empty] | 0 | CHINA | OE
EPO | RU8330 | 5954 | Yibin Tianyuan Haifeng Hetai Co. LTD | 222-41729 | P-Yibin Tianyuan Haifeng Hetai Co. LTD_Z2GF1706092522:Pump_Circulation | 6179 | POC | USD |  | 295750 | 2017-06-26 | 2018-06-28 |  | 295750 |  | 2874475 |  | 1023562 |  | 408472 | [8 empty] | 0 | CHINA | OE
EPO | RU8330 | 6263 | Zachry Industrial, Inc. | 050-36201 | P-Zachry Industrial_4687-405438:Pump | 7502 | POC | USD | 4589335 | 4589335 | 2016-10-21 | 2018-02-21 |  | 4589335 | 458934 | 72889509 |  | 72889509 |  | 0 |  | 2018-05-08 |  |  | 534084 | may/16/2018 | 2018-05-16 | SCF28360-28361; SCF28447-28448 | 0 | US | OE
EPO | RU8330 | 7711 | Nova Chemical Corporation | 2017Q0000596 Rev. 3 | P-Nova Chemical Corporation-2017Q0000596 Rev. 3-Nova Chemical_4500947131: Pump | 7729 | POC | USD | 706500 | 717270 | 2017-03-09 | 2018-01-29 |  | 706500 | [7 empty] | 2018-03-29 |  |  | 70650 | may/25/2018 | 2018-05-25 | SCF28610 | 0 | US | OE
EPO | RU8330 | 8009 | Enterprise Products Operating LLC | 193784 | P-Enterprise Products Operating LLC-193784-Enterprise Products Operating _193784:Pump | 8029 | POC | USD | 481400 | 481400 | 2017-05-25 | 2018-03-26 |  | 481400 | [7 empty] | 2018-02-28 |  |  |  | 0 |  |  | 0 | US | OE
EPO | RU8330 | 10533 | Eastman Chemical Company | 070-41736 | P-Eastman Chemical Company-070-41736-Pump: Horizontal HE 4" identical to S/N 74282-1 | 10666 | POC | USD | 369000 | 369000 | 2017-08-23 | 2018-06-14 |  | 369000 |  | 4712572 |  | 0 |  | 1806098 | [5 empty] | 0 |  |  | 0 | US | OE
EPO | RU8330 | 10939 | CB&I, LLC. | 050-36257 | P-CB&I LLC.-050-36257-Pump: 10-CWS-P-0001A/B_Circulating Water Pump A/B | 11032 | POC | USD | 627157 | 627157 | 2017-08-17 | 2018-09-03 |  | 627157 |  | 10757000 |  | 1605362 |  | 4899556 | [5 empty] | 0 |  |  | 0 | US | OE
EPO | RU8330 | 14276 | Equilon Enterprices LLC | 051-17832 | P - Equilon Enterprices_LLC 4523064177 | 16062 | POC | USD | 359770 | 355470 | 2017-08-28 | 2018-05-14 |  | 359770 |  | 6153006 |  | 5051613 |  | 1101393 | [5 empty] | 0 |  |  | 0 | US | OE
EPO | RU8330 | 14902 | VWS Wastgarth Limited (Veolia Westgarth Ltd.) | 106-17304 | P-VWS Wastgarth Limited-106-17304-VWS Wastgarth Limited_PO:20029-03913_17HE0400/401 | 14907 | POC | USD | 433500 | 433500 | 2017-09-12 | 2018-05-25 |  | 433500 |  | 7218142 |  | 0 |  | 4100332 | [5 empty] | 0 |  |  | 0 | CHINA | OE
EPO | RU8330 | 14915 | Smith Pump Company, Inc | 047-88862 | P-Smith Pump Company-047-88862-Smith Pump Company_PU48558_17WE0415_416:Pump | 14922 | POC | USD | 816800 | 816800 | 2017-09-29 | 2018-10-01 |  | 816800 |  | 12935080 |  | 2899454 |  | 2113077 | [5 empty] | 0 |  |  | 0 | US | OE
EPO | RU8330 | 14923 | Burns & McDonnell Engineering Company | 051-17830 | P-Burns & McDonnell-051-17830-Pump:Burns & McDonnellTag:P2901 _17HE0353-354 | 15427 | POC | USD | 1417450.99 | 394951.57 | 2017-08-02 | 2018-04-27 |  | 394951.57 |  | 6067626 |  | 2807406 |  | 2441484 | [5 empty] | 0 |  |  | 0 | US | OE
EPO | RU8330 | 14923 | Burns & McDonnell Engineering Company | 051-17830 | P-Burns & McDonnell-051-17830-Pump:Burns & McDonnellTag:P2921 _17HE0355-356 | 15428 | POC | USD |  | 183135.57 | 2017-08-02 | 2018-04-27 |  | 183135.57 |  | 2813505 |  | 1556893 |  | 887779 | [8 empty] | 0 | US | OE
EPO | RU8330 | 14923 | Burns & McDonnell Engineering Company | 051-17830 | P-Burns & McDonnell-051-17830-Pump:Burns & McDonnellTag:P2922 _17HE0357-358 | 15429 | POC | USD |  | 346469.57 | 2017-08-02 | 2018-04-27 |  | 346469.57 |  | 5322799 |  | 1250475 |  | 2222459 | [8 empty] | 0 | US | OE
EPO | RU8330 | 14923 | Burns & McDonnell Engineering Company | 051-17830 | P-Burns & McDonnell-051-17830-Pump:Burns & McDonnellTag:P2960 _17HE0359-360 | 15430 | POC | USD |  | 118773.57 | 2017-08-02 | 2018-04-27 |  | 118773.57 |  | 1824714 |  | 791631 |  | 793274 | [8 empty] | 0 | US | OE
EPO | RU8330 | 14923 | Burns & McDonnell Engineering Company | 051-17830 | P-Burns & McDonnell-051-17830-Pump:Burns & McDonnellTag:P2971 _17HE0361-362 | 15431 | POC | USD |  | 135837.57 | 2017-08-02 | 2018-04-27 |  | 135837.57 |  | 2086867 |  | 996138 |  | 1024594 | [8 empty] | 0 | US | OE
EPO | RU8330 | 14923 | Burns & McDonnell Engineering Company | 051-17830 | P-Burns & McDonnell-051-17830-Pump:Burns & McDonnellTag:P2981 _17HE0363-364 | 15432 | POC | USD |  | 113621.57 | 2017-08-02 | 2018-04-27 |  | 113621.57 |  | 1745564 |  | 758826 |  | 830797 | [8 empty] | 0 | US | OE
EPO | RU8330 | 14923 | Burns & McDonnell Engineering Company | 051-17830 | P-Burns & McDonnell-051-17830-Pump:Burns & McDonnellTag:P2999 _17HE0365-366 | 15433 | POC | USD |  | 124661.57 | 2017-08-02 | 2018-04-27 |  | 124661.57 |  | 1915171 |  | 934425 |  | 660157 | [8 empty] | 0 | US | OE
EPO | RU8330 | 15066 | Equilon Enterprices LLC | 051-17806 | P-Equilon Enterprices LLC-051-17806-Pump: Equilon_Tag:P-8144/8145_17HE0063-064 | 15345 | POC | USD | 488660 | 354020 | 2017-04-05 | 2018-03-16 |  | 340852.6 |  | 5756831 |  | 5446352 |  | 310479 | [5 empty] | 0 |  |  | 0 | US | OE
EPO | RU8330 | 15066 | Equilon Enterprices LLC | 051-17806 | P-Equilon Enterprices LLC-051-17806-Pump: Equilon_Tag:P-8202/8203_17HE0065-066 | 15346 | POC | USD |  | 126729 | 2017-04-05 | 2018-03-16 |  | 147807.4 |  | 2153819 |  | 2153819 |  | 0 |  | 2018-04-16 | 2153819 | [5 empty] | 0 | US | OE
EPO | RU8330 | 15112 | Samsung Heavy Industries Co LTD | 052-17841 | P-Samsung Heavy Industries Co LTD-052-17841-Pump:Tag:PBA-242101/242201/242301_17HE0456-458 | 16123 | POC | USD | 1579659.99 | 661764.54 | 2017-10-26 | 2018-08-08 |  | 661764.54 |  | 10371147 |  | 1084226 |  | 5411215 | [5 empty] | 0 |  |  | 0 | US | OE
EPO | RU8330 | 15112 | Samsung Heavy Industries Co LTD | 052-17841 | P-Samsung Heavy Industries Co LTD-052-17841-Pump: Tag: PBE-804002/804003/804004_17HE0459-461 | 16124 | POC | USD |  | 470092.97 | 2017-10-26 | 2018-08-08 |  | 470092.97 |  | 7509257 |  | 0 |  | 2991015 | [8 empty] | 0 | US | OE
EPO | RU8330 | 15112 | Samsung Heavy Industries Co LTD | 052-17841 | P-Samsung Heavy Industries Co LTD-052-17841-Pump:Tag: PBA-212003/212004_17HE0462-463 | 16125 | POC | USD |  | 264206.31 | 2017-10-26 | 2018-08-08 |  | 264206.31 |  | 4155407 |  | 179393 |  | 1187507 | [8 empty] | 0 | US | OE
EPO | RU8330 | 15112 | Samsung Heavy Industries Co LTD | 052-17841 | P-Samsung Heavy Industries Co LTD-052-17841-Pump: Tag PBA-423001_17HE0464 | 16126 | POC | USD |  | 183596.17 | 2017-10-26 | 2018-08-08 |  | 183596.17 |  | 2887077 |  | 0 |  | 699997 | [8 empty] | 0 | US | OE
EPO | RU8330 | 15164 | Valero Partners Meraux, LLC | 024-17637 | P-Valero Partners Meraux-024-17637-Pump:TagK-P-159A/B_17HE0490_0491 | 15519 | POC | USD | 294382 | 295966 | 2017-12-05 | 2018-06-20 |  | 294382 |  | 4345872 |  | 25574 |  | 2725675 | [5 empty] | 0 |  |  | 0 | US | OE
EPO | RU8330 | 15173 | Indorama Ventures (Oxide & Glycols) LLC | 052-41748 | P-Indorama Ventures (Oxide & Glycols) LLC-052-41748-Pump:Indorama_Tag:P-2952/P-2953_17IE05004_505 | 15744 | POC | USD | 319000 | 185846 | 2017-11-28 | 2018-07-19 |  | 185846 |  | 2289333 |  | 1081824 |  | 980778 | [5 empty] | 0 |  |  | 0 | US | OE
EPO | RU8330 | 15173 | Indorama Ventures (Oxide & Glycols) LLC | 052-41748 | P-Indorama Ventures (Oxide & Glycols) LLC-052-41748-Pump:Indorama_Tag:P-2954/P-2955_17IE506_507 | 15745 | POC | USD |  | 133154 | 2017-11-28 | 2018-07-19 |  | 133154 |  | 1640249 |  | 447497 |  | 626673 | [8 empty] | 0 | US | OE
EPO | RU8330 | 15189 | Targa Downstream LLC -HAA | 027-17638 | P-Targa Downstream LLC -HAA-027-17638-Targa_Tag:28-558-1-1/2_17HE0509-510 | 15906 | POC | USD | 951007.4 | 119449.7 | 2017-11-27 | 2018-06-08 |  | 119449.68 |  | 1761694 |  | 990466 |  | 660678 | [5 empty] | 0 |  |  | 0 | US | OE
EPO | RU8330 | 15189 | Targa Downstream LLC -HAA | 027-17638 | P-Targa Downstream LLC -HAA-027-17638-Targa_Tag:28-558-2-1/2_17HE0511-512 | 15907 | POC | USD |  | 114906.22 | 2017-11-27 | 2018-06-08 |  | 114906.2 |  | 1695304 |  | 559793 |  | 676609 | [8 empty] | 0 | US | OE
EPO | RU8330 | 15189 | Targa Downstream LLC -HAA | 027-17638 | P-Targa Downstream LLC -HAA-027-17638-Targa_Tag:28-558-4-1/2_17HE0513-514 | 15908 | POC | USD |  | 105126.68 | 2017-11-27 | 2018-06-08 |  | 105126.66 |  | 1542378 |  | 987081 |  | 541559 | [8 empty] | 0 | US | OE
EPO | RU8330 | 15189 | Targa Downstream LLC -HAA | 027-17638 | P-Targa Downstream LLC -HAA-027-17638-Targa_Tag:28-558-5-1/2_17HE0515-516 | 15909 | POC | USD |  | 84972.02 | 2017-11-27 | 2018-06-08 |  | 84972 |  | 1390863 |  | 1044505 |  | 346359 | [8 empty] | 0 | US | OE
EPO | RU8330 | 15189 | Targa Downstream LLC -HAA | 027-17638 | P-Targa Downstream LLC -HAA-027-17638-Targa_Tag:28-558-7-1/2_17HE0517-518 | 15910 | POC | USD |  | 63567.99 | 2017-11-27 | 2018-06-08 |  | 63567.98 |  | 1154202 |  | 812473 |  | 341729 | [8 empty] | 0 | US | OE
EPO | RU8330 | 15189 | Targa Downstream LLC -HAA | 027-17638 | P-Targa Downstream LLC -HAA-027-17638-Targa_Tag:28-558-8-1/2_17HE0519-520 | 15911 | POC | USD |  | 114667.6 | 2017-11-27 | 2018-06-08 |  | 114667.58 |  | 1684781 |  | 740381 |  | 639436 | [8 empty] | 0 | US | OE
EPO | RU8330 | 15189 | Targa Downstream LLC -HAA | 027-17638 | P-Targa Downstream LLC -HAA-027-17638-Targa_Tag:28-559_17HE0521 | 15912 | POC | USD |  | 32334.96 | 2017-11-27 | 2018-06-08 |  | 32334.95 |  | 563776 |  | 419180 |  | 144596 | [8 empty] | 0 | US | OE
EPO | RU8330 | 15189 | Targa Downstream LLC -HAA | 027-17638 | P-Targa Downstream LLC -HAA-027-17638-Targa_Tag:28-558-29A/B/C_17HE0522-524 | 15913 | POC | USD |  | 230672.83 | 2017-11-27 | 2018-06-08 |  | 230672.79 |  | 3394947 |  | 2109136 |  | 927646 | [8 empty] | 0 | US | OE
EPO | RU8330 | 15189 | Targa Downstream LLC -HAA | 027-17638 | P-Targa Downstream LLC -HAA-027-17638-Targa_Tag:28-558-37-1/2_17HE0525-526 | 15914 | POC | USD |  | 85309.56 | 2017-11-27 | 2018-06-08 |  | 85309.56 |  | 1290033 |  | 16752 |  | 69160 | [8 empty] | 0 | US | OE
EPO | RU8330 | 15217 | Southwestern Electric Power, Co. | 15PM159N | P-Southwestern Electric Power Co-15PM159N-Pump:16802958200_15PM159N_17PE0535_0536 | 16825 | POC | USD | 590000 | 590000 | 2017-12-05 | 2018-11-01 |  | 590000 |  | 8926086 |  | 1225526 |  | 1614866 | [5 empty] | 0 |  |  | 0 | US | OE
EPO | RU8330 | 15302 | Colonial Pipeline Company | 17HE0449-450 | P-Colonial Pipeline Company-17HE0449-450-Pump:TAG:P-003/P-004_17HE0449-450 | 17023 | POC | USD | 876410.6 | 892897.6 | 2017-11-17 | 2018-08-15 |  | 876410.6 |  | 11268318 |  | 1177653 |  | 6570017 | [5 empty] | 0 |  |  | 0 | US | OE
EPO | RU8330 | 17438 | EQUILON ENTERPRISES LLC | 051-17816 | P-EQUILON ENTERPRISES LLC-051-17816-API 610 CENTRIFUGAL PUMPS | 19282 | POC | USD | 760729 | 760729 | 2017-04-26 | 2018-04-07 |  | 760729 | 8492 | 11745069 |  | 3240461 |  | 7595032 | [5 empty] | 0 |  |  | 0 | US | OE
EPO | RU8330 | 17499 | MONAY INDUSTRIES LLC (NOLIMIT C.A) | 16-EC-00169 | P-MONAY INDUSTRIES LLC (NOLIMIT C.A)-16-EC-00169-MONAY INDUSTRIES_310117-08 B-SETRIA_17HE0026-0027 | 19050 | POC | USD | 894348.64 | 503160.24 | 2017-02-24 | 2018-01-01 |  | 503160.24 |  | 7622051 |  | 2138650 |  | 2230729 | [5 empty] | 0 |  |  | 0 | US | OE
EPO | RU8330 | 17499 | MONAY INDUSTRIES LLC (NOLIMIT C.A) | 16-EC-00169 | P-MONAY INDUSTRIES LLC (NOLIMIT C.A)-16-EC-00169-MONAY INDUSTRIES_310117-08 B-SETRIA_17HE0028-0031 | 19051 | POC | USD |  | 391188.4 | 2017-02-24 | 2018-01-01 |  | 391188.4 |  | 5919662 |  | 4680067 |  | 74748 | [8 empty] | 0 | US | OE
EPO | RU8330 | 17539 | REPOTENCIACION CT MANZANILLO S.A. DE C.V. | 291-17075 | P-REPOTENCIACION CT MANZANILLO_PED RCM 17 0013_17ME0019-0021 | 20310 | POC | USD | 803195.9 | 811556.9 | 2017-01-16 | 2018-04-20 |  | 803195.9 | 80320 | 14131021 |  | 4363227 |  | 8186497 |  |  | 10455176 |  |  | 0 |  |  | 0 | LA | OE
EPO | RU8330 | 17556 | LOTE ENGINEERING & CONSTRUCTION CO LTD | 330-16040 | P-LOTE ENGINEERING & CONSTRUCTION CO LTD_TPP3-MR-PO-0001_330-16040_16LW0431-433 | 18642 | POC | USD | 1491500 | 1491500 | 2017-02-17 | 2018-01-29 |  | 1491500 | [7 empty] | 2018-01-24 |  |  |  | 0 |  |  | 0 | ASIA | OE
EPO | RU8330 | 17813 | Marathon Petroleum Corporation | 16LW0380-0381 | P-MARATHON PETROLEUM CORP_4100901573_16LW0380-0381 | 20027 | POC | USD | 336200 | 336200 | 2016-12-02 | 2018-01-31 |  | 336200 | [7 empty] | 2018-01-30 |  |  |  | 0 |  |  | 0 | US | OE
EPO | RU8330 | 17876 | JACOBS Engineering Group Inc | 052-41520 | P-Jacobs Engineering Group Inc_58NQ1560-HH116939_15HE0562-0563 | 20019 | POC | USD | 335158 | 335158.07 | 2015-09-30 | 2018-01-31 |  | 335158 | [7 empty] | 2018-02-01 |  |  |  | 0 |  |  | 0 | US | OE
EPO | RU8330 | 17936 | FLUOR ENTERPRISES, INC. | 052-16244 | P-Fluor Enterprises-17HE0433-0434-T3GB Pumps for Texas City | 20043 | POC | USD | 808976 | 808976 | 2016-06-20 | 2018-07-02 |  | 808976 |  | 11921094 |  | 9251397 |  | 1651534 |  |  | 9251397 |  |  | 0 |  |  | 0 | US | OE
EPO | RU8330 | 17941 | ICA FLUOR DANIEL S DE RL DE CV MA116-3-H-PO-2603-00 291-15359 15ME0424-425 | 291-15359 | P-ICA FLUOR DANIEL_MA116-3-H-PO-2603-00_291-15359_15ME0424-425-291-15359-BOMBAS CENTRIFUGAS VERTICALES for DUBA MADERO | 20030 | POC | USD | 306098 | 306098 | 2016-03-18 | 2018-01-01 |  | 306098 |  | 4343435 |  | 3029819 |  | 0 | [5 empty] | 0 |  |  | 0 | LA | OE
EPO | RU8330 | 17942 | ICA FLUOR DANIEL S DE RL DE CV | 291-15603 | P-ICA FLUOR DANIEL_MA-116-3-H-PO-2603-01_291-15603_15ME0656-657 | 20035 | POC | USD | 314958 | 314958 | 2016-05-07 | 2018-01-01 |  | 314958 |  | 4112882 |  | 4112882 |  | 0 | [5 empty] | 0 |  |  | 0 | LA | OE
EPO | RU8330 | 17943 | FLORIDA POWER & LIGHT COMPANY | 050-36208 | P-FLORIDA POWER & LIGHT COMPANY-050-36208-Removal and Installation of 2 Circ Water Pumps | 19954 | POC | USD | 3008323 | 2428622 | 2016-12-07 | 2018-08-07 |  | 2428622 |  | 56793342 | [5 empty] | 2017-12-16 |  |  |  | 0 |  |  | 0 | US | OE
EPO | RU8330 | 17943 | FLORIDA POWER & LIGHT COMPANY | 050-36208 | P-FLORIDA POWER & LIGHT COMPANY-050-36208-1 Circulating Water Pump - Spare | 19955 | POC | USD |  | 403461 | 2016-12-07 | 2018-08-07 |  | 403461 |  | 8549178.1983 | [5 empty] | 2018-04-24 | [6 empty] | 0 | US | OE
EPO | RU8330 | 17943 | FLORIDA POWER & LIGHT COMPANY | 050-36208 | P-FLORIDA POWER & LIGHT COMPANY-050-36208-2 Purchase and Installation Turning Guides (T&M) | 19956 | POC | USD |  | 176240 | 2016-12-07 | 2018-08-07 |  | 176240 |  | 3734455.5376 | [12 empty] | 0 | US | OE
EPO | RU8330 | 17944 | ICA FLUOR DANIEL S DE RL DE CV | 291-15283,291-15284 | P-ICA FLOUR DANIEL, S.DE R.L.DE C.V-ART-03-300-H-2603_291-15283, 291-15284_15ME0328-0331-VERTICAL PUMP 6X8X22 VS4 Tag: GA-31009 | 19069 | POC | USD | 1633260 | 1633260 | 2015-07-21 | 2018-01-01 |  | 1633260 |  | 27590945 |  | 24175622 |  | 0 | [5 empty] | 0 |  |  | 0 | LA | OE
EPO | RU8330 | 17945 | ICA FLUOR DANIEL S DE RL DE CV ART-03-300-H-2601 291-15318 15ME0356-392 | 291-15318 | P-ICA FLUOR DANIEL, S.DE R.L.DE C.V- ART-03-300-H-2601_291-15318_15ME0356-392-FURNACE PUMPSWATER PUMPSRACK -S-ESTE PUMPS | 19035 | POC | USD | 5582418 | 5582418 | 2015-08-13 | 2018-02-28 |  | 5582418 |  | 82762150 |  | 80494430 |  | 1324332 | [5 empty] | 0 |  |  | 0 | LA | OE
EPO | RU8330 | 18184 | TREUNIDAS MEXICO INGENIERIA Y CONSTRUCCION S. DE R.L. DE C.V. | 291-16406 | P-TREUNIDAS MEXICO INGENIERIA Y CONSTRUCCION_0228505090_291-16406_16ME0262-0273-291-16406-CENTRIFUGAL PUMPS OH2 (OSBL) | 19952 | POC | USD | 427415.07 | 427415.07 | 2016-08-04 | 2018-01-01 |  | 427415.07 |  | 7042088 |  | 124889 |  | 0 | [5 empty] | 0 |  |  | 0 | LA | OE
EPO | RU8330 | 18219 | Tecnicas Reunidas (TR ETO) | 195-41630 | P-Tecnicas Reunidas (TR ETO)-195-41630-Centrifugal API Pumps | 19823 | POC | USD | 3031704.12 | 3000873.12 | 2016-09-27 | 2018-02-28 |  | 3000873.12 |  | 45046179.1 | [5 empty] | 2018-04-20 |  |  | 52333 | 979281.5147 | 2018-05-09 | SCF28394 | 0 | US | OE
EPO | RU8330 | 18219 | Tecnicas Reunidas (TR ETO) | 195-41630 | P-Tecnicas Reunidas (TR ETO)-195-41630-Centrifugal API Pumps | 19824 | POC | USD |  | 30831 | 2016-09-27 | 2018-02-28 |  | 30831 |  | 465747.3 | [5 empty] | 2018-04-06 | [6 empty] | 0 | US | OE
EPO | RU8330 | 18320 | Avanzia Instalaciones, S.A. de C.V. | 291-16744 | P-AVANZIA INSTALACIONES_PED CGA 16 0019_291-16744_16PE0474-475 BOMBAS ALTA PRESION MEDIA PRESION CONDENSADOS AUXILIARES | 19359 | POC | USD | 2800000 | 2520000 | 2016-11-30 | 2018-01-01 |  | 2800000 |  | 58867934 |  | 54835207.32 |  | 0 |  |  | 54835207 |  |  | 0 |  |  | 0 | LA | OE
EPO | RU8330 | 18456 | Fluor Enterprises, Inc. | 052-17854 | P-Fluor Enterprises-052-17854-GASOLINE BOOSTER PUMPS - SANTA CLARA | 20049 | POC | USD | 373306 | 373306 | 2017-12-21 | 2018-09-03 |  | 373306 |  | 5590023 |  | 0 |  | 3860577 | [5 empty] | 0 |  |  | 0 | US | OE
EPO | RU8330 | 18517 | CB&I_ | 052-41753 | P-CB&I_191058E-PO-110110-03_052-41753_17HE0576-616 (41) API 610 Overhung Pumps | 20031 | POC | USD | 2188294 | 2188294 | 2017-12-30 | 2018-11-13 |  | 2188294 |  | 31628584 |  | 0 |  | 14719843 | [5 empty] | 0 |  |  | 0 | US | OE
EPO | RU8330 | 18636 | Hanwha Total Petrochemil CO., LTD. (HTC) | 330-41755 | P-Hanwha Total Petrochemil_4500244663_330-41755_17LW0647-17LW0648-330-41755-Reactor Circulation Pumps | 19048 | POC | USD | 5950000 | 5322436 | 2018-01-08 | 2019-04-30 |  | 5322436 |  | 53460134 |  | 1815513 |  | 4938279 | [5 empty] | 0 |  |  | 0 | ASIA | OE
EPO | RU8330 | 18636 | Hanwha Total Petrochemil CO., LTD. (HTC) | 330-41755 | P-Hanwha Total Petrochemil_4500244663_330-41755_17LW0647-17LW0648-330-41755-Two Years Spares | 19049 | POC | USD |  | 627564 | 2018-01-08 | 2019-04-30 |  | 627564 |  | 7263687 |  | 0 |  | 0 | [8 empty] | 0 | ASIA | OE
EPO | RU8330 | 18637 | SINOPEC USA Inc. | 222-41752 | P-Sinopec USA_17MXUSY25SPECUS12023_222-41752_17LW0549-0551 | 20306 | POC | USD | 1216487 | 1216487 | 2017-12-21 | 2019-01-08 |  | 1216487 |  | 17546973 |  | 4649 |  | 981417 |  |  |  |  | 121649 | 2276357.4987 | 2018-05-08 | SCF28372 | 0 | US | OE
EPO | RU8330 | 18644 | Jacobs Engineering Group | 052-17852 | P-Jacobs Engineering Group Inc_58FF25C6-BB141698_052-17852_17HE0554-0559 | 19256 | POC | USD | 551126.16 | 530714.08 | 2017-12-13 | 2018-08-03 |  | 551126.16 |  | 7432736 |  | 0 |  | 4109814 | [5 empty] | 0 |  |  | 0 | US | OE
EPO | RU8330 | 19805 | ICA FLUOR DANIEL S DE RL DE CV | 291-15365 | P-ICA FLUOR DANIEL_ART-03-300-H-2602_291-15365_15ME0414-415 | 20198 | POC | USD | 258869.08 | 258869.08 | 2015-08-31 | 2018-01-01 |  | 258869.08 |  | 3523095 |  | 421320 |  | 1257760 | [5 empty] | 0 |  |  | 0 | LA | OE
EPO | RU8330 | 19897 | TREUNIDAS MEXICO INGENIERIA Y CONSTRUCCION S. DE R.L. DE C.V. | 291-16407 | P-TREUNIDAS MEXICO INGENIERIA Y CONSTRUCCION_0228105090_291-16407_16ME0287-0293-291-16407-CENTRIFUGAL PUMPS OH2 (U-25000) | 19953 | POC | USD | 314504.29 | 314504.29 | 2016-08-08 | 2018-01-01 |  | 314504.29 |  | 5126732 |  | 138043 |  | 0 | [5 empty] | 0 |  |  | 0 | LA | OE
EPO | RU8330 | 20466 | CB&I LLC | 050-36199 | P-CB&I LLC_155426-PO-110112-01_050-36199_16PE0371/72 | 20508 | POC | USD | 664657 | 664657 | 2016-11-04 | 2018-02-15 |  | 664657 | [7 empty] | 2018-02-13 |  |  |  | 0 |  |  | 0 | US | OE
EPO | RU8330 | 21785 | Sinopec USA Inc. | 222-41801 | P-Sinopec USA _17MXUSY26SPECUS12034_222-41801_18LW0006-007 | 22213 | POC | USD | 6400000 | 6400000 | 2018-01-31 | 2019-03-15 |  | 6400000 |  | 65854040 |  | 1077016 |  | 658989 | [5 empty] | 0 |  |  | 0 | CHINA | OE
EPO | RU8330 | 23250 | Hongkong Wisdom Universal Technology Co. Limited | 222-41808 | P-Hongkong Wisdom_WUT-20180206FS_222-41808_18LW0044 | 23345 | POC | USD | 1871720 | 471980 | 2018-02-13 | 2019-04-12 |  | 471980 |  | 5680695 |  | 733044 |  | 0 | [5 empty] | 0 |  |  | 0 | CHINA | OE
EPO | RU8330 | 23250 | Hongkong Wisdom Universal Technology Co. Limited | 222-41808 | P-Hongkong Wisdom_WUT-20180206FS_222-41808_18LW0045 | 23346 | POC | USD |  | 1399740 | 2018-02-13 | 2019-04-12 |  | 1399740 |  | 16847103 |  | 517427 |  | 0 | [8 empty] | 0 | CHINA | OE
EPO | RU8330 | 23668 | JG Summit Petrochemical Corporation | 10003330 | P-JG Summit Petrochemical Corporation _3500003056_10003330_18LW0060-0061 | 23701 | POC | USD | 5800000 | 5800000 | 2018-03-07 | 2019-08-14 |  | 5800000 |  | 52923853 |  | 1225239 |  | 471177 | [5 empty] | 0 |  |  | 0 | ASIA | OE
EPO | RU8330 | 23732 | Westlake CA&O Corporation | 015-41811 | P-Westlake CA&O Corporation_4500909207_015-41811_18LW0062 | 23753 | POC | USD | 381460 | 381460 | 2018-03-26 | 2019-03-01 |  | 381460 |  | 3941264 |  | 1058296 |  | 0 | [5 empty] | 0 |  |  | 0 | US | OE
EPO | RU8330 | 23760 | Hengli Petrochemical (Dalian) Chemical Co., Ltd. | 222-18024 | P-Hengli Petrochemical (Dalian) Chemical_18HCF-FS0302-142-0006_222-18024_18LW0064 | 23803 | POC | USD | 1272150 | 250530 | 2018-03-13 | 2018-04-02 |  | 250530 |  | 3715726 |  | 173251 |  | 0 | [5 empty] | 0 |  |  | 0 | CHINA | OE
EPO | RU8330 | 23760 | Hengli Petrochemical (Dalian) Chemical Co., Ltd. | 222-18024 | P-Hengli Petrochemical (Dalian) Chemical_18HCF-FS0302-142-0006_222-18024_18LW0065-0066-0067 | 23804 | POC | USD |  | 1021620 | 2018-03-13 | 2018-04-02 |  | 1021620 |  | 15152116 |  | 394408 |  | 0 | [8 empty] | 0 | CHINA | OE
EPO | RU8330 | 23810 | Sinopec USA | 222-41810 | P-Sinopec USA_18MXUSY26SPECUS12008_222-41810_18LW0067:Pump+Spare Parts | 23815 | POC | USD | 434000 | 434000 | 2018-03-27 | 2019-04-22 |  | 434000 |  | 6410780 |  | 466411 |  | 0 | [5 empty] | 0 |  |  | 0 | CHINA | OE
EPO | RU8330 | 23942 | Lion Oil Company | 052-18815 | P-Lion Oil Company_81734_052-18815_18HE0077-0078-0079 | 23964 | POC | USD | 262272 | 262272 | 2018-03-16 | 2018-11-19 |  | 262272 |  | 4265940 |  | 1253 |  | 0 | [5 empty] | 0 |  |  | 0 | US | OE
EPO | RU8330 | 26448 | Eagle Natrium LLC An Axiall Company | 034-41816 | P-Eagle Natrium LLC An Axiall Company_4500917397_034-41816_18LW0088-0089 | 26451 | POC | USD | 398000 | 398000 | 2018-04-20 | 2019-05-29 |  | 398000 |  | 3255217 |  | 78384 |  | 0 | [5 empty] | 0 |  |  | 0 | US | OE
EPO | RU8330 | 27262 | S&B Engineers and Constructors LTD | 052-18825 | P-S&B Engineers and Constructors_E1124-M0006_052-18825_18HE0141-142 | 27289 | POC | USD | 452206 | 183504 | 2018-04-30 | 2018-12-06 |  | 183504 |  | 2872509 |  | 0 |  | 0 | [5 empty] | 0 |  |  | 0 | US | OE
EPO | RU8330 | 27262 | S&B Engineers and Constructors LTD | 052-18825 | P-S&B Engineers and Constructors_E1124-M0006_052-18825_18HE0143-144 | 27290 | POC | USD |  | 174218 | 2018-04-30 | 2018-12-06 |  | 174218 |  | 2727149 |  | 0 |  | 0 | [8 empty] | 0 | US | OE
EPO | RU8330 | 27262 | S&B Engineers and Constructors LTD | 052-18825 | P-S&B Engineers and Constructors_E1124-M0006_052-18825_18HE0145-146 | 27291 | POC | USD |  | 94484 | 2018-04-30 | 2018-12-06 |  | 94484 |  | 1479020 |  | 0 |  | 0 | [8 empty] | 0 | US | OE
EPO | RU8330 | 27331 | Phillips 66 Company | 052-18804 | P-Phillips 66_4524817118_052-18804_18HE0032-033 | 27358 | POC | USD | 646726 | 646726 | 2018-04-27 | 2018-11-15 |  | 646726 |  | 8823252 |  | 21533 |  | 0 | [5 empty] | 0 |  |  | 0 | US | OE
IPO | RU8333 | 17248 | ICA Fluor Daniel S. de R.L. de C.V. | 15MIG0001-0003 | P-ICA FLUOR DANIEL_MA-220-3-H-PO-2602_15MIG0001-0003 | 20185 | POC | USD | 960522 | 960522 | 2015-03-23 | 2018-01-01 |  | 960522 |  | 16041475 |  | 13477257 |  | 0 | [5 empty] | 0 |  |  | 0 | LA | OE
AMSS | RU8341 | 19390 | Sulzer Pumps Mexico SA de CV | 176571 | P-SULZER PUMPS MEXICO SA de CV-176571-Tier III Gasoline Project_176571_171PR176571 | 20668 | POC | USD | 250348 | 250348 | 2017-12-15 | 2018-04-09 |  | 250348 |  |  |  | 5696.02 | [7 empty] | 0 |  |  | 0 | LA | OE
AMSS | RU8355 | 8579 | Saudi Arabian Oil Company | DAM-1001849 | P- C4C Saudi Arabian Oil - 1001849/6510761080 DGS Ethane Machines | 10295 | PIT | SAR | 9337498.8328 | 1750000 | 2016-01-27 | 2018-02-09 |  | 6562499.1797 | 0 | [6 empty] | 2016-12-31 | [6 empty] | 0 | EUROPE | AM
AMSS | RU8355 | 8579 | Saudi Arabian Oil Company | DAM-1001849 | P - C4C Saudi Arabian Oil - 1001849/6510761080 Junction Box2 | 10298 | POC | SAR |  | 640000 | 2016-01-27 | 2018-02-09 |  | 2399999.7 | 0 | 2795528 |  | 2199323.34 | 0 | 0 | [8 empty] | 0 | EUROPE | AM
AMSS | RU8355 | 8579 | Saudi Arabian Oil Company | DAM-1001849 | P - C4C Saudi Arabian Oil - 1001849/6510761080 Site Installation2 | 10299 | PIT | SAR |  | 100000 | 2016-01-27 | 2018-02-09 |  | 374999.9531 | 0 | 375000 |  | 0 | 0 | 0 | [8 empty] | 0 | EUROPE | AM
AMSS | RU8355 | 24185 | SABIC AR-RAZI | DAM-1009676 | P - SABIC AR-RAZI - 1009676/4300172138- Repair Service for DRY GAS SEAL | 26187 | POC | USD | 373334 | 373334 | 2018-03-01 | 2018-12-31 |  | 373334 | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | EUROPE | AM
FCO | RU8356 | 5223 | Petrofac Sadui Arabia Limited | 5604718 | P-Petrofac International Limited-5604718-60" - Butterfly Valves (6-nos) | 5280 | POC | USD | 978306.16 | 576773.76 | 2017-01-12 | 2018-03-31 |  | 626927.76 | 50154 | 2658875 |  | 2281614 | 0 | 0 |  |  | 1324495.48 |  | 410405 / 410584 | #VALUE! | 2018-05-30 | 482724 | 0 | MIDEAST | OE
FCO | RU8356 | 5223 | Petrofac Sadui Arabia Limited | 5604718 | P-Petrofac International Limited-5604718-42" - Butterfly Valves (6-nos) | 5281 | POC | USD |  | 311438.4 | 2017-01-12 | 2018-03-31 |  | 338520.4 | 27082 | 1658401 |  | 1370356 | 0 | 0 |  |  | 840844 | [5 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 5223 | Petrofac Sadui Arabia Limited | 5604718 | P-Petrofac International Limited-5604718-16" - Butterfly Valves (12-nos) | 5282 | POC | USD |  | 112200 | 2017-01-12 | 2018-03-31 |  |  | 11220 | 533834 |  | 533834 | 0 | 0 |  | 2018-02-06 | 533834 | [5 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 5223 | Petrofac Sadui Arabia Limited | 5604718 | P-Petrofac International Limited-5604718-Spares Parts | 5283 | PIT | USD |  | 12858 | 2017-01-12 | 2018-03-31 |  | 12858 | 0 | 9223 |  | 9223 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-Mark 100 Globe 14.00 in | 12882 | POC | USD | 2690000 | 74032 | 2017-08-30 | 2018-08-31 |  | 74032 | 0 | 444698 |  | 55442 | 0 | 0 | [5 empty] | 0 |  |  | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-Mark 100 Globe 16.00 in | 12883 | POC | USD |  | 52186 | 2017-08-30 | 2018-08-31 |  | 52186 | 0 | 247244 |  | 141913 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-Mark 100 Globe 30.00 in | 12884 | POC | USD |  | 89340 | 2017-08-30 | 2018-08-31 |  | 89340 | 0 | 418869 |  | 14001 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-Mark One Globe 1.00 in | 12885 | POC | USD |  | 43423 | 2017-08-30 | 2018-08-31 |  | 43423 | 0 | 336211 |  | 181407 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-Mark One Globe 1.50 in | 12886 | POC | USD |  | 7221 | 2017-08-30 | 2018-08-31 |  | 7221 | 0 | 63875 |  | 29928 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-Mark One Globe 10.00 in | 12887 | POC | USD |  | 82504 | 2017-08-30 | 2018-08-31 |  | 82504 | 0 | 269948 |  | 0 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-Mark One Globe 12.00 in | 12888 | POC | USD |  | 410721 | 2017-08-30 | 2018-08-31 |  | 410721 | 0 | 1514756 |  | 381604 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-Mark One Globe 16.00 in | 12889 | POC | USD |  | 52656 | 2017-08-30 | 2018-08-31 |  | 52656 | 0 | 239159 |  | 22224 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-Mark One Globe 2.00 in | 12890 | POC | USD |  | 29785 | 2017-08-30 | 2018-08-31 |  | 29785 | 0 | 266362 |  | 138875 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-Mark One Globe 24.00 in | 12891 | POC | USD |  | 197240 | 2017-08-30 | 2018-08-31 |  | 197240 | 0 | 645345 |  | 7043 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-Mark One Globe 3.00 in | 12892 | POC | USD |  | 7546 | 2017-08-30 | 2018-08-31 |  | 7546 | 0 | 54694 |  | 23516 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-Mark One Globe 4.00 in | 12893 | POC | USD |  | 31300 | 2017-08-30 | 2018-08-31 |  | 31300 | 0 | 180094 |  | 95043 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-Mark One Globe 6.00 in | 12894 | POC | USD |  | 95866 | 2017-08-30 | 2018-08-31 |  | 95866 | 0 | 686691 |  | 325183 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-Mark One Globe 8.00 in | 12895 | POC | USD |  | 41070 | 2017-08-30 | 2018-08-31 |  | 41070 | 0 | 232303 |  | 175259 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-Mark One-X Expand-Outlet 8x6 in | 12896 | POC | USD |  | 6630 | 2017-08-30 | 2018-08-31 |  | 6630 | 0 | 35005 |  | 20268 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-Pressure Regulating Valve (PRV) 1.00 in CL 300 | 12897 | POC | USD |  | 10557 | 2017-08-30 | 2018-08-31 |  | 10557 | 0 | 66169 |  | 9325 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-Pressure Regulating Valve (PRV) 1.00 in CL 600 | 12898 | POC | USD |  | 15699 | 2017-08-30 | 2018-08-31 |  | 15699 | 0 | 136948 |  | 0 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-ShearStream HP Segmented Ball 6.00 in | 12899 | POC | USD |  | 14168 | 2017-08-30 | 2018-08-31 |  | 14168 | 0 | 46358 |  | 0 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-TMCBV Full Port Ball Valve 12.00 in | 12900 | POC | USD |  | 180020 | 2017-08-30 | 2018-08-31 |  | 180020 | 0 | 589005 |  | 143135 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-TMCBV Full Port Ball Valve 16.00 in | 12901 | POC | USD |  | 78430 | 2017-08-30 | 2018-08-31 |  | 78430 | 0 | 256613 |  | 62357 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-TMCBV Full Port Ball Valve 18.00 in | 12902 | POC | USD |  | 84066 | 2017-08-30 | 2018-08-31 |  | 84066 | 0 | 275055 |  | 66838 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-TMCBV Full Port Ball Valve 20.00 in | 12903 | POC | USD |  | 174696 | 2017-08-30 | 2018-08-31 |  | 174696 | 0 | 571583 |  | 138896 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-TMCBV Full Port Ball Valve 8.00 in | 12904 | POC | USD |  | 70949 | 2017-08-30 | 2018-08-31 |  | 70949 | 0 | 232133 |  | 39369 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-TMCBV Reduced Port Ball Valve 20x18 in | 12905 | POC | USD |  | 86262 | 2017-08-30 | 2018-08-31 |  | 86262 | 0 | 282240 |  | 68584 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-TMCBV Reduced Port Ball Valve 8x6 in | 12906 | POC | USD |  | 47768 | 2017-08-30 | 2018-08-31 |  | 47768 | 0 | 156293 |  | 38756 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-Valdisk Double Flanged(Short Pattern) 20.00 in | 12907 | POC | USD |  | 21533 | 2017-08-30 | 2018-08-31 |  | 21533 | 0 | 89226 |  | 56877 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-Valdisk TX3 Double Flanged(Short Pattern) 12.00 in | 12908 | POC | USD |  | 56998 | 2017-08-30 | 2018-08-31 |  | 56998 | 0 | 285504 |  | 1082 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-Valdisk TX3 Double Flanged(Short Pattern) 16.00 in | 12909 | POC | USD |  | 194658 | 2017-08-30 | 2018-08-31 |  | 194658 | 0 | 682655 |  | 0 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-Valdisk TX3 Double Flanged(Short Pattern) 18.00 in | 12910 | POC | USD |  | 138560 | 2017-08-30 | 2018-08-31 |  | 138560 | 0 | 714708 |  | 0 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-Valdisk TX3 Double Flanged(Short Pattern) 24.00 in | 12911 | POC | USD |  | 282172 | 2017-08-30 | 2018-08-31 |  | 282172 | 0 | 923231 |  | 0 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 9403 | HYUNDAI ENGINEERING & CONSTRUCTION LTD | 5605692 | P-HYUNDAI ENGINEERING & CONSTRUCTION LTD-5605692-COMMISSIONING SPARES | 12912 | PIT | USD |  | 11944 | 2017-08-30 | 2018-08-31 |  | 11944 | 0 | 28463 |  | 0 | 0 | 0 | [8 empty] | 0 | MIDEAST | OE
FCO | RU8356 | 15520 | SAUDI ARABIAN OIL COMPANY-SAOC | 5606235 | P - Saudi Aramco - 5606235-Ctl Valves - 4" - 20" CL 300 Mark Ones (25-nos) | 18306 | POC | USD | 903465 | 903465 | 2017-11-29 | 2018-08-31 |  | 903465 | 0 | 2642636 |  | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | MIDEAST | OE
FCO | RU8356 | 15522 | M.R. AL KHATLAN | 5604421 | P-M.R. AL KHATLAN-5604421-CAST STEEL PLUG VALVES | 17908 | POC | USD | 0 | 270882 | 2016-10-16 | 2018-02-28 |  |  | 0 | 901985 |  | 901985 | 0 | 0 |  | 2018-03-29 | 901985 |  |  | 0 |  |  | 0 | MIDEAST | OE
FCO | RU8356 | 15530 | Saudi Aramco | 5604303 | P - Saudi Aramco - 5604303-Mark One Valves | 17834 | POC | USD | 0 | 277470 | 2016-09-04 | 2018-02-28 |  |  | 0 | 1095036 |  | 1095036 | 0 | 0 |  | 2018-03-29 | 1095036 |  |  | 0 |  |  | 0 | MIDEAST | OE
FCO | RU8356 | 18934 | Snamprogetti Saudi Arabia Co. Ltd. | 5604461 | P - Snamprogetti Saudi Arabia Co. Ltd - 5604461 | 20234 | POC | USD | 0 | 466016.08 | 2016-10-20 | 2018-01-31 |  |  | 11852 | 1306740 |  | 1306740 | 0 | 0 |  | 2017-12-31 | 1306740 |  |  | 0 |  |  | 0 | MIDEAST | OE
FCO | RU8356 | 18934 | Snamprogetti Saudi Arabia Co. Ltd. | 5604461 | P - Snamprogetti Saudi Arabia Co. Ltd - 5604461 - Remaining items (delivery 2018) | 20383 | POC | USD |  | 262990.92 | 2016-10-20 | 2018-01-31 |  |  | 13584 | 1186963 |  | 1186963 | 0 | 0 |  | 2018-01-31 | 1186963 | [5 empty] | 0 |  | OE
FCO | RU8356 | 19152 | Snamprogetti Saudi Arabia Co. Ltd. | 5604910 | P-Snamprogetti Saudi Arabia Co. Ltd. - 5604910-5604910-Rotating Control Valves | 20375 | POC | USD | 0 | 493833 | 2017-01-30 | 2018-01-31 |  |  | 0 | 1326611 |  | 1326611 | 0 | 0 |  | 2017-11-27 | 1326611 |  |  | 0 |  |  | 0 | MIDEAST | OE
FCO | RU8356 | 19152 | Snamprogetti Saudi Arabia Co. Ltd. | 5604910 | P-Snamprogetti Saudi Arabia Co. Ltd. - 5604910-5604910-Backlog items | 20376 | POC | USD |  | 60749 | 2017-01-30 | 2018-01-31 |  |  | 4277 | 154838 |  | 154838 | 0 | 0 |  | 2018-03-25 | 154838 | [5 empty] | 0 |  | OE
FCO | RU8357 | 8582 | PetroChina International FZE Iraq Branch | 5805075 | P-PetroChina Internation FZE Iraq Branch-5805075-Control Valves spares training & commissioning | 22518 | POC | USD | 7300339 | 1360086 | 2017-04-17 | 2018-03-31 |  | 1360086 | 0 | 4914905 |  | 4453241 |  |  |  | 2018-05-10 |  |  | 1360086 | May/10/2018 | 2018-05-10 | 180608 | 0 | IRAQ | OE
FCO | RU8357 | 8582 | PetroChina International FZE Iraq Branch | 5805075 | P-PetroChina Internation FZE Iraq Branch-5805075-Shutdown Valves spares training & commissioning | 22519 | POC | USD |  | 4403657 | 2017-04-17 | 2018-03-31 |  | 4403657 | 0 | 15913372 |  | 14418608 |  |  |  |  | 10328535 |  | 3007504 |  | 2018-05-31 | 180608 /180711/180718 | 0 | IRAQ | OE
FCO | RU8357 | 8582 | PetroChina International FZE Iraq Branch | 5805075 | P-PetroChina Internation FZE Iraq Branch-5805075-ON-Off Valves spares training & commissioning | 22520 | POC | USD |  | 1226010 | 2017-04-17 | 2018-03-31 |  | 1226010 | 0 | 4430398 |  | 4014245 | [10 empty] | 0 | IRAQ | OE
FCO | RU8357 | 8582 | PetroChina International FZE Iraq Branch | 5805075 | P-PetroChina Internation FZE Iraq Branch-5805075-Site Training Start-up_Commissioning Site Service | 22521 | PIT | USD |  | 252000 | 2017-04-17 | 2018-03-31 |  | 252000 | 0 | 740275 |  | 0 | [10 empty] | 0 | IRAQ | OE
FCO | RU8357 | 8582 | PetroChina International FZE Iraq Branch | 5805075 | P-PetroChina Internation FZE Iraq Branch-5805075-Volume Tank 5 Cycle Operation - 8 Tanks | 22522 | PIT | USD |  | 41536 | 2017-04-17 | 2018-03-31 |  | 41536 | 0 | 122016 |  | 0 | [10 empty] | 0 | IRAQ | OE
FCO | RU8357 | 8582 | PetroChina International FZE Iraq Branch | 5805075 | P-PetroChina Internation FZE Iraq Branch-5805075-Volume Tank 2 valve stroke - 5 Tanks | 22523 | PIT | USD |  | 17050 | 2017-04-17 | 2018-03-31 |  | 17050 | 0 | 50086 |  | 0 | [10 empty] | 0 | IRAQ | OE
FCO | RU8357 | 8662 | Abener Energia S.A | 5805316 | P-Abener Energia S.A.-5805316 Various Valves | 12588 | POC | USD | 459000 | 459000 | 2017-07-23 | 2018-02-07 |  | 459000 | 0 | 1321506 |  | 1131580 |  |  |  |  | 965646 |  |  | 0 |  |  | 0 | MIDEAST | OE
FCO | RU8357 | 9042 | Emirates Global Aluminium | 5804358 | P - Emirates Global Aluminium Co 5804358 HP Steam Valve System Initial PO + (6) 2017 Change Orders | 13066 | POC | USD | 4820990 | 4820990 | 2017-07-06 | 2018-01-31 |  | 3571356 | 0 | 9924235 |  | 9924235 |  |  |  | 2017-12-31 |  |  |  | 0 |  |  | 0 | MIDEAST | OE
FCO | RU8357 | 9042 | Emirates Global Aluminium | 5804358 | P-Emirates Aluminium-5804358 2018 delivery | 13068 | POC | USD |  | 1249634 | 2017-07-06 | 2018-01-31 |  | 1249634 |  | 3544599 |  | 3544599 |  |  |  | 2018-01-13 | [6 empty] | 0 | MIDEAST | OE
FCO | RU8357 | 9075 | Emirates Global Aluminium | 5803308 | P-Emirates Global Aluminium PJSA (EGA)-5803308 - 2017 delivery | 13074 | POC | AED | 16197480.2677 | 3551292 | 2015-10-28 | 2018-03-31 |  | 13041836 |  | 9293937 |  | 9293937 |  |  |  | 2017-12-31 | [6 empty] | 0 | MIDEAST | OE
FCO | RU8357 | 9075 | Emirates Global Aluminium | 5803308 | P-Emirates Global Aluminium PJSA (EGA)-5803308 - first quarter 2018 delivery | 13075 | POC | AED |  | 683573 | 2015-10-28 | 2018-03-31 |  | 2510367 |  | 1441234 |  | 1276685 |  |  |  | 2018-05-21 |  |  | 428367 | May/21/2018 | 2018-05-21 | 180657 | 0 | MIDEAST | OE
FCO | RU8357 | 9075 | Emirates Global Aluminium | 5803308 | P - Emirates Global Aluminium PJSA (EGA) - 5803308 - Control Valves ordered in 2017 | 13076 | POC | AED |  | 4410574 | 2015-10-28 | 2018-03-31 |  | 645277.2677 | 0 | 397692 |  | 352287 |  |  |  |  | 255827 |  | 376217 |  | 2018-05-21 | 180658 | 0 | MIDEAST | OE
FCO | RU8357 | 14954 | Emirates Global Aluminium Company Limited PJSC | 5805179 | P-Emirates Global Aluminium Company Limited PJSC-5805179-Steam System Motorized Valves | 20396 | POC | USD | 2549100 | 1085020 | 2017-05-07 | 2018-05-31 |  | 1085020 | 0 | 2667426 |  | 2667426 |  |  |  | 2017-12-31 |  |  |  | 0 |  |  | 0 | MIDEAST | OE
FCO | RU8357 | 14954 | Emirates Global Aluminium Company Limited PJSC | 5805179 | P-Emirates Global Aluminium Company Limited PJSC-5805179-three addional motorized valves | 20398 | POC | USD |  | 1464080 | 2017-05-07 | 2018-05-31 |  | 1464080 | 0 | 4558895 |  | 2170199 |  |  |  | 2018-01-13 | 3672797 |  | 8120 |  | 2018-05-24 | 180673 | 0 | MIDEAST | OE
FCO | RU8357 | 15653 | Abener Energia S.A | 5804965 | P - Abener Energia S.A.-5804965-HTF Control Valves Pre2018 | 16087 | POC | USD | 1096738 | 740154 | 2017-03-31 | 2018-01-31 |  | 740154 | 0 | 2711651 |  | 2711651 |  |  |  | 2017-12-31 |  |  |  | 0 |  |  | 0 | MIDEAST | OE
FCO | RU8357 | 15653 | Abener Energia S.A | 5804965 | P - Abener Energia S.A.-5804965-HTF Control Valves 2018 | 20367 | POC | USD |  | 356584 | 2017-03-31 | 2018-01-31 |  | 356584 | 0 | 1253470 |  | 940219 |  |  |  |  | 324300 | [5 empty] | 0 | MIDEAST | OE
FCO | RU8357 | 16617 | Abener Energia S.A | 5804614 | P - Abener Energia S.A - 5804614 - Ship pre2018 | 17928 | POC | USD | 377520 | 238541 | 2016-10-24 | 2018-04-15 |  | 238541 | 0 | 558169 |  | 558169 |  |  |  | 2017-12-31 |  |  |  | 0 |  |  | 0 | MIDEAST | OE
FCO | RU8357 | 16617 | Abener Energia S.A | 5804614 | P - Abener Energia S.A - 5804614 - Ship 2018 | 20223 | POC | USD |  | 138979 | 2016-10-24 | 2018-04-15 |  | 138979 | 0 | 209391 |  | 209391 |  |  |  | 2018-04-29 | [6 empty] | 0 | MIDEAST | OE
FCO | RU8357 | 17126 | PetroChina International FZE Iraq Branch | 5804818 | P- PetroChina International FZE Iraq Branch- 5804818-Valves with various sizes Batch 1 | 21912 | POC | USD | 1524628 | 1000999.5 | 2017-02-19 | 2018-02-20 |  | 1001000 | 0 | 3349098 |  | 3349098 |  |  |  | 2017-12-31 |  |  |  | 0 |  |  | 0 | IRAQ | OE
FCO | RU8357 | 17126 | PetroChina International FZE Iraq Branch | 5804818 | P- PetroChina International FZE Iraq Branch- 5804818-Valves with various sizes Batch 2 | 21913 | POC | USD |  | 343627.5 | 2017-02-19 | 2018-02-20 |  | 343628 | 0 | 846488 |  | 846488 |  |  |  | 2018-05-22 |  |  | 343628 |  | 2018-05-22 | 180665 | 0 | IRAQ | OE
FCO | RU8357 | 17126 | PetroChina International FZE Iraq Branch | 5804818 | P- PetroChina International FZE Iraq Branch- 5804818-Startup and commissioning site service | 21914 | PIT | USD |  | 90000 | 2017-02-19 | 2018-02-20 |  | 90000 | 0 | 66096 |  | 0 | [10 empty] | 0 | IRAQ | OE
FCO | RU8357 | 17126 | PetroChina International FZE Iraq Branch | 5804818 | P- PetroChina International FZE Iraq Branch- 5804818-Site training | 21915 | PIT | USD |  | 90000 | 2017-02-19 | 2018-02-20 |  | 90000 | 0 | 66096 |  | 0 | [10 empty] | 0 | IRAQ | OE
FCO | RU8357 | 27613 | CB & I Nederland B.V | 5805777 | P-CB&I Nederland B.V.-5805777-Motor Operated Valves | 27791 | POC | USD | 381500 | 381500 | 2018-04-12 | 2019-01-15 |  | 381500 | 0 | 1269699 |  | 0 | [7 empty] | 0 |  |  | 0 | MIDEAST | OE
AMSS | RU8358 | 4887 | Saudi Arabian Oil Company | 1003962 | P-ARAMCO-1003962-6510820237 | 13787 | POC | SAR | 4093798.2752 | 1091816 | 2017-04-12 | 2018-04-04 |  | 4093798.2752 | 0 | 3807232 |  | 21678 | [10 empty] | 0 | MIDEAST | AM
AMSS | RU8358 | 4897 | SAUDI ARAMCO | 1003892 | P-SAUDI ARAMCO ALK0003631-Centrifugal Pumps | 15595 | POC | USD | 251400 | 251400 | 2017-03-30 | 2018-04-11 |  | 251400 | 0 | 681226 | [5 empty] | 2018-04-29 |  |  |  | 0 |  |  | 0 | MIDEAST
AMSS | RU8358 | 4902 | Saudi Arabian Oil Company | 1003875 | P-ARAMCO-1003875-4505290030 | 10365 | POC | USD | 333000 | 333000 | 2017-03-22 | 2018-04-19 |  | 333000 | 0 | 784026 | [5 empty] | 2018-04-29 |  |  |  | 0 |  |  | 0 | MIDEAST | AM
AMSS | RU8358 | 5264 | Saudi Aramco Oil Company | 1004157 | P-ARAMCO-ALK0003891 | 5395 | POC | USD | 346324 | 346324 | 2017-07-27 | 2018-09-10 |  | 346324 | 0 | 1038972 |  | 64409 | [7 empty] | 0 |  |  | 0 | MIDEAST | OE
AMSS | RU8358 | 9140 | Saudi Arabian Oil Company | 1003337 | P-ARAMCO-ALK0003096 | 10579 | POC | USD | 0 | 246560 | 2016-09-19 | 2018-02-15 | [13 empty] | 0 |  |  | 0 | MIDEAST
AMSS | RU8358 | 9140 | Saudi Arabian Oil Company | 1003337 | P-ARAMCO-ALK0003096 | 20564 | POC | USD |  | 246560 | 2016-09-19 | 2018-02-15 | [16 empty] | 0
AMSS | RU8358 | 10580 | Saudi Aramco Oil Company | 1003959 | P-ARAMCO/10003959/4505323250 | 10585 | POC | USD | 295999 | 295999 | 2017-05-01 | 2018-04-03 |  | 295999 | 0 | 1043396 |  | 230235 | [7 empty] | 0 |  |  | 0 | MIDEAST | OE
AMSS | RU8358 | 10701 | SAUDI ARABIAN OIL COMPANY | 1003157 | P-ARAMCO-1003157-4505066925 | 13848 | POC | USD | 308503 | 308503 | 2017-10-17 | 2018-06-27 |  | 308503 | 0 | 1041198 |  | 622200 | [7 empty] | 0 |  |  | 0 | MIDEAST | OE
AMSS | RU8358 | 12926 | Saudi Arabian Oil Company | 1002648 | P-ARAMCO-1002648-4504838475 | 12931 | POC | USD | 556292 | 556292 | 2015-10-15 | 2018-09-20 |  | 556292 | 0 | 2864839 |  | 1833485 | [7 empty] | 0 |  |  | 0 | MIDEAST | AM
AMSS | RU8358 | 12943 | Saudi Arabian Oil Company | 1002755 | P-ARAMCO-1002755-4504895480 | 12950 | POC | USD | 0 | 353118 | 2015-12-10 | 2018-02-20 |  |  | 0 | [10 empty] | 0 |  |  | 0 | MIDEAST | AM
AMSS | RU8358 | 12953 | Saudi Arabian Oil Company | 1003976 | P-ARAMCO-1003976-4505324374 | 12958 | POC | USD | 451725 | 451725 | 2017-05-30 | 2018-07-11 |  | 451725 | 0 | 1558365 |  | 1485601 | [7 empty] | 0 |  |  | 0 | MIDEAST | AM
AMSS | RU8358 | 12998 | Saudi Arabian Oil Company | 1004289 | P-ARAMCO-1004289-4505422785 | 13003 | POC | USD | 2257331 | 601955 | 2017-09-18 | 2018-11-02 |  | 2257331 | 0 | 2076745 |  | 15075 | [7 empty] | 0 |  |  | 0 | MIDEAST | AM
AMSS | RU8358 | 13007 | Saudi Arabian Oil Company | 1004290 | P-ARAMCO-1004290-4505424079 | 13012 | POC | USD | 257100 | 85700 | 2017-09-20 | 2018-07-12 |  | 85700 | 0 | 289238 |  | 27237 | [7 empty] | 0 |  |  | 0 | MIDEAST | AM
AMSS | RU8358 | 13007 | Saudi Arabian Oil Company | 1004290 | P-ARAMCO-1004290-4505424079 | 20518 | POC | USD |  | 85700 | 2017-09-20 | 2018-07-12 |  | 85700 | 0 | 289238 | [12 empty] | 0
AMSS | RU8358 | 13007 | Saudi Arabian Oil Company | 1004290 | P-ARAMCO-1004290-4505424079 | 20519 | POC | USD |  | 85700 | 2017-09-20 | 2018-07-12 |  | 85700 | 0 | 289238 | [12 empty] | 0
AMSS | RU8358 | 13036 | Saudi Arabian Oil Company | 1004120 | P-ARAMCO-1004120-4505373810 | 13042 | POC | USD | 366770 | 366270 | 2017-07-19 | 2018-07-04 |  | 366770 | 0 | 1098810 |  | 206076 | [7 empty] | 0 |  |  | 0 | MIDEAST | OE
AMSS | RU8358 | 13764 | SNAMPROGETTI SAUDI ARABIAN CO LTD | 1003367 | P-SAIPEM-1003367-1123118 (Order ALK0003126) | 15491 | POC | USD | 1146901 | 550800 | 2016-09-22 | 2018-06-06 |  | 550800 | 0 | 1962225 |  | 1349503 | [6 empty] | 2163290.25 | 8112337.4235 | 2018-05-30 | 407946/47/70/71 | 0 | MIDEAST | OE
AMSS | RU8358 | 13764 | SNAMPROGETTI SAUDI ARABIAN CO LTD | 1003367 | P-SAIPEM-1003367-1123118 (Order ALK0003126) | 15492 | POC | USD |  | 596101 | 2016-09-22 | 2018-06-06 |  | 596101 | 0 | 2123610 |  | 1349502 | [10 empty] | 0
AMSS | RU8358 | 13794 | Saudi Arabian Oil Company | 1003480 | P-ARAMCO-ALK0003237 | 13802 | POC | USD | 279940 | 279940 | 2016-11-06 | 2018-07-31 |  | 279940 | 0 | 860816 |  | 351708 | [7 empty] | 0 |  |  | 0 | MIDEAST | AM
AMSS | RU8358 | 14000 | eTEC E&C LIMITED | 1003879 | P-ETEC-ALK0003618 | 14006 | POC | USD | 675382 | 675382 | 2017-03-29 | 2018-07-31 |  | 675382 | 0 | 2279415 |  | 1491892 | [7 empty] | 0 |  |  | 0 | MIDEAST | AM
AMSS | RU8358 | 16190 | Saudi Aramco | 1001922 | P-ARAMCO-1001922-P-ARAMCO-ALK0001748 | 20553 | POC | USD | 942616 | 724636.63 | 2015-09-14 | 2018-02-28 |  | 724637 | 0 | 2798909 |  | 3784044 | [7 empty] | 0 |  |  | 0 | MIDEAST | OE
AMSS | RU8358 | 16190 | Saudi Aramco | 1001922 | P-ARAMCO-1001922-P-ARAMCO-ALK0001748 | 20554 | POC | USD |  | 217979.29 | 2015-09-14 | 2018-02-28 |  | 217979 | 0 | 874642 | [12 empty] | 0 | MIDEAST | OE
AMSS | RU8358 | 16348 | Saudi Aramco | 1003350 | P-ARAMCO-ALK0003109 | 20249 | POC | USD | 599457 | 599457 | 2016-09-19 | 2018-01-15 |  | 599457 | 0 | 2219454 |  | 2129910 | [7 empty] | 0 |  |  | 0 | MIDEAST | OE
AMSS | RU8358 | 20879 | TECNICAS REUNIDAS SAUDIA FOR SERVICES & CONTRACTING CO LTD (TRS) | 1004708 dated 27-Dec-2017 | P-TRS-ALK0004425-1 | 21042 | POC | USD | 4107838 | 4107837.7 | 2018-03-07 | 2019-02-20 |  | 4107838 | 0 | 15404393 |  | 46447 | [6 empty] | 18750 | 70312.4912 | 2018-05-30 | 407944 | 0 | MIDEAST | OE
AMSS | RU8358 | 22238 | TECNICAS REUNIDAS SAUDIA FOR SERVICES & CONTRACTING CO LTD (TRS) | 1004840 Dated 28.01.18 | P-TRS-ALK0004553 | 22240 | POC | USD | 2432218 | 2558613.18 | 2018-03-01 | 2019-03-10 |  | 2432218 |  | 8664777 |  | 56331 | [7 empty] | 0 |  |  | 0 | MIDEAST | OE
AMSS | RU8358 | 23382 | BR C.A.T INTERNATIONAL CO LTD | 1004950 Dated 27.02.18 | P-CAT INTERNATIONAL-ALK0004661 | 23400 | POC | SAR | 1279688 | 341250 | 2018-03-08 | 2019-01-20 |  | 1279688 |  | 1215703 |  | 5688 | [10 empty] | 0 | MIDEAST | OE
AMSS | RU8358 | 26316 | Saudi Arabian Oil Company | 1004295 | P-ARAMCO-ALK0004026-1004295-4505424080 | 26325 | POC | USD | 956554 | 255066 | 2017-09-20 | 2019-01-31 |  | 956554 |  | 860898 |  | 4570 | [7 empty] | 0 |  |  | 0 | MIDEAST | OE
AMSS | RU8358 | 28562 | Saudi Arabian Oil Company | 1005322 | P-Aramco-1005322-ALK0005040 | 28567 | POC | USD | 472500 | 472500 | 2018-05-23 | 2019-05-23 |  | 472500 |  | 1417500 |  | 5452 | [7 empty] | 0 |  |  | 0 | MIDEAST | OE
AMSS | RU8375 | 23268 | Grand Alpha | 715-I062-I5 | P - Grand Alpha - I062I5715 Feb18 | 23321 | POC | TWD | 9316899.9541 | 318578.35 | 2018-02-23 | 2018-07-06 |  | 9316899.9541 | 0 | 819739 |  | 294991 | 0 | 0 | [8 empty] | 0 | ASIA | AM
AMSS | RU8377 | 7809 | Korea Hydro & Nuclear Power Co., Ltd | 710-H065A-04 | P - KHNP - H065A-04 delivery on 15 Dec 2017 | 13511 | PIT | KRW | 385034996 | 44527.97 | 2017-07-13 | 2018-02-05 |  | 49802002 |  | 10442364 |  | 10442364 | 0 | 0 |  | 2017-12-04 | [6 empty] | 0 | ASIA | AM
AMSS | RU8377 | 7809 | Korea Hydro & Nuclear Power Co., Ltd | 710-H065A-04 | P - KHNP - H065A-04 delivery on 29 Dec 2017 | 13512 | PIT | KRW |  | 11326.45 | 2017-07-13 | 2018-02-05 |  | 12667990 |  | 290000 |  | 290000 | 0 | 0 |  | 2017-12-04 | [6 empty] | 0 | ASIA | AM
AMSS | RU8377 | 7809 | Korea Hydro & Nuclear Power Co., Ltd | 710-H065A-04 | P - KHNP - H065A-04 delivery on 05 Feb 2018 | 13513 | POC | KRW |  | 288405.37 | 2017-07-13 | 2018-02-05 |  | 322565004 |  | 131017466 |  | 131017466 | 0 | 0 |  | 2018-03-31 | [6 empty] | 11090324 | ASIA | AM
AMSS | RU8377 | 7815 | Korea Hydro & Nuclear power Co., Ltd | 720-H058-04 / 380-17049 | P - KHNP - H058-04 delivery on 29 Jun 2018 | 13090 | POC | KRW | 1657800000 | 1482238.98 | 2017-07-03 | 2018-06-29 |  | 1657800000 |  | 549047447 |  | 431137447 | 0 | 0 | [8 empty] | 24499507 | ASIA | AM
AMSS | RU8377 | 13751 | Korea Hydro & Nuclear power Co., Ltd | 720-H085-04 | P - KHNP - H085-04 delivery on 30 Aug 2018 | 13976 | POC | KRW | 616295997 | 545052.18 | 2017-09-13 | 2018-08-30 |  | 616295997 |  | 77384000 |  | 48704025 | 0 | 0 | [8 empty] | 9107823 | ASIA | AM
AMSS | RU8377 | 13755 | Korea Hydro & Nuclear power Co., Ltd | 720-H084-04 | P_KHNP - H084-04 delivery on 23 Feb 2018 | 13984 | POC | KRW | 871417887 | 167577.88 | 2017-08-29 | 2018-06-05 |  | 189481999 | 18948200 | 39744800 |  | 39444800 | 0 | 0 |  |  |  |  | 144409000 |  | 2018-05-11 | 2018051141000009a000014r (H084C) | 12878098 | ASIA | AM
AMSS | RU8377 | 13755 | Korea Hydro & Nuclear power Co., Ltd | 720-H084-04 | P_KHNP - H084-04 delivery on 16 Mar 2018 | 15028 | POC | KRW |  | 45208.76 | 2017-08-29 | 2018-06-05 |  | 51118001 | 2108618 | 8315073 |  | 8315073 | 0 | 0 |  | 2018-04-28 | [6 empty] | 0 | ASIA | AM
AMSS | RU8377 | 13755 | Korea Hydro & Nuclear power Co., Ltd | 720-H084-04 | P_KHNP - H084-04 delivery on 10 May 2018 | 15029 | POC | KRW |  | 127715.32 | 2017-08-29 | 2018-06-05 |  | 144409000 |  | 26576600 |  | 26576600 | 0 | 0 |  | 2018-05-11 | [6 empty] | 0 | ASIA | AM
AMSS | RU8377 | 13755 | Korea Hydro & Nuclear power Co., Ltd | 720-H084-04 | P_KHNP - H084-04 delivery on 05 Jun 2018 | 15030 | POC | KRW |  | 430180.02 | 2017-08-29 | 2018-06-05 |  | 486408887 |  | 58122091 |  | 48322091 | 0 | 0 | [8 empty] | 0 | ASIA | AM
AMSS | RU8377 | 13958 | Korea Hydro & Nuclear power Co., Ltd | 710-H082-04 | P - KHNP - H082-04 delivery on 31 Mar 2018 | 13989 | POC | KRW | 422283005 | 173337.98 | 2017-08-21 | 2018-02-19 |  | 195995002 |  | 46868505 |  | 46868505 | 0 | 0 |  | 2018-03-31 | [6 empty] | 0 | ASIA | AM
AMSS | RU8377 | 13958 | Korea Hydro & Nuclear power Co., Ltd | 710-H082-04 | P_KHNP - H082-04 delivery on 28 Feb 2018 | 15034 | PIT | KRW |  | 200129.11 | 2017-08-21 | 2018-02-19 |  | 226288003 |  | 74422844 |  | 74422844 | 0 | 0 |  | 2018-01-24 | [6 empty] | 0 | ASIA | AM
AMSS | RU8377 | 13974 | Doosan Heavy Industries & Contruction | 720-G142-04 | P - Doosan - G142-04 delivery on 30 Mar 2018 delay to June 2018 | 13994 | POC | KRW | 2173469000 | 1774985.19 | 2016-12-23 | 2018-03-30 |  | 2173469000 | 217346900 | 673971483 |  | 513848318 | 0 | 0 |  | 2018-03-31 | 129632244 |  | 482590536 |  | 2018-05-31 | 201805314100008fh601ipj (G142A) | 28587006 | ASIA | AM
AMSS | RU8377 | 15636 | Korea Hydro & Nuclear power Co., Ltd | 720-H114-04 | P - KHNP - H114 - 04 delivery on 18 Jan 2019 | 15679 | POC | KRW | 1757000000 | 1594301.8 | 2017-12-13 | 2019-01-18 |  | 1757000000 |  | 731638635 |  | 34189340 | 0 | 0 | [8 empty] | 25965517 | ASIA | AM
AMSS | RU8377 | 19070 | Korea Hydro & Nuclear power Co., Ltd | 720-H119-04 | P - KHNP - H119-04 delivery on 15 Jun 2018 | 19071 | POC | KRW | 2184860310 | 52653.76 | 2017-12-20 | 2019-02-08 |  | 56678500 |  | 19763785 |  | 19763785 | 0 | 0 |  | 2018-05-25 |  |  | 56684000 |  | 2018-05-25 | 2018052541000009a00007fw (I0119A) | 51203320 | ASIA | AM
AMSS | RU8377 | 19070 | Korea Hydro & Nuclear power Co., Ltd | 720-H119-04 | P - KHNP - H119-04 delivery on 24 Aug 2018 | 19163 | POC | KRW |  | 629996.7 | 2017-12-20 | 2019-02-08 |  | 678152294 |  | 253839880 |  | 17158000 | 0 | 0 | [8 empty] | 0 | ASIA | AM
AMSS | RU8377 | 19070 | Korea Hydro & Nuclear power Co., Ltd | 720-H119-04 | P - KHNP - H119-04 delivery on 8 Feb 2019 | 19166 | POC | KRW |  | 1347062.92 | 2017-12-20 | 2019-02-08 |  | 1450029516 |  | 948500000 |  | 19053946 | 0 | 0 | [8 empty] | 0 | ASIA | AM
AMSS | RU8377 | 22644 | Korea Hydro & Nuclear power Co., Ltd | 720-I010-04 | P - KHNP - I010B-04 Feb18_delivery on 12 Dec 2018 | 22667 | POC | KRW | 791648004 | 740573.37 | 2018-02-06 | 2019-02-15 |  | 790704004 |  | 581741600 |  | 0 | 0 | 0 | [8 empty] | 19258463 | ASIA | AM
AMSS | RU8377 | 22644 | Korea Hydro & Nuclear power Co., Ltd | 720-I010-04 | P - KHNP - I010A-04 Feb18_delivery on 2 May 2018 | 22668 | PIT | KRW |  | 884.15 | 2018-02-06 | 2019-02-15 |  | 944000 |  | 574872 |  | 0 | 0 | 0 | [8 empty] | 2024 | ASIA | AM
AMSS | RU8377 | 22646 | Korea Hydro & Nuclear power Co., Ltd | 710-I018-04 | P - KHNP - I018A - 04 Feb 18 delivery in Aug 2018 | 22865 | PIT | KRW | 699663997 | 44340.51 | 2018-02-13 | 2018-10-26 |  | 47341992 |  | 22766175 |  | 2274515 | 0 | 0 | [8 empty] | 602926 | ASIA | AM
AMSS | RU8377 | 22646 | Korea Hydro & Nuclear power Co., Ltd | 710-I018-04 | P - KHNP - I018B - 04 Feb 18 delivery on 7 Sep 2018 | 22866 | PIT | KRW |  | 51713.43 | 2018-02-13 | 2018-10-26 |  | 55213997 |  | 11301200 |  | 0 | 0 | 0 | [8 empty] | 0 | ASIA | AM
AMSS | RU8377 | 22646 | Korea Hydro & Nuclear power Co., Ltd | 710-I018-04 | P - KHNP - I018C - 04 Feb 18 delivery in Oct 2018 | 22867 | POC | KRW |  | 559251.36 | 2018-02-13 | 2018-10-26 |  | 597108008 |  | 193733770 |  | 2516670 | 0 | 0 | [8 empty] | 8824256 | ASIA | AM
AMSS | RU8377 | 22657 | Korea Hydro & Nuclear power Co., Ltd | 720-I017-04 | P - KHNP - I017A-04 Feb18_delivery on 28 May 2018 | 22858 | POC | KRW | 682406001 | 157397.5 | 2018-02-19 | 2018-06-25 |  | 168051997 |  | 44331073 |  | 44331073 | 0 | 0 |  | 2018-05-28 |  |  | 168052000 |  | 2018-05-30 | 2018053041000009a000043c (I017A) | 0 | ASIA | AM
AMSS | RU8377 | 22657 | Korea Hydro & Nuclear power Co., Ltd | 720-I017-04 | P - KHNP - I017B-04 Feb18_delivery on 25 June 2018 | 22859 | POC | KRW |  | 481743.96 | 2018-02-19 | 2018-06-25 |  | 514354004 |  | 71167650 |  | 5167650 | 0 | 0 | [8 empty] | 12545220 | ASIA | AM
AMSS | RU8377 | 24148 | Korea Hydro & Nuclear power Co., Ltd | 710-I20-04 | P - KHNP - I020 - 29 Mar 18_ Delivery on 31 Dec 2018 | 24155 | POC | KRW | 490000000 | 455161 | 2018-03-15 | 2018-12-14 |  | 490000000 |  | 90933934 |  | 17087934 | 0 | 0 | [8 empty] | 16570048 | ASIA | AM
AMSS | RU8377 | 26360 | Korea Hydro & Nuclear power Co., Ltd | 710-I022-04 | P - KHNP - I022A -17 Apr 18_delivery on Aug 2018 | 26394 | POC | KRW | 138638000 | 129321.53 | 2018-03-30 | 2018-10-31 |  | 2328000 |  | 1080430 |  | 1080430 | 0 | 0 |  | 2018-05-25 |  |  | 2328000 |  | 2018-05-25 | 2018052541000009a00007nu (I022A) | 9842880 | ASIA | AM
AMSS | RU8377 | 26360 | Korea Hydro & Nuclear power Co., Ltd | 710-I022-04 | P - KHNP - I022B - 17 Apr18_delivery on Oct 2018 | 26395 | POC | KRW |  | 142186.7 | 2018-03-30 | 2018-10-31 |  | 136310000 |  | 34765541 |  | 455000 | 0 | 0 | [8 empty] | 0 | ASIA | AM
AMSS | RU8377 | 27212 | Korea Hydro & Nuclear power Co., Ltd | 710-I033-04 | P_KHNP - I033A_Apr_ delivery on 11 Aug 2018 | 27292 | POC | KRW | 755405000 | 115108.45 | 2018-04-11 | 2018-11-17 |  | 114293000 |  | 30823277 |  | 1797939 | 0 | 0 | [8 empty] | 12110881 | ASIA | AM
AMSS | RU8377 | 27212 | Korea Hydro & Nuclear power Co., Ltd | 710-I033-04 | P_KHNP - I033A_Apr_ delivery on 19 Oct 2018 | 27293 | POC | KRW |  | 480240.89 | 2018-04-11 | 2018-11-17 |  | 459848000 |  | 54346090 |  | 11946551 | 0 | 0 | [8 empty] | 0 | ASIA | AM
AMSS | RU8377 | 27212 | Korea Hydro & Nuclear power Co., Ltd | 710-I033-04 | P_KHNP - I033A_Apr_ delivery on 17 Nov 2018 | 27294 | POC | KRW |  | 169083.06 | 2018-04-11 | 2018-11-17 |  | 181264000 |  | 86856710 |  | 0 | 0 | 0 | [8 empty] | 0 | ASIA | AM
AMSS | RU8377 | 28139 | Korea Hydro & Nuclear power Co., Ltd | 710-I04004 | P - KHNP - I040A - 23 May 18 delivery on Sep 2018 | 28214 | POC | KRW | 522958997 | 86625.23 | 2018-05-14 | 2018-11-19 |  | 92232996 |  | 18261408 |  | 0 | 0 | 0 | [8 empty] | 2249585 | ASIA | AM
AMSS | RU8377 | 28139 | Korea Hydro & Nuclear power Co., Ltd | 710-I04004 | P - KHNP - I040B - 23 May 18 delivery on Nov 2018 | 28215 | POC | KRW |  | 404537.86 | 2018-05-14 | 2018-11-19 |  | 430726001 |  | 59339990 |  | 0 | 0 | 0 | [8 empty] | 10505512 | ASIA | AM
AMSS | RU8389 | 16167 | Kaxu Solar One (Pty) | 702388-229/702388-395 | P - Kaxu Solar One (Pty) Ltd - 702388-229/702388-395 - POb1: Part Upgrade/Repairs | 16794 | POC | ZAR | 4279382 | 307779.17 | 2017-07-03 | 2017-12-31 |  | 4279382 | [7 empty] | 2018-02-28 | [6 empty] | 0 | OTHERAFRICA | AM
EPO | RU8405 | 3896 | BECHTEL INFRASTRUCTURE & POWER CORPORATION | 1028395 | P - BECHTEL INFRASTRUCTURE & POWER CORPORATION - 1028395 - POb1: Boiler feed water pumps+Warranty extension | 4016 | POC | USD | 1301695 | 1206590 | 2017-03-23 | 2018-09-18 |  | 1206590 |  | 941295 |  | 779606 | [7 empty] | 0 |  |  | 0 | US | OE
EPO | RU8405 | 3896 | BECHTEL INFRASTRUCTURE & POWER CORPORATION | 1028395 | P - BECHTEL INFRASTRUCTURE & POWER CORPORATION - 1028395 - POb2: Allowance based on Buyer´s estimate for Technical Advisory Services during erection | 4017 | PIT | USD |  | 41345 | 2017-03-23 | 2018-09-18 |  | 41345 |  | 30518 | [12 empty] | 0 | US | AM
EPO | RU8405 | 3896 | BECHTEL INFRASTRUCTURE & POWER CORPORATION | 1028395 | P - BECHTEL INFRASTRUCTURE & POWER CORPORATION - 1028395 - POb3: Allowance based on Buyer´s estimate for Technical Advisory Services during start-up and commissioning. | 4018 | PIT | USD |  | 53760 | 2017-03-23 | 2018-09-18 |  | 53760 |  | 39682 | [12 empty] | 0 | US | AM
EPO | RU8405 | 4503 | TECNICAS REUNIDAS,S.A. | 1028460 | P - TECNICAS REUNIDAS SA - 1028460 - POb1: Condensate extraction pumps + warranty extension | 4635 | POC | USD | 1020054 | 947255 | 2017-04-06 | 2018-05-31 |  | 947255 |  | 981345 |  | 948346 | [7 empty] | 0 |  |  | 0 | EUROPE | OE
EPO | RU8405 | 4503 | TECNICAS REUNIDAS,S.A. | 1028460 | P - TECNICAS REUNIDAS SA - 1028460 - POb2: Supervision for inst comm and test | 4636 | PIT | USD |  | 27927 | 2017-04-06 | 2018-05-31 |  | 27927 |  | 19914 | [12 empty] | 0 | EUROPE | AM
EPO | RU8405 | 4503 | TECNICAS REUNIDAS,S.A. | 1028460 | P - TECNICAS REUNIDAS SA - 1028460 - POb3: Training | 4637 | PIT | USD |  | 11857 | 2017-04-06 | 2018-05-31 |  | 11857 |  | 8455 | [12 empty] | 0 | EUROPE | AM
EPO | RU8405 | 4503 | TECNICAS REUNIDAS,S.A. | 1028460 | P - TECNICAS REUNIDAS SA - 1028460 - POb4: ABB Variable frequency drives training | 4638 | PIT | USD |  | 11164 | 2017-04-06 | 2018-05-31 |  | 11164 |  | 7961 | [12 empty] | 0 | EUROPE | AM
EPO | RU8405 | 4503 | TECNICAS REUNIDAS,S.A. | 1028460 | P - TECNICAS REUNIDAS SA - 1028460 - POb5: Variable Frequency Drives parametrization services at site | 13864 | PIT | USD |  | 21851 | 2017-04-06 | 2018-05-31 |  | 21851 |  | 15581 | [12 empty] | 0 | EUROPE | AM
EPO | RU8405 | 5333 | CHINA NATIONAL MACHINERY IMPORT & EXPORT CORPORATION (CMC) | 1020450/1027717 | P - CHINA NATIONAL MACHINERY IMPORT & EXPORT CORPORATION (CMC) - 1020450/1027717 - POb1: Circulating Water Pumps (2)+Warranty extension | 5338 | POC | USD | 8652420 | 4206622 | 2016-06-16 | 2018-10-31 |  | 4206622 |  | 2626790 |  | 2546350 | [7 empty] | 0 |  |  | 136728 | ASIA | OE
EPO | RU8405 | 5333 | CHINA NATIONAL MACHINERY IMPORT & EXPORT CORPORATION (CMC) | 1020450/1027717 | P - CHINA NATIONAL MACHINERY IMPORT & EXPORT CORPORATION (CMC) - 1020450/1027717 - POb3: Tecnical Field Services and Training | 5339 | PIT | USD |  | 202600 | 2016-06-16 | 2018-10-31 |  | 202600 |  | 107727 | [12 empty] | 0 | ASIA | AM
EPO | RU8405 | 5333 | CHINA NATIONAL MACHINERY IMPORT & EXPORT CORPORATION (CMC) | 1020450/1027717 | P - CHINA NATIONAL MACHINERY IMPORT & EXPORT CORPORATION (CMC) - 1020450/1027717 - POb4: Engineering | 5341 | PIT | USD |  | 400170 | 2016-06-16 | 2018-10-31 | [9 empty] | 2014-12-31 | [6 empty] | 0 | ASIA | OE
EPO | RU8405 | 5333 | CHINA NATIONAL MACHINERY IMPORT & EXPORT CORPORATION (CMC) | 1020450/1027717 | P - CHINA NATIONAL MACHINERY IMPORT & EXPORT CORPORATION (CMC) - 1020450/1027717 - POb5: Seismic calculation | 5342 | PIT | USD |  | 36575 | 2016-06-16 | 2018-10-31 |  | 36575 |  | 16500 | [5 empty] | 2014-12-31 | [6 empty] | 0 | ASIA | OE
EPO | RU8405 | 5333 | CHINA NATIONAL MACHINERY IMPORT & EXPORT CORPORATION (CMC) | 1020450/1027717 | P - CHINA NATIONAL MACHINERY IMPORT & EXPORT CORPORATION (CMC) - 1020450/1027717 - POb2: Circulating Water Pumps (2)+Warranty extension | 5344 | POC | USD |  | 4206623 | 2016-06-16 | 2018-10-31 |  | 4206623 |  | 2453061 |  | 1785192 | [10 empty] | 0 | ASIA | OE
EPO | RU8405 | 5353 | CISCO ENGINEERING CO LTD | 1027824 | P - CISCO ENGINEERING CO LTD - 1027824 - POb1: Concrete volute pumps (1+1+1+1+1) | 5358 | POC | EUR | 2442099 | 2493513 | 2016-12-29 | 2018-01-09 |  | 2363743 | [7 empty] | 2018-03-31 | [6 empty] | 0 | ASIA | OE
EPO | RU8405 | 5353 | CISCO ENGINEERING CO LTD | 1027824 | P - CISCO ENGINEERING CO LTD - 1027824 - POb2: Supervision and Training | 5376 | PIT | EUR |  | 82658 | 2016-12-29 | 2018-01-09 |  | 78356 | [14 empty] | 0 | ASIA | AM
EPO | RU8405 | 5378 | SOUTHERN COMPANY SERVICES INC | 1028446 | P - SOUTHERN COMPANY SERVICES INC - 1028446 - POb1: Boiler feed water pumps | 5383 | POC | USD | 1222327 | 1213187 | 2017-04-06 | 2018-04-11 |  | 1213187 |  | 919484 | [5 empty] | 2018-04-28 |  |  |  | 0 |  |  | 0 | US | OE
EPO | RU8405 | 5378 | SOUTHERN COMPANY SERVICES INC | 1028446 | P - SOUTHERN COMPANY SERVICES INC - 1028446 - POb2: Site services engineer field services | 5384 | PIT | USD |  | 9140 | 2017-04-06 | 2018-04-11 |  | 9140 |  | 6197 | [12 empty] | 0 | US | AM
EPO | RU8405 | 5405 | BLACK & VEATCH CONSTRUCTION, INC. | 1026720 | P - BLACK & VEATCH CONSTRUCTION, INC. - 1026720 - POb1: 2 Circulating water pumps (Unit 5)+ Warranty extension | 5413 | POC | USD | 9209270 | 4261495 | 2017-04-04 | 2018-12-16 |  | 4214510 |  | 3331228 |  | 1701358 | [7 empty] | 0 |  |  | 72638 | ASIA | OE
EPO | RU8405 | 5405 | BLACK & VEATCH CONSTRUCTION, INC. | 1026720 | P - BLACK & VEATCH CONSTRUCTION, INC. - 1026720 - POb2: 2 Circulating water pumps (Unit 6)+ Warranty extension | 5415 | POC | USD |  | 4771430 | 2017-04-04 | 2018-12-16 |  | 4724730 |  | 3732144 |  | 1382022 | [10 empty] | 0 | ASIA | OE
EPO | RU8405 | 5405 | BLACK & VEATCH CONSTRUCTION, INC. | 1026720 | P - BLACK & VEATCH CONSTRUCTION, INC. - 1026720 - POb3: Initial Spare parts (Unit 5) | 5416 | PIT | USD |  | 46912 | 2017-04-04 | 2018-12-16 |  | 46912 |  | 21000 | [12 empty] | 0 | ASIA | AM
EPO | RU8405 | 5405 | BLACK & VEATCH CONSTRUCTION, INC. | 1026720 | P - BLACK & VEATCH CONSTRUCTION, INC. - 1026720 - POb4: Initial Spare parts (Unit 6) | 5417 | PIT | USD |  | 53798 | 2017-04-04 | 2018-12-16 |  | 53798 |  | 27500 | [12 empty] | 0 | ASIA | AM
EPO | RU8405 | 5405 | BLACK & VEATCH CONSTRUCTION, INC. | 1026720 | P - BLACK & VEATCH CONSTRUCTION, INC. - 1026720 - POb5: Field Service Representative and Training (Unit 5) and (Unit 6) | 5418 | PIT | USD |  | 169320 | 2017-04-04 | 2018-12-16 |  | 169320 |  | 126448 | [12 empty] | 0 | ASIA | AM
EPO | RU8405 | 5729 | SIEMENS LTD SEOUL | 1028603 | P-SIEMENS LTD SEOUL-1028603-Pob1- 39APM Cooling water pumps | 5737 | POC | EUR | 346940.5308 | 836984 | 2017-04-19 | 2018-04-22 |  | 346940.5308 |  | 318565 | [5 empty] | 2018-04-19 | [6 empty] | 0 | ASIA | OE
EPO | RU8405 | 5847 | POSCO ENGINEERING & CONSTRUCTION CO LTD | 1028010 | P-POSCO ENGINEERING & CONSTRUCTION CO LTD -1028010 - Pob1: Seawater Lift Pump+Circulating Water Pump +Aux. Circulating Water Pump + NPRSr testing + DAP Jobsite Freight + Training Buyer's and/or Owner's personnel | 5852 | POC | EUR | 4081528.0646 | 3927926 | 2017-01-26 | 2018-01-29 |  | 3793949.6903 | 87351 | 3812491 | [5 empty] | 2018-04-19 | [6 empty] | 0 | ASIA | OE
EPO | RU8405 | 5847 | POSCO ENGINEERING & CONSTRUCTION CO LTD | 1028010 | P-POSCO ENGINEERING & CONSTRUCTION CO LTD -1028010- Pob 2: Spare Parts (Rotors) | 5853 | PIT | EUR |  | 250132 | 2017-01-26 | 2018-01-29 |  | 234777.5483 |  | 152606 | [12 empty] | 0 | ASIA | AM
EPO | RU8405 | 5847 | POSCO ENGINEERING & CONSTRUCTION CO LTD | 1028010 | P-POSCO ENGINEERING & CONSTRUCTION CO LTD -1028010 - Pob3 : Supervision Services | 5854 | PIT | EUR |  | 56254 | 2017-01-26 | 2018-01-29 |  | 52800.826 |  | 45498 | [12 empty] | 0 | ASIA | AM
EPO | RU8405 | 6085 | CB & I LLC | 1027454 | P-CB & I LLC-1027454- Pob1 : 2 Boiler Feed Water pumps A + 2 Boiler Feed Water pumps B+Cancellation fee for the Turbine Air cooler pumps | 6209 | POC | USD | 3923753 | 3893991 | 2017-07-17 | 2018-03-13 |  | 3893991 |  | 1826398 | [5 empty] | 2018-04-24 |  |  |  | 0 |  |  | 0 | US | OE
EPO | RU8405 | 6085 | CB & I LLC | 1027454 | P-CB & I LLC-1027454- Pob2 :Technical field advisory services during installation, start-up and commissioning | 6753 | PIT | USD |  | 29762 | 2017-07-17 | 2018-03-13 |  | 29762 |  | 21968 | [12 empty] | 0 | US | AM
EPO | RU8405 | 7377 | CB & I LLC | 1028992 | P-CB & I LLC-1028992-Pob1: 2 Boiler Feed Water pumps A + 2 Boiler Feed Water pumps B | 9344 | POC | USD | 2456167 | 2426405 | 2017-07-17 | 2018-11-15 |  | 2426405 |  | 1831881 |  | 1106187 | [7 empty] | 0 |  |  | 0 | US | OE
EPO | RU8405 | 7377 | CB & I LLC | 1028992 | P-CB & I LLC-1028992-Pob2: Technical field advisory services | 9346 | PIT | USD |  | 29762 | 2017-07-17 | 2018-11-15 |  | 29762 |  | 21968 | [12 empty] | 0 | US | AM
EPO | RU8405 | 7381 | SEPCO Ⅲ Electric Power Construction Corp. | 1028990 | P - SEPCO Ⅲ Electric Power Construction Corp. - 1028990 - POb1: 2 Circulating water pumps + warranty extension | 10137 | POC | USD | 1664116 | 1561866 | 2017-07-26 | 2018-07-18 |  | 1561866 |  | 1229227 |  | 1180715 | [7 empty] | 0 |  |  | 12691 | MIDEAST | OE
EPO | RU8405 | 7381 | SEPCO Ⅲ Electric Power Construction Corp. | 1028990 | P - SEPCO Ⅲ Electric Power Construction Corp. - 1028990 - POb2: 3 years operational spare parts | 10138 | PIT | USD |  | 66270 | 2017-07-26 | 2018-07-18 |  | 66270 |  | 31765 | [12 empty] | 0 | MIDEAST | AM
EPO | RU8405 | 7381 | SEPCO Ⅲ Electric Power Construction Corp. | 1028990 | P - SEPCO Ⅲ Electric Power Construction Corp. - 1028990 - POb3:Supervision | 10139 | PIT | USD |  | 35980 | 2017-07-26 | 2018-07-18 |  | 35980 |  | 22623 | [12 empty] | 0 | MIDEAST | AM
EPO | RU8405 | 7387 | PCC GmbH | 1028993 | P - PCC GmbH - 1028993-POb1: Full Cartridge Inners (1+1+1) | 10404 | POC | EUR | 746759.2314 | 868593 | 2017-08-03 | 2018-06-25 |  | 746759.2314 |  | 573207 |  | 241955 | [10 empty] | 0 | CHINA | OE
EPO | RU8405 | 7388 | PCC GmbH | 1029094 | P - PCC GmbH - 1029094-POb1: Full Cartridge Inners (1+1) | 10532 | POC | EUR | 493764.3468 | 574322 | 2017-08-03 | 2018-06-25 |  | 493764.3468 |  | 379063 |  | 133572 | [10 empty] | 0 | CHINA | OE
EPO | RU8405 | 9005 | AECOM Energy & Construction Inc | 1028552 / 050-36245 / 10004636 | P - AECOM Energy & Construction Inc - 1028552 / 050-36245 / 10004636 (Combined Contracts) - POb1: 2+2 Boiler Feed water pumps+2 Vertical Circulating water pumps+1 Auxiliary Circulating water pump+3 Condensate pumps+warranty extension | 17446 | POC | USD | 1401027 | 1401027 | 2017-05-03 | 2018-04-18 |  | 1401027 |  | 1160371.2383 | [5 empty] | 2018-04-24 |  |  |  | 0 |  |  | 11384 | US | OE
EPO | RU8405 | 9006 | OCP S.A. | 1028839 | P - OCP S.A.-1028839 2 Sea Water pumps for SAP unit D+warranty extension | 19856 | POC | EUR | 2171342.4405 | 573225 | 2017-05-29 | 2018-05-19 |  | 1413112 |  | 1356232 |  | 1356232 |  |  |  | 2018-05-05 | [6 empty] | 19190 | OTHERAFRICA | OE
EPO | RU8405 | 9006 | OCP S.A. | 1028839 | P - OCP S.A.-1028839 Spare parts for two years (Auxiliary Sea Water pump for power plant) | 19862 | PIT | EUR |  | 66768 | 2017-05-29 | 2018-05-19 |  | 190845.3936 |  | 108710 | [12 empty] | 0 | OTHERAFRICA | AM
EPO | RU8405 | 9006 | OCP S.A. | 1028839 | P - OCP S.A.-1028839 Supervision | 20098 | PIT | EUR |  | 70144 | 2017-05-29 | 2018-05-19 |  | 61899.0469 |  | 53247 | [12 empty] | 0 | OTHERAFRICA | AM
EPO | RU8405 | 9006 | OCP S.A. | 1028839 | P - OCP S.A.-1028839 3 Sea Water pumps and 1 Auxiliary Sea Water pump for power plant+warranty extension | 26254 | POC | EUR |  | 1601267 | 2017-05-29 | 2018-05-19 |  | 505486 |  | 514470 |  | 514470 |  |  |  | 2018-05-05 | [6 empty] | 0 | OTHERAFRICA | AM
EPO | RU8405 | 9006 | OCP S.A. | 1028839 | P - OCP S.A.-1028839 Spare parts for two years (Sea Water pumps for SAP unit D) | 26255 | PIT | EUR |  | 57029 | 2017-05-29 | 2018-05-19 | [16 empty] | 0 | OTHERAFRICA | AM
EPO | RU8405 | 9006 | OCP S.A. | 1028839 | P - OCP S.A.-1028839 Spare parts for two years (Sea Water pumps for power plant) | 26256 | PIT | EUR |  | 92469 | 2017-05-29 | 2018-05-19 | [16 empty] | 0 | OTHERAFRICA | AM
EPO | RU8405 | 9272 | MINERA ESCONDIDA LTDA | 1029100 | P - MINERA ESCONDIDA LTDA - 1029100 - POb1: 3 x (1 RO High Pressure Feed Pumps + 1 ERS Booster Pumps)+warranty extension | 17860 | POC | USD | 3901528 | 3678399.2 | 2017-08-17 | 2018-07-23 |  | 3678398 |  | 2336082 |  | 1857476 | [7 empty] | 0 |  |  | 62463.03 | LA | OE
EPO | RU8405 | 9272 | MINERA ESCONDIDA LTDA | 1029100 | P - MINERA ESCONDIDA LTDA - 1029100 - POb2: Field Services | 17861 | PIT | USD |  | 196468.8 | 2017-08-17 | 2018-07-23 |  | 184030 |  | 139839 | [12 empty] | 0 | LA | AM
EPO | RU8405 | 9272 | MINERA ESCONDIDA LTDA | 1029100 | P - MINERA ESCONDIDA LTDA - 1029100 - POb3: Training | 17862 | PIT | USD |  | 39100 | 2017-08-17 | 2018-07-23 |  | 39100 |  | 28861 | [12 empty] | 0 | LA | OE
EPO | RU8405 | 12230 | AMEC FOSTER WHEELER INDUSTRIAL POWER CO | 1029440 | P - AMEC FOSTER WHEELER INDUSTRIAL POWER CO - 1029440 - POb1: 2 Feedwater pumps | 12782 | POC | USD | 431471 | 431471 | 2017-10-20 | 2018-07-29 |  | 431471 |  | 307304 |  | 203361 | [7 empty] | 0 |  |  | 0 | US | OE
EPO | RU8405 | 12424 | AMEC FOSTER WHEELER INDUSTRIAL POWER CO | 1029441 | P - AMEC FOSTER WHEELER INDUSTRIAL POWER CO - 1029441 - POb1: 2 Feedwater pumps | 12787 | POC | USD | 431471 | 431471 | 2017-10-20 | 2018-07-29 |  | 431471 |  | 308757 |  | 161417 | [7 empty] | 0 |  |  | 0 | US | OE
EPO | RU8405 | 12425 | IBERDROLA ENERGIA ESCOBEDO SA DE CV | 1029248-1029250 | P - IBERDROLA ENERGIA ESCOBEDO SA DE CV - 1029248/1029250 - POb1: (2 HP Boiler Feed Water Pumps+2 MP Boiler Feed Water Pumps+3 Condensate Water Pumps)+(2 HP Boiler Feed Water Pumps+2 MP Boiler Feed Water Pumps)+warranty extension | 12673 | POC | USD | 2852138 | 2763941 | 2017-09-05 | 2018-07-31 |  | 2763941 |  | 2079854 |  | 1418276 | [7 empty] | 0 |  |  | 0 | LA | OE
EPO | RU8405 | 12425 | IBERDROLA ENERGIA ESCOBEDO SA DE CV | 1029248-1029250 | P - IBERDROLA ENERGIA ESCOBEDO SA DE CV - 1029248/1029250 - POb2: Supervision of the erection and commissioning | 12676 | PIT | USD |  | 88197 | 2017-09-05 | 2018-07-31 |  | 88197 |  | 65717 | [12 empty] | 0 | LA | AM
EPO | RU8405 | 12434 | DOW CHEMICAL IBERICA, S.L. | 1029208 | P - DOW CHEMICAL IBERICA, S.L. - 1029208 - POb1: 2 Axial-split pumps | 14031 | POC | EUR | 473272 | 562286 | 2017-08-30 | 2018-07-23 |  | 473272 |  | 399053 |  | 327707 | [10 empty] | 0 | EUROPE | AM
EPO | RU8405 | 12622 | CENTRAL NUCLEAR DE TRILLO C.B | 1029554 | P - CENTRAL NUCLEAR DE TRILLO C.B - 1029554 - POb1: (1)ECP80-200 Essential Chilled Water pump (UF11/21/31/41D001)+(1)ECP40-250 Recirculating Demineralised Water Pump (RS14/24/34/44D001)+(1)WPG32-200 Diesel oil transfer pump (UT11/21/31/41D001) | 14301 | POC | EUR | 498688.6085 | 584862 | 2017-11-09 | 2018-08-16 |  | 498688.6085 |  | 346489 |  | 38377 | [10 empty] | 0 | EUROPE | AM
EPO | RU8405 | 15652 | RESPONSE ENGINEERING LTD | 1027273 | P - RESPONSE ENGINEERING LTD - 1027273 - POb1: River intake pumps | 18399 | POC | EUR | 992484.9338 | 1120194 | 2016-10-17 | 2018-02-15 |  | 992484.9338 | [7 empty] | 2018-02-28 | [6 empty] | 0 | EUROPE | OE
EPO | RU8405 | 15661 | DAELIM INDUSTRIAL CO LTD | 1022694 | P-DAELIM INDUSTRIAL CO LTD-1022694-POb1 8 feed water pumps+spart parts installation+probe sensor+warranty extended+1 year spare parts | 18309 | POC | USD | 0 | 3577030 | 2014-12-23 | 2018-01-20 | [9 empty] | 2018-01-31 |  |  |  | 0 |  |  | 15027.01 | OTHERAFRICA | OE
EPO | RU8405 | 15662 | PSEG POWER CONNECTICUT LLC | 1027458 | P - PSEG POWER CONNECTICUT LLC - 1027458 - POb1: Boiled feed pumps | 18787 | POC | USD | 43000 | 901100 | 2016-10-27 | 2018-01-31 | [9 empty] | 2018-01-31 |  |  |  | 0 |  |  | 0 | US | OE
EPO | RU8405 | 15662 | PSEG POWER CONNECTICUT LLC | 1027458 | P - PSEG POWER CONNECTICUT LLC - 1027458 - POb2: Technical services and training | 18791 | PIT | USD |  | 43000 | 2016-10-27 | 2018-01-31 |  | 43000 | [14 empty] | 0 | US | OE
EPO | RU8405 | 15678 | CMD. DE BIENES CENTRAL NUCLEAR ALMARAZ | 1027842 | P - CMD. DE BIENES CENTRAL NUCLEAR ALMARAZ - 1027842 - POb1: 2 Centrifugal chilled water pump | 18977 | POC | EUR | 371791.639 | 392203 | 2016-12-20 | 2018-05-31 |  | 371791.639 |  | 251517 |  | 186943 | [10 empty] | 0 | EUROPE | AM
EPO | RU8405 | 15915 | STATE NUCLEAR POWER ENGINEERING CORPORATION LTD | 1021946 | P - STATE NUCLEAR POWER ENGINEERING CORPORATION LTD - 1021946 - POb1: 2 pumps + warranty extension | 18398 | POC | EUR | 976419.1733 | 1227751.2 | 2014-06-30 | 2018-10-05 |  | 953037.9973 |  | 551534 |  | 549003 | [10 empty] | 33356 | CHINA | OE
EPO | RU8405 | 15915 | STATE NUCLEAR POWER ENGINEERING CORPORATION LTD | 1021946 | P - STATE NUCLEAR POWER ENGINEERING CORPORATION LTD - 1021946 - POb2: Services | 18425 | PIT | EUR |  | 30120.8 | 2014-06-30 | 2018-10-05 |  | 23381.176 |  | 14028 | [12 empty] | 0 | CHINA | AM
EPO | RU8405 | 15916 | SHANGHAI FOREIGN TRADE (PUDONG) CO LTD | 1027288 | P-SHANGHAI FOREIGN TRADE (PUDONG) CO LTD-1027288-Pob 1 Inner 1+Inner 2+ transport | 18823 | POC | EUR | 558000 | 583363.7 | 2016-10-20 | 2018-06-30 |  | 521000 |  | 414596 | [5 empty] | 2018-04-26 | [6 empty] | 0 | CHINA | OE
EPO | RU8405 | 15916 | SHANGHAI FOREIGN TRADE (PUDONG) CO LTD | 1027288 | P-SHANGHAI FOREIGN TRADE (PUDONG) CO LTD-1027288-Spare parts | 18825 | PIT | EUR |  | 41428.9 | 2016-10-20 | 2018-06-30 |  | 37000 | [7 empty] | 2018-03-25 | [6 empty] | 0 | CHINA | AM
EPO | RU8405 | 16028 | STATE NUCLEAR POWER ENGINEERING CORPORATION LTD | 1021948 | P - STATE NUCLEAR POWER ENGINEERING CORPORATION LTD - 1021948 - POb1: (2)+(2) pumps + warranty extension | 18607 | POC | EUR | 1906504.1723 | 2395815.21 | 2014-06-30 | 2019-05-04 |  | 1859744.0016 |  | 1066060 |  | 666799 | [10 empty] | 65091 | CHINA | OE
EPO | RU8405 | 16028 | STATE NUCLEAR POWER ENGINEERING CORPORATION LTD | 1021948 | P - STATE NUCLEAR POWER ENGINEERING CORPORATION LTD - 1021948 - POb2: Services | 18689 | PIT | EUR |  | 60238.79 | 2014-06-30 | 2019-05-04 |  | 46760.1708 |  | 28056 | [12 empty] | 0 | CHINA | AM
EPO | RU8405 | 18799 | AL FATAH INTERNATIONAL FOR WATER AND POWER CO | 1024563/1028783 | P - AL FATAH INTERNATIONAL FOR WATER AND POWER CO- 1024563/1028783 POb 1 3 pumps+electric motors+testings+warranty extended | 19109 | POC | EUR | 2305782 | 2307843.42 | 2015-07-14 | 2018-01-31 |  | 2086469 | [7 empty] | 2018-03-31 | [6 empty] | 0 | MIDEAST | OE
EPO | RU8405 | 18799 | AL FATAH INTERNATIONAL FOR WATER AND POWER CO | 1024563/1028783 | P - AL FATAH INTERNATIONAL FOR WATER AND POWER CO - 1024563/1028783 POb 2 2 year spare parts | 19550 | PIT | EUR |  | 200372.12 | 2015-07-14 | 2018-01-31 |  | 181152 | [7 empty] | 2018-03-31 | [6 empty] | 0 | MIDEAST | AM
EPO | RU8405 | 18799 | AL FATAH INTERNATIONAL FOR WATER AND POWER CO | 1024563/1028783 | P - AL FATAH INTERNATIONAL FOR WATER AND POWER CO - 1024563/1028783 POb 3 Commisioning and start-up for each pump | 19557 | PIT | EUR |  | 42209.46 | 2015-07-14 | 2018-01-31 |  | 38161 | [7 empty] | 2018-03-31 | [6 empty] | 0 | MIDEAST | AM
EPO | RU8405 | 18803 | TECNICAS REUNIDAS,S.A. | 1029786/1029788 | P - TECNICAS REUNIDAS,S.A. - 1029786/1029788/1029890/1029891 - POb1: Feed Water pumps + condensate pumps + warranties extension | 19129 | POC | EUR | 1741841.8036 | 2024221 | 2018-01-04 | 2018-11-09 |  | 1719439 |  | 1507764 |  | 194636 | [10 empty] | 0 | LA | OE
EPO | RU8405 | 18803 | TECNICAS REUNIDAS,S.A. | 1029786/1029788 | P - TECNICAS REUNIDAS,S.A. - 1029786/1029788/1029890/1029891 - POb2: Services (ACCOUNTED BY FLS MEXICO) | 19899 | PIT | EUR |  | 26769 | 2018-01-04 | 2018-11-09 |  | 22402.8036 |  | 20000 | [12 empty] | 0 | LA | OE
EPO | RU8405 | 18808 | BLACK & VEATCH CORPORATION, INC | 1029783/1029784/1029907 | P - Black & Veatch Corporation - 1029783/1029784/1029907 - POb1: 2x(2 Boiler feed WP+2 Condensate pumps+2 Circulating WP+1 Cooling tower Makeup) | 19677 | POC | USD | 6885945 | 6522103 | 2017-12-26 | 2019-06-03 |  | 6522103 |  | 4963421 |  | 485584 | [7 empty] | 0 |  |  | 56784 | ASIA | OE
EPO | RU8405 | 18808 | BLACK & VEATCH CORPORATION, INC | 1029783/1029784/1029907 | P - Black & Veatch Corporation - 1029783/1029784/1029907 - POb2: Spare parts for Boiler feed water pumps | 19678 | PIT | USD |  | 162571 | 2017-12-26 | 2019-06-03 |  | 162571 |  | 158630 | [12 empty] | 0 | ASIA | AM
EPO | RU8405 | 18808 | BLACK & VEATCH CORPORATION, INC | 1029783/1029784/1029907 | P - Black & Veatch Corporation - 1029783/1029784/1029907 - POb5: Tecnical services | 19679 | PIT | USD |  | 22628 | 2017-12-26 | 2019-06-03 |  | 22628 |  | 15401 | [12 empty] | 0 | ASIA | AM
EPO | RU8405 | 18808 | BLACK & VEATCH CORPORATION, INC | 1029783/1029784/1029907 | P - Black & Veatch Corporation - 1029783/1029784/1029907 - POb3: Spare parts for Condensate pumps | 23428 | PIT | USD |  | 62810 | 2017-12-26 | 2019-06-03 |  | 62810 | [14 empty] | 0 | ASIA | AM
EPO | RU8405 | 18808 | BLACK & VEATCH CORPORATION, INC | 1029783/1029784/1029907 | P - Black & Veatch Corporation - 1029783/1029784/1029907 - POb4: Spare parts for CT Makeup and CW pumps | 23429 | PIT | USD |  | 115833 | 2017-12-26 | 2019-06-03 |  | 115833 | [14 empty] | 0 | ASIA | AM
EPO | RU8405 | 18855 | STATE NUCLEAR POWER ENGINEERING CORPORATION LTD | 1021950 | P - STATE NUCLEAR POWER ENGINEERING CORPORATION LTD - 1021950 - POb1: (2) + (2) pump + extension warranty | 19531 | POC | EUR | 2291107.0347 | 2462404.32 | 2014-06-30 | 2018-10-05 |  | 1921910 |  | 1093040 |  | 16884 | [10 empty] | 67267 | CHINA | OE
EPO | RU8405 | 18855 | STATE NUCLEAR POWER ENGINEERING CORPORATION LTD | 1021950 | P - STATE NUCLEAR POWER ENGINEERING CORPORATION LTD - 1021950 - POb2: Spare parts | 19539 | PIT | EUR |  | 415379.51 | 2014-06-30 | 2018-10-05 |  | 322437.0347 |  | 112852 | [12 empty] | 0 | CHINA | AM
EPO | RU8405 | 18855 | STATE NUCLEAR POWER ENGINEERING CORPORATION LTD | 1021950 | P - STATE NUCLEAR POWER ENGINEERING CORPORATION LTD - 1021950 - POb3: Services | 19549 | PIT | EUR |  | 60238.57 | 2014-06-30 | 2018-10-05 |  | 46760 |  | 28056 | [12 empty] | 0 | CHINA | AM
EPO | RU8405 | 18856 | STATE NUCLEAR POWER ENGINEERING CORPORATION LTD | 1021947 | P - STATE NUCLEAR POWER ENGINEERING CORPORATION LTD - 1021947 - POb1: (2) + (2) pumps + warranty extension | 19583 | POC | EUR | 2591236.7768 | 2490315.27 | 2014-06-30 | 2018-10-05 |  | 1947967 |  | 1113244 |  | 75405 | [10 empty] | 68179 | CHINA | OE
EPO | RU8405 | 18856 | STATE NUCLEAR POWER ENGINEERING CORPORATION LTD | 1021947 | P - STATE NUCLEAR POWER ENGINEERING CORPORATION LTD - 1021947 - POb2: Spare parts | 19585 | PIT | EUR |  | 768453.72 | 2014-06-30 | 2018-10-05 |  | 596509.7768 |  | 208780 | [12 empty] | 0 | CHINA | AM
EPO | RU8405 | 18856 | STATE NUCLEAR POWER ENGINEERING CORPORATION LTD | 1021947 | P - STATE NUCLAER POWER ENGINEERING CORPORATION LTD - 1021947 - POb3: Services | 19587 | PIT | EUR |  | 60238.57 | 2014-06-30 | 2018-10-05 |  | 46760 |  | 28056 | [12 empty] | 0 | CHINA | AM
EPO | RU8405 | 20258 | UTE TECNICAS REUNIDAS INTEGRATED GAS (TRIG) | 1027888 | P - UTE TECNICAS REUNIDAS INTEGRATED GAS (TRIG) - 1027888 - POb1: 6 High Flow Pumps + extended warranty | 20379 | POC | USD | 0 | 730682 | 2017-03-27 | 2018-01-15 | [9 empty] | 2018-01-31 |  |  |  | 0 |  |  | 0 | MIDEAST | OE
EPO | RU8405 | 20258 | UTE TECNICAS REUNIDAS INTEGRATED GAS (TRIG) | 1027888 | P - UTE TECNICAS REUNIDAS INTEGRATED GAS (TRIG) - 1027888 - POb2: 2 sea water pumps + 2 off spec pumps | 20380 | POC | USD |  | 491446 | 2017-03-27 | 2018-01-15 | [9 empty] | 2018-01-31 | [6 empty] | 0 | MIDEAST | OE
EPO | RU8405 | 21389 | DANIELI & C. OFFICINE MECCANICHE SPA | 1029968 | P - DANIELI & C. OFFICINE MECCANICHE SPA - 1029968 - POb1: 2 Main Descaling pumps + 2 Booster pumps + warranty extensión | 21406 | POC | EUR | 446900 | 545560 | 2018-01-26 | 2018-10-24 |  | 446900 |  | 467936 |  | 65374 | [10 empty] | 0 | EUROPE | OE
EPO | RU8405 | 21390 | SENER INGENIERIA Y SISTEMAS S.A | 1030017 | P - SENER INGENIERIA Y SISTEMAS SA - 1030017 - POb1: 2 Feed Water Pumps+spare parts | 21413 | POC | EUR | 346940 | 423545 | 2018-01-31 | 2018-09-27 |  | 346940 |  | 318565 |  | 68981 | [10 empty] | 0 | EUROPE | OE
EPO | RU8405 | 21390 | SENER INGENIERIA Y SISTEMAS S.A | 1030017 | P - SENER INGENIERIA Y SISTEMAS SA - 1030017 - POb2: Erection, Start Up Supervision and training | 21415 | PIT | EUR |  | 50445 | 2018-01-31 | 2018-09-27 | [16 empty] | 0 | EUROPE | AM
EPO | RU8405 | 23331 | Infraestructura del Agua de Castilla la Mancha | 1030204 | P - INFRAESTRUCTURA DEL AGUA DE CASTILLA LA MANCHA- 1030204 #POB1: 4 X Water Pumps Reparation | 23384 | POC | EUR | 541903.0594 | 666893 | 2018-02-28 | 2018-08-30 |  | 541903.0594 |  | 443863 |  | 220721 | [10 empty] | 0 | EUROPE | AM
EPO | RU8405 | 24521 | PCC GmbH | 1030367 | P - PCC GmbH - 1030367 - POb1: Full Cartridge Inners (1+1+1) | 27146 | POC | EUR | 433060.2921 | 530802 | 2018-03-21 | 2019-02-15 |  | 433060.2921 |  | 315779 |  | 534 | [10 empty] | 0 | EUROPE | OE
EPO | RU8405 | 24522 | INITEC ENERGIA S.A | 1030188 | P - INITEC ENERGIA S.A - 1030188 - POb1: 2 Boiler Feed Water pumps | 27230 | POC | EUR | 465499.7144 | 570563 | 2018-03-16 | 2018-12-07 |  | 465499.7144 |  | 394070 |  | 24327 | [10 empty] | 0 |  | OE
EPO | RU8405 | 24523 | CMD. DE BIENES CENTRAL NUCLEAR ALMARAZ | 1030390 | P - CMD. DE BIENES CENTRAL NUCLEAR ALMARAZ - 1030390 - POb1: Internal charge pump CS-1-CSAPCH-02. | 27165 | POC | EUR | 425600.8811 | 521659 | 2018-03-27 | 2019-11-05 |  | 425600.8811 |  | 279960 |  | 11592 | [10 empty] | 0 |  | AM
EPO | RU8405 | 25650 | INTERNATIONAL DEVELOPMENT COMPANY | 1030374 | P - INTERNATIONAL DEVELOPMENT COMPANY(IDC) - 1030374 - POb1: Spare parts (Centrifugal vertical mixed frow type) & (Vertical mixed flow or double suction radial) | 27790 | POC | EUR | 1087302.7658 | 1332707 | 2018-03-20 | 2018-11-19 |  | 1087302.7658 | [14 empty] | 0 |  | OE
EPO | RU8405 | 25844 | GE GLOBAL PARTS & PRODUCTS GMBH | 1030419 | P - GE GLOBAL PARTS & PRODUCTS GMBH - 1030419 - Pob1 - 2 FEEDWATER PUMPS | 27847 | POC | EUR | 783984.6618 | 960930 | 2018-03-28 | 2019-02-23 |  | 783984.6618 |  | 619348 |  | 13320 | [10 empty] | 0 |  | OE
EPO | RU8405 | 25981 | CASALE SA. | 1030211 | P - CASALE SA - 1030211 - POb1: 2 Boiler Feed Water Pumps | 27259 | POC | EUR | 760000 | 931532 | 2018-03-06 | 2019-01-31 |  | 760000 |  | 663835 |  | 99364 | [10 empty] | 0 |  | OE
EPO | RU8405 | 26092 | COBRA MONTAJES SERVICIOS Y AGUA LIMITADA | 1030391 | P - COBRA MONTAJES SERVICIOS Y AGUA LIMITADA - 1030391 - Pob1 MAIN AND VERTICAL PUMPS FOR DESALINATION PLANT | 27799 | POC | EUR | 3300000 | 4044810 | 2018-03-27 | 2018-12-20 |  | 3300000 |  | 2681540 |  | 38960 | [10 empty] | 0 |  | OE
EPO | RU8405 | 27834 | HENGLI PETROCHEMICAL (DALIAN) CHEMICAL CO., LTD. | 1030396 | P - HENGLI PETROCHEMICAL (DALIAN) CHEMICAL CO., LTD. - 1030396 - Pob1: 2 Propylene Feed Pumps | 28235 | POC | EUR | 431500.123 | 526387 | 2018-04-24 | 2019-02-02 |  | 431500.123 |  | 341117 |  | 2220 | [10 empty] | 0 |  | OE
EPO | RU8405 | 27835 | JGC GULF INTERNATIONAL CO. LTD. | 1030383 | P - JGC GULF INTERNATIONAL CO. LTD. - 1030383 - Pob1: 2 Propane Pumps & 2 Booster Pumps & 1 Hot Oil Pump | 28326 | POC | EUR | 457939 | 631908 | 2018-04-06 | 2018-09-23 |  | 457939 |  | 361627 |  | 8560 | [10 empty] | 0 |  | OE
EPO | RU8405 | 27874 | GE GLOBAL PARTS & PRODUCTS GMBH | 1030503 | P - GE GLOBAL PARTS & PRODUCTS GMBH - 1030503 - Pob1 - 2 COOLING WATER PUMPS | 27890 | POC | EUR | 492660.0541 | 600996 | 2018-04-13 | 2019-03-04 |  | 492660.0541 |  | 381873 |  | 8000 | [10 empty] | 0 |  | OE
FCO | RU8416 | 18549 | Outotec (Finland) Oy | X170785 | P - Outotec (Finland) Oy - X170785 | 18553 | POC | EUR | 327001 | 392270.4 | 2017-11-07 | 2018-02-23 |  | 327001 | 19620 |  |  | 2077635 |  |  |  | 2018-03-12 |  |  |  | 0 |  |  | 0 | EUROPE | OE
EPO | RU8421 | 8600 | MINERA ESCONDIDA LTDA | A3892 | P - MINERA ESCONDIDA LTDA - A3892 | 9938 | POC | USD | 1207516 | 1207516 | 2017-08-16 | 2018-05-24 |  | 1207516 | 0 | 905656 |  | 865510 | 35804 | [6 empty] | 0 |  |  | 32435.73 | LA | OE
EPO | RU8421 | 26297 | SHANGHAI KOHFEE INDUSTRIAL TECHNOLOGY CO LTD | A3900 | P - SHANGHAI KOHFEE INDUSTRIAL TECHNOLOGY CO LTD - A3900 - DWEER Units | 27841 | POC | EUR | 498000 | 607211.4 | 2018-03-28 | 2018-10-26 |  | 498000 |  | 458850 | [8 empty] | 99600 |  | 2018-05-30 | 21830 | 0
AMSS | RU8455 | 8101 | Shell UK Limited | 17319901 | P - Shell 17319901/4513041072 | 8109 | POC | GBP | 251471.5777 | 327541.73 | 2017-07-28 | 2018-02-09 |  | 251471.5777 |  | 203209.36 |  | 189465.5 | [10 empty] | 0 | EUROPE | AM
AMSS | RU8455 | 16998 | Neste OYJ | 17139904 | P-Neste OJY-17139904-Main Fractionation & Depropanizer Pump Assym | 18483 | POC | EUR | 523638.3604 | 557622.49 | 2017-04-28 | 2018-03-22 |  | 523638.3604 | [7 empty] | 2018-04-24 |  |  |  | 0 |  |  | 0 | EUROPE | AM
AMSS | RU8455 | 19478 | Esso Petroleum Company Limited | 17099902 | P - Esso Petroleum 17099902/4520041377 Repairs, Spare Rotors with Installation | 19509 | POC | GBP | 201480 | 251416.82 | 2017-02-27 | 2018-01-28 |  | 201480 | [7 empty] | 2018-01-31 | [6 empty] | 0 | EUROPE | AM
AMSS | RU8455 | 27632 | DOW SILICONES UK LIMITED | 18169906 | P - DOW SILICONES UK LIMITED - 18169906 | 27644 | POC | GBP | 252979.0036 | 348326.79 | 2018-04-30 | 2018-10-10 |  | 252979.0036 |  | 308034 |  | 1516.13 | [10 empty] | 0 | EUROPE | AM
AMSS | RU8455 | 27739 | CNR International | 18-ABD-035 | P - CNR International - 18-ABD-035 | 27741 | POC | GBP | 399833.0017 | 550530.06 | 2018-04-16 | 2018-12-14 |  | 399833.0017 |  | 321213 |  | 6795 | [6 empty] | 99958.25 |  | 2018-05-01 | 8215 | 0 | EUROPE | AM
FCO | RU8458 | 7294 | Al-Yamama Company | 9000086183 | P-Al-Yamama Company-9000086183 | 7400 | POC | USD | 366022 | 399846.1 | 2017-08-31 | 2018-01-23 |  | 366022 |  | 184678.19 | [9 empty] | 0 |  |  | 0 | MIDEAST | OE
FCO | RU8458 | 10392 | Aramco Overseas Company B.V | 9000086968 | P - Aramco Overseas Company B.V. - 9000086968 | 4514 | POC | USD | 438362.17 | 438362.17 | 2017-06-23 | 2018-05-08 |  | 438362.17 |  | 309514.8 | [9 empty] | 0 |  |  | 0 | MIDEAST | OE
FCO | RU8458 | 10406 | Petronash FZE | 9000087234 | P-Petronash FZE-9000087234 | 10439 | POC | USD | 1064340 | 1064340 | 2017-06-30 | 2018-03-28 |  | 1064340 |  | 860390 | [9 empty] | 0 |  |  | 0 | MIDEAST | OE
FCO | RU8458 | 10430 | Aramco Overseas Company BV | 9000079851 | P - Aramco Overseas Company B.V - 9000079851 | 10432 | PIT | USD | 1866485.43 | 873603.93 | 2016-11-28 | 2018-01-16 |  | 1224392.43 |  | 888802 | [9 empty] | 0 |  |  | 0 | MIDEAST | OE
FCO | RU8458 | 10430 | Aramco Overseas Company BV | 9000079851 | P - Aramco Overseas Company B.V - 9000079851 | 10443 | POC | USD |  | 642093.07 | 2016-11-28 | 2018-01-16 |  | 642093 |  | 319780.56 | [5 empty] | 2018-03-31 | [6 empty] | 0 | MIDEAST | OE
FCO | RU8458 | 10588 | GASCO ENGINEERING & CONTRACTING | 9000087915 | P-Gasco Engineering-9000087915 | 10661 | POC | USD | 590240 | 590240 | 2017-07-20 | 2018-04-13 |  | 590240 |  | 435252.25 | [9 empty] | 0 |  |  | 0 | MIDEAST | OE
FCO | RU8458 | 10676 | Frames Process Systems International B.V | 9000087690 | P-Frames Energy Systems-9000087690 | 10686 | POC | USD | 340975.2236 | 364824.2 | 2017-09-04 | 2018-03-02 |  | 340975.2236 |  | 199243.14 | [9 empty] | 0 |  |  | 0 | MIDEAST | OE
FCO | RU8458 | 10690 | Aramco Overseas Company BV | 9000089400 | P-Aramco Overseas Company BV-9000089400 | 10699 | POC | USD | 1379533.1 | 1379533.1 | 2017-09-15 | 2018-08-03 |  | 1379533.1 |  | 1002326.19 | [9 empty] | 0 |  |  | 0 | MIDEAST | OE
FCO | RU8458 | 19612 | Frames Process Systems International B.V | 9000092739 | P - Frames Energy Systems - 9000092739 | 20305 | POC | USD | 261999.2 | 261999.2 | 2017-12-14 | 2018-07-30 |  | 261999.2 |  | 149644.12 | [9 empty] | 0 |  |  | 0 | MIDEAST | OE
FCO | RU8458 | 22099 | Score Danmark A/S | 9000093257 | P-Score Danmark A/S-9000093257 | 22259 | POC | GBP | 318550.9584 | 452023.81 | 2018-02-01 | 2018-07-13 |  | 318550.9584 | 0 | 283510 | [12 empty] | 0 | MIDEAST | OE
FCO | RU8458 | 22100 | Gasco Engineering | 9000093073 | P-Gasco Engineering-9000093073 | 22254 | POC | USD | 1160625 | 1160625 | 2018-01-10 | 2018-10-15 |  | 1160625 | 0 | 774607.5 | [9 empty] | 0 |  |  | 0 | MIDEAST | OE
FCO | RU8458 | 23530 | China Petroleum Pipelines Co | 9000094414 | P-China Petroleum Pipelines-9000094414 | 23534 | POC | USD | 2095526 | 2095526 | 2018-02-23 | 2018-11-30 |  | 2095526 | 0 | 1275999 | [9 empty] | 0 |  |  | 0 | MIDEAST | OE
FCO | RU8458 | 26307 | L&T HYDROCARBON ENGINEERING | 9000082070 | P - L&T HYDROCARBON ENGINEERING - 9000082070 | 26326 | POC | USD | 542737 | 515600.15 | 2017-01-24 | 2018-05-31 |  | 542737 |  | 343731.15 | [9 empty] | 0 |  |  | 0
FCO | RU8458 | 27882 | L&T Hydrocarbon Engineering Limited | 9000096695 | P - L&T Hydrocarbon Engineering Limited - 9000096695 | 27877 | POC | USD | 252292 | 252292 | 2018-04-30 | 2018-10-30 |  | 252292 | [11 empty] | 0 |  |  | 0
FCO | RU8458 | 28175 | ARAMCO OVERSEAS COMPANY BV | 9000096757 and 9000096757 | P - ARAMCO OVERSEAS COMPANY BV- 9000096757-9000096758 | 28177 | POC | USD | 0 |  | 2018-05-03 | 2019-05-02 | [13 empty] | 0 |  |  | 0
FCO | RU8459 | 8660 | Fagerberg | 9000071132 | P-Fagerberg-9000071132- A26 Ball Valves | 8801 | POC | GBP | 3628784.2544 | 4793624 | 2016-03-31 | 2018-05-18 |  | 3628784.2544 | 0 | 3525887 | [12 empty] | 0 | EUROPE | OE
FCO | RU8459 | 13006 | Mobile Valve | 9000091065 | P-Mobile Valve-9000091065 | 13043 | POC | GBP | 261035.8209 | 349788 | 2017-12-20 | 2018-06-06 |  | 261035.8209 | 0 | 135742.8 |  | 119506.9 | 0 | 0 | [8 empty] | 0 | OTHER | OE
IPO | RU8470 | 17169 | Doosan Enpure Ltd | 643662 | P - Doosan - 643662 | 17285 | POC | GBP | 243501.7597 | 329336.13 | 2017-09-04 | 2018-04-19 |  | 243501.7597 | [14 empty] | 0 | EUROPE | OE
IPO | RU8470 | 19634 | Devonport Royal Dockyard Limited | 643947 | P - Devonport Royal Dockyard Limited - 643947 - 01 - 02 - 03 | 19637 | PIT | GBP | 689659.9985 | 193875.58 | 2017-12-06 | 2018-12-19 |  | 143483.9994 | [14 empty] | 0 | EUROPE | AM
IPO | RU8470 | 19634 | Devonport Royal Dockyard Limited | 643947 | P - Devonport Royal Dockyard Limited - 643947 - 04 | 19894 | POC | GBP |  | 230622.81 | 2017-12-06 | 2018-12-19 |  | 170679.9956 | [14 empty] | 0 | EUROPE | AM
IPO | RU8470 | 19634 | Devonport Royal Dockyard Limited | 643947 | P - Devonport Royal Dockyard Limited - 643947 - 05 | 19898 | POC | GBP |  | 507370.2 | 2017-12-06 | 2018-12-19 |  | 375496.0036 | [14 empty] | 0 | EUROPE | AM
IPO | RU8470 | 27615 | BAE Systems Marine Limited | 644315 | P - BAE Systems Marine Limited - 644315 | 27692 | POC | GBP | 1120966.9983 | 1543459.46 | 2018-04-26 | 2019-02-07 |  | 1120966.9983 | [14 empty] | 0
AMSS | RU8500 | 17804 | Exxon Neftegas Limited | 1631243 | P-Exxon Neftegas Limited-1631243 | 17810 | POC | EUR | 301500.0042 | 350689.76 | 2017-07-28 | 2018-04-30 |  | 301500.0042 |  | 20075186 | [5 empty] | 2018-01-02 |  |  |  | 0 |  |  | 0 | RUSCIS | AM
AMSS | RU8500 | 23202 | Exxon Neftegas Limited | MSK-1731042_ECH | P - EXXON NEFTEGAS LIMITED - MSK-1731042_ECH | 23211 | POC | EUR | 547999.9839 | 680615.98 | 2018-02-28 | 2018-08-20 |  | 547999.9839 | 0 | 438400 |  | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | RUSCIS | OE
AMSS | RU8503 | 17439 | AtyrauNefteMash LLP | 172560444/1-2KZ & 171560454KZ | P-AtyrauNefthemashLLP-172560444/1-2KZ | 17451 | POC | KZT | 356586396.2862 | 1136833.09 | 2017-03-31 | 2018-02-28 |  | 356586396.2862 | [7 empty] | 2018-01-18 | [6 empty] | 0 | RUSCIS | OE
FCO | RU8701 | 19391 | Petronas Chemical Isononanol Sdn. Bhd. | 1017100 | P-Petronas Chemicals Isononanol Sdn. Bhd. - A7MF-7-0022-F-00/A7MF100070 | 19424 | POC | USD | 328064 | 328064 | 2017-12-25 | 2018-07-25 |  | 328064 | 0 | 1966085 | [9 empty] | 0 |  |  | 0 | ASIA | OE
FCO | RU8701 | 26458 | Zhejiang Petroleum Chemical Corp. Ltd | 1017464 | P-Zhejiang Petroleum Chemical Corp. Ltd-1017464-PIT | 27781 | PIT | CNY | 6376068.3575 | 861650.08 | 2018-04-11 | 2018-07-30 |  | 5404786.293 |  | 4088782.39 | [12 empty] | 0 | ASIA | OE
FCO | RU8701 | 26458 | Zhejiang Petroleum Chemical Corp. Ltd | 1017464 | P-Zhejiang Petroleum Chemical Corp. Ltd-1017464-POC | 27782 | POC | CNY |  | 154845.21 | 2018-04-11 | 2018-07-30 |  | 971282.0645 |  | 706108.15 | [12 empty] | 0 | ASIA | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-Diesel Hydrocracker Reaction Unit - Train A-2 HDO Pump | 10329 | POC | CNY | 200913224.8534 | 1154395.15 | 2017-02-15 | 2018-08-30 |  | 7932591.5853 |  | 7123468 |  | 3334244 | [6 empty] | 22671441 | May/31/2018 | 2018-05-31 |  | 2009132.25 | CHINA | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-Diesel Hydrocracker Reaction Unit - Train B-2 HDO Pumps | 10330 | POC | CNY |  | 1154395.15 | 2017-02-15 | 2018-08-30 |  | 7932591.5853 |  | 7123468 |  | 3292620 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-H-Oil-Train Fraction Section Unit - Train A-2 HDO/HSO Pumps | 10331 | POC | CNY |  | 1044892.72 | 2017-02-15 | 2018-08-30 |  | 7180129.9565 |  | 6449775 |  | 4397648 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-H-Oil-Train Fraction Section Unit - Train B-2 HDO/HSO Pumps | 10332 | POC | CNY |  | 1044892.72 | 2017-02-15 | 2018-08-30 |  | 7180129.9565 |  | 6449775 |  | 4198419 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-VGO Hydrocracker-Fractionator Section Unit - SR VGO Unit-2 HDO/HSO Pumps | 10333 | POC | CNY |  | 1008897.76 | 2017-02-15 | 2018-08-30 |  | 6932785.4343 |  | 6240968 |  | 4434159 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-VGO Hydrocracker-Fractionator Section Unit - Mixed VGO Unit-3 HDO/HSO Pumps | 10334 | POC | CNY |  | 1876810.54 | 2017-02-15 | 2018-08-30 |  | 12896772.3892 |  | 11645965 |  | 5892328 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-Base Oil Isodewaxing Unit - Dewaxing Unit-1 HDO Pump | 10335 | POC | CNY |  | 477832.17 | 2017-02-15 | 2018-08-30 |  | 3283492.1828 |  | 2954997 |  | 2161840 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-Atomsphericand & Vacoom Distallation Unit-2 HDX Pumps | 10336 | POC | CNY |  | 413324.37 | 2017-02-15 | 2018-08-30 |  | 2840217.5975 |  | 3029406 |  | 3080463 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-Atomsphericand & Vacoom Distallation Unit-2 HDX Pumps | 10337 | POC | CNY |  | 333806.24 | 2017-02-15 | 2018-08-30 |  | 2293797.38 |  | 1926790 |  | 2098022 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-Atomsphericand & Vacoom Distallation Unit-2 HDX Pumps | 10338 | POC | CNY |  | 234472.42 | 2017-02-15 | 2018-08-30 |  | 1611210.811 |  | 1892195 |  | 1921172 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-H-Oil-Train Fraction Section Unit-4 HED Pumps | 10339 | POC | CNY |  | 458661.67 | 2017-02-15 | 2018-08-30 |  | 3151759.3468 |  | 3290359 |  | 2943597 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-H-Oil-Train Fraction Section Unit-4 HED Pumps | 10340 | POC | CNY |  | 431685.56 | 2017-02-15 | 2018-08-30 |  | 2966389.1439 |  | 3061017 |  | 2964780 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-H-Oil-Train Fraction Section Unit-4 HDX Pumps | 10341 | POC | CNY |  | 511874.09 | 2017-02-15 | 2018-08-30 |  | 3517416.111 |  | 3788527 |  | 3748326 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-VGO Hydrocracker-Fractionator Section Unit-2 HDX Pumps | 10342 | POC | CNY |  | 181540.25 | 2017-02-15 | 2018-08-30 |  | 1247479.8249 |  | 1360151 |  | 1297037 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-VGO Hydrocracker-Fractionator Section Unit-2 HDX Pumps | 10343 | POC | CNY |  | 420667.47 | 2017-02-15 | 2018-08-30 |  | 2890676.7607 |  | 3052906 |  | 3050522 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-VGO Hydrocracker-Fractionator Section Unit-2 HDX Pumps | 10344 | POC | CNY |  | 181937.33 | 2017-02-15 | 2018-08-30 |  | 1250208.4169 |  | 1362988 |  | 1293394 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-H-Oil-Train Fraction Section Unit-4 HPX Pumps | 10345 | POC | CNY |  | 199097.37 | 2017-02-15 | 2018-08-30 |  | 1368126.0892 |  | 1844809 |  | 1865655 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-Continuous Catalytic Reforming Unit-6 HDX Pumps | 10346 | POC | CNY |  | 740944.38 | 2017-02-15 | 2018-08-30 |  | 5091505.4121 |  | 5523396 |  | 5519565 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-Continuous Catalytic Reforming Unit-6 HED Pumps | 10347 | POC | CNY |  | 668117.89 | 2017-02-15 | 2018-08-30 |  | 4591067.7572 |  | 4668142 |  | 4253532 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-Disproportionate Unit-4 HED Pumps | 10348 | POC | CNY |  | 583468.49 | 2017-02-15 | 2018-08-30 |  | 4009387.2831 |  | 4126418 |  | 3539788 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-Aromatic hydrocarbon Isomerization-6 HDX Pumps | 10349 | POC | CNY |  | 899561.98 | 2017-02-15 | 2018-08-30 |  | 6181468.9649 |  | 6894630 |  | 6947781 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-PX Unit-4 HED Pumps | 10350 | POC | CNY |  | 756980.8 | 2017-02-15 | 2018-08-30 |  | 5201701.9686 |  | 5409345 |  | 4956561 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-PX Unit-6 HED Pumps | 10351 | POC | CNY |  | 866746.17 | 2017-02-15 | 2018-08-30 |  | 5955970.4272 |  | 6233302 |  | 5659688 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-PX Unit-4 HED Pumps | 10352 | POC | CNY |  | 756980.8 | 2017-02-15 | 2018-08-30 |  | 5201701.9686 |  | 5409345 |  | 5305153 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-PX Unit-6 HED Pumps | 10353 | POC | CNY |  | 866746.17 | 2017-02-15 | 2018-08-30 |  | 5955970.4272 |  | 6233302 |  | 5892421 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-PX Unit-8 HED Pumps | 10354 | POC | CNY |  | 1735224.34 | 2017-02-15 | 2018-08-30 |  | 11923842.5404 |  | 12400796 |  | 12065220 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-PX Unit-14 HDX Pumps | 10355 | POC | CNY |  | 2067067.31 | 2017-02-15 | 2018-08-30 |  | 14204149.0294 |  | 14772315 |  | 12737697 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-PX Unit-8 HDX Pumps | 10356 | POC | CNY |  | 1081675.53 | 2017-02-15 | 2018-08-30 |  | 7432888.3028 |  | 7878862 |  | 7647198 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-PX Unit-14 HDX Pumps | 10357 | POC | CNY |  | 2870794.88 | 2017-02-15 | 2018-08-30 |  | 19727078.1223 |  | 21049847 |  | 20153473 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-PX Unit-8 HDX Pumps | 10358 | POC | CNY |  | 1078379.69 | 2017-02-15 | 2018-08-30 |  | 7410240.4663 |  | 8006466 |  | 7732056 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-Atomsphericand & Vacoom Distallation Unit-2 HDX Pumps | 10359 | POC | CNY |  | 330489.37 | 2017-02-15 | 2018-08-30 |  | 2271005.0328 |  | 2031049 |  | 2113762 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-Atomsphericand & Vacoom Distallation Unit-2 HDX Pumps | 10360 | POC | CNY |  | 413324.37 | 2017-02-15 | 2018-08-30 |  | 2840217.5975 |  | 2919500 |  | 2962452 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-Atomsphericand & Vacoom Distallation Unit-2 HDX Pumps | 10361 | POC | CNY |  | 333806.24 | 2017-02-15 | 2018-08-30 |  | 2293797.38 |  | 1963392 |  | 2102713 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-Atomsphericand & Vacoom Distallation Unit-2 HDX Pumps | 10362 | POC | CNY |  | 228264.16 | 2017-02-15 | 2018-08-30 |  | 1568549.8634 |  | 1840778 |  | 1869755 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-Atomsphericand & Vacoom Distallation Unit-2 HDX Pumps | 10363 | POC | CNY |  | 337243.45 | 2017-02-15 | 2018-08-30 |  | 2317416.6607 |  | 2261173 |  | 2410666 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-Naphtha Hydrotreating Unit-2 WTB Pumps | 10364 | POC | CNY |  | 484459.61 | 2017-02-15 | 2018-08-30 |  | 3329033.5858 |  | 3505139 |  | 2841197 | [10 empty] | 0 |  | OE
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-Extended warranty service 12 months | 11067 | SL | CNY |  | 50722.06 | 2017-02-15 | 2018-08-30 |  | 348544 |  |  |  | 0 | [10 empty] | 0 |  | OE | 2020-02-22 | 2021-02-16
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-Atomsphericand & Vacoom Distallation Unit-Spares for 2 HDX Pumps | 17560 | POC | CNY |  | 15845.77 | 2017-02-15 | 2018-08-30 |  | 108886.4777 |  | 69535 |  | 20445 | [10 empty] | 0 |  | AM
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-Atomsphericand & Vacoom Distallation Unit-Spares for 2 HDX Pumps | 17561 | POC | CNY |  | 12064.15 | 2017-02-15 | 2018-08-30 |  | 82900.5343 |  | 54014 |  | 14259 | [10 empty] | 0 |  | AM
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-Atomsphericand & Vacoom Distallation Unit-Spares for 2 HDX Pumps | 17562 | POC | CNY |  | 12016.13 | 2017-02-15 | 2018-08-30 |  | 82570.558 |  | 50656 |  | 20523 | [10 empty] | 0 |  | AM
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-H-Oil-Train Fraction Section Unit-spares for 4 HED Pumps | 17563 | POC | CNY |  | 27602.54 | 2017-02-15 | 2018-08-30 |  | 189674.8064 |  | 126808 |  | 43665 | [10 empty] | 0 |  | AM
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-H-Oil-Train Fraction Section Unit-spares for 4 HED Pumps | 17564 | POC | CNY |  | 26918.15 | 2017-02-15 | 2018-08-30 |  | 184971.9225 |  | 119377 |  | 22434 | [10 empty] | 0 |  | AM
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-H-Oil-Train Fraction Section Unit-spares for 4 HDX Pumps | 17565 | POC | CNY |  | 23760.16 | 2017-02-15 | 2018-08-30 |  | 163271.3419 |  | 100202 |  | 35646 | [10 empty] | 0 |  | AM
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-VGO Hydrocracker-Fractionator Section Unit- spares for 2 HDX Pumps | 17566 | POC | CNY |  | 11491.5 | 2017-02-15 | 2018-08-30 |  | 78965.4879 |  | 48966 |  | 9983 | [10 empty] | 0 |  | AM
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-VGO Hydrocracker-Fractionator Section Unit-spares for 2 HDX Pumps | 17567 | POC | CNY |  | 15141.78 | 2017-02-15 | 2018-08-30 |  | 104048.9096 |  | 69413 |  | 15992 | [10 empty] | 0 |  | AM
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-VGO Hydrocracker-Fractionator Section Unit-spares for 2 HDX Pumps | 17568 | POC | CNY |  | 11491.5 | 2017-02-15 | 2018-08-30 |  | 78965.4879 |  | 48966 |  | 8280 | [10 empty] | 0 |  | AM
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-H-Oil-Train Fraction Section Unit-spares for 4 HPX Pumps | 17569 | POC | CNY |  | 17285.61 | 2017-02-15 | 2018-08-30 |  | 118780.5445 |  | 82944 |  | 5567 | [10 empty] | 0 |  | AM
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-Continuous Catalytic Reforming Unit-spares for 6 HDX Pumps | 17570 | POC | CNY |  | 40265.3 | 2017-02-15 | 2018-08-30 |  | 276688.775 |  | 202151 |  | 43993 | [10 empty] | 0 |  | AM
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-Continuous Catalytic Reforming Unit-spares for 6 HED Pumps | 17571 | POC | CNY |  | 42654.43 | 2017-02-15 | 2018-08-30 |  | 293106.024 |  | 203131 |  | 49530 | [10 empty] | 0 |  | AM
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-Disproportionate Unit-spares for 4 HED Pumps | 17572 | POC | CNY |  | 32356.53 | 2017-02-15 | 2018-08-30 |  | 222342.5294 |  | 160263 |  | 43269 | [10 empty] | 0 |  | AM
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-Aromatic hydrocarbon Isomerization-spares for 6 HDX Pumps | 17573 | POC | CNY |  | 37278.45 | 2017-02-15 | 2018-08-30 |  | 256164.2075 |  | 197075 |  | 41462 | [10 empty] | 0 |  | AM
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-PX Unit-spares for 4 HED Pumps | 17574 | POC | CNY |  | 40798.21 | 2017-02-15 | 2018-08-30 |  | 280350.7424 |  | 191723 |  | 46429 | [10 empty] | 0 |  | AM
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-PX Unit-spares for 6 HED Pumps | 17575 | POC | CNY |  | 46019.88 | 2017-02-15 | 2018-08-30 |  | 316232.1956 |  | 241607 |  | 47404 | [10 empty] | 0 |  | AM
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-PX Unit-spares for 4 HED Pumps | 17576 | POC | CNY |  | 40798.21 | 2017-02-15 | 2018-08-30 |  | 280350.7424 |  | 191723 |  | 62424 | [10 empty] | 0 |  | AM
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-PX Unit-spares for 6 HED Pumps | 17577 | POC | CNY |  | 46019.88 | 2017-02-15 | 2018-08-30 |  | 316232.1956 |  | 241607 |  | 47499 | [10 empty] | 0 |  | AM
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-PX Unit-spares for 8 HED Pumps | 17578 | POC | CNY |  | 81788.55 | 2017-02-15 | 2018-08-30 |  | 562021.7336 |  | 374208 |  | 92499 | [10 empty] | 0 |  | AM
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-PX Unit-spares for 14 HDX Pumps | 17579 | POC | CNY |  | 87079.09 | 2017-02-15 | 2018-08-30 |  | 598376.4369 |  | 451715 |  | 92874 | [10 empty] | 0 |  | AM
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-PX Unit-spares for 8 HDX Pumps | 17580 | POC | CNY |  | 55852.42 | 2017-02-15 | 2018-08-30 |  | 383797.9022 |  | 272711 |  | 63519 | [10 empty] | 0 |  | AM
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-PX Unit-spares for 14 HDX Pumps | 17581 | POC | CNY |  | 94763.88 | 2017-02-15 | 2018-08-30 |  | 651183.5718 |  | 464847 |  | 109740 | [10 empty] | 0 |  | AM
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-PX Unit-spares for 8 HDX Pumps | 17582 | POC | CNY |  | 53098.93 | 2017-02-15 | 2018-08-30 |  | 364876.9014 |  | 252267 |  | 59757 | [10 empty] | 0 |  | AM
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-Atomsphericand & Vacoom Distallation Unit-Spares for 2 HDX Pumps | 17583 | POC | CNY |  | 12496.42 | 2017-02-15 | 2018-08-30 |  | 85870.9395 |  | 53770 |  | 13191 | [10 empty] | 0 |  | AM
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-Atomsphericand & Vacoom Distallation Unit-Spares for 2 HDX Pumps | 17584 | POC | CNY |  | 15845.77 | 2017-02-15 | 2018-08-30 |  | 108886.4777 |  | 69535 |  | 20075 | [10 empty] | 0 |  | AM
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-Atomsphericand & Vacoom Distallation Unit-Spares for 2 HDX Pumps | 17585 | POC | CNY |  | 12064.15 | 2017-02-15 | 2018-08-30 |  | 82900.5343 |  | 54014 |  | 14091 | [10 empty] | 0 |  | AM
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-Atomsphericand & Vacoom Distallation Unit-Spares for 2 HDX Pumps | 17586 | POC | CNY |  | 12016.13 | 2017-02-15 | 2018-08-30 |  | 82570.558 |  | 50656 |  | 9761 | [10 empty] | 0 |  | AM
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-Atomsphericand & Vacoom Distallation Unit-Spares for 2 HDX Pumps | 17587 | POC | CNY |  | 12496.42 | 2017-02-15 | 2018-08-30 |  | 85870.9395 |  | 53770 |  | 13433 | [10 empty] | 0 |  | AM
EPO | RU8709 | 4844 | Hengli Petrochemical (Dalian) Refinery Co., Ltd. | 22217015 | P-Hengli Petrochemical (Dalian) Refinery Co Ltd-1004226-Naphtha Hydrotreating Unit-spares for 2 WTB Pumps | 17588 | POC | CNY |  | 20526.97 | 2017-02-15 | 2018-08-30 |  | 141054.0139 |  | 243954 |  | 313418 | [10 empty] | 0 |  | AM
EPO | RU8709 | 6885 | Shanghai Tai Ao Machine & Electric Co. | 22217049 | P-Shanghai Tai Ao Machine & Electric Co-1004500-2 units HED Pumps | 6892 | POC | CNY | 5550040.9867 | 210823.78 | 2017-06-12 | 2018-06-01 |  | 1429237.6517 |  | 1275166 |  | 660740 | [10 empty] | 0 | CHINA | OE
EPO | RU8709 | 6885 | Shanghai Tai Ao Machine & Electric Co. | 22217049 | P-Shanghai Tai Ao Machine & Electric Co-1004500-Spare parts for 2 units HED Pumps | 6893 | POC | CNY |  | 20816.76 | 2017-06-12 | 2018-06-01 |  | 141123.0611 |  | 125910 |  | 24963 | [10 empty] | 0 | - | AM
EPO | RU8709 | 6885 | Shanghai Tai Ao Machine & Electric Co. | 22217049 | P-Shanghai Tai Ao Machine & Electric Co-1004500-4 units HDX/HED Pumps | 6894 | POC | CNY |  | 357625.6 | 2017-06-12 | 2018-06-01 |  | 2424451.23 |  | 2163095 |  | 1282097 | [10 empty] | 0 | - | OE
EPO | RU8709 | 6885 | Shanghai Tai Ao Machine & Electric Co. | 22217049 | P-Shanghai Tai Ao Machine & Electric Co-1004500-2 units WXB Pumps | 6895 | POC | CNY |  | 155623.82 | 2017-06-12 | 2018-06-01 |  | 1055020.5629 |  | 941289 |  | 552928 | [10 empty] | 0 | - | OE
EPO | RU8709 | 6885 | Shanghai Tai Ao Machine & Electric Co. | 22217049 | P-Shanghai Tai Ao Machine & Electric Co-1004500-Spare parts for 4 units HDX/HED Pumps | 17366 | POC | CNY |  | 56919.88 | 2017-06-12 | 2018-06-01 |  | 385876.9425 |  | 344279 |  | 41941 | [10 empty] | 0 |  | AM
EPO | RU8709 | 6885 | Shanghai Tai Ao Machine & Electric Co. | 22217049 | P-Shanghai Tai Ao Machine & Electric Co-1004500-Spare parts for 2 units WXB Pumps | 17367 | POC | CNY |  | 16864.8 | 2017-06-12 | 2018-06-01 |  | 114331.5386 |  | 102007 |  | 31090 | [10 empty] | 0 |  | AM
EPO | RU8709 | 6919 | Zhejiang Petroleum & Chemical Co., Ltd. | 222-17025 | P-Zhejiang Petroleum & Chemical Co Ltd-1004325-2 units WTB Pumps | 7000 | POC | CNY | 3831794.8611 | 430488.94 | 2017-06-05 | 2018-04-30 |  | 2918413.6708 |  | 2627448 |  | 2504642 | [10 empty] | 0 | CHINA | OE
EPO | RU8709 | 6919 | Zhejiang Petroleum & Chemical Co., Ltd. | 222-17025 | P-Zhejiang Petroleum & Chemical Co Ltd-1004325-Service | 7366 | POC | CNY |  | 2950.16 | 2017-06-05 | 2018-04-30 |  | 20000.0197 |  | 18006 |  | 0 | [10 empty] | 0 | - | OE
EPO | RU8709 | 6919 | Zhejiang Petroleum & Chemical Co., Ltd. | 222-17025 | P-Zhejiang Petroleum & Chemical Co Ltd-1004325-Spare parts for 2 units WTB Pumps | 17368 | POC | CNY |  | 131780.74 | 2017-06-05 | 2018-04-30 |  | 893381.1706 |  | 804311 |  | 610245 | [10 empty] | 0 | - | AM
EPO | RU8709 | 7013 | Guangdong Huizhou LNG Power Co., Ltd | 22217054 | P-Guangdong Huizhou LNG Power Co Ltd-1004527-7 units WXH Pumps | 7033 | POC | CNY | 8180964.0689 | 1097582.03 | 2017-06-13 | 2018-03-05 |  | 7440837.8556 |  | 7267854 |  | 7792515 | [6 empty] | 1306965 | May/31/2018 | 2018-05-31 |  | 0 | CHINA | OE
EPO | RU8709 | 7013 | Guangdong Huizhou LNG Power Co., Ltd | 22217054 | P-Guangdong Huizhou LNG Power Co Ltd-1004527-Service | 7035 | POC | CNY |  | 11346.76 | 2017-06-13 | 2018-03-05 |  | 76923.0901 |  | 74615 |  | 2850 | [10 empty] | 0 | - | AM
EPO | RU8709 | 7013 | Guangdong Huizhou LNG Power Co., Ltd | 22217054 | P-Guangdong Huizhou LNG Power Co Ltd-1004527-Extended warranty 12 months | 7036 | SL | CNY |  | 2534.19 | 2017-06-13 | 2018-03-05 |  | 17180.0343 |  | 16665 |  | 0 | [10 empty] | 0 | - | OE | 2019-09-22 | 2020-09-16
EPO | RU8709 | 7013 | Guangdong Huizhou LNG Power Co., Ltd | 22217054 | P-Guangdong Huizhou LNG Power Co Ltd-1004527-Spare parts for 7 units WXH Pumps | 17369 | POC | CNY |  | 95293.48 | 2017-06-13 | 2018-03-05 |  | 646023.0889 |  | 626642 |  | 446932 | [10 empty] | 0 | - | AM
EPO | RU8709 | 7284 | Zhejiang Petroleum & Chemical Co., Ltd. | 222 - 17068 | P-Zhejiang Petroleum & Chemical Co Ltd-1004576-8 units HDX Pumps | 7373 | POC | CNY | 8829059.8859 | 1182386.35 | 2017-06-29 | 2018-06-30 |  | 7950365.8177 |  | 6686258 |  | 3577743 | [10 empty] | 0 | CHINA | OE
EPO | RU8709 | 7284 | Zhejiang Petroleum & Chemical Co., Ltd. | 222 - 17068 | P-Zhejiang Petroleum & Chemical Co Ltd-1004576-Technical Service | 7375 | POC | CNY |  | 4164.19 | 2017-06-29 | 2018-06-30 |  | 28000.0136 |  | 23548 |  | 0 | [10 empty] | 0 |  | OE
EPO | RU8709 | 7284 | Zhejiang Petroleum & Chemical Co., Ltd. | 222 - 17068 | P-Zhejiang Petroleum & Chemical Co Ltd-1004576-Spare parts for 8 units HDX Pumps | 17370 | POC | CNY |  | 126516.07 | 2017-06-29 | 2018-06-30 |  | 850694.0547 |  | 952064 |  | 952051 | [10 empty] | 0 |  | AM
EPO | RU8709 | 8620 | Zhejiang Petroleum & Chemical Co., Ltd. | 22217090 | P-Zhejiang Petroleum & Chemical Co Ltd-1004658-4 units WX Pumps | 8625 | POC | CNY | 4871794.8923 | 338211.83 | 2017-08-01 | 2018-05-31 |  | 2251040.321 |  | 1551642 |  | 556941 | [10 empty] | 0 | CHINA | OE
EPO | RU8709 | 8620 | Zhejiang Petroleum & Chemical Co., Ltd. | 22217090 | P-Zhejiang Petroleum & Chemical Co Ltd-1004658-2 units HED Pumps | 16947 | POC | CNY |  | 339440.07 | 2017-08-01 | 2018-05-31 |  | 2259215.1319 |  | 1557277 |  | 738437 | [10 empty] | 0 |  | OE
EPO | RU8709 | 8620 | Zhejiang Petroleum & Chemical Co., Ltd. | 22217090 | P-Zhejiang Petroleum & Chemical Co Ltd-1004658-Spare parts for 4 units WX Pumps | 17371 | POC | CNY |  | 21353.3 | 2017-08-01 | 2018-05-31 |  | 142121.4015 |  | 103737 |  | 110575 | [10 empty] | 0 |  | AM
EPO | RU8709 | 8620 | Zhejiang Petroleum & Chemical Co., Ltd. | 22217090 | P-Zhejiang Petroleum & Chemical Co Ltd-1004658-Spare parts for 2 units HED Pumps | 17372 | POC | CNY |  | 32966.88 | 2017-08-01 | 2018-05-31 |  | 219418.0379 |  | 151245 |  | 147629 | [10 empty] | 0 |  | AM
EPO | RU8709 | 10092 | PETRONAS CHEMICALS ISONONANOL SDN.BHD. | 22217098 | P-PETRONAS CHEMICALS ISONONANOL SDN.BHD.-1004726-2 units Mark3 ISO pumps | 10904 | PIT | USD | 680800 | 66418 | 2017-09-13 | 2018-03-30 |  | 66418 |  | 363858 |  | 285410 | [7 empty] | 0 |  |  | 0 | OTHER | OE
EPO | RU8709 | 10092 | PETRONAS CHEMICALS ISONONANOL SDN.BHD. | 22217098 | P-PETRONAS CHEMICALS ISONONANOL SDN.BHD.-1004726-8 units HPX pumps | 17113 | POC | USD |  | 282922 | 2017-09-13 | 2018-03-30 |  | 282922 |  | 1549933 |  | 1393160 | [10 empty] | 0 |  | OE
EPO | RU8709 | 10092 | PETRONAS CHEMICALS ISONONANOL SDN.BHD. | 22217098 | P-PETRONAS CHEMICALS ISONONANOL SDN.BHD.-1004726-Spare parts for 8 units HPX pumps | 17114 | POC | USD |  | 432 | 2017-09-13 | 2018-03-30 |  | 432 |  | 2367 |  | 555 | [10 empty] | 0 |  | AM
EPO | RU8709 | 10092 | PETRONAS CHEMICALS ISONONANOL SDN.BHD. | 22217098 | P-PETRONAS CHEMICALS ISONONANOL SDN.BHD.-1004726-4 units ERPN pumps | 17117 | POC | USD |  | 201804 | 2017-09-13 | 2018-03-30 |  | 201804 |  | 1105544 |  | 906867 | [10 empty] | 0 |  | OE
EPO | RU8709 | 10092 | PETRONAS CHEMICALS ISONONANOL SDN.BHD. | 22217098 | P-PETRONAS CHEMICALS ISONONANOL SDN.BHD.-1004726-Spare parts for 4 units ERPN pumps | 17118 | POC | USD |  | 216 | 2017-09-13 | 2018-03-30 |  | 216 |  | 1183 |  | 647 | [10 empty] | 0 |  | AM
EPO | RU8709 | 10092 | PETRONAS CHEMICALS ISONONANOL SDN.BHD. | 22217098 | P-PETRONAS CHEMICALS ISONONANOL SDN.BHD.-1004726-2 units WXB pumps | 17119 | POC | USD |  | 126572 | 2017-09-13 | 2018-03-30 |  | 126572 |  | 693400 |  | 642593 | [10 empty] | 0 |  | OE
EPO | RU8709 | 10092 | PETRONAS CHEMICALS ISONONANOL SDN.BHD. | 22217098 | P-PETRONAS CHEMICALS ISONONANOL SDN.BHD.-1004726-Spare parts for 2 units Mark3 ISO pumps | 17373 | PIT | USD |  | 80 | 2017-09-13 | 2018-03-30 |  | 80 |  | 2801 |  | 2801 | [10 empty] | 0 |  | AM
EPO | RU8709 | 10092 | PETRONAS CHEMICALS ISONONANOL SDN.BHD. | 22217098 | P-PETRONAS CHEMICALS ISONONANOL SDN.BHD.-1004726-Spare parts for 2 units WXB pumps | 17374 | POC | USD |  | 2356 | 2017-09-13 | 2018-03-30 |  | 2356 |  | 12907 |  | 290 | [10 empty] | 0 |  | AM
EPO | RU8709 | 10098 | Shanghai Tai Ao Machine & Electric Co. | 22217103 | P-Shanghai Tai Ao Machine & Electric Co.-1004739-2 units WXB pumps | 10969 | POC | CNY | 4017094.012 | 135638.33 | 2017-09-18 | 2018-04-30 |  | 898046.4402 |  | 776451 |  | 431541 | [10 empty] | 0 | CHINA | OE
EPO | RU8709 | 10098 | Shanghai Tai Ao Machine & Electric Co. | 22217103 | P-Shanghai Tai Ao Machine & Electric Co.-1004739-Field Service | 10971 | POC | CNY |  | 12702.61 | 2017-09-18 | 2018-04-30 |  | 84102.5814 |  | 72715 |  | 0 | [10 empty] | 0 | CHINA | OE
EPO | RU8709 | 10098 | Shanghai Tai Ao Machine & Electric Co. | 22217103 | P-Shanghai Tai Ao Machine & Electric Co.-1004739-2 units HDX pumps | 16950 | POC | CNY |  | 156301.25 | 2017-09-18 | 2018-04-30 |  | 1034853.3572 |  | 894734 |  | 431249 | [10 empty] | 0 |  | OE
EPO | RU8709 | 10098 | Shanghai Tai Ao Machine & Electric Co. | 22217103 | P-Shanghai Tai Ao Machine & Electric Co.-1004739-6 units HPX pumps | 16951 | POC | CNY |  | 253035.21 | 2017-09-18 | 2018-04-30 |  | 1675318.2496 |  | 1448480 |  | 665672 | [10 empty] | 0 |  | OE
EPO | RU8709 | 10098 | Shanghai Tai Ao Machine & Electric Co. | 22217103 | P-Shanghai Tai Ao Machine & Electric Co.-1004739-Spare parts for 2 units WXB pumps | 17375 | POC | CNY |  | 12859.45 | 2017-09-18 | 2018-04-30 |  | 85141.0018 |  | 73613 |  | 39511 | [10 empty] | 0 |  | AM
EPO | RU8709 | 10098 | Shanghai Tai Ao Machine & Electric Co. | 22217103 | P-Shanghai Tai Ao Machine & Electric Co.-1004739-Spare parts for 2 units HDX pumps | 17377 | POC | CNY |  | 7140.05 | 2017-09-18 | 2018-04-30 |  | 47273.4845 |  | 48780 |  | 48780 | [10 empty] | 0 |  | AM
EPO | RU8709 | 10098 | Shanghai Tai Ao Machine & Electric Co. | 22217103 | P-Shanghai Tai Ao Machine & Electric Co.-1004739-Spare parts for 6 units HPX pumps | 17378 | POC | CNY |  | 29053.33 | 2017-09-18 | 2018-04-30 |  | 192358.8973 |  | 166314 |  | 14918 | [10 empty] | 0 |  | AM
EPO | RU8709 | 10569 | Huairen Town Hongsifang Industrial Equipment Co., | 22213096 | P-Huairen Town Hongsifang Industrial Equipment Co., -1001593-4 units DMXD Pumps | 10972 | POC | CNY | 3504273.5196 | 491713.29 | 2013-11-20 | 2018-12-31 |  | 3255579.5232 |  | 3255579.5232 |  | 1477492 | [10 empty] | 0 | CHINA | OE
EPO | RU8709 | 10569 | Huairen Town Hongsifang Industrial Equipment Co., | 22213096 | P-Huairen Town Hongsifang Industrial Equipment Co., -1001593-Spare parts for 4 units DMXD Pumps | 17360 | POC | CNY |  | 37562.02 | 2013-11-20 | 2018-12-31 |  | 248693.9964 |  | 248693.9964 |  | 225238 | [10 empty] | 0 |  | AM
EPO | RU8709 | 10616 | Hunan Taohuajiang Nuclear Power Co., Ltd. | 22215105 | P-Hunan Taohuajiang Nuclear Power Co Ltd.-1003088-2 units CAM Pump (THJ1-CVS-MP-01A/B) | 10973 | POC | CNY | 14145461.1857 | 782424.52 | 2015-10-27 | 2018-08-30 |  | 5180346.5506 |  | 4227397 |  | 72979 | [10 empty] | 0 | CHINA | OE
EPO | RU8709 | 10616 | Hunan Taohuajiang Nuclear Power Co., Ltd. | 22215105 | P-Hunan Taohuajiang Nuclear Power Co Ltd.-1003088-2 units CAM Pump (THJ2-CVS-MP-01A/B) | 10974 | POC | CNY |  | 778074.11 | 2015-10-27 | 2018-08-30 |  | 5151542.9653 |  | 4203892 |  | 53828 | [10 empty] | 0 | - | OE
EPO | RU8709 | 10616 | Hunan Taohuajiang Nuclear Power Co., Ltd. | 22215105 | P-Hunan Taohuajiang Nuclear Power Co Ltd.-1003088-Technical service | 10976 | POC | CNY |  | 22720.11 | 2015-10-27 | 2018-08-30 |  | 150427.3453 |  | 122756 |  | 0 | [10 empty] | 0 | - | OE
EPO | RU8709 | 10616 | Hunan Taohuajiang Nuclear Power Co., Ltd. | 22215105 | P-Hunan Taohuajiang Nuclear Power Co Ltd.-1003088-Extended warranty service | 11064 | SL | CNY |  | 113594 | 2015-10-27 | 2018-08-30 |  | 752093 |  |  |  | 0 | [10 empty] | 0 | - | OE | 2019-01-01 | 2020-01-01
EPO | RU8709 | 10616 | Hunan Taohuajiang Nuclear Power Co., Ltd. | 22215105 | P-Hunan Taohuajiang Nuclear Power Co Ltd.-1003088-Spare parts for 2 units CAM Pump (THJ1-CVS-MP-01A/B) | 17361 | POC | CNY |  | 413393.71 | 2015-10-27 | 2018-08-30 |  | 2737034.2121 |  | 2233544 |  | 7285 | [10 empty] | 0 | - | AM
EPO | RU8709 | 10616 | Hunan Taohuajiang Nuclear Power Co., Ltd. | 22215105 | P-Hunan Taohuajiang Nuclear Power Co Ltd.-1003088-Mini-flow orifice | 17362 | POC | CNY |  | 26283.04 | 2015-10-27 | 2018-08-30 |  | 174017.1124 |  | 142006 |  | 0 | [10 empty] | 0 |  | OE
EPO | RU8709 | 11530 | Beijing Maowei Yuning Gaokeji Ltd. | 22212023 | P-Beijing Maowei Yuning Gaokeji Ltd.-1001426-2 units HDXN Pumps | 12659 | POC | CNY | 3418803.4005 | 542210.38 | 2012-03-13 | 2018-12-31 |  | 3414423.0479 |  | 2936404 |  | 0 | [10 empty] | 0 | CHINA | OE
EPO | RU8709 | 11530 | Beijing Maowei Yuning Gaokeji Ltd. | 22212023 | P-Beijing Maowei Yuning Gaokeji Ltd.-1001426- Spare parts for 2 units HDXN pumps | 17359 | POC | CNY |  | 695.6 | 2012-03-13 | 2018-12-31 |  | 4380.3526 |  | 3767 |  | 0 | [10 empty] | 0 | - | AM
EPO | RU8709 | 11540 | BEIJING MERRYDELY TECHNOLOGY DEVELOPMENT CO., LTD | 370-17435 | P-BEIJING MERRYDELY TECHNOLOGY DEVELOPMENT CO., LTD-1004767-3 units HDX pumps and spare parts | 12668 | POC | CNY | 5032833.3124 | 757611.02 | 2017-09-10 | 2018-05-28 |  | 5032833.3124 |  | 3724297 |  | 1709561 | [10 empty] | 0 | CHINA | OE
EPO | RU8709 | 17059 | LLC Mariisky NPZ ltd | 24700997KT | P-LLC Mariisky NPZ ltd-1003780-6 units Mark 3 ISO Pumps | 17127 | PIT | USD | 1140250 | 185366.4 | 2016-11-28 | 2018-01-30 |  | 185366.4 |  | 996197 |  | 990046 | [7 empty] | 0 |  |  | 148376 | EUROPE | OE
EPO | RU8709 | 17059 | LLC Mariisky NPZ ltd | 24700997KT | P-LLC Mariisky NPZ ltd-1003780-Spare parts for 6 units Mark 3 ISO Pumps | 17128 | PIT | USD |  | 26858.29 | 2016-11-28 | 2018-01-30 |  | 26858.29 |  | 190904 |  | 190904 | [10 empty] | 0 |  | AM
EPO | RU8709 | 17059 | LLC Mariisky NPZ ltd | 24700997KT | P-LLC Mariisky NPZ ltd-1003780-14 units HPX pumps | 17130 | POC | USD |  | 845317.64 | 2016-11-28 | 2018-01-30 |  | 845317.64 |  | 5291571 |  | 5291810 | [10 empty] | 0 |  | OE
EPO | RU8709 | 17059 | LLC Mariisky NPZ ltd | 24700997KT | P-LLC Mariisky NPZ ltd-1003780-Spare parts for 14 units HPX pumps | 17131 | POC | USD |  | 82707.67 | 2016-11-28 | 2018-01-30 |  | 82707.67 |  | 576514 |  | 576514 | [10 empty] | 0 |  | AM
EPO | RU8709 | 17065 | CNPC Materials Company | 22216116 | P-CNPC Materials Company-1003928-2 units HDO pumps | 17138 | POC | CNY | 2677777.7703 | 372179.47 | 2016-10-31 | 2018-03-30 |  | 2501264.9491 |  | 3019485 |  | 3045663 | [10 empty] | 0 | CHINA | OE
EPO | RU8709 | 17065 | CNPC Materials Company | 22216116 | P-CNPC Materials Company-1003928-Spare parts for 2 units HDO pumps | 17363 | POC | CNY |  | 26264.49 | 2016-10-31 | 2018-03-30 |  | 176512.8212 |  | 152860 |  | 72731 | [10 empty] | 0 |  | AM
EPO | RU8709 | 17078 | PetroChina International Iraq FZE Iraq Branch | 22216114 | P-PetroChina International Iraq FZE Iraq Branch-1003993-5 units DMXD pumps | 17141 | POC | USD | 1693502 | 1249999.98 | 2016-11-10 | 2018-09-30 |  | 1249999.98 |  | 8132874.1187 |  | 8375049 | [7 empty] | 0 |  |  | 0 | IRAQ | OE
EPO | RU8709 | 17078 | PetroChina International Iraq FZE Iraq Branch | 22216114 | P-PetroChina International Iraq FZE Iraq Branch-1003993-Start-up and Commissioning and training | 17143 | POC | USD |  | 115200 | 2016-11-10 | 2018-09-30 |  | 115200 |  | 749525.6908 |  | 13049 | [10 empty] | 0 |  | OE
EPO | RU8709 | 17078 | PetroChina International Iraq FZE Iraq Branch | 22216114 | P-PetroChina International Iraq FZE Iraq Branch-1003993-System Eng. for maintenance Services for three years | 17144 | SL | USD |  | 294000 | 2016-11-10 | 2018-09-30 |  | 294000 |  |  |  | 13049 | [10 empty] | 0 |  | OE | 2018-01-01 | 2020-12-31
EPO | RU8709 | 17078 | PetroChina International Iraq FZE Iraq Branch | 22216114 | P-PetroChina International Iraq FZE Iraq Branch-1003993-Spare parts for 5 units DMXD pumps | 17364 | POC | USD |  | 34302.02 | 2016-11-10 | 2018-09-30 |  | 34302.02 |  | 223179.2121 |  | 139547 | [10 empty] | 0 |  | AM
EPO | RU8709 | 17083 | Sp Olefins(Taixing) Co.,Ltd | 22217005 | P-Sp Olefins(Taixing) Co.,Ltd-1004166-4 units HDX pums | 17145 | POC | CNY | 8170940.1645 | 1117121.67 | 2017-02-01 | 2018-04-30 |  | 7676461.5298 |  | 6953831 |  | 6719279 | [10 empty] | 0 | CHINA | OE
EPO | RU8709 | 17083 | Sp Olefins(Taixing) Co.,Ltd | 22217005 | P-Sp Olefins(Taixing) Co.,Ltd-1004166-Spare parts for 4 units HDX pums | 17365 | POC | CNY |  | 71959.3 | 2017-02-01 | 2018-04-30 |  | 494478.6347 |  | 447930 |  | 172927 | [10 empty] | 0 |  | AM
EPO | RU8709 | 17088 | ALC Aquaecology | 24300982 | P-ALC Aquaecology-1004566-9 units HPX pumps | 17146 | POC | USD | 444676 | 361615 | 2017-08-18 | 2018-04-30 |  | 361615 |  | 2036798 |  | 2445906 | [7 empty] | 0 |  |  | 0 | EUROPE | OE
EPO | RU8709 | 17088 | ALC Aquaecology | 24300982 | P-ALC Aquaecology-1004566-Spare parts for 9 units HPX pums | 17147 | POC | USD |  | 83061 | 2017-08-18 | 2018-04-30 |  | 83061 |  | 467841 |  | 365611 | [10 empty] | 0 |  | AM
EPO | RU8709 | 17855 | Zhongke（Guangdong）Refinery & Petrochemical Co., Ltd. | 22217132 | P-Zhongke（Guangdong）Refinery & Petrochemical Co., Ltd.-1004969-P-201A/B Pumps | 20624 | POC | CNY | 4986859.2749 | 742604 | 2017-12-18 | 2019-01-30 |  | 4869438.634 |  | 3846859 |  | 103503 | [10 empty] | 0 | CHINA | OE
EPO | RU8709 | 17855 | Zhongke（Guangdong）Refinery & Petrochemical Co., Ltd. | 22217132 | P-Zhongke（Guangdong）Refinery & Petrochemical Co., Ltd.-1004969-P-201A/B Pumps Spare Parts | 20625 | POC | CNY |  | 12979 | 2017-12-18 | 2019-01-30 |  | 85106.5225 |  | 67234 |  | 0 | [10 empty] | 0 |  | AM
EPO | RU8709 | 17855 | Zhongke（Guangdong）Refinery & Petrochemical Co., Ltd. | 22217132 | P-Zhongke（Guangdong）Refinery & Petrochemical Co., Ltd.-1004969-P-201A/B Pumps Field Service | 20626 | POC | CNY |  | 4928 | 2017-12-18 | 2019-01-30 |  | 32314.1184 |  | 25528 |  | 0 | [10 empty] | 0 |  | OE
IPO | RU8715 | 7376 | Dunhuang Shouhang Resources Saving New Energy Co., | 22217072 | P-Dunhuang Shouhang Resources Saving New Energy Co-1004559-4 units APCK pumps | 7819 | POC | CNY | 26121300.0164 | 1919992.95 | 2017-06-27 | 2018-06-08 |  | 13016208.2053 |  | 11928442 |  | 4580574 | [10 empty] | 0 | CHINA | OE
IPO | RU8715 | 7376 | Dunhuang Shouhang Resources Saving New Energy Co., | 22217072 | P-Dunhuang Shouhang Resources Saving New Energy Co-1004559-Service | 8046 | POC | CNY |  | 22063.14 | 2017-06-27 | 2018-06-08 |  | 149572.645 |  | 137073 |  | 36658 | [10 empty] | 0 | - | OE
IPO | RU8715 | 7376 | Dunhuang Shouhang Resources Saving New Energy Co., | 22217072 | P-Dunhuang Shouhang Resources Saving New Energy Co-1004559-2 units EMM pumps | 17264 | POC | CNY |  | 355769 | 2017-06-27 | 2018-06-08 |  | 2411864.7816 |  | 2210305 |  | 1147802 | [10 empty] | 0 |  | OE
IPO | RU8715 | 7376 | Dunhuang Shouhang Resources Saving New Energy Co., | 22217072 | P-Dunhuang Shouhang Resources Saving New Energy Co-1004559-3 units ENH pumps(16ENH-2) | 17265 | POC | CNY |  | 863398.61 | 2017-06-27 | 2018-06-08 |  | 5853238.1965 |  | 5364083 |  | 1948954 | [10 empty] | 0 |  | OE
IPO | RU8715 | 7376 | Dunhuang Shouhang Resources Saving New Energy Co., | 22217072 | P-Dunhuang Shouhang Resources Saving New Energy Co-1004559-2 units ENH pumps(12ENH-3) | 17266 | POC | CNY |  | 480391.21 | 2017-06-27 | 2018-06-08 |  | 3256716.1298 |  | 2984552 |  | 1352605 | [10 empty] | 0 |  | OE
IPO | RU8715 | 7376 | Dunhuang Shouhang Resources Saving New Energy Co., | 22217072 | P-Dunhuang Shouhang Resources Saving New Energy Co-1004559-Spare parts for 4 units APCK pumps | 17384 | POC | CNY |  | 70195.96 | 2017-06-27 | 2018-06-08 |  | 475879.4716 |  | 436110 |  | 74221 | [10 empty] | 0 |  | AM
IPO | RU8715 | 7376 | Dunhuang Shouhang Resources Saving New Energy Co., | 22217072 | P-Dunhuang Shouhang Resources Saving New Energy Co-1004559-Spare parts for 2 units EMM pumps | 17385 | POC | CNY |  | 50071.73 | 2017-06-27 | 2018-06-08 |  | 339451.2792 |  | 311083 |  | 43402 | [10 empty] | 0 |  | AM
IPO | RU8715 | 7376 | Dunhuang Shouhang Resources Saving New Energy Co., | 22217072 | P-Dunhuang Shouhang Resources Saving New Energy Co-1004559-Spare parts for 3 units ENH pumps(16ENH-2) | 17386 | POC | CNY |  | 54433.43 | 2017-06-27 | 2018-06-08 |  | 369020.552 |  | 338181 |  | 43402 | [10 empty] | 0 |  | AM
IPO | RU8715 | 7376 | Dunhuang Shouhang Resources Saving New Energy Co., | 22217072 | P-Dunhuang Shouhang Resources Saving New Energy Co-1004559-Spare parts for 2 units ENH pumps(12ENH-3) | 17387 | POC | CNY |  | 36780.9 | 2017-06-27 | 2018-06-08 |  | 249348.7554 |  | 228511 |  | 43402 | [10 empty] | 0 |  | AM
IPO | RU8715 | 8655 | Qinghai SUPCON Solar Power Co., Ltd | 22217095 | P-Qinghai SUPCON Solar Power Co Ltd-1004693-2 units APCK Pumps | 8665 | POC | CNY | 7415514.3802 | 1012582.77 | 2017-08-22 | 2018-08-22 |  | 6739458.6511 |  | 5829632 |  | 329433 | [10 empty] | 0 | CHINA | OE
IPO | RU8715 | 8655 | Qinghai SUPCON Solar Power Co., Ltd | 22217095 | P-Qinghai SUPCON Solar Power Co Ltd-1004693-Field Service | 8667 | POC | CNY |  | 14125.78 | 2017-08-22 | 2018-08-22 |  | 94017.1145 |  | 81325 |  | 0 | [10 empty] | 0 | - | AM
IPO | RU8715 | 8655 | Qinghai SUPCON Solar Power Co., Ltd | 22217095 | P-Qinghai SUPCON Solar Power Co Ltd-1004693-Extended warranty 12 months | 8668 | SL | CNY |  | 16355.9 | 2017-08-22 | 2018-08-22 |  | 108860 |  |  |  | 0 | [10 empty] | 0 | - | OE | 2020-02-22 | 2021-02-16
IPO | RU8715 | 8655 | Qinghai SUPCON Solar Power Co., Ltd | 22217095 | P-Qinghai SUPCON Solar Power Co Ltd-1004693-Spare parts for 2 units APCK Pumps | 17390 | POC | CNY |  | 71093.62 | 2017-08-22 | 2018-08-22 |  | 473178.6147 |  | 409300 |  | 0 | [10 empty] | 0 |  | AM
IPO | RU8715 | 15513 | Foster Wheeler (Hebei) Engineering Design Co., Ltd | 22217089 | P-Foster Wheeler (Hebei) Engineering Design Co., Ltd-1004653-5 units ERPN pumps | 15518 | POC | CNY | 3299073.5915 | 91175.13 | 2017-08-01 | 2018-04-30 |  | 606835.349 |  | 492143 |  | 517349 | [10 empty] | 0 | CHINA | OE
IPO | RU8715 | 15513 | Foster Wheeler (Hebei) Engineering Design Co., Ltd | 22217089 | P-Foster Wheeler (Hebei) Engineering Design Co., Ltd-1004653-50 units Mark 3 ANSI pumps | 15773 | PIT | CNY |  | 230292.41 | 2017-08-01 | 2018-04-30 |  | 1532759.8107 |  | 1765477 |  | 1844670 | [10 empty] | 0 |  | OE
IPO | RU8715 | 15513 | Foster Wheeler (Hebei) Engineering Design Co., Ltd | 22217089 | P-Foster Wheeler (Hebei) Engineering Design Co., Ltd-1004653-8 units Mark 3 ISO pumps | 15774 | PIT | CNY |  | 110032.1 | 2017-08-01 | 2018-04-30 |  | 732341.8986 |  | 651648 |  | 811863 | [10 empty] | 0 |  | OE
IPO | RU8715 | 15513 | Foster Wheeler (Hebei) Engineering Design Co., Ltd | 22217089 | P-Foster Wheeler (Hebei) Engineering Design Co., Ltd-1004653-Spare parts for 5 units ERPN pumps | 17391 | POC | CNY |  | 13281.82 | 2017-08-01 | 2018-04-30 |  | 88399.9603 |  | 71692 |  | 27886 | [10 empty] | 0 |  | AM
IPO | RU8715 | 15513 | Foster Wheeler (Hebei) Engineering Design Co., Ltd | 22217089 | P-Foster Wheeler (Hebei) Engineering Design Co., Ltd-1004653-Spare parts for 50 units Mark 3 ANSI pumps | 17392 | PIT | CNY |  | 28802.44 | 2017-08-01 | 2018-04-30 |  | 191700.7273 |  | 155469 |  | 89488 | [10 empty] | 0 |  | AM
IPO | RU8715 | 15513 | Foster Wheeler (Hebei) Engineering Design Co., Ltd | 22217089 | P-Foster Wheeler (Hebei) Engineering Design Co., Ltd-1004653-Spare parts for 8 units Mark 3 ISO pumps | 17393 | PIT | CNY |  | 20242.49 | 2017-08-01 | 2018-04-30 |  | 134728.1708 |  | 109265 |  | 49083 | [10 empty] | 0 |  | AM
IPO | RU8715 | 15513 | Foster Wheeler (Hebei) Engineering Design Co., Ltd | 22217089 | P-Foster Wheeler (Hebei) Engineering Design Co., Ltd-1004653-Field service | 17441 | POC | CNY |  | 1849.19 | 2017-08-01 | 2018-04-30 |  | 12307.6749 |  | 9982 |  | 0 | [10 empty] | 0 |  | AM
IPO | RU8715 | 17096 | CTCI Corporation | 32000606 | P-CTCI Corporation-1003372-4 units HPX Pumps | 17261 | POC | USD | 1531231 | 311151 | 2016-04-11 | 2018-03-31 |  | 311151 |  |  |  | 1598100 |  |  |  | 2018-03-31 |  |  |  | 0 |  |  | 99626 | OTHER | OE
IPO | RU8715 | 17096 | CTCI Corporation | 32000606 | P-CTCI Corporation-1003372-4 units Mark 3 ANSI Pumps | 17262 | PIT | USD |  | 73223 | 2016-04-11 | 2018-03-31 |  | 73223 |  |  |  | 533346 |  |  |  | 2018-03-31 | [6 empty] | 0 |  | OE
IPO | RU8715 | 17096 | CTCI Corporation | 32000606 | P-CTCI Corporation-1003372-6 units M Pumps | 17263 | POC | USD |  | 1004020.02 | 2016-04-11 | 2018-03-31 |  | 1004020 |  |  |  | 6418409 |  |  |  | 2018-03-31 | [6 empty] | 0 |  | OE
IPO | RU8715 | 17096 | CTCI Corporation | 32000606 | P-CTCI Corporation-1003372-Spare parts for 4 units HPX Pumps | 17381 | POC | USD |  | 21849 | 2016-04-11 | 2018-03-31 |  | 21849 |  |  |  | 107538 |  |  |  | 2018-03-31 | [6 empty] | 0 |  | AM
IPO | RU8715 | 17096 | CTCI Corporation | 32000606 | P-CTCI Corporation-1003372-Spare parts for 4 units Mark 3 ANSI Pumps | 17382 | PIT | USD |  | 12315 | 2016-04-11 | 2018-03-31 |  | 12315 |  |  |  | 25569 |  |  |  | 2018-03-31 | [6 empty] | 0 |  | AM
IPO | RU8715 | 17096 | CTCI Corporation | 32000606 | P-CTCI Corporation-1003372-Spare parts for 6 units M Pumps | 17383 | POC | USD |  | 108672.98 | 2016-04-11 | 2018-03-31 |  | 108673 |  |  |  | 338072 |  |  |  | 2018-03-31 | [6 empty] | 0 |  | AM
IPO | RU8715 | 21965 | Beijing Sinimpex Technologies Co., Ltd | 22218008 | P-Beijing Sinimpex Technologies Co Ltd-1005037-3 units of 26APKC MC-5 pumps | 22053 | POC | CNY | 9558119.6756 | 1467179.24 | 2018-01-31 | 2019-01-31 |  | 9380071.7964 |  | 7879260 |  | 2607 | [10 empty] | 0 |  | OE
IPO | RU8715 | 21965 | Beijing Sinimpex Technologies Co., Ltd | 22218008 | P-Beijing Sinimpex Technologies Co Ltd-1005037-Spare parts | 22054 | POC | CNY |  | 16113.1 | 2018-01-31 | 2019-01-31 |  | 103015.3854 |  | 86533 |  | 0 | [10 empty] | 0 |  | AM
IPO | RU8715 | 21965 | Beijing Sinimpex Technologies Co., Ltd | 22218008 | P-Beijing Sinimpex Technologies Co Ltd-1005037-Field service | 22055 | PIT | CNY |  | 11736.17 | 2018-01-31 | 2019-01-31 |  | 75032.4938 |  | 63027 |  | 0 | [10 empty] | 0 |  | OE
IPO | RU8715 | 24511 | Beijing Sinimpex Technologies Co., Ltd | 22218034 | P-Beijing Sinimpex Technologies Co., Ltd-1005157-8 units APKC pumps | 26404 | POC | CNY | 19734465.8111 | 3004457.86 | 2018-03-30 | 2019-01-30 |  | 18928616.2228 |  | 8269655 |  | 5470 | [10 empty] | 0 | CHINA | OE
IPO | RU8715 | 24511 | Beijing Sinimpex Technologies Co., Ltd | 22218034 | P-Beijing Sinimpex Technologies Co., Ltd-1005157-Spare parts for 8 units APKC pumps | 26437 | POC | CNY |  | 97370.89 | 2018-03-30 | 2019-01-30 |  | 613453.8389 |  | 301048 |  | 0 | [10 empty] | 0 | CHINA | AM
IPO | RU8715 | 24511 | Beijing Sinimpex Technologies Co., Ltd | 22218034 | P-Beijing Sinimpex Technologies Co., Ltd-1005157-Field service | 26438 | PIT | CNY |  | 30538.15 | 2018-03-30 | 2019-01-30 |  | 192395.7494 |  | 173733 |  | 0 | [10 empty] | 0 | CHINA | OE
IPO | RU8715 | 28132 | SEPCOIII Electric Power Construction Corporation | 22218039 | P-SEPCOIII Electric Power Construction Corporation-1005233-7 units APKC/CKHF/EJH pumps | 28137 | POC | CNY | #DIV/0! |  | 2018-04-23 | 2019-03-30 |  | #DIV/0! | [14 empty] | 0
IPO | RU8715 | 28132 | SEPCOIII Electric Power Construction Corporation | 22218039 | P-SEPCOIII Electric Power Construction Corporation-1005233-Spare parts for 7 units APKC/CKHF/EJH pumps | 28222 | POC | CNY |  |  | 2018-04-23 | 2019-03-30 |  | #DIV/0! | [14 empty] | 0
IPO | RU8715 | 28132 | SEPCOIII Electric Power Construction Corporation | 22218039 | P-SEPCOIII Electric Power Construction Corporation-1005233-Field service | 28223 | PIT | CNY |  |  | 2018-04-23 | 2019-03-30 |  | #DIV/0! | [14 empty] | 0
IPO | RU8910 | 4784 | Goldings | 150709 | P-Goldings-150709-Pumpsets & Motors | 4951 | POC | AUD | 701200 | 522875 | 2017-06-29 | 2018-01-05 |  | 701200 | [7 empty] | 2018-03-31 | [6 empty] | 0 | ASIA | OE
IPO | RU8910 | 5438 | Koppers Carbon | 151434 | P - Koppers Carbon - 151434 | 5447 | POC | AUD | 429818.9699 | 337150 | 2017-07-17 | 2018-02-15 |  | 429818.9699 |  | 420630 |  | 358060 | [10 empty] | 0 | ASIA | AM
IPO | RU8910 | 8694 | Oil Search | 151831 | P - Oilsearch - 151831 - Pump Repair | 8715 | POC | AUD | 320392.6504 | 254584 | 2017-08-23 | 2018-03-05 |  | 320392.6504 |  | 208948 |  | 185003 | [10 empty] | 0 | ASIA | OE
IPO | RU8910 | 10126 | Woodside Energy | 147745 | P - Woodside - 147745 - Spare Kits | 11062 | POC | AUD | 8979445.24 | 534959.05 | 2017-10-02 | 2018-08-31 |  | 435203.74 | [10 empty] | 1288063 |  | 2018-05-31 | 20380 | 0 | ASIA | AM
IPO | RU8910 | 10126 | Woodside Energy | 147745 | P - Woodside - 147745 - Site Commissioning Services | 11063 | PIT | AUD |  | 265823.5 | 2017-10-02 | 2018-08-31 |  | 334537.5 | [14 empty] | 0 |  | AM
IPO | RU8910 | 10126 | Woodside Energy | 147745 | P - Woodside - 147745 - Pumps with motors | 18151 | POC | AUD |  | 6004589.06 | 2017-10-02 | 2018-08-31 |  | 8209704 |  | 6448831 |  | 6287487 | [10 empty] | 0 |  | OE
IPO | RU8910 | 17101 | Sydney Water | 151258 | P - Sydney Water - 151258 | 17108 | POC | AUD | 495923 | 375215 | 2017-07-14 | 2018-01-31 |  | 495923 | [7 empty] | 2018-03-31 | [6 empty] | 0 | ASIA | OE
IPO | RU8910 | 18145 | John Holland | 150387 | P - John Holland - 150387 | 18150 | POC | AUD | 808760.9007 | 621371 | 2017-03-31 | 2018-04-10 |  | 808760.9007 |  | 660000 |  | 658796 | [10 empty] | 0 | ASIA | AM
IPO | RU8910 | 18153 | Bechtel | 149940 | P - Bechtel - 149940 | 18158 | POC | AUD | 0 | 268314.17 | 2017-05-30 | 2018-01-09 | [9 empty] | 2018-01-07 | [6 empty] | 0 | ASIA | AM
x |  | x | x |  | x | x | x | x | x | x | x | x |  | x | x | xx |  | x | xx | x |  | x | x |  | x | x | x | x | x | x | x | x | x
Note on H2624: Flowserve: Manually change to PiT as Right to Invoice revenue type not supported in POCC model.

## Descriptions
SECTION | FIELDS | SOURCE DATA
Contract Based Information from PIQ | Platform | This section is populated by the application from the contract information imported from Policy IQ files
Reporting Unit
C-ID
Customer Name
Sales Order #
POb Name (P-page Name)
POb ID
Rev Rec Method
Contract Currency
Total Trans Price Contract Curr
Allocated Transaction Price (USD)
Approval Date
Estimated Completion Date
Blank
EOM Input 1 | Allocated Trans Price (net LD) in Contract Curr | This section should be empty when the EOM process is started. After information is either updated in the screen or via Import Excel files, this should be populated with the latest version available in the system.
Amount of Probable LD Contract Curr
Updated Cost EAC Local Curr
EOM Input 2 | Cumulative Cost Incurred /Received Local Curr
Interco Progress (Not Received) Local Curr
3rd Party Progress (Not Received) Local Curr
EOM Input 3 | Shipment / Delivery Date (if complete)
If partial POB shipped Enter Cumulative COGS
EOM Input 4 | Billing Amount Contract Curr
Billing Amount Local Curr
Billing Date
Billing Invoice #
New Contract Input | Total Third-Party Commission Local Curr | This section should be populated with the latest information from the system. Will be empty for new contracts created in the current month. Site can update these in any month, system will maintain the new value for that month and going forward.
Contract Sales Destination
Disagg. Revenue OE vs AM
Straight Line POb Revenue Start Date
Straight Line POb Revenue End Date